## Sheet1
Portfolio WBS | Description | Quantity | UOM | BAC | BAC Rate | Final Qty (AQ) | Final Cost (AC) | Final Rate | PQ | PV | AQ | AC | EV | Date | Project Name | Start | End | Planned Quantity | Planned Value | Actual Quantity | Actual Cost | Earned Value | Month | predicted_DT | predicted_RF | predicted_LR | predicted_SVM | _merge | Predicted
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 10 | 2519.1489 | 7.6 | 1400 | 1232.6575 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 10 | 2519.15 | 7.6 | 1400 | 1232.6575 | april | 3058.72 | 2155.8 | 577.97 | 2565.94 | both | TRUE
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 35 | 8817.0213 | 31.9 | 5908.3 | 5173.9178 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 25 | 6297.87 | 24.3 | 4508.3 | 3941.2603 | june | 5629.51 | 4702.71 | 4850.67 | 5056.96 | both | TRUE
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 50 | 12595.7447 | 49 | 9071.75 | 7947.3973 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 15 | 3778.72 | 17.1 | 3163.45 | 2773.4795 | july | 3058.72 | 2685.77 | 2338.94 | 2656.28 | both | TRUE
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 70 | 17634.0426 | 107.4 | 19878.3 | 17419.3973 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 20 | 5038.3 | 58.4 | 10806.55 | 9472 | august | 3058.72 | 7975.93 | 10375.69 | 6229.62 | both | TRUE
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 90 | 22672.3404 | 111.7 | 20668.8 | 18116.8219 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 20 | 5038.3 | 4.3 | 790.5 | 697.4247 | september | 1654.63 | 2912.43 | 1406.43 | 2370.42 | both | TRUE
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 90 | 22672.3404 | 130.9 | 24220.2 | 24220 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 19.2 | 3551.4 | 6103.1781 | october | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 94 | hrs | 23680 | 251.91 | 146 | 27030 | 185.137 | 94 | 23680 | 146 | 28430.2 | 23680 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 1007.66 | 15.1 | 4210 | -540 | november | 2954.94 | 3595.87 | 3454.91 | 3430.9 | both | TRUE
13 | QA Testing | 1 | item | 14950 | 14950 | 1 | 7650 | 7650 | 0.1 | 1495 | 0 | 90 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0.1 | 1495 | 0 | 90 | 0 | may | 2681.29 | 1918.93 | 1768.83 | 2419.05 | both | TRUE
13 | QA Testing | 1 | item | 14950 | 14950 | 1 | 7650 | 7650 | 0.25 | 3737.5 | 0.25 | 2650 | 3737.5 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0.15 | 2242.5 | 0.25 | 2560 | 3737.5 | june | 1899.18 | 2248.43 | 2977.86 | 2015.82 | both | TRUE
13 | QA Testing | 1 | item | 14950 | 14950 | 1 | 7650 | 7650 | 0.5 | 7475 | 0.65 | 5050 | 9717.5 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0.25 | 3737.5 | 0.4 | 2400 | 5980 | july | 1899.18 | 1642.74 | 1641.13 | 1410.27 | both | TRUE
13 | QA Testing | 1 | item | 14950 | 14950 | 1 | 7650 | 7650 | 0.75 | 11212.5 | 0.9 | 6850 | 13455 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0.25 | 3737.5 | 0.25 | 1800 | 3737.5 | august | 1899.18 | 2012.06 | 2028.1 | 1777.36 | both | TRUE
13 | QA Testing | 1 | item | 14950 | 14950 | 1 | 7650 | 7650 | 1 | 14950 | 1 | 7650 | 14950 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0.25 | 3737.5 | 0.1 | 800 | 1495 | september | 1654.63 | 2110.13 | 968.43 | 1618.23 | both | TRUE
15 | Service Locations | 0 | none | 0 | 0 | 1 | 1105 | 1105 | 0 | 0 | 0.1 | 130 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0.1 | 130 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | none | 0 | 0 | 1 | 1105 | 1105 | 0 | 0 | 0.9 | 910 | 0 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0.8 | 780 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | none | 0 | 0 | 1 | 1105 | 1105 | 0 | 0 | 1 | 1105 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0.1 | 195 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
21 | Clearing to Stockpile | 2350 | m3 | 4482 | 1.91 | 2350 | 12096 | 5.1472 | 500 | 953.617 | 0 | 0 | 0 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 500 | 953.62 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
21 | Clearing to Stockpile | 2350 | m3 | 4482 | 1.91 | 2350 | 12096 | 5.1472 | 2350 | 4482 | 1750 | 9101.37 | 3337.6596 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 1850 | 3528.38 | 1750 | 9101.37 | 3337.6596 | may | 7179.81 | 7385.02 | 8519.76 | 7146.88 | both | TRUE
21 | Clearing to Stockpile | 2350 | m3 | 4482 | 1.91 | 2350 | 12096 | 5.1472 | 2350 | 4482 | 2200 | 11312.405 | 4195.9149 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 450 | 2211.03 | 858.2553 | july | 0 | 0 | 0 | 0 | left_only | FALSE
21 | Clearing to Stockpile | 2350 | m3 | 4482 | 1.91 | 2350 | 12096 | 5.1472 | 2350 | 4482 | 2350 | 12095.585 | 4482 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 150 | 783.18 | 286.0851 | august | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 14033 | none | 8832 | 0.63 | 0 | 0 | 0 | 4500 | 2832.1813 | 0 | 0 | 0 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 4500 | 2832.18 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 14033 | none | 8832 | 0.63 | 0 | 0 | 0 | 14033 | 8832 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 9533 | 5999.82 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 14033 | none | 8832 | 0.63 | 0 | 0 | 0 | 14033 | 8832 | 0 | 0 | 8268.2553 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 0 | 0 | 8268.2553 | july | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 14033 | none | 8832 | 0.63 | 0 | 0 | 0 | 14033 | 8832 | 0 | 0 | 8832 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 0 | 0 | 563.7447 | august | 0 | 0 | 0 | 0 | left_only | FALSE
23 | Mulching | 14033 | none | 7000 | 0.5 | 0 | 0 | 0 | 14033 | 7000 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-08-01 | 14033 | 7000 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
23 | Mulching | 14033 | none | 7000 | 0.5 | 0 | 0 | 0 | 14033 | 7000 | 0 | 0 | 7000 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-08-01 | 0 | 0 | 0 | 0 | 7000 | august | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 1151 | m3 | 9869.83 | 8.58 | 1151 | 17447 | 15.1581 | 500 | 4287.5 | 0 | 0 | 0 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 500 | 4287.5 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 1151 | m3 | 9869.83 | 8.58 | 1151 | 17447 | 15.1581 | 1151 | 9869.825 | 850 | 13286.15 | 7288.75 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 651 | 5582.32 | 850 | 13286.15 | 7288.75 | may | 7179.81 | 10938.69 | 9043.35 | 9634.63 | both | TRUE
31 | Strip Topsoil to Stockpile | 1151 | m3 | 9869.83 | 8.58 | 1151 | 17447 | 15.1581 | 1151 | 9869.825 | 1050 | 16303.485 | 9003.75 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 200 | 3017.34 | 1715 | july | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 1151 | m3 | 9869.83 | 8.58 | 1151 | 17447 | 15.1581 | 1151 | 9869.825 | 1151 | 17446.665 | 9869.825 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 101 | 1143.18 | 866.075 | august | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - topsoil | 27 | m3 | 353.02 | 13.08 | 0 | 0 | 0 | 27 | 353.025 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 27 | 353.02 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - topsoil | 27 | m3 | 353.02 | 13.08 | 0 | 0 | 0 | 27 | 353.025 | 0 | 0 | 353.025 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 0 | 0 | 0 | 0 | 353.025 | august | 0 | 0 | 0 | 0 | left_only | FALSE
33 | Re-spread topsoil | 389 | m3 | 5539.36 | 14.24 | 389 | 14500 | 37.2751 | 0 | 0 | 100 | 4051.73 | 1424 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-10-01 | 0 | 0 | 100 | 4051.73 | 1424 | august | 0 | 0 | 0 | 0 | left_only | FALSE
33 | Re-spread topsoil | 389 | m3 | 5539.36 | 14.24 | 389 | 14500 | 37.2751 | 389 | 5539.36 | 325 | 12235.91 | 4628 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-10-01 | 389 | 5539.36 | 225 | 8184.18 | 3204 | september | 7179.81 | 9554.52 | 10236.46 | 8184.28 | both | TRUE
33 | Re-spread topsoil | 389 | m3 | 5539.36 | 14.24 | 389 | 14500 | 37.2751 | 389 | 5539.36 | 389 | 14500.11 | 5539.36 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-10-01 | 0 | 0 | 64 | 2264.2 | 911.36 | october | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 29059.43 | 29059.43 | 1 | 13911 | 13911 | 0.25 | 7264.8563 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0.25 | 7264.86 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 29059.43 | 29059.43 | 1 | 13911 | 13911 | 0.5 | 14529.7125 | 0.6 | 8267.735 | 17435.655 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0.25 | 7264.86 | 0.6 | 8267.74 | 17435.655 | july | 5629.51 | 5822.63 | 7435.54 | 4937.28 | both | TRUE
41 | Demolition works | 1 | item | 29059.43 | 29059.43 | 1 | 13911 | 13911 | 0.75 | 21794.5688 | 0.65 | 9050.675 | 18888.6263 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0.25 | 7264.86 | 0.05 | 782.94 | 1452.9713 | august | 5629.51 | 2410.34 | 1830.98 | 2859.19 | both | TRUE
41 | Demolition works | 1 | item | 29059.43 | 29059.43 | 1 | 13911 | 13911 | 1 | 29059.425 | 1 | 13910.675 | 29059.425 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0.25 | 7264.86 | 0.35 | 4860 | 10170.7988 | september | 4719.61 | 5775.11 | 6101 | 4604.22 | both | TRUE
51 | Cut to Fill | 2848 | m3 | 20085.73 | 7.05 | 2848 | 49136 | 17.2528 | 0 | 0 | 200 | 2823.9 | 1410.5148 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0 | 0 | 200 | 2823.9 | 1410.5148 | may | 0 | 0 | 0 | 0 | left_only | FALSE
51 | Cut to Fill | 2848 | m3 | 20085.73 | 7.05 | 2848 | 49136 | 17.2528 | 1400 | 9873.6038 | 1100 | 19971.645 | 7757.8315 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 1400 | 9873.6 | 900 | 17147.74 | 6347.3167 | july | 23096.37 | 14289.34 | 8372.15 | 16372.54 | both | TRUE
51 | Cut to Fill | 2848 | m3 | 20085.73 | 7.05 | 2848 | 49136 | 17.2528 | 2848 | 20085.7311 | 2100 | 36896.175 | 14810.4057 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 1448 | 10212.13 | 1000 | 16924.53 | 7052.5741 | august | 23096.37 | 14652.09 | 8696.14 | 16736.04 | both | TRUE
51 | Cut to Fill | 2848 | m3 | 20085.73 | 7.05 | 2848 | 49136 | 17.2528 | 2848 | 20085.7311 | 2848 | 49136.349 | 20085.7311 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0 | 0 | 748 | 12240.17 | 5275.3255 | september | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 7508 | m3 | 94981.44 | 12.65 | 7508 | 164871 | 21.9594 | 1000 | 12650.6976 | 0 | 1484 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 1000 | 12650.7 | 0 | 1484 | 0 | may | 23096.37 | 12239.08 | 8785.62 | 14915.63 | both | TRUE
52 | Stockpile to Fill | 7508 | m3 | 94981.44 | 12.65 | 7508 | 164871 | 21.9594 | 5000 | 63253.4882 | 3500 | 87840.845 | 44277.4418 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 4000 | 50602.79 | 3500 | 86356.85 | 44277.4418 | june | 20347.42 | 28289.85 | 30221.56 | 24423.59 | both | TRUE
52 | Stockpile to Fill | 7508 | m3 | 94981.44 | 12.65 | 7508 | 164871 | 21.9594 | 6000 | 75904.1859 | 5900 | 130649.97 | 74639.1161 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 1000 | 12650.7 | 2400 | 42809.12 | 30361.6744 | july | 23096.37 | 29399.01 | 36361.29 | 25380.91 | both | TRUE
52 | Stockpile to Fill | 7508 | m3 | 94981.44 | 12.65 | 7508 | 164871 | 21.9594 | 7508 | 94981.4379 | 7508 | 164870.94 | 94981.4379 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 1508 | 19077.25 | 1608 | 34220.97 | 20342.3218 | august | 70121.96 | 33831.17 | 31418.13 | 43144.72 | both | TRUE
53 | Cut to Spoil | 2052 | m3 | 33153.16 | 16.16 | 2052 | 11630 | 5.6676 | 500 | 8078.255 | 10 | 317.56 | 161.5651 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 500 | 8078.25 | 10 | 317.56 | 161.5651 | june | 6413.21 | 2289.72 | -3370.16 | 3878.93 | both | TRUE
53 | Cut to Spoil | 2052 | m3 | 33153.16 | 16.16 | 2052 | 11630 | 5.6676 | 1500 | 24234.7649 | 0 | 317.56 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 1000 | 16156.51 | -10 | 0 | -161.5651 | july | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 2052 | m3 | 33153.16 | 16.16 | 2052 | 11630 | 5.6676 | 2052 | 33153.1583 | 645 | 3858.56 | 10420.9489 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 552 | 8918.39 | 645 | 3541 | 10420.9489 | august | 6413.21 | 4787.17 | 72.47 | 5388.53 | both | TRUE
53 | Cut to Spoil | 2052 | m3 | 33153.16 | 16.16 | 2052 | 11630 | 5.6676 | 2052 | 33153.1583 | 2052 | 11630.28 | 33153.1583 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 1407 | 7771.72 | 22732.2094 | september | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 473 | m3 | 27999.42 | 59.2 | 473 | 29372 | 62.0973 | 200 | 11839.0796 | 90 | 8333.54 | 5327.5858 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 200 | 11839.08 | 90 | 8333.54 | 5327.5858 | june | 5114.24 | 8789.33 | 7727 | 7332.83 | both | TRUE
57 | Remove & Replace unsuitable | 473 | m3 | 27999.42 | 59.2 | 473 | 29372 | 62.0973 | 473 | 27999.4232 | 330 | 29372.455 | 19534.4813 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 273 | 16160.34 | 240 | 21038.92 | 14206.8955 | july | 14835.1 | 14555.98 | 13890.28 | 13934.63 | both | TRUE
57 | Remove & Replace unsuitable | 473 | m3 | 27999.42 | 59.2 | 473 | 29372 | 62.0973 | 473 | 27999.4232 | 460 | 40753.905 | 27229.883 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 130 | 11381.45 | 7695.4017 | august | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 473 | m3 | 27999.42 | 59.2 | 473 | 29372 | 62.0973 | 473 | 27999.4232 | 473 | 41783.66 | 27999.4232 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 13 | 1029.75 | 769.5402 | september | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 22003 | m2 | 44898.2 | 2.04 | 22003 | 6723 | 0.30555 | 2500 | 5101.3727 | 6000 | 2730.24 | 12243.2944 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 2500 | 5101.37 | 6000 | 2730.24 | 12243.2944 | may | 6156.67 | 7290.71 | 2175.09 | 6145.29 | both | TRUE
61 | Subgrade Preparation | 22003 | m2 | 44898.2 | 2.04 | 22003 | 6723 | 0.30555 | 6000 | 12243.2944 | 15000 | 4354.06 | 30608.2361 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 3500 | 7141.92 | 9000 | 1623.82 | 18364.9417 | june | 6156.67 | 4251.61 | -2564.53 | 3707.57 | both | TRUE
61 | Subgrade Preparation | 22003 | m2 | 44898.2 | 2.04 | 22003 | 6723 | 0.30555 | 12500 | 25506.8634 | 14500 | 4354.06 | 29587.9616 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 6500 | 13263.57 | -500 | 0 | -1020.2745 | july | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 22003 | m2 | 44898.2 | 2.04 | 22003 | 6723 | 0.30555 | 22003 | 44898.2013 | 21000 | 6279.92 | 42851.5305 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 9503 | 19391.34 | 6500 | 1925.86 | 13263.569 | august | 5410.44 | 11466.83 | 5535.13 | 7507.51 | both | TRUE
61 | Subgrade Preparation | 22003 | m2 | 44898.2 | 2.04 | 22003 | 6723 | 0.30555 | 22003 | 44898.2013 | 22003 | 6722.72 | 44898.2013 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0 | 0 | 1003 | 442.8 | 2046.6707 | september | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 7995 | tonne | 40636.32 | 5.08 | 5536 | 91849 | 16.5912 | 2500 | 12706.7927 | 275 | 4650.18 | 2018.6035 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 2500 | 12706.79 | 275 | 4650.18 | 2018.6035 | june | 23096.37 | 20264.59 | 20327.03 | 19322.8 | both | TRUE
62 | Place & Compact Gravel | 7995 | tonne | 40636.32 | 5.08 | 5536 | 91849 | 16.5912 | 4000 | 20330.8683 | 1036 | 17611.695 | 7604.6298 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 1500 | 7624.08 | 761 | 12961.52 | 5586.0263 | july | 27472.44 | 14766.86 | 11266.99 | 16918.28 | both | TRUE
62 | Place & Compact Gravel | 7995 | tonne | 40636.32 | 5.08 | 5536 | 91849 | 16.5912 | 7000 | 35579.0196 | 2423 | 48779.54 | 17785.7317 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 3000 | 15248.15 | 1387 | 31167.84 | 10181.1019 | august | 23096.37 | 28735.44 | 32911.53 | 24671.9 | both | TRUE
62 | Place & Compact Gravel | 7995 | tonne | 40636.32 | 5.08 | 5536 | 91849 | 16.5912 | 7995 | 40636.3231 | 5100 | 84713.125 | 37435.919 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 995 | 5057.3 | 2677 | 35933.58 | 19650.1873 | september | 27472.44 | 26720.11 | 29173.98 | 24642.29 | both | TRUE
62 | Place & Compact Gravel | 7995 | tonne | 40636.32 | 5.08 | 5536 | 91849 | 16.5912 | 7995 | 40636.3231 | 5536 | 91849.125 | 40636.3231 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 0 | 0 | 436 | 7136 | 3200.4041 | october | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 18417 | m2 | 45346.75 | 2.46 | 18417 | 45940 | 2.4944 | 0 | 0 | 0 | 78.78 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0 | 0 | 0 | 78.78 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 18417 | m2 | 45346.75 | 2.46 | 18417 | 45940 | 2.4944 | 3050 | 7509.7778 | 2700 | 6951.665 | 6648 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 3050 | 7509.78 | 2700 | 6872.88 | 6648 | june | 6156.67 | 8716.71 | 7636.82 | 6783.46 | both | TRUE
63 | Trim All Layers | 18417 | m2 | 45346.75 | 2.46 | 18417 | 45940 | 2.4944 | 9000 | 22160 | 8460 | 21171.29 | 20830.4 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 5950 | 14650.22 | 5760 | 14219.62 | 14182.4 | july | 18318.04 | 16625.91 | 15509.42 | 15231.77 | both | TRUE
63 | Trim All Layers | 18417 | m2 | 45346.75 | 2.46 | 18417 | 45940 | 2.4944 | 14000 | 34471.1111 | 14350 | 35928.425 | 35332.8889 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 5000 | 12311.11 | 5890 | 14757.13 | 14502.4889 | august | 18318.04 | 14638.95 | 12700.27 | 14149.09 | both | TRUE
63 | Trim All Layers | 18417 | m2 | 45346.75 | 2.46 | 18417 | 45940 | 2.4944 | 18417 | 45346.7467 | 18417 | 45939.655 | 45346.7467 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 4417 | 10875.64 | 4067 | 10011.23 | 10013.8578 | september | 18318.04 | 19708.41 | 19790.23 | 17326.19 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 14781 | m2 | 69649.1 | 4.71 | 14781 | 105958 | 7.1685 | 3050 | 14371.8131 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 3050 | 14371.81 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 14781 | m2 | 69649.1 | 4.71 | 14781 | 105958 | 7.1685 | 3050 | 14371.8131 | 3075 | 22054.7472 | 14489.6148 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 3075 | 22054.75 | 14489.6148 | july | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 14781 | m2 | 69649.1 | 4.71 | 14781 | 105958 | 7.1685 | 8200 | 38638.9728 | 8150 | 58444.7472 | 38403.3693 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 5150 | 24267.16 | 5075 | 36390 | 23913.7545 | august | 25708.8 | 24573.02 | 22881.64 | 23298.06 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 14781 | m2 | 69649.1 | 4.71 | 14781 | 105958 | 7.1685 | 14781 | 69649.1045 | 14781 | 105957.8072 | 69649.1045 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 6581 | 31010.13 | 6631 | 47513.06 | 31245.7352 | september | 25708.8 | 42200.99 | 48358.93 | 34503.15 | both | TRUE
65 | Asphalt | 1369 | tonne | 392816.9 | 307.85 | 1276 | 307649 | 241.1042 | 700 | 200855.9752 | 0 | 0 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-10-01 | 700 | 200855.98 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 1369 | tonne | 392816.9 | 307.85 | 1276 | 307649 | 241.1042 | 1369 | 392816.9 | 509 | 315.12 | 156695.7697 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-10-01 | 669 | 191960.92 | 509 | 315.12 | 156695.7697 | september | 112816.37 | 43641 | 26344.67 | 65246.71 | both | TRUE
65 | Asphalt | 1369 | tonne | 392816.9 | 307.85 | 1276 | 307649 | 241.1042 | 1369 | 392816.9 | 1276 | 185012.62 | 392816.9 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-10-01 | 0 | 0 | 767 | 184697.5 | 236121.1303 | october | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 12634.34 | 12634.34 | 1 | 11724 | 11724 | 0.5 | 6317.1687 | 0 | 753.39 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0.5 | 6317.17 | 0 | 753.39 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 12634.34 | 12634.34 | 1 | 11724 | 11724 | 1 | 12634.3374 | 0 | 753.39 | 0 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0.5 | 6317.17 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 12634.34 | 12634.34 | 1 | 11724 | 11724 | 1 | 12634.3374 | 1 | 11724.39 | 12634.3374 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 1 | 10971 | 12634.3374 | november | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 96 | each | 16715.5 | 174.12 | 96 | 2865 | 29.8438 | 26 | 4527.1146 | 0 | 0 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 26 | 4527.11 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 96 | each | 16715.5 | 174.12 | 96 | 2865 | 29.8438 | 96 | 16715.5 | 20 | 713.5 | 3482.3958 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 70 | 12188.39 | 20 | 713.5 | 3482.3958 | september | 5114.24 | 4826.81 | 6361.35 | 4281.44 | both | TRUE
67 | Install Road Furniture | 96 | each | 16715.5 | 174.12 | 96 | 2865 | 29.8438 | 96 | 16715.5 | 96 | 2865.175 | 16715.5 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 76 | 2151.68 | 13233.1042 | november | 0 | 0 | 0 | 0 | left_only | FALSE
68 | In-situ Stabilising | 3890 | m2 | 42787.12 | 11 | 3890 | 13280 | 3.4139 | 0 | 0 | 3250 | 0 | 35747.595 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 3250 | 0 | 35747.595 | august | 0 | 0 | 0 | 0 | left_only | FALSE
68 | In-situ Stabilising | 3890 | m2 | 42787.12 | 11 | 3890 | 13280 | 3.4139 | 0 | 0 | 3500 | 0 | 38497.41 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 250 | 0 | 2749.815 | september | 0 | 0 | 0 | 0 | left_only | FALSE
68 | In-situ Stabilising | 3890 | m2 | 42787.12 | 11 | 3890 | 13280 | 3.4139 | 3890 | 42787.1214 | 3500 | 0 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 3890 | 42787.12 | 0 | 0 | -38497.41 | october | 0 | 0 | 0 | 0 | left_only | FALSE
68 | In-situ Stabilising | 3890 | m2 | 42787.12 | 11 | 3890 | 13280 | 3.4139 | 3890 | 42787.1214 | 3890 | 868.4 | 42787.1214 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 390 | 868.4 | 42787.1214 | november | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 1517 | m | 30932.82 | 20.39 | 1517 | 37067 | 24.4344 | 100 | 2039.0786 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 100 | 2039.08 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 1517 | m | 30932.82 | 20.39 | 1517 | 37067 | 24.4344 | 100 | 2039.0786 | 81 | 1995.8 | 1651.6537 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 81 | 1995.8 | 1651.6537 | july | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 1517 | m | 30932.82 | 20.39 | 1517 | 37067 | 24.4344 | 400 | 8156.3143 | 81 | 2580.3 | 1651.6537 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 300 | 6117.24 | 0 | 584.5 | 0 | august | 14835.1 | 6426.03 | 4062.53 | 7660.02 | both | TRUE
71 | Place Kerb & Channel / Inverts | 1517 | m | 30932.82 | 20.39 | 1517 | 37067 | 24.4344 | 1571 | 32033.9246 | 150 | 3724.5 | 3058.6179 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 1171 | 23877.61 | 69 | 1144.2 | 1406.9642 | september | 13330.1 | 8301.62 | 3816.48 | 8499.46 | both | TRUE
71 | Place Kerb & Channel / Inverts | 1517 | m | 30932.82 | 20.39 | 1517 | 37067 | 24.4344 | 1517 | 30932.8221 | 1517 | 37066.6 | 30932.8221 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 1317 | 32042.1 | 26854.665 | november | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1005 | m2 | 19964.45 | 19.87 | 1005 | 33677 | 33.5095 | 250 | 4966.2802 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 250 | 4966.28 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1005 | m2 | 19964.45 | 19.87 | 1005 | 33677 | 33.5095 | 500 | 9932.5604 | 475 | 16041.175 | 9435.9324 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 250 | 4966.28 | 475 | 16041.18 | 9435.9324 | august | 12590.7 | 12375.46 | 14744.17 | 12346.54 | both | TRUE
73 | Form & Place Footpath | 1005 | m2 | 19964.45 | 19.87 | 1005 | 33677 | 33.5095 | 500 | 9932.5604 | 535 | 18009.8 | 10627.8397 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 0 | 0 | 60 | 1968.63 | 1191.9073 | september | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1005 | m2 | 19964.45 | 19.87 | 1005 | 33677 | 33.5095 | 1005 | 19964.4465 | 940 | 31516.9 | 18673.2136 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 505 | 10031.89 | 405 | 13507.1 | 8045.374 | october | 6413.21 | 11353.49 | 14174.45 | 10009.32 | both | TRUE
73 | Form & Place Footpath | 1005 | m2 | 19964.45 | 19.87 | 1005 | 33677 | 33.5095 | 1005 | 19964.4465 | 1005 | 33676.9 | 19964.4465 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 0 | 0 | 65 | 2160 | 1291.2329 | november | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 202 | m | 10313.81 | 51.06 | 202 | 17495 | 86.6089 | 50 | 2552.9226 | 0 | 157.56 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 50 | 2552.92 | 0 | 157.56 | 0 | june | 1899.18 | 720.11 | 705.56 | 702.92 | both | TRUE
81 | > 450 | 202 | m | 10313.81 | 51.06 | 202 | 17495 | 86.6089 | 202 | 10313.8071 | 151 | 13194.42 | 7709.8261 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 152 | 7760.88 | 151 | 13036.86 | 7709.8261 | july | 8981.05 | 11555.05 | 15399.22 | 9770.56 | both | TRUE
81 | > 450 | 202 | m | 10313.81 | 51.06 | 202 | 17495 | 86.6089 | 202 | 10313.8071 | 151 | 13464.42 | 7709.8261 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 270 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 202 | m | 10313.81 | 51.06 | 202 | 17495 | 86.6089 | 202 | 10313.8071 | 202 | 17494.82 | 10313.8071 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 51 | 4030.4 | 2603.981 | september | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 24 | each | 21867 | 911.12 | 24 | 25121 | 1046.7083 | 0 | 0 | 3.75 | 4000 | 3416.7188 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 3.75 | 4000 | 3416.7188 | july | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 24 | each | 21867 | 911.12 | 24 | 25121 | 1046.7083 | 18 | 16400.25 | 12.5 | 13197.58 | 11389.0625 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 18 | 16400.25 | 8.75 | 9197.58 | 7972.3438 | august | 5629.51 | 7322.9 | 7335.85 | 6073.25 | both | TRUE
85 | Install SW Pits & Chambers | 24 | each | 21867 | 911.12 | 24 | 25121 | 1046.7083 | 24 | 21867 | 23.5 | 24799.29 | 21411.4375 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 6 | 5466.75 | 11 | 11601.71 | 10022.375 | september | 11114.42 | 8956.3 | 8647.77 | 8482.33 | both | TRUE
85 | Install SW Pits & Chambers | 24 | each | 21867 | 911.12 | 24 | 25121 | 1046.7083 | 24 | 21867 | 24 | 25120.69 | 21867 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0.5 | 321.4 | 455.5625 | october | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 0.15 | 26200.86 | 0.17 | 29539.91 | 29694.308 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.15 | 26200.86 | 0.17 | 29539.91 | 29694.308 | may | 29134.33 | 24398.29 | 24587.5 | 24757.84 | both | TRUE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 0.45 | 78602.58 | 0.4 | 62560.92 | 69868.96 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.3 | 52401.72 | 0.23 | 33021.01 | 40174.652 | june | 96278.32 | 60289.27 | 63483 | 69097.68 | both | TRUE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 0.5 | 87336.2 | 0.45 | 63546.92 | 78602.58 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.05 | 8733.62 | 0.05 | 986 | 8733.62 | july | 1405.82 | 7164.81 | 6103.24 | 3965.17 | both | TRUE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 0.5 | 87336.2 | 0.47 | 65136.92 | 82096.028 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0.02 | 1590 | 3493.448 | august | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 1 | 174672.4 | 0.99 | 138951.92 | 172925.676 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.5 | 87336.2 | 0.52 | 73815 | 90829.648 | september | 96278.32 | 70075.06 | 73282.01 | 75859.51 | both | TRUE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 1 | 174672.4 | 1 | 139556.12 | 174672.4 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0.01 | 604.2 | 1746.724 | october | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 1 | item | 174672.4 | 174672.4 | 1 | 139556 | 139556 | 1 | 174672.4 | 1 | 145242.12 | 174672.4 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 5686 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 285 | m | 24123.64 | 84.64 | 285 | 8135 | 28.5439 | 0 | 0 | 30 | 2320 | 2539.3309 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 30 | 2320 | 2539.3309 | may | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 285 | m | 24123.64 | 84.64 | 285 | 8135 | 28.5439 | 50 | 4232.2181 | 35 | 2905 | 2962.5527 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 50 | 4232.22 | 5 | 585 | 423.2218 | june | 3058.72 | 1388.56 | -1218.83 | 975.33 | both | TRUE
103 | Water Sub-contractor | 285 | m | 24123.64 | 84.64 | 285 | 8135 | 28.5439 | 50 | 4232.2181 | 95 | 2905 | 8041.2144 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 60 | 0 | 5078.6617 | july | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 285 | m | 24123.64 | 84.64 | 285 | 8135 | 28.5439 | 285 | 24123.6432 | 285 | 8135 | 24123.6432 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 235 | 19891.43 | 190 | 5230 | 16082.4288 | august | 14835.1 | 7589.55 | 3618.97 | 8840.73 | both | TRUE
103 | Water Sub-contractor | 285 | m | 24123.64 | 84.64 | 285 | 8135 | 28.5439 | 285 | 24123.6432 | 285 | 8325 | 24123.6432 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 190 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.52 | 65.74 | 995 | 39338 | 39.5357 | 400 | 26294.0794 | 295 | 13375 | 19391.8836 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 400 | 26294.08 | 295 | 13375 | 19391.8836 | june | 22048.5 | 12643.51 | 8988.58 | 14412.42 | both | TRUE
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.52 | 65.74 | 995 | 39338 | 39.5357 | 995 | 65406.5226 | 860 | 34451.34 | 56532.2707 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 595 | 39112.44 | 565 | 21076.34 | 37140.3872 | july | 13119.91 | 17560.02 | 17106.04 | 14786.17 | both | TRUE
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.52 | 65.74 | 995 | 39338 | 39.5357 | 995 | 65406.5226 | 860 | 34631.34 | 56532.2707 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 180 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.52 | 65.74 | 995 | 39338 | 39.5357 | 995 | 65406.5226 | 930 | 37173.59 | 61133.7346 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 70 | 2542.25 | 4601.4639 | september | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.52 | 65.74 | 995 | 39338 | 39.5357 | 995 | 65406.5226 | 995 | 39337.69 | 65406.5226 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 65 | 2164.1 | 4272.7879 | october | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 995 | m | 65406.52 | 65.74 | 995 | 39338 | 39.5357 | 995 | 65406.5226 | 995 | 40668.49 | 65406.5226 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 1330.8 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
112 | Electrical Conduit Sub-contractor | 1 | item | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 1 | 0 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
112 | Electrical Conduit Sub-contractor | 1 | item | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 0 | 0 | 1 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
112 | Electrical Conduit Sub-contractor | 1 | item | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 150 | 0 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 0 | 0 | 0 | 150 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 1 | item | 69827 | 69827 | 1 | 84469 | 84469 | 0 | 0 | 0 | 1705.425 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0 | 1705.42 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 1 | item | 69827 | 69827 | 1 | 84469 | 84469 | 0 | 0 | 0.15 | 12625.425 | 10474.05 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0.15 | 10920 | 10474.05 | august | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 1 | item | 69827 | 69827 | 1 | 84469 | 84469 | 1 | 69827 | 0.35 | 29136.825 | 24439.45 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 1 | 69827 | 0.2 | 16511.4 | 13965.4 | september | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 1 | item | 69827 | 69827 | 1 | 84469 | 84469 | 1 | 69827 | 1 | 84469.435 | 69827 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 0.65 | 55332.61 | 45387.55 | october | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 3271 | m2 | 0 | 0 | 3271 | 7800 | 2.3846 | 3271 | 0 | 0 | 0 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-10-01 | 2011-11-01 | 3271 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 3271 | m2 | 0 | 0 | 3271 | 7800 | 2.3846 | 3271 | 0 | 3271 | 7800 | 0 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-10-01 | 2011-11-01 | 0 | 0 | 3271 | 7800 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 1602 | m | 54957.33 | 34.31 | 1602 | 59187 | 36.9457 | 800 | 27444.3615 | 45 | 1680.35 | 1543.7453 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 800 | 27444.36 | 45 | 1680.35 | 1543.7453 | august | 13119.91 | 8324.47 | 5133.69 | 8716.39 | both | TRUE
131 | Fencing Sub-contractors | 1602 | m | 54957.33 | 34.31 | 1602 | 59187 | 36.9457 | 1602 | 54957.334 | 53 | 1963.53 | 1818.189 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 802 | 27512.97 | 8 | 283.18 | 274.4436 | october | 13119.91 | 6715.75 | 2852.48 | 7864.15 | both | TRUE
131 | Fencing Sub-contractors | 1602 | m | 54957.33 | 34.31 | 1602 | 59187 | 36.9457 | 1602 | 54957.334 | 1602 | 63042.17 | 54957.334 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 1549 | 61078.64 | 53139.145 | november | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
134 | Hire of Temporary Fencing | 0 | none | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708.3 | 0 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 708.3 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 24 | 1246.6983 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 24 | 1246.7 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 48 | 2493.3966 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 24 | 1246.7 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 72 | 3740.0949 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 24 | 1246.7 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 96 | 4986.7932 | 28 | 1485.7 | 903.3095 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 24 | 1246.7 | 28 | 1485.7 | 903.3095 | august | 1824.94 | 1430.32 | 1097.73 | 1898.57 | both | TRUE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 177 | 9194.4 | 94 | 4892 | 3032.5389 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 81 | 4207.61 | 66 | 3406.3 | 2129.2295 | september | 1654.63 | 3974.05 | 3538.06 | 3395.76 | both | TRUE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 177 | 9194.4 | 120 | 6323.675 | 3871.3263 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 26 | 1431.68 | 838.7874 | october | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 177 | hrs | 9194.4 | 51.95 | 285 | 14798 | 51.9228 | 177 | 9194.4 | 285 | 14798.475 | 9194.4 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 165 | 8474.8 | 5323.0737 | november | 0 | 0 | 0 | 0 | left_only | FALSE
142 | Hire of Control Devices | 16 | weeks | 16500 | 1031.25 | 8 | 4339 | 542.375 | 2 | 2062.5 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 2 | 2062.5 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
142 | Hire of Control Devices | 16 | weeks | 16500 | 1031.25 | 8 | 4339 | 542.375 | 6 | 6187.5 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 4 | 4125 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
142 | Hire of Control Devices | 16 | weeks | 16500 | 1031.25 | 8 | 4339 | 542.375 | 10 | 10312.5 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 4 | 4125 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
142 | Hire of Control Devices | 16 | weeks | 16500 | 1031.25 | 8 | 4339 | 542.375 | 14 | 14437.5 | 4 | 1454.11 | 8250 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 4 | 4125 | 4 | 1454.11 | 8250 | august | 0 | 0 | 0 | 0 | left_only | FALSE
142 | Hire of Control Devices | 16 | weeks | 16500 | 1031.25 | 8 | 4339 | 542.375 | 16 | 16500 | 4 | 1454.11 | 8250 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 2 | 2062.5 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
142 | Hire of Control Devices | 16 | weeks | 16500 | 1031.25 | 8 | 4339 | 542.375 | 16 | 16500 | 8 | 4339.41 | 16500 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 0 | 0 | 4 | 2885.3 | 8250 | october | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 2000 | m | 19140.03 | 9.57 | 0 | 177 | 0 | 1000 | 9570.0154 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-07-01 | 1000 | 9570.02 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 2000 | m | 19140.03 | 9.57 | 0 | 177 | 0 | 2000 | 19140.0308 | 0 | 177.255 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-07-01 | 1000 | 9570.02 | 0 | 177.26 | 0 | june | 1628.04 | 3982.88 | 494.86 | 1884.76 | both | TRUE
151 | Supply & Place Silt fences & protective devices | 2000 | m | 19140.03 | 9.57 | 0 | 177 | 0 | 2000 | 19140.0308 | 0 | 177.255 | 19140.0308 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-07-01 | 0 | 0 | 0 | 0 | 19140.0308 | july | 0 | 0 | 0 | 0 | left_only | FALSE
152 | Supply & install safety devices | 1 | item | 12768 | 12768 | 1 | 2806 | 2806 | 1 | 12768 | 0.05 | 590.85 | 638.4 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 1 | 12768 | 0.05 | 590.85 | 638.4 | may | 0 | 0 | 0 | 0 | left_only | FALSE
152 | Supply & install safety devices | 1 | item | 12768 | 12768 | 1 | 2806 | 2806 | 1 | 12768 | 0.4 | 1343.85 | 5107.2 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 0 | 0 | 0.35 | 753 | 4468.8 | june | 0 | 0 | 0 | 0 | left_only | FALSE
152 | Supply & install safety devices | 1 | item | 12768 | 12768 | 1 | 2806 | 2806 | 1 | 12768 | 0.6 | 1931.275 | 7660.8 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 0 | 0 | 0.2 | 587.43 | 2553.6 | july | 0 | 0 | 0 | 0 | left_only | FALSE
152 | Supply & install safety devices | 1 | item | 12768 | 12768 | 1 | 2806 | 2806 | 1 | 12768 | 1 | 2805.915 | 12768 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-08-01 | 0 | 0 | 0.4 | 874.64 | 5107.2 | august | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Day Works | 1 | item | 325.24 | 325.24 | 1 | 424 | 424 | 1 | 325.24 | 1 | 491.47 | 325.24 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 1 | 325.24 | 1 | 491.47 | 325.24 | november | 609.44 | 1007.67 | 696.6 | 670.32 | both | TRUE
901 | Project Management | 9 | weeks | 29792.75 | 3310.31 | 15 | 2728 | 181.8667 | 0 | 0 | 1.9 | 342.19 | 3773.7483 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-09-01 | 0 | 0 | 1.9 | 342.19 | 3773.7483 | april | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 9 | weeks | 29792.75 | 3310.31 | 15 | 2728 | 181.8667 | 2 | 6620.6111 | 5.7 | 1035.5 | 11321.245 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-09-01 | 2 | 6620.61 | 3.8 | 693.31 | 7547.4967 | may | 4719.61 | 2209.16 | -688.76 | 3165.3 | both | TRUE
901 | Project Management | 9 | weeks | 29792.75 | 3310.31 | 15 | 2728 | 181.8667 | 4 | 13241.2222 | 11.1 | 2025.5 | 22046.635 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-09-01 | 2 | 6620.61 | 5.4 | 990 | 10725.39 | june | 589.26 | 1286.84 | -601.97 | 890.69 | both | TRUE
901 | Project Management | 9 | weeks | 29792.75 | 3310.31 | 15 | 2728 | 181.8667 | 6 | 19861.8333 | 12.9 | 2340.5 | 25621.765 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-09-01 | 2 | 6620.61 | 1.8 | 315 | 3575.13 | july | 589.26 | 1637.11 | -251.55 | 873.5 | both | TRUE
901 | Project Management | 9 | weeks | 29792.75 | 3310.31 | 15 | 2728 | 181.8667 | 8 | 26482.4444 | 15 | 2727.54 | 29792.75 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-09-01 | 2 | 6620.61 | 2.1 | 387.04 | 4170.985 | august | 589.26 | 1142.7 | -1233.06 | 682.1 | both | TRUE
901 | Project Management | 9 | weeks | 29792.75 | 3310.31 | 15 | 2728 | 181.8667 | 9 | 29792.75 | 15 | 2727.54 | 29792.75 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-09-01 | 1 | 3310.31 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 1 | 2400.6937 | 0.6 | 1723.44 | 768.222 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 1 | 2400.69 | 0.6 | 1723.44 | 768.222 | april | 5051.4 | 3911.94 | 1670.33 | 4415.63 | both | TRUE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 3 | 7202.0812 | 5.3 | 14752.42 | 6785.961 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 2 | 4801.39 | 4.7 | 13028.98 | 6017.739 | may | 5051.4 | 9009.73 | 10150.29 | 8113 | both | TRUE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 7 | 16804.8563 | 10.5 | 29150.325 | 13443.885 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 9602.78 | 5.2 | 14397.9 | 6657.924 | june | 11719.06 | 15087.71 | 18274.76 | 13836.94 | both | TRUE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 11 | 26407.6312 | 16.6 | 45989.77 | 21254.142 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 9602.77 | 6.1 | 16839.44 | 7810.257 | july | 11719.06 | 15510.61 | 18740.26 | 13866.71 | both | TRUE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 15 | 36010.4062 | 22.7 | 62865.12 | 29064.399 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 9602.78 | 6.1 | 16875.35 | 7810.257 | august | 7116.63 | 13851.77 | 16978.95 | 11483.11 | both | TRUE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 16 | 38411.1 | 28.4 | 78771.035 | 36362.508 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 1 | 2400.69 | 5.7 | 15905.92 | 7298.109 | september | 11114.42 | 13029.47 | 14311.15 | 11912.47 | both | TRUE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 16 | 38411.1 | 29.5 | 81894.77 | 37770.915 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 1.1 | 3123.74 | 1408.407 | october | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 38411.1 | 2400.69 | 30 | 83151 | 2771.7 | 16 | 38411.1 | 30 | 84084.975 | 38411.1 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 0.5 | 2190.2 | 640.185 | november | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 1 | 1914.8 | 0 | 0 | 0 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 1 | 1914.8 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 3 | 5744.4 | 5.7 | 3200 | 5820.992 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 2 | 3829.6 | 5.7 | 3200 | 5820.992 | may | 5051.4 | 4041.21 | 4032.06 | 4434.4 | both | TRUE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 7 | 13403.6 | 10 | 5655.58 | 10212.2667 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 7659.2 | 4.3 | 2455.58 | 4391.2747 | june | 1849.43 | 2452.24 | 2405.31 | 2095.08 | both | TRUE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 11 | 21062.8 | 12.3 | 6907.74 | 12561.088 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 7659.2 | 2.3 | 1252.16 | 2348.8213 | july | 1849.43 | 2226.23 | 1842.69 | 1705.27 | both | TRUE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 15 | 28722 | 17.9 | 10075.24 | 18279.9573 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 4 | 7659.2 | 5.6 | 3167.5 | 5718.8693 | august | 1849.43 | 2871.04 | 2666.14 | 2250.49 | both | TRUE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 16 | 30636.8 | 18.3 | 10310.44 | 18688.448 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 1 | 1914.8 | 0.4 | 235.2 | 408.4907 | september | 1856.64 | 4377.51 | 4443.33 | 2966.71 | both | TRUE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 16 | 30636.8 | 27.7 | 15568.75 | 28287.9787 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 9.4 | 5258.31 | 9599.5307 | october | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 30636.8 | 1914.8 | 30 | 16884 | 562.8 | 16 | 30636.8 | 30 | 16883.86 | 30636.8 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 2.3 | 1315.11 | 2348.8213 | november | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 26060 | 26060 | 1 | 18189 | 18189 | 0.5 | 13030 | 0.3 | 5968.45 | 7818 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0.5 | 13030 | 0.3 | 5968.45 | 7818 | april | 2795.89 | 6430.91 | 6909.43 | 4997.97 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 26060 | 26060 | 1 | 18189 | 18189 | 1 | 26060 | 0.9 | 16540.17 | 23454 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0.5 | 13030 | 0.6 | 10571.72 | 15636 | may | 10491.91 | 9244.62 | 10266.76 | 9577.5 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 26060 | 26060 | 1 | 18189 | 18189 | 1 | 26060 | 0.98 | 17953.64 | 25538.8 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 0.08 | 1413.47 | 2084.8 | june | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 26060 | 26060 | 1 | 18189 | 18189 | 1 | 26060 | 1 | 18142.96 | 26060 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 0.02 | 189.32 | 521.2 | july | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 26060 | 26060 | 1 | 18189 | 18189 | 1 | 26060 | 1 | 18188.8 | 26060 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-08-01 | 0 | 0 | 0 | 45.84 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 0 | 0 | 0.02 | 98 | 78.2222 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0.02 | 98 | 78.2222 | may | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 0.25 | 1056 | 0.6 | 2503.936 | 2346.6667 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.25 | 1056 | 0.58 | 2405.94 | 2268.4444 | june | 1158.64 | 1734.21 | 2561.66 | 1381.98 | both | TRUE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 0.5 | 2112 | 0.7 | 3037.006 | 2737.7778 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.25 | 1056 | 0.1 | 533.07 | 391.1111 | july | 1158.64 | 1435.23 | 1883.42 | 944.98 | both | TRUE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 0.75 | 3168 | 1.02 | 4319.696 | 3989.3333 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.25 | 1056 | 0.32 | 1282.69 | 1251.5556 | august | 645.88 | 1369.72 | 1700.12 | 870.57 | both | TRUE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 1 | 4224 | 1 | 4374.156 | 3911.1111 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0.25 | 1056 | -0.02 | 54.46 | -78.2222 | september | 609.44 | 392.89 | -1110.78 | 81.49 | both | TRUE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 1 | 4224 | 1 | 4428.606 | 3911.1111 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 54.45 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 4224 | 4224 | 1.08 | 4559 | 4221.2963 | 1 | 4224 | 1.08 | 4558.836 | 4224 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0.08 | 130.23 | 312.8889 | november | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 0.25 | 3475 | 0 | 0 | 0 | 2011-04-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0.25 | 3475 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 1 | 13900 | 0.2 | 2425.73 | 2780 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0.75 | 10425 | 0.2 | 2425.73 | 2780 | may | 2514.97 | 4949.99 | 5576.45 | 4501.79 | both | TRUE
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 1 | 13900 | 0.5 | 4334.78 | 6950 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 0.3 | 1909.05 | 4170 | june | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 1 | 13900 | 0.5 | 4594.78 | 6950 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 0 | 260 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 1 | 13900 | 1 | 8228.36 | 13900 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 0.5 | 3633.58 | 6950 | october | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13900 | 13900 | 1 | 8228 | 8228 | 1 | 13900 | 1 | 8728.36 | 13900 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-04-01 | 2011-11-01 | 0 | 0 | 0 | 500 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 16740 | 16740 | 1 | 3875 | 3875 | 1 | 16740 | 0 | 350 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-10-01 | 2011-11-01 | 1 | 16740 | 0 | 350 | 0 | october | 2514.97 | 1030.38 | -724.23 | 1672.4 | both | TRUE
910 | De-Establishment & Cleanup | 1 | item | 16740 | 16740 | 1 | 3875 | 3875 | 1 | 16740 | 1 | 3874.9 | 16740 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-10-01 | 2011-11-01 | 0 | 0 | 1 | 3524.9 | 16740 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100.7 | m3 | 15804.83 | 156.95 | 136.5 | 21588 | 158.1538 | 25 | 3923.7402 | 4.5 | 708.96 | 521.0382 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 25 | 3923.74 | 4.5 | 708.96 | 521.0382 | july | 3058.72 | 2324.69 | 1428.48 | 1984.66 | both | TRUE
c25 | 25 Mpa | 100.7 | m3 | 15804.83 | 156.95 | 136.5 | 21588 | 158.1538 | 50 | 7847.4804 | 58 | 9225.8 | 6715.6036 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 25 | 3923.74 | 53.5 | 8516.84 | 6194.5653 | august | 3058.72 | 6185.45 | 7347.24 | 4609.3 | both | TRUE
c25 | 25 Mpa | 100.7 | m3 | 15804.83 | 156.95 | 136.5 | 21588 | 158.1538 | 50 | 7847.4804 | 112 | 16426.64 | 12968.062 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 0 | 0 | 54 | 7200.84 | 6252.4585 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100.7 | m3 | 15804.83 | 156.95 | 136.5 | 21588 | 158.1538 | 100.7 | 15804.8256 | 125 | 18574.52 | 14473.2835 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 50.7 | 7957.35 | 13 | 2147.88 | 1505.2215 | october | 5114.24 | 5122.14 | 4990.3 | 4828.51 | both | TRUE
c25 | 25 Mpa | 100.7 | m3 | 15804.83 | 156.95 | 136.5 | 21588 | 158.1538 | 100.7 | 15804.8256 | 136.5 | 20388.2 | 15804.8256 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-11-01 | 0 | 0 | 11.5 | 1813.68 | 1331.5421 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 51.26 | m3 | 9507.22 | 185.47 | 213 | 39263 | 184.3333 | 0 | 0 | 49 | 9010.3 | 2187.106 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 49 | 9010.3 | 2187.106 | july | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 51.26 | m3 | 9507.22 | 185.47 | 213 | 39263 | 184.3333 | 35 | 6491.466 | 84 | 15597.72 | 3749.3245 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 35 | 6491.47 | 35 | 6587.42 | 1562.2185 | august | 8981.05 | 8532.29 | 9587.28 | 8707.35 | both | TRUE
c32 | 32 Mpa | 51.26 | m3 | 9507.22 | 185.47 | 213 | 39263 | 184.3333 | 51.26 | 9507.2157 | 186 | 34343.428 | 8302.0757 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 16.26 | 3015.75 | 102 | 18745.71 | 4552.7512 | september | 11114.42 | 13763.26 | 16516.14 | 12543.91 | both | TRUE
c32 | 32 Mpa | 51.26 | m3 | 9507.22 | 185.47 | 213 | 39263 | 184.3333 | 51.26 | 9507.2157 | 213 | 39263.228 | 9507.2157 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-10-01 | 0 | 0 | 27 | 4919.8 | 1205.14 | october | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 111 | m3 | 25589.7 | 230.54 | 136 | 25054 | 184.2206 | 8 | 1844.3026 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 8 | 1844.3 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 111 | m3 | 25589.7 | 230.54 | 136 | 25054 | 184.2206 | 8 | 1844.3026 | 7.5 | 1377.4 | 1411.1966 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 7.5 | 1377.4 | 1411.1966 | july | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 111 | m3 | 25589.7 | 230.54 | 136 | 25054 | 184.2206 | 29 | 6685.597 | 9 | 1673.43 | 1693.4359 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 21 | 4841.29 | 1.5 | 296.03 | 282.2393 | august | 3058.72 | 2577.02 | -402.65 | 2330.74 | both | TRUE
ckm | Kerb Mix | 111 | m3 | 25589.7 | 230.54 | 136 | 25054 | 184.2206 | 111 | 25589.6987 | 16 | 2873.13 | 3010.5528 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 82 | 18904.1 | 7 | 1199.7 | 1317.1168 | september | 5114.24 | 3757.99 | -1918.72 | 3863.49 | both | TRUE
ckm | Kerb Mix | 111 | m3 | 25589.7 | 230.54 | 136 | 25054 | 184.2206 | 111 | 25589.6987 | 19 | 3561.83 | 3575.0314 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 3 | 688.7 | 564.4786 | october | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 111 | m3 | 25589.7 | 230.54 | 136 | 25054 | 184.2206 | 111 | 25589.6987 | 136 | 3561.83 | 25589.6987 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 117 | 0 | 22014.6673 | november | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder ( stabilising) | 36 | tonne | 332 | 9.22 | 36 | 12852 | 357 | 0 | 0 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-09-01 | 0 | 0 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder ( stabilising) | 36 | tonne | 332 | 9.22 | 36 | 12852 | 357 | 36 | 332 | 0 | 12852 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-09-01 | 36 | 332 | 0 | 12852 | 0 | august | 5326.7 | 8924.51 | 11918.93 | 7465.13 | both | TRUE
csa | Cement Powder ( stabilising) | 36 | tonne | 332 | 9.22 | 36 | 12852 | 357 | 36 | 332 | 36 | 12852 | 332 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-09-01 | 0 | 0 | 0 | 0 | 332 | september | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1465 | m | 7656.14 | 5.23 | 1465 | 12317 | 8.4075 | 1465 | 7656.1375 | 1465 | 6927.4 | 7656.1375 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 1465 | 7656.14 | 1465 | 6927.4 | 7656.1375 | june | 9322.64 | 12817.67 | 15983.58 | 10160.15 | both | TRUE
etc | Conduits | 1465 | m | 7656.14 | 5.23 | 1465 | 12317 | 8.4075 | 1465 | 7656.1375 | 1465 | 9843.5 | 7656.1375 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 2916.1 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1465 | m | 7656.14 | 5.23 | 1465 | 12317 | 8.4075 | 1465 | 7656.1375 | 1465 | 12304.5 | 7656.1375 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 2461 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1465 | m | 7656.14 | 5.23 | 1465 | 12317 | 8.4075 | 1465 | 7656.1375 | 1465 | 12317.34 | 7656.1375 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 12.84 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.49 | 14766.49 | 1 | 9591 | 9591 | 1 | 14766.488 | 0 | 133.5 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 1 | 14766.49 | 0 | 133.5 | 0 | june | 2795.89 | 1449.67 | 274.72 | 1629.99 | both | TRUE
etm | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.49 | 14766.49 | 1 | 9591 | 9591 | 1 | 14766.488 | 0 | 1367.31 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 1233.81 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.49 | 14766.49 | 1 | 9591 | 9591 | 1 | 14766.488 | 0 | 7011.31 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 5644 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.49 | 14766.49 | 1 | 9591 | 9591 | 1 | 14766.488 | 0.75 | 8711.31 | 11074.866 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 1700 | 11074.866 | september | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.49 | 14766.49 | 1 | 9591 | 9591 | 1 | 14766.488 | 1 | 8711.31 | 14766.488 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0.25 | 0 | 3691.622 | october | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 1 | item | 14766.49 | 14766.49 | 1 | 9591 | 9591 | 1 | 14766.488 | 1 | 9591.31 | 14766.488 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 880 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 21 | each | 17803.8 | 847.8 | 21 | 13861 | 660.0476 | 0 | 0 | 9 | 11286 | 7630.2 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 9 | 11286 | 7630.2 | june | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 21 | each | 17803.8 | 847.8 | 21 | 13861 | 660.0476 | 21 | 17803.8 | 15 | 11286 | 12717 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 21 | 17803.8 | 6 | 0 | 5086.8 | july | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 21 | each | 17803.8 | 847.8 | 21 | 13861 | 660.0476 | 21 | 17803.8 | 21 | 11286 | 17803.8 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 6 | 0 | 5086.8 | august | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 21 | each | 17803.8 | 847.8 | 21 | 13861 | 660.0476 | 21 | 17803.8 | 21 | 13786 | 17803.8 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 2500 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 21 | each | 17803.8 | 847.8 | 21 | 13861 | 660.0476 | 21 | 17803.8 | 21 | 13861 | 17803.8 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 75 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.1 | CBR80 | 7995 | tonne | 170720.16 | 21.35 | 5536 | 120191 | 21.7108 | 2500 | 53383.4135 | 1472 | 31974.728 | 45393.7988 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 2500 | 53383.41 | 1472 | 31974.73 | 45393.7988 | june | 77534.32 | 70132.88 | 77335.98 | 69498.58 | both | TRUE
qm2.1 | CBR80 | 7995 | tonne | 170720.16 | 21.35 | 5536 | 120191 | 21.7108 | 4000 | 85413.4615 | 1472 | 31974.728 | 45393.7988 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 1500 | 32030.05 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.1 | CBR80 | 7995 | tonne | 170720.16 | 21.35 | 5536 | 120191 | 21.7108 | 7000 | 149473.5577 | 2423 | 104735.335 | 74720.9065 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 3000 | 64060.1 | 951 | 72760.61 | 29327.1078 | august | 77534.32 | 75125.18 | 83470.38 | 72760.51 | both | TRUE
qm2.1 | CBR80 | 7995 | tonne | 170720.16 | 21.35 | 5536 | 120191 | 21.7108 | 7995 | 170720.1562 | 5536 | 179448.091 | 170720.1562 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 995 | 21246.6 | 3113 | 74712.76 | 95999.2497 | september | 36035.78 | 54106.13 | 64004.3 | 45447.24 | both | TRUE
qm2.1 | CBR80 | 7995 | tonne | 170720.16 | 21.35 | 5536 | 120191 | 21.7108 | 7995 | 170720.1562 | 5536 | 275197.551 | 170720.1562 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-10-01 | 0 | 0 | 0 | 95749.46 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 9.4 | tonne | 385.4 | 41 | 0 | 0 | 0 | 9.4 | 385.4 | 9.4 | 0 | 385.4 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-11-01 | 2011-11-01 | 9.4 | 385.4 | 9.4 | 0 | 385.4 | november | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 2200 | tonne | 10432.68 | 4.74 | 2297 | 50632 | 22.0427 | 100 | 474.2127 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 100 | 474.21 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 2200 | tonne | 10432.68 | 4.74 | 2297 | 50632 | 22.0427 | 300 | 1422.6381 | 15 | 337.16 | 68.1281 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 200 | 948.43 | 15 | 337.16 | 68.1281 | june | 6869.26 | 1726.06 | 404.13 | 3046 | both | TRUE
qms | Sand | 2200 | tonne | 10432.68 | 4.74 | 2297 | 50632 | 22.0427 | 1300 | 6164.7652 | 51 | 1132.0014 | 231.6355 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 1000 | 4742.13 | 36 | 794.84 | 163.5074 | july | 2472.03 | 1986.58 | 967.19 | 1569.85 | both | TRUE
qms | Sand | 2200 | tonne | 10432.68 | 4.74 | 2297 | 50632 | 22.0427 | 2200 | 10432.6795 | 2297 | 1418.3574 | 10432.6795 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 900 | 4267.91 | 2246 | 286.36 | 10201.0441 | august | 2472.03 | 3607.4 | 3419.87 | 2749.39 | both | TRUE
qms | Sand | 2200 | tonne | 10432.68 | 4.74 | 2297 | 50632 | 22.0427 | 2200 | 10432.6795 | 2297 | 117805.621 | 10432.6795 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 116387.26 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 2200 | tonne | 10432.68 | 4.74 | 2297 | 50632 | 22.0427 | 2200 | 10432.6795 | 2297 | 117965.4818 | 10432.6795 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 159.86 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | item | 840 | 840 | 1 | 4982 | 4982 | 0 | 0 | 0 | 132.8 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0 | 0 | 0 | 132.8 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | item | 840 | 840 | 1 | 4982 | 4982 | 0 | 0 | 0.5 | 2814.84 | 420 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 0 | 0 | 0.5 | 2682.04 | 420 | august | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | item | 840 | 840 | 1 | 4982 | 4982 | 1 | 840 | 1 | 4982.43 | 840 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-09-01 | 1 | 840 | 0.5 | 2167.59 | 420 | september | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 750 | m | 1243.65 | 1.66 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 750 | 1243.65 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 750 | m | 1243.65 | 1.66 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 1243.65 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 1243.65 | september | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 750 | m | 1243.65 | 1.66 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 0 | 0 | -1243.65 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 750 | m | 1243.65 | 1.66 | 0 | 0 | 0 | 750 | 1243.65 | 0 | 0 | 1243.65 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-08-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 1243.65 | november | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1009 | m2 | 7815.02 | 7.75 | 1009 | 2626 | 2.6026 | 500 | 3872.6554 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-09-01 | 500 | 3872.66 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1009 | m2 | 7815.02 | 7.75 | 1009 | 2626 | 2.6026 | 500 | 3872.6554 | 0 | 136.65 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-09-01 | 0 | 0 | 0 | 136.65 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1009 | m2 | 7815.02 | 7.75 | 1009 | 2626 | 2.6026 | 1009 | 7815.0187 | 1009 | 2625.85 | 7815.0187 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-09-01 | 509 | 3942.36 | 1009 | 2489.2 | 7815.0187 | september | 7179.81 | 5250.81 | 4304.8 | 5096.31 | both | TRUE
swh | Headwalls | 4 | each | 1378 | 344.5 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 4 | 1378 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 4 | each | 1378 | 344.5 | 0 | 0 | 0 | 4 | 1378 | 0 | 0 | 1378 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 1378 | november | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 13 | each | 17624 | 1355.69 | 13 | 17615 | 1355 | 0 | 0 | 12 | 16131 | 16268.3077 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-08-01 | 0 | 0 | 12 | 16131 | 16268.3077 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 13 | each | 17624 | 1355.69 | 13 | 17615 | 1355 | 13 | 17624 | 13 | 17615 | 17624 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-07-01 | 2011-08-01 | 13 | 17624 | 1 | 1484 | 1355.6923 | august | 2795.89 | 3631.56 | 1683.47 | 2982.59 | both | TRUE
swp | RCP | 197.6 | m | 15635.44 | 79.13 | 197.6 | 13684 | 69.251 | 100 | 7912.6733 | 183 | 12762 | 14480.1921 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 100 | 7912.67 | 183 | 12762 | 14480.1921 | june | 5114.24 | 6268.94 | 4543.23 | 4948.47 | both | TRUE
swp | RCP | 197.6 | m | 15635.44 | 79.13 | 197.6 | 13684 | 69.251 | 197.6 | 15635.4424 | 183 | 12762 | 14480.1921 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 97.6 | 7722.77 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 197.6 | m | 15635.44 | 79.13 | 197.6 | 13684 | 69.251 | 197.6 | 15635.4424 | 197.6 | 13464 | 15635.4424 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 14.6 | 702 | 1155.2503 | august | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 197.6 | m | 15635.44 | 79.13 | 197.6 | 13684 | 69.251 | 197.6 | 15635.4424 | 197.6 | 13684 | 15635.4424 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 220 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 25 | 81.1966 | 0 | 0 | 0 | 2011-05-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 25 | 81.2 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 50 | 162.3932 | 0 | 0 | 0 | 2011-06-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 25 | 81.2 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 75 | 243.5897 | 0 | 0 | 0 | 2011-07-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 25 | 81.2 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 100 | 324.7863 | 0 | 0 | 0 | 2011-08-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 25 | 81.2 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 117 | 380 | 0 | 0 | 0 | 2011-09-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 17 | 55.21 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 117 | 380 | 0 | 0 | 0 | 2011-10-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
ww | Wet Weather Allowance for labourers for down time | 117 | hrs | 380 | 3.25 | 0 | 0 | 0 | 117 | 380 | 0 | 0 | 380 | 2011-11-01 | P018 - P01 Airport Carpark | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 380 | november | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 110 | hrs | 20350 | 185 | 103 | 19038.5 | 184.8398 | 20 | 3700 | 16 | 2954.4 | 3161.165 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 20 | 3700 | 16 | 2954.4 | 3161.165 | april | 3058.72 | 2602.61 | 1185.71 | 2890.07 | both | TRUE
11 | Survey - Construction | 110 | hrs | 20350 | 185 | 103 | 19038.5 | 184.8398 | 40 | 7400 | 59.5 | 11016.8 | 11755.5825 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 20 | 3700 | 43.5 | 8062.4 | 8594.4175 | may | 3058.72 | 4073.67 | 4196.78 | 4194.71 | both | TRUE
11 | Survey - Construction | 110 | hrs | 20350 | 185 | 103 | 19038.5 | 184.8398 | 70 | 12950 | 91 | 16842.3 | 17979.1262 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 30 | 5550 | 31.5 | 5825.5 | 6223.5437 | june | 3058.72 | 5431.2 | 6723.6 | 4721.49 | both | TRUE
11 | Survey - Construction | 110 | hrs | 20350 | 185 | 103 | 19038.5 | 184.8398 | 110 | 20350 | 103 | 19038.5 | 20350 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 40 | 7400 | 12 | 2196.2 | 2370.8738 | july | 13406.07 | 7306.86 | 6879.93 | 8962.06 | both | TRUE
13 | QA Testing | 1 | item | 5460 | 5460 | 1 | 11878.85 | 11878.85 | 0.5 | 2730 | 0.65 | 7389.85 | 3549 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 0.5 | 2730 | 0.65 | 7389.85 | 3549 | may | 5795.74 | 5238.29 | 6413.82 | 5609.06 | both | TRUE
13 | QA Testing | 1 | item | 5460 | 5460 | 1 | 11878.85 | 11878.85 | 1 | 5460 | 0.65 | 7389.85 | 3549 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 0.5 | 2730 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 5460 | 5460 | 1 | 11878.85 | 11878.85 | 1 | 5460 | 1 | 11878.85 | 5460 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 0 | 0 | 0.35 | 4489 | 1911 | july | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 2500 | m3 | 20012 | 8 | 2500 | 8287.17 | 3.3149 | 2500 | 20012 | 2500 | 8287.17 | 20012 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 2500 | 20012 | 2500 | 8287.17 | 20012 | april | 6413.21 | 14802.4 | 12528.69 | 11532.03 | both | TRUE
51 | Cut to Fill | 22919 | m3 | 244936.52 | 10.69 | 22919 | 292965.585 | 12.7827 | 0 | 0 | 1400 | 34066.54 | 14961.871 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-06-01 | 0 | 0 | 1400 | 34066.54 | 14961.871 | april | 0 | 0 | 0 | 0 | left_only | FALSE
51 | Cut to Fill | 22919 | m3 | 244936.52 | 10.69 | 22919 | 292965.585 | 12.7827 | 16000 | 170992.8116 | 12500 | 169440.325 | 133588.134 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-06-01 | 16000 | 170992.81 | 11100 | 135373.79 | 118626.263 | may | 112816.37 | 125082.28 | 140034.53 | 116861.5 | both | TRUE
51 | Cut to Fill | 22919 | m3 | 244936.52 | 10.69 | 22919 | 292965.585 | 12.7827 | 22919 | 244936.5155 | 22919 | 292965.585 | 244936.5155 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-06-01 | 6919 | 73943.7 | 10419 | 123525.26 | 111348.3815 | june | 96278.32 | 105444.55 | 127093.03 | 97822.91 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 86600 | m2 | 138448.83 | 1.6 | 86600 | 105179.34 | 1.2145 | 10000 | 15987.1632 | 5000 | 6900 | 7993.5816 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 10000 | 15987.16 | 5000 | 6900 | 7993.5816 | april | 4191.71 | 16371.4 | 24079.75 | 9150.12 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 86600 | m2 | 138448.83 | 1.6 | 86600 | 105179.34 | 1.2145 | 45000 | 71942.2344 | 49500 | 62115 | 79136.4579 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 35000 | 55955.07 | 44500 | 55215 | 71142.8763 | may | 50751.9 | 44884.24 | 47516.32 | 40128.76 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 86600 | m2 | 138448.83 | 1.6 | 86600 | 105179.34 | 1.2145 | 86600 | 138448.8333 | 82500 | 99312.8 | 131894.0964 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 41600 | 66506.6 | 33000 | 37197.8 | 52757.6386 | june | 50751.9 | 45249.51 | 45613.26 | 39352.24 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 86600 | m2 | 138448.83 | 1.6 | 86600 | 105179.34 | 1.2145 | 86600 | 138448.8333 | 86600 | 105179.34 | 138448.8333 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 4100 | 5866.54 | 6554.7369 | july | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 1056 | tonne | 6320.13 | 5.98 | 641 | 3632.5 | 5.6669 | 1056 | 6320.1284 | 641 | 3632.5 | 6320.1284 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-06-01 | 1056 | 6320.13 | 641 | 3632.5 | 6320.1284 | june | 9322.64 | 8736.33 | 5933.35 | 7859.18 | both | TRUE
91 | InstallLeachate Pipes | 740 | m | 14825 | 20.03 | 740 | 11473.04 | 15.5041 | 740 | 14825 | 245 | 3235.4 | 4908.277 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-07-01 | 740 | 14825 | 245 | 3235.4 | 4908.277 | june | 0 | 0 | 0 | 0 | left_only | FALSE
91 | InstallLeachate Pipes | 740 | m | 14825 | 20.03 | 740 | 11473.04 | 15.5041 | 740 | 14825 | 740 | 11473.04 | 14825 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-07-01 | 0 | 0 | 495 | 8237.64 | 9916.723 | july | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 300 | m | 2970 | 9.9 | 300 | 18430 | 61.4333 | 300 | 2970 | 300 | 18430 | 2970 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-06-01 | 300 | 2970 | 300 | 18430 | 2970 | june | 12590.7 | 12597.23 | 15799.07 | 11230.29 | both | TRUE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14239 | 14239 | 0 | 0 | 0 | 1 | 14238.9998 | 0 | 0 | 0 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 1 | 14239 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14239 | 14239 | 0 | 0 | 0 | 1 | 14238.9998 | 0 | 0 | 14238.9998 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0 | 0 | 14238.9998 | may | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14239 | 14239 | 0 | 0 | 0 | 1 | 14238.9998 | 0 | 0 | 14238.9998 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14239 | 14239 | 0 | 0 | 0 | 1 | 14238.9998 | 0 | 0 | 14238.9998 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
161 | Supply & Place A64 Protection Geotextile | 15960 | m2 | 50804.59 | 3.18 | 15960 | 48447.015 | 3.0355 | 7500 | 23874.3384 | 0 | 0 | 0 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 7500 | 23874.34 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
161 | Supply & Place A64 Protection Geotextile | 15960 | m2 | 50804.59 | 3.18 | 15960 | 48447.015 | 3.0355 | 15960 | 50804.5921 | 12550 | 38097 | 39949.7262 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 8460 | 26930.25 | 12550 | 38097 | 39949.7262 | june | 0 | 0 | 0 | 0 | left_only | FALSE
161 | Supply & Place A64 Protection Geotextile | 15960 | m2 | 50804.59 | 3.18 | 15960 | 48447.015 | 3.0355 | 15960 | 50804.5921 | 15960 | 48447.015 | 50804.5921 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 0 | 0 | 3410 | 10350.01 | 10854.8658 | july | 0 | 0 | 0 | 0 | left_only | FALSE
162 | Supply & Place A24 Separation Geotextile | 15960 | m2 | 27502.99 | 1.72 | 15960 | 16222.5 | 1.0164 | 15960 | 27502.9921 | 15960 | 16222.5 | 27502.9921 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-06-01 | 15960 | 27502.99 | 15960 | 16222.5 | 27502.9921 | june | 0 | 0 | 0 | 0 | left_only | FALSE
191 | Dayworks | 0 | none | 0 | 0 | 1 | 7230 | 7230 | 0 | 0 | 0 | 7230 | 0 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-07-01 | 0 | 0 | 0 | 7230 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
191 | Dayworks | 0 | none | 0 | 0 | 1 | 7230 | 7230 | 0 | 0 | 1 | 7230 | 0 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-07-01 | 0 | 0 | 1 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Construct Spillway | 1 | item | 1512.5 | 1512.5 | 1 | 1180.15 | 1180.15 | 1 | 1512.5045 | 1 | 1180.15 | 1512.5045 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-06-01 | 1 | 1512.5 | 1 | 1180.15 | 1512.5045 | june | 409.36 | 2212.74 | 3361.42 | 1376.2 | both | TRUE
222 | Supply & Install HDPE Liner | 3400 | m2 | 40831 | 12.01 | 3400 | 36108.2 | 10.6201 | 0 | 0 | 2880 | 30608.2 | 34586.2588 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-06-01 | 0 | 0 | 2880 | 30608.2 | 34586.2588 | may | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Install HDPE Liner | 3400 | m2 | 40831 | 12.01 | 3400 | 36108.2 | 10.6201 | 3400 | 40831 | 3400 | 36108.2 | 40831 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-06-01 | 3400 | 40831 | 520 | 5500 | 6244.7412 | june | 5410.44 | 16639.78 | 11113.22 | 12269.81 | both | TRUE
223 | Supply & Place GCL Liner | 16118 | m2 | 140573.16 | 8.72 | 16118 | 141962.25 | 8.8077 | 16118 | 140573.1568 | 3100 | 28403.76 | 27036.6538 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-07-01 | 16118 | 140573.16 | 3100 | 28403.76 | 27036.6538 | june | 0 | 0 | 0 | 0 | left_only | FALSE
223 | Supply & Place GCL Liner | 16118 | m2 | 140573.16 | 8.72 | 16118 | 141962.25 | 8.8077 | 16118 | 140573.1568 | 16118 | 141962.25 | 140573.1568 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-07-01 | 0 | 0 | 13018 | 113558.49 | 113536.503 | july | 0 | 0 | 0 | 0 | left_only | FALSE
224 | Place Drainage Gravel | 6008 | tonne | 30776.01 | 5.12 | 6656 | 11791.5 | 1.7716 | 2000 | 10245.0115 | 0 | 0 | 0 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 2000 | 10245.01 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
224 | Place Drainage Gravel | 6008 | tonne | 30776.01 | 5.12 | 6656 | 11791.5 | 1.7716 | 6008 | 30776.0146 | 4000 | 6132 | 18495.2011 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 4008 | 20531 | 4000 | 6132 | 18495.2011 | june | 0 | 0 | 0 | 0 | left_only | FALSE
224 | Place Drainage Gravel | 6008 | tonne | 30776.01 | 5.12 | 6656 | 11791.5 | 1.7716 | 6008 | 30776.0146 | 6656 | 11791.5 | 30776.0146 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 0 | 0 | 2656 | 5659.5 | 12280.8135 | july | 0 | 0 | 0 | 0 | left_only | FALSE
510 | High Energy Compaction | 20000 | m2 | 28424.12 | 1.42 | 20000 | 25880 | 1.294 | 20000 | 28424.12 | 20000 | 25880 | 28424.12 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-05-01 | 20000 | 28424.12 | 20000 | 25880 | 28424.12 | may | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 7.2 | weeks | 22750 | 3159.72 | 0.5 | 1359.33 | 2718.66 | 2 | 6319.4444 | 0.4 | 954.33 | 18200 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 2 | 6319.44 | 0.4 | 954.33 | 18200 | april | 589.26 | 2702.55 | 481.35 | 1861.18 | both | TRUE
901 | Project Management | 7.2 | weeks | 22750 | 3159.72 | 0.5 | 1359.33 | 2718.66 | 4 | 12638.8889 | 0.4 | 954.33 | 18200 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 2 | 6319.44 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 7.2 | weeks | 22750 | 3159.72 | 0.5 | 1359.33 | 2718.66 | 7.2 | 22750 | 1 | 1359.33 | 45500 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 3.2 | 10111.11 | 0.6 | 405 | 27300 | june | 1849.43 | 2008.85 | -74.64 | 1848.98 | both | TRUE
901 | Project Management | 7.2 | weeks | 22750 | 3159.72 | 0.5 | 1359.33 | 2718.66 | 7.2 | 22750 | 0.5 | 1359.33 | 22750 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | -0.5 | 0 | -22750 | july | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 12 | weeks | 40200 | 3350 | 16 | 42014.91 | 2625.9319 | 3 | 10050 | 3.3 | 8554.76 | 8291.25 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 3 | 10050 | 3.3 | 8554.76 | 8291.25 | april | 7116.63 | 10053.69 | 10005.63 | 9177.04 | both | TRUE
902 | Project Supervision | 12 | weeks | 40200 | 3350 | 16 | 42014.91 | 2625.9319 | 6 | 20100 | 8.8 | 22594.225 | 22110 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 3 | 10050 | 5.5 | 14039.46 | 13818.75 | may | 11719.06 | 13898.84 | 15713.1 | 13456.06 | both | TRUE
902 | Project Supervision | 12 | weeks | 40200 | 3350 | 16 | 42014.91 | 2625.9319 | 12 | 40200 | 14.5 | 37978.995 | 36431.25 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 6 | 20100 | 5.7 | 15384.77 | 14321.25 | june | 11719.06 | 15572.62 | 17796.76 | 14351.55 | both | TRUE
902 | Project Supervision | 12 | weeks | 40200 | 3350 | 16 | 42014.91 | 2625.9319 | 12 | 40200 | 16 | 42014.91 | 40200 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 1.5 | 4035.92 | 3768.75 | july | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 12 | weeks | 15000 | 1250 | 16 | 12881.8 | 805.1125 | 3 | 3750 | 3.6 | 2875.04 | 3375 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 3 | 3750 | 3.6 | 2875.04 | 3375 | april | 1899.18 | 2961.62 | 2558.18 | 2457.77 | both | TRUE
903 | Project Facilities | 12 | weeks | 15000 | 1250 | 16 | 12881.8 | 805.1125 | 6 | 7500 | 9.9 | 8006.04 | 9281.25 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 3 | 3750 | 6.3 | 5131 | 5906.25 | may | 1899.18 | 3054.18 | 3385.19 | 2871.08 | both | TRUE
903 | Project Facilities | 12 | weeks | 15000 | 1250 | 16 | 12881.8 | 805.1125 | 12 | 15000 | 13.8 | 11155.56 | 12937.5 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 6 | 7500 | 3.9 | 3149.52 | 3656.25 | june | 1849.43 | 3294.13 | 3935.56 | 2698.4 | both | TRUE
903 | Project Facilities | 12 | weeks | 15000 | 1250 | 16 | 12881.8 | 805.1125 | 12 | 15000 | 16 | 12881.8 | 15000 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 2.2 | 1726.24 | 2062.5 | july | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 24843.75 | 24843.75 | 1 | 6981.2 | 6981.2 | 0.75 | 18632.8125 | 0.9 | 4736.04 | 22359.375 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0.75 | 18632.81 | 0.9 | 4736.04 | 22359.375 | april | 2795.89 | 5131.89 | 4236.64 | 4275.39 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 24843.75 | 24843.75 | 1 | 6981.2 | 6981.2 | 1 | 24843.75 | 0.9 | 4736.04 | 22359.375 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0.25 | 6210.94 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 24843.75 | 24843.75 | 1 | 6981.2 | 6981.2 | 1 | 24843.75 | 0.98 | 5129.73 | 24346.875 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0.08 | 393.69 | 1987.5 | june | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 24843.75 | 24843.75 | 1 | 6981.2 | 6981.2 | 1 | 24843.75 | 1 | 6981.2 | 24843.75 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0.02 | 1851.47 | 496.875 | july | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 614.9 | 614.9 | 0.25 | 1456 | 0.01 | 68.4 | 58.24 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-06-01 | 0.25 | 1456 | 0.01 | 68.4 | 58.24 | april | 409.36 | 442.37 | -672.49 | 345.82 | both | TRUE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 614.9 | 614.9 | 0.75 | 4368 | 0.06 | 349.82 | 349.44 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-06-01 | 0.5 | 2912 | 0.05 | 281.42 | 291.2 | may | 5795.74 | 3968.11 | 4179.4 | 4692.44 | both | TRUE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 614.9 | 614.9 | 1 | 5824 | 1 | 614.9 | 5824 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-06-01 | 0.25 | 1456 | 0.94 | 265.08 | 5474.56 | june | 409.36 | 740.81 | 1072.95 | 505.67 | both | TRUE
907 | Site Establishment | 1 | item | 18995 | 18995 | 1 | 27660.31 | 27660.31 | 0.25 | 4748.75 | 0.25 | 8330.655 | 4748.75 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0.25 | 4748.75 | 0.25 | 8330.66 | 4748.75 | april | 5051.4 | 6611.08 | 7462.24 | 5878.31 | both | TRUE
907 | Site Establishment | 1 | item | 18995 | 18995 | 1 | 27660.31 | 27660.31 | 1 | 18995 | 0.9 | 23383.375 | 17095.5 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0.75 | 14246.25 | 0.65 | 15052.72 | 12346.75 | may | 10491.91 | 10475.95 | 11910.95 | 10621.29 | both | TRUE
907 | Site Establishment | 1 | item | 18995 | 18995 | 1 | 27660.31 | 27660.31 | 1 | 18995 | 0.95 | 25178.49 | 18045.25 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0.05 | 1795.12 | 949.75 | june | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 18995 | 18995 | 1 | 27660.31 | 27660.31 | 1 | 18995 | 1 | 27660.31 | 18995 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 0 | 0 | 0.05 | 2481.82 | 949.75 | july | 0 | 0 | 0 | 0 | left_only | FALSE
910 | Site de-Establishment | 1 | item | 0 | 0 | 1 | 2117.6 | 2117.6 | 0 | 0 | 1 | 2117.6 | 0 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-07-01 | 2011-07-01 | 0 | 0 | 1 | 2117.6 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 84 | days | 10500 | 125 | 84 | 4579.81 | 54.5215 | 24 | 3000 | 24 | 1040 | 3000 | 2011-04-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 24 | 3000 | 24 | 1040 | 3000 | april | 1899.18 | 3500.98 | 2572.64 | 2382.28 | both | TRUE
911 | Accommodation | 84 | days | 10500 | 125 | 84 | 4579.81 | 54.5215 | 48 | 6000 | 48 | 3191.24 | 6000 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 24 | 3000 | 24 | 2151.24 | 3000 | may | 1899.18 | 2862.02 | 2240.64 | 2322.6 | both | TRUE
911 | Accommodation | 84 | days | 10500 | 125 | 84 | 4579.81 | 54.5215 | 72 | 9000 | 72 | 4231.24 | 9000 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 24 | 3000 | 24 | 1040 | 3000 | june | 1899.18 | 1999.4 | 1466.15 | 1378.25 | both | TRUE
911 | Accommodation | 84 | days | 10500 | 125 | 84 | 4579.81 | 54.5215 | 84 | 10500 | 84 | 4579.81 | 10500 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-04-01 | 2011-07-01 | 12 | 1500 | 12 | 348.57 | 1500 | july | 958.97 | 1282.54 | 519.87 | 348.67 | both | TRUE
qm2.3 | CBR 45 | 1056 | tonne | 29884.8 | 28.3 | 641 | 14753.12 | 23.0158 | 1056 | 29884.8 | 641 | 14753.12 | 29884.8 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-06-01 | 1056 | 29884.8 | 641 | 14753.12 | 29884.8 | june | 13330.1 | 17559.1 | 18670.52 | 15664.68 | both | TRUE
qmd40 | 40mm Drainage Aggregate | 6008 | tonne | 166421.25 | 27.7 | 6656 | 187089.96 | 28.1085 | 2000 | 55399.8835 | 0 | 0 | 0 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 2000 | 55399.88 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
qmd40 | 40mm Drainage Aggregate | 6008 | tonne | 166421.25 | 27.7 | 6656 | 187089.96 | 28.1085 | 6008 | 166421.25 | 5313 | 150155.81 | 132841.9623 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 4008 | 111021.37 | 5313 | 150155.81 | 132841.9623 | june | 0 | 0 | 0 | 0 | left_only | FALSE
qmd40 | 40mm Drainage Aggregate | 6008 | tonne | 166421.25 | 27.7 | 6656 | 187089.96 | 28.1085 | 6008 | 166421.25 | 6656 | 187089.96 | 166421.25 | 2011-07-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-07-01 | 0 | 0 | 1343 | 36934.15 | 33579.2877 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 37 | tonne | 21862.5 | 590.88 | 62 | 1741.04 | 28.0813 | 37 | 21862.5 | 62 | 1741.04 | 21862.5 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-06-01 | 2011-06-01 | 37 | 21862.5 | 62 | 1741.04 | 21862.5 | june | 1849.43 | 6680.86 | 5444.79 | 5085.54 | both | TRUE
spf | Supply HDPE Leachate Pipe | 740 | m | 16946 | 22.9 | 740 | 23479.5 | 31.7291 | 0 | 0 | 740 | 23479.5 | 16946 | 2011-05-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-06-01 | 0 | 0 | 740 | 23479.5 | 16946 | may | 0 | 0 | 0 | 0 | left_only | FALSE
spf | Supply HDPE Leachate Pipe | 740 | m | 16946 | 22.9 | 740 | 23479.5 | 31.7291 | 740 | 16946 | 740 | 23479.5 | 16946 | 2011-06-01 | P019 - P02 Landfill Cell | 2011-05-01 | 2011-06-01 | 740 | 16946 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 24 | 3486.0477 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 74 | 10748.6472 | 121 | 27510.7 | 13890.9015 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 50 | 7262.6 | 121 | 27510.7 | 13890.9015 | november | 19644.48 | 22443.07 | 28419.22 | 20828.36 | both | TRUE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 150 | 21787.7984 | 330 | 49553.2 | 37884.2767 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 76 | 11039.15 | 209 | 22042.5 | 23993.3753 | december | 16429.38 | 17133.8 | 21071.2 | 16204.18 | both | TRUE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 250 | 36312.9973 | 423 | 63518.2 | 48560.7547 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 100 | 14525.2 | 93 | 13965 | 10676.478 | january | 16429.38 | 14117.61 | 15608.11 | 14368.53 | both | TRUE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 325 | 47206.8966 | 423 | 63518.2 | 48560.7547 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 75 | 10893.9 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 377 | 54760 | 423 | 63518.2 | 48560.7547 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 52 | 7553.1 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 377 | hrs | 54760 | 145.25 | 477 | 71680.95 | 150.2745 | 377 | 54760 | 477 | 71680.95 | 54760 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 54 | 8162.75 | 6199.2453 | june | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 37361.67 | 37361.67 | 1 | 12680 | 12680 | 0 | 0 | 0 | 200 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 37361.67 | 37361.67 | 1 | 12680 | 12680 | 0.2 | 7472.3333 | 0 | 350 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0.2 | 7472.33 | 0 | 150 | 0 | november | 19644.48 | 10461.14 | 9813.91 | 12901.65 | both | TRUE
13 | QA Testing | 1 | item | 37361.67 | 37361.67 | 1 | 12680 | 12680 | 0.5 | 18680.8333 | 0 | 350 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0.3 | 11208.5 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 37361.67 | 37361.67 | 1 | 12680 | 12680 | 0.7 | 26153.1667 | 0 | 350 | 0 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0.2 | 7472.33 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 37361.67 | 37361.67 | 1 | 12680 | 12680 | 1 | 37361.6667 | 1 | 12680 | 37361.6667 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0.3 | 11208.5 | 1 | 12330 | 37361.6667 | february | 16429.38 | 10882.76 | 11534.59 | 12182.28 | both | TRUE
15 | Service Locations | 20 | hrs | 6800 | 340 | 12 | 4080 | 340 | 20 | 6800 | 3.6 | 1260 | 2040 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 20 | hrs | 6800 | 340 | 12 | 4080 | 340 | 20 | 6800 | 8.8 | 3010 | 4986.6667 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-01-01 | 0 | 0 | 5.2 | 1750 | 2946.6667 | december | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 20 | hrs | 6800 | 340 | 12 | 4080 | 340 | 20 | 6800 | 12 | 4080 | 6800 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-01-01 | 0 | 0 | 3.2 | 1070 | 1813.3333 | january | 0 | 0 | 0 | 0 | left_only | FALSE
21 | Clearing to Stockpile | 16000 | m2 | 24842.93 | 1.55 | 16000 | 1562.955 | 0.097685 | 2000 | 3105.3658 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
21 | Clearing to Stockpile | 16000 | m2 | 24842.93 | 1.55 | 16000 | 1562.955 | 0.097685 | 16000 | 24842.9261 | 16000 | 1520.005 | 24842.9261 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-01-01 | 14000 | 21737.56 | 16000 | 1520 | 24842.9261 | november | 5410.44 | 14230.04 | 2100.88 | 9286.65 | both | TRUE
21 | Clearing to Stockpile | 16000 | m2 | 24842.93 | 1.55 | 16000 | 1562.955 | 0.097685 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-01-01 | 0 | 0 | 0 | 42.95 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 802 | m3 | 18732.1 | 23.36 | 802 | 3969.35 | 4.9493 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2011-12-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 802 | m3 | 18732.1 | 23.36 | 802 | 3969.35 | 4.9493 | 600 | 14014.0376 | 500 | 2656.775 | 11678.3647 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2011-12-01 | 600 | 14014.04 | 500 | 2656.78 | 11678.3647 | november | 1628.04 | 7794.27 | 4874.23 | 6152.18 | both | TRUE
53 | Cut to Spoil | 802 | m3 | 18732.1 | 23.36 | 802 | 3969.35 | 4.9493 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2011-12-01 | 202 | 4718.06 | 302 | 1312.57 | 7053.7323 | december | 3058.72 | 2588.64 | -1757.03 | 2841.19 | both | TRUE
57 | Remove & Replace unsuitable | 153.5 | m3 | 9587.67 | 62.46 | 153 | 4381.225 | 28.6355 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 153.5 | m3 | 9587.67 | 62.46 | 153 | 4381.225 | 28.6355 | 50 | 3123.0212 | 0 | 0 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-03-01 | 50 | 3123.02 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 153.5 | m3 | 9587.67 | 62.46 | 153 | 4381.225 | 28.6355 | 153.5 | 9587.675 | 0 | 0 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-03-01 | 103.5 | 6464.65 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 153.5 | m3 | 9587.67 | 62.46 | 153 | 4381.225 | 28.6355 | 153.5 | 9587.675 | 135 | 3616.465 | 8459.7132 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-03-01 | 0 | 0 | 135 | 3616.47 | 8459.7132 | january | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 153.5 | m3 | 9587.67 | 62.46 | 153 | 4381.225 | 28.6355 | 153.5 | 9587.675 | 153 | 4381.225 | 9587.675 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-03-01 | 0 | 0 | 18 | 764.76 | 1127.9618 | march | 0 | 0 | 0 | 0 | left_only | FALSE
59 | Trim unpaved areas - footpaths, batters, drains etc | 29830 | m2 | 22887.07 | 0.77 | 29830 | 13518.27 | 0.45318 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
59 | Trim unpaved areas - footpaths, batters, drains etc | 29830 | m2 | 22887.07 | 0.77 | 29830 | 13518.27 | 0.45318 | 5000 | 3836.25 | 13600 | 4299.595 | 10434.6 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 5000 | 3836.25 | 13600 | 4299.6 | 10434.6 | november | 4191.71 | 5787.8 | 4976.18 | 4022.29 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 29830 | m2 | 22887.07 | 0.77 | 29830 | 13518.27 | 0.45318 | 20000 | 15345 | 25500 | 8091.27 | 19564.875 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 15000 | 11508.75 | 11900 | 3791.68 | 9130.275 | december | 4191.71 | 6498.4 | 3166.79 | 3109.77 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 29830 | m2 | 22887.07 | 0.77 | 29830 | 13518.27 | 0.45318 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 9830 | 7542.07 | 4330 | 5427 | 3322.1925 | january | 4191.71 | 5088.94 | 2570.37 | 2822.71 | both | TRUE
61 | Subgrade Preparation | 12535 | m2 | 37229.32 | 2.97 | 12535 | 213777.52 | 17.0544 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12535 | m2 | 37229.32 | 2.97 | 12535 | 213777.52 | 17.0544 | 6500 | 19305.1919 | 6000 | 103959.82 | 17820.1771 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 6500 | 19305.19 | 6000 | 103959.82 | 17820.1771 | november | 70121.96 | 87877.38 | 110954.31 | 77849.77 | both | TRUE
61 | Subgrade Preparation | 12535 | m2 | 37229.32 | 2.97 | 12535 | 213777.52 | 17.0544 | 12535 | 37229.32 | 11500 | 198512.82 | 34155.3394 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 6035 | 17924.13 | 5500 | 94553 | 16335.1623 | december | 70121.96 | 80450.76 | 100240.79 | 72821.44 | both | TRUE
61 | Subgrade Preparation | 12535 | m2 | 37229.32 | 2.97 | 12535 | 213777.52 | 17.0544 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 1035 | 15264.7 | 3073.9806 | january | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 4019 | m3 | 131637.15 | 32.75 | 4610 | 102754.37 | 22.2895 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 4019 | m3 | 131637.15 | 32.75 | 4610 | 102754.37 | 22.2895 | 1000 | 32753.7074 | 800 | 18755.945 | 22843.7571 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 1000 | 32753.71 | 800 | 18755.94 | 22843.7571 | november | 36035.78 | 25285.38 | 23375.85 | 27049.1 | both | TRUE
62 | Place & Compact Gravel | 4019 | m3 | 131637.15 | 32.75 | 4610 | 102754.37 | 22.2895 | 3000 | 98261.1223 | 1950 | 44983.34 | 55681.6579 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 2000 | 65507.41 | 1150 | 26227.4 | 32837.9008 | december | 34485.97 | 27737.32 | 24321.61 | 28417.85 | both | TRUE
62 | Place & Compact Gravel | 4019 | m3 | 131637.15 | 32.75 | 4610 | 102754.37 | 22.2895 | 4019 | 131637.1501 | 4500 | 100730.83 | 128496.1335 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 1019 | 33376.03 | 2550 | 55747.49 | 72814.4757 | january | 62249.6 | 43972.81 | 47328.05 | 47130.51 | both | TRUE
62 | Place & Compact Gravel | 4019 | m3 | 131637.15 | 32.75 | 4610 | 102754.37 | 22.2895 | 4019 | 131637.1501 | 4610 | 102754.37 | 131637.1501 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 110 | 2023.54 | 3141.0166 | february | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 9107 | m2 | 75658.85 | 8.31 | 9107 | 21913.25 | 2.4062 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 9107 | m2 | 75658.85 | 8.31 | 9107 | 21913.25 | 2.4062 | 2500 | 20769.4222 | 0 | 0 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 2500 | 20769.42 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 9107 | m2 | 75658.85 | 8.31 | 9107 | 21913.25 | 2.4062 | 9107 | 75658.8513 | 5750 | 14389.575 | 47769.6711 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 6607 | 54889.43 | 5750 | 14389.58 | 47769.6711 | january | 5183.5 | 20895.78 | 18861 | 14689.54 | both | TRUE
63 | Trim All Layers | 9107 | m2 | 75658.85 | 8.31 | 9107 | 21913.25 | 2.4062 | 9107 | 75658.8513 | 9107 | 21913.25 | 75658.8513 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 0 | 0 | 3357 | 7523.67 | 27889.1802 | february | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 25142 | m2 | 217171.38 | 8.64 | 21275 | 277417.806 | 13.0396 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 25142 | m2 | 217171.38 | 8.64 | 21275 | 277417.806 | 13.0396 | 12500 | 107972.4082 | 12535 | 112816.375 | 127955.0311 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-06-01 | 12500 | 107972.41 | 12535 | 112816.38 | 127955.0311 | december | 50751.9 | 71869.48 | 80230.57 | 61591.8 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 25142 | m2 | 217171.38 | 8.64 | 21275 | 277417.806 | 13.0396 | 25142 | 217171.383 | 19500 | 175198.256 | 199052.5015 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-06-01 | 12642 | 109198.97 | 6965 | 62381.88 | 71097.4704 | february | 50751.9 | 72264.1 | 80651.12 | 62050.17 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 25142 | m2 | 217171.38 | 8.64 | 21275 | 277417.806 | 13.0396 | 25142 | 217171.383 | 19500 | 176683.256 | 199052.5015 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-06-01 | 0 | 0 | 0 | 1485 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 25142 | m2 | 217171.38 | 8.64 | 21275 | 277417.806 | 13.0396 | 25142 | 217171.383 | 21275 | 277417.806 | 217171.383 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-06-01 | 0 | 0 | 1775 | 100734.55 | 18118.8815 | june | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 605 | tonne | 296792.99 | 490.57 | 605 | 202459.38 | 334.6436 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 605 | tonne | 296792.99 | 490.57 | 605 | 202459.38 | 334.6436 | 605 | 296792.9945 | 605 | 202459.38 | 296792.9945 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 605 | 296792.99 | 605 | 202459.38 | 296792.9945 | february | 112816.37 | 151263.89 | 187261.5 | 137551.75 | both | TRUE
66 | Linemarking | 1 | item | 35476.8 | 35476.8 | 1 | 5622 | 5622 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 35476.8 | 35476.8 | 1 | 5622 | 5622 | 1 | 35476.8 | 0 | 0 | 0 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-06-01 | 1 | 35476.8 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 35476.8 | 35476.8 | 1 | 5622 | 5622 | 1 | 35476.8 | 1 | 5622 | 35476.8 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-06-01 | 0 | 0 | 1 | 5622 | 35476.8 | june | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 33024 | 33024 | 1 | 2209.45 | 2209.45 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 33024 | 33024 | 1 | 2209.45 | 2209.45 | 1 | 33024 | 1 | 2209.45 | 33024 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 1 | 33024 | 1 | 2209.45 | 33024 | february | 14412.59 | 7232.89 | 3032.17 | 9446.71 | both | TRUE
68 | Insitu Stabilisation of Subgrade (cement/lime) | 600 | m2 | 13641.07 | 22.74 | 12535 | 51538.065 | 4.1115 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-06-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation of Subgrade (cement/lime) | 600 | m2 | 13641.07 | 22.74 | 12535 | 51538.065 | 4.1115 | 600 | 13641.0744 | 12535 | 51538.065 | 13641.0744 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2012-06-01 | 2012-06-01 | 600 | 13641.07 | 12535 | 51538.06 | 13641.0744 | june | 29799.52 | 35239.88 | 47727.24 | 32916.47 | both | TRUE
71 | Place Kerb & Channel / Inverts | 134 | m | 6700 | 50 | 134 | 4537.241 | 33.86 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 134 | m | 6700 | 50 | 134 | 4537.241 | 33.86 | 134 | 6700.0025 | 0 | 0 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 134 | 6700 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 134 | m | 6700 | 50 | 134 | 4537.241 | 33.86 | 134 | 6700.0025 | 46 | 1562.241 | 2300.0009 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 0 | 0 | 46 | 1562.24 | 2300.0009 | february | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 134 | m | 6700 | 50 | 134 | 4537.241 | 33.86 | 134 | 6700.0025 | 134 | 4537.241 | 6700.0025 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 0 | 0 | 88 | 2975 | 4400.0016 | march | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 11 | each | 32902.26 | 2991.11 | 11 | 18303.345 | 1663.9405 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 11 | each | 32902.26 | 2991.11 | 11 | 18303.345 | 1663.9405 | 11 | 32902.2621 | 8 | 12371.185 | 23928.9179 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 11 | 32902.26 | 8 | 12371.18 | 23928.9179 | november | 13330.1 | 12657.56 | 11584.99 | 12259.4 | both | TRUE
72 | Form & Pour Headwalls | 11 | each | 32902.26 | 2991.11 | 11 | 18303.345 | 1663.9405 | 11 | 32902.2621 | 9.5 | 14502.865 | 28415.59 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 1.5 | 2131.68 | 4486.6721 | december | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 11 | each | 32902.26 | 2991.11 | 11 | 18303.345 | 1663.9405 | 11 | 32902.2621 | 10.5 | 17386.22 | 31406.7047 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 1 | 2883.36 | 2991.1147 | january | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 11 | each | 32902.26 | 2991.11 | 11 | 18303.345 | 1663.9405 | 11 | 32902.2621 | 11 | 18303.345 | 32902.2621 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0.5 | 917.13 | 1495.5574 | february | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 12.2 | m | 31756.3 | 2602.98 | 12.2 | 29127.06 | 2387.4639 | 6.1 | 15878.1486 | 6 | 11906.41 | 15617.8511 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 12.2 | m | 31756.3 | 2602.98 | 12.2 | 29127.06 | 2387.4639 | 12.2 | 31756.2972 | 9.76 | 27821.715 | 25405.0377 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 6.1 | 15878.15 | 3.76 | 15915.3 | 9787.1867 | november | 10491.91 | 13303.05 | 15957.07 | 11742 | both | TRUE
81 | > 450 | 12.2 | m | 31756.3 | 2602.98 | 12.2 | 29127.06 | 2387.4639 | 12.2 | 31756.2972 | 12.2 | 28091.715 | 31756.2972 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 2.44 | 270 | 6351.2594 | january | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 12.2 | m | 31756.3 | 2602.98 | 12.2 | 29127.06 | 2387.4639 | 12.2 | 31756.2972 | 12.2 | 29127.06 | 31756.2972 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 1035.35 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 157 | m | 12960.46 | 82.55 | 157 | 8890.215 | 56.6256 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 157 | m | 12960.46 | 82.55 | 157 | 8890.215 | 56.6256 | 157 | 12960.464 | 35 | 2010.27 | 2889.2754 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 157 | 12960.46 | 35 | 2010.27 | 2889.2754 | december | 8981.05 | 8320.31 | 7121.09 | 7286.82 | both | TRUE
111 | Install Conduits / pits / rag bolts | 157 | m | 12960.46 | 82.55 | 157 | 8890.215 | 56.6256 | 157 | 12960.464 | 130 | 7286.295 | 10731.5944 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 0 | 0 | 95 | 5276.02 | 7842.319 | february | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 157 | m | 12960.46 | 82.55 | 157 | 8890.215 | 56.6256 | 157 | 12960.464 | 157 | 8890.215 | 12960.464 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-03-01 | 0 | 0 | 27 | 1603.92 | 2228.8696 | march | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Lanscaping Sub-contractors | 29830 | none | 29981.05 | 1.01 | 0 | 57433.5525 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Lanscaping Sub-contractors | 29830 | none | 29981.05 | 1.01 | 0 | 57433.5525 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Lanscaping Sub-contractors | 29830 | none | 29981.05 | 1.01 | 0 | 57433.5525 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Lanscaping Sub-contractors | 29830 | none | 29981.05 | 1.01 | 0 | 57433.5525 | 0 | 0 | 0 | 0 | 0 | 0 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Lanscaping Sub-contractors | 29830 | none | 29981.05 | 1.01 | 0 | 57433.5525 | 0 | 29830 | 29981.05 | 0 | 0 | 29981.05 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 50 | 5249.853 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 250 | 26249.2648 | 122 | 12821.645 | 25948.3374 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 200 | 20999.41 | 122 | 12821.64 | 25948.3374 | november | 6137.31 | 12230.38 | 13366.05 | 10309.76 | both | TRUE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 450 | 47248.6766 | 219 | 23008.6915 | 46579.3925 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 200 | 20999.41 | 97 | 10187.05 | 20631.0551 | december | 6137.31 | 10004.43 | 10602.24 | 8612.75 | both | TRUE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 750 | 78747.7943 | 330 | 34629.2515 | 70188.1258 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 300 | 31499.12 | 111 | 11620.56 | 23608.7332 | january | 13119.91 | 11542.23 | 9907.84 | 12035.4 | both | TRUE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 1104 | 115916.7531 | 480 | 50846.5065 | 102091.8193 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 354 | 37168.96 | 150 | 16217.26 | 31903.6935 | february | 13119.91 | 17429.93 | 18818.87 | 16097.02 | both | TRUE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 1104 | 115916.7531 | 481 | 51017.0025 | 102304.5106 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 1 | 170.5 | 212.6913 | march | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 1104 | hrs | 115916.75 | 105 | 545 | 2466.425 | 4.5256 | 1104 | 115916.7531 | 545 | 57433.5525 | 115916.7531 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 64 | 6416.55 | 13612.2426 | june | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 40 | each | 4542.67 | 113.57 | 40 | 23785.751 | 594.6438 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 40 | each | 4542.67 | 113.57 | 40 | 23785.751 | 594.6438 | 40 | 4542.6667 | 0 | 0 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 40 | 4542.67 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 40 | each | 4542.67 | 113.57 | 40 | 23785.751 | 594.6438 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 40 | 2466.43 | 4542.6667 | january | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 59.48 | m | 8767.5 | 147.4 | 59.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 59.48 | m | 8767.5 | 147.4 | 59.48 | 0 | 0 | 40 | 5896.0995 | 44 | 17252.126 | 6485.7095 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 40 | 5896.1 | 44 | 17252.13 | 6485.7095 | november | 9322.64 | 13243.59 | 16962.66 | 10926.86 | both | TRUE
181 | Place Box Culverts | 59.48 | m | 8767.5 | 147.4 | 59.48 | 0 | 0 | 59.48 | 8767.5 | 44 | 17252.126 | 6485.7095 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 19.48 | 2871.4 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 59.48 | m | 8767.5 | 147.4 | 59.48 | 0 | 0 | 59.48 | 8767.5 | 59.48 | 23785.751 | 8767.5 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 15.48 | 6533.63 | 2281.7905 | february | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 1 | 3240 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 3 | 9720 | 1.8 | 5950 | 32400 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 2 | 6480 | 1.8 | 5950 | 32400 | november | 4719.61 | 5160.83 | 3691.98 | 4702.94 | both | TRUE
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 5 | 16200 | 1.8 | 5950 | 32400 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 2 | 6480 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 7 | 22680 | 1.8 | 5950 | 32400 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 2 | 6480 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 9 | 29160 | 1.8 | 5950 | 32400 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 2 | 6480 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 10 | 32400 | 1.8 | 5950 | 32400 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 1 | 3240 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 2 | 6700 | 1.1 | 3721.65 | 3023.5897 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 9 | 30150 | 7.9 | 26574.775 | 21714.8718 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 7 | 23450 | 6.8 | 22853.12 | 18691.2821 | november | 29134.33 | 20180.07 | 19658.08 | 22819.22 | both | TRUE
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 12 | 40200 | 10.5 | 35074.775 | 28861.5385 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 3 | 10050 | 2.6 | 8500 | 7146.6667 | december | 11719.06 | 9249.44 | 8680.31 | 9781.2 | both | TRUE
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 15 | 50250 | 15.8 | 53029.9 | 43429.7436 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 3 | 10050 | 5.3 | 17955.13 | 14568.2051 | january | 11719.06 | 9777.64 | 9241.92 | 10170.95 | both | TRUE
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 16 | 53600 | 18 | 62991.05 | 49476.9231 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 1 | 3350 | 2.2 | 9961.15 | 6047.1795 | february | 5051.4 | 7080.12 | 7536.78 | 6356.96 | both | TRUE
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 16 | 53600 | 19.5 | 65379.85 | 53600 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 0 | 0 | 1.5 | 2388.8 | 4123.0769 | march | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 2 | 3062.5 | 2.7 | 4260.94 | 11025 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 2 | 3062.5 | 2.7 | 4260.94 | 11025 | november | 5051.4 | 3757.06 | 3457.38 | 3902.1 | both | TRUE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 5 | 7656.25 | 4.7 | 7137.94 | 19191.6667 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 3 | 4593.75 | 2 | 2877 | 8166.6667 | december | 5051.4 | 2974.22 | 2803.05 | 3168.57 | both | TRUE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 8 | 12250 | 4.7 | 7137.94 | 19191.6667 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 3 | 4593.75 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 12 | 18375 | 5 | 7347.94 | 20416.6667 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 4 | 6125 | 0.3 | 210 | 1225 | february | 589.26 | 1282.05 | 954.46 | 906.14 | both | TRUE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 16 | 24500 | 5 | 7347.94 | 20416.6667 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 4 | 6125 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 16 | 24500 | 6 | 8814.25 | 24500 | 2012-04-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-04-01 | 0 | 0 | 1 | 1466.31 | 4083.3333 | april | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 25000 | 25000 | 1 | 1203.86 | 1203.86 | 1 | 25000 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 25000 | 25000 | 1 | 1203.86 | 1203.86 | 1 | 25000 | 0 | 60 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 60 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 25000 | 25000 | 1 | 1203.86 | 1203.86 | 1 | 25000 | 0.9 | 1170.86 | 22500 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.9 | 1110.86 | 22500 | february | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 25000 | 25000 | 1 | 1203.86 | 1203.86 | 1 | 25000 | 1 | 1203.86 | 25000 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.1 | 33 | 2500 | june | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 0.25 | 1456 | 0.25 | 3029.05 | 1456 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 0.5 | 2912 | 0.5 | 5050.058 | 2912 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0.25 | 1456 | 0.25 | 2021.01 | 1456 | november | 2681.29 | 1528.08 | 917.13 | 1753.95 | both | TRUE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 0.75 | 4368 | 0.5 | 5821.508 | 2912 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0.25 | 1456 | 0 | 771.45 | 0 | december | 409.36 | 654.95 | 822.5 | 221.18 | both | TRUE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 1 | 5824 | 0.75 | 7695.898 | 4368 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0.25 | 1456 | 0.25 | 1874.39 | 1456 | january | 409.36 | 683.66 | 592.7 | 287.95 | both | TRUE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 1 | 5824 | 0.8 | 8904.81 | 4659.2 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.05 | 1208.91 | 291.2 | february | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 1 | 5824 | 0.9 | 9111.85 | 5241.6 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.1 | 207.04 | 582.4 | march | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 1 | 5824 | 1 | 9544.94 | 5824 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.1 | 433.09 | 582.4 | june | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 0.5 | 9792.5 | 0.1 | 5412.915 | 1958.5 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 0.25 | 10632.845 | 4896.25 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0.5 | 9792.5 | 0.15 | 5219.93 | 2937.75 | november | 4719.61 | 8631.18 | 10537.29 | 7173.98 | both | TRUE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 0.35 | 15208.395 | 6854.75 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.1 | 4575.55 | 1958.5 | december | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 0.7 | 31625.37 | 13709.5 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.35 | 16416.98 | 6854.75 | january | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 0.85 | 37969.525 | 16647.25 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.15 | 6344.16 | 2937.75 | february | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 0.9 | 39974.125 | 17626.5 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.05 | 2004.6 | 979.25 | march | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 0.9 | 40378.175 | 17626.5 | 2012-04-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0 | 404.05 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 1 | 19585 | 1 | 45323.639 | 19585 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-06-01 | 0 | 0 | 0.1 | 4945.46 | 1958.5 | june | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 5040 | 5040 | 1 | 530.25 | 530.25 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 5040 | 5040 | 1 | 530.25 | 530.25 | 1 | 5040 | 0 | 0 | 0 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-03-01 | 1 | 5040 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 5040 | 5040 | 1 | 530.25 | 530.25 | 1 | 5040 | 1 | 530.25 | 5040 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2012-02-01 | 2012-03-01 | 0 | 0 | 1 | 530.25 | 5040 | march | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 254 | days | 31750.17 | 125 | 198 | 24904.43 | 125.7799 | 18 | 2250.0122 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 254 | days | 31750.17 | 125 | 198 | 24904.43 | 125.7799 | 78 | 9750.0528 | 60 | 7525.35 | 9621.2642 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 60 | 7500.04 | 60 | 7525.35 | 9621.2642 | november | 5114.24 | 7644.66 | 8050.62 | 6061.12 | both | TRUE
911 | Accommodation | 254 | days | 31750.17 | 125 | 198 | 24904.43 | 125.7799 | 138 | 17250.0934 | 67 | 8338.99 | 10743.745 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 60 | 7500.04 | 7 | 813.64 | 1122.4808 | december | 5114.24 | 3217.88 | 1799.84 | 2941.06 | both | TRUE
911 | Accommodation | 254 | days | 31750.17 | 125 | 198 | 24904.43 | 125.7799 | 198 | 24750.1339 | 128 | 15958.22 | 20525.3636 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 60 | 7500.04 | 61 | 7619.23 | 9781.6186 | january | 5114.24 | 6366.7 | 6513.53 | 5025.29 | both | TRUE
911 | Accommodation | 254 | days | 31750.17 | 125 | 198 | 24904.43 | 125.7799 | 254 | 31750.1718 | 180 | 22436.24 | 28863.7926 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 56 | 7000.04 | 52 | 6478.02 | 8338.429 | february | 5114.24 | 5461.14 | 5389.64 | 4578.86 | both | TRUE
911 | Accommodation | 254 | days | 31750.17 | 125 | 198 | 24904.43 | 125.7799 | 254 | 31750.1718 | 198 | 24904.43 | 31750.1718 | 2012-03-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-03-01 | 0 | 0 | 18 | 2468.19 | 2886.3793 | march | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | C2020MPA | 10 | m3 | 0 | 0 | 8.5 | 2513.5 | 295.7059 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | C2020MPA | 10 | m3 | 0 | 0 | 8.5 | 2513.5 | 295.7059 | 10 | 0 | 3.5 | 1035.5 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 10 | 0 | 3.5 | 1035.5 | 0 | november | 5326.7 | 2747.45 | 1723.91 | 3227.39 | both | TRUE
c20 | C2020MPA | 10 | m3 | 0 | 0 | 8.5 | 2513.5 | 295.7059 | 10 | 0 | 6.2 | 1825.5 | 0 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 2.7 | 790 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | C2020MPA | 10 | m3 | 0 | 0 | 8.5 | 2513.5 | 295.7059 | 10 | 0 | 8.5 | 2513.5 | 0 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 2.3 | 688 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 4 | m3 | 1236 | 309 | 22 | 6886.8 | 313.0364 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 4 | m3 | 1236 | 309 | 22 | 6886.8 | 313.0364 | 0 | 0 | 7.8 | 2438.1 | 438.2182 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 7.8 | 2438.1 | 438.2182 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 4 | m3 | 1236 | 309 | 22 | 6886.8 | 313.0364 | 0 | 0 | 8.8 | 2716.5 | 494.4 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 1 | 278.4 | 56.1818 | december | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 4 | m3 | 1236 | 309 | 22 | 6886.8 | 313.0364 | 4 | 1236 | 22 | 6886.8 | 1236 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 4 | 1236 | 13.2 | 4170.3 | 741.6 | january | 5326.7 | 3488.49 | 3151.5 | 4170.4 | both | TRUE
c40 | 40 MPa Concrete | 50 | m3 | 19981.04 | 399.62 | 23.3 | 7571.2 | 324.9442 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c40 | 40 MPa Concrete | 50 | m3 | 19981.04 | 399.62 | 23.3 | 7571.2 | 324.9442 | 50 | 19981.0413 | 21.6 | 7044.6 | 18523.1971 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 50 | 19981.04 | 21.6 | 7044.6 | 18523.1971 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c40 | 40 MPa Concrete | 50 | m3 | 19981.04 | 399.62 | 23.3 | 7571.2 | 324.9442 | 50 | 19981.0413 | 23.3 | 7571.2 | 19981.0413 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 1.7 | 526.6 | 1457.8442 | february | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 14.4 | m3 | 4452.26 | 309.18 | 7 | 2177.4 | 311.0571 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 14.4 | m3 | 4452.26 | 309.18 | 7 | 2177.4 | 311.0571 | 14.4 | 4452.2577 | 0 | 0 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 14.4 | 4452.26 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 14.4 | m3 | 4452.26 | 309.18 | 7 | 2177.4 | 311.0571 | 14.4 | 4452.2577 | 7 | 2177.4 | 4452.2577 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-12-01 | 2012-02-01 | 0 | 0 | 7 | 2177.4 | 4452.2577 | february | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 50 | tonne | 19915.28 | 398.31 | 50.1 | 20711.157 | 413.3963 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-06-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 50 | tonne | 19915.28 | 398.31 | 50.1 | 20711.157 | 413.3963 | 50 | 19915.2797 | 50.1 | 20711.157 | 19915.2797 | 2012-06-01 | P020 - P03 Regional Bypass Road | 2012-06-01 | 2012-06-01 | 50 | 19915.28 | 50.1 | 20711.16 | 19915.2797 | june | 13406.07 | 14364.79 | 16592.09 | 13935.2 | both | TRUE
css | Stabilised Sand | 245 | m3 | 0 | 0 | 244 | 6711.32 | 27.5054 | 0 | 0 | 0 | 304 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
css | Stabilised Sand | 245 | m3 | 0 | 0 | 244 | 6711.32 | 27.5054 | 200 | 0 | 48 | 1813.02 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 200 | 0 | 48 | 1509.02 | 0 | november | 1153.96 | 6579.84 | 9230.4 | 4528.54 | both | TRUE
css | Stabilised Sand | 245 | m3 | 0 | 0 | 244 | 6711.32 | 27.5054 | 245 | 0 | 48 | 1813.02 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 45 | 0 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
css | Stabilised Sand | 245 | m3 | 0 | 0 | 244 | 6711.32 | 27.5054 | 245 | 0 | 244 | 6711.32 | 0 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 196 | 4898.3 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 157 | m | 3521.49 | 22.43 | 157 | 5070.29 | 32.2948 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 157 | m | 3521.49 | 22.43 | 157 | 5070.29 | 32.2948 | 0 | 0 | 0 | 0 | 0 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 157 | m | 3521.49 | 22.43 | 157 | 5070.29 | 32.2948 | 0 | 0 | 0 | 0 | 0 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 157 | m | 3521.49 | 22.43 | 157 | 5070.29 | 32.2948 | 0 | 0 | 0 | 3350.29 | 0 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 3350.29 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 157 | m | 3521.49 | 22.43 | 157 | 5070.29 | 32.2948 | 157 | 3521.4875 | 157 | 5070.29 | 3521.4875 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-02-01 | 0 | 3521.49 | 0 | 1720 | 3521.4875 | february | 5795.74 | 2201.13 | 618.62 | 2300.06 | both | TRUE
etp | Pits & Lids | 4 | each | 3120 | 780 | 4 | 3525 | 881.25 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 4 | each | 3120 | 780 | 4 | 3525 | 881.25 | 4 | 3120 | 4 | 3525 | 3120 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2012-01-01 | 2012-01-01 | 4 | 3120 | 4 | 3525 | 3120 | january | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 354 | tonne | 12390 | 35 | 178 | 6005.268 | 33.7375 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 354 | tonne | 12390 | 35 | 178 | 6005.268 | 33.7375 | 150 | 5250 | 35 | 1222.028 | 2436.236 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 150 | 5250 | 35 | 1222.03 | 2436.236 | november | 1899.18 | 3349.22 | 1311.1 | 2663.39 | both | TRUE
qmr | Rock | 354 | tonne | 12390 | 35 | 178 | 6005.268 | 33.7375 | 354 | 12390 | 35 | 1222.028 | 2436.236 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 204 | 7140 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 354 | tonne | 12390 | 35 | 178 | 6005.268 | 33.7375 | 354 | 12390 | 178 | 6005.268 | 12390 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-01-01 | 0 | 0 | 143 | 4783.24 | 9953.764 | january | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 147.81 | tonne | 4061.3 | 27.48 | 56 | 1428.3 | 0 | 100 | 2747.6524 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 147.81 | tonne | 4061.3 | 27.48 | 56 | 1428.3 | 0 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 47.81 | 1313.65 | 56 | 1428.3 | 4061.305 | november | 1153.96 | 1815.06 | 814.17 | 1428.2 | both | TRUE
qms | Sand | 147.81 | tonne | 4061.3 | 27.48 | 56 | 1428.3 | 0 | 147.81 | 4061.305 | 56 | 1428.3 | 0 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 147.81 | tonne | 4061.3 | 27.48 | 56 | 1428.3 | 0 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 2.71 | tonne | 5959.84 | 2199.2 | 1.4 | 2909.52 | 2078.2286 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 2.71 | tonne | 5959.84 | 2199.2 | 1.4 | 2909.52 | 2078.2286 | 0 | 0 | 1.4 | 2909.52 | 5959.8388 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 1.4 | 2909.52 | 5959.8388 | november | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 2.71 | tonne | 5959.84 | 2199.2 | 1.4 | 2909.52 | 2078.2286 | 0 | 0 | 1.4 | 2909.52 | 5959.8388 | 2011-12-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 2.71 | tonne | 5959.84 | 2199.2 | 1.4 | 2909.52 | 2078.2286 | 0 | 0 | 1.4 | 2909.52 | 5959.8388 | 2012-01-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 2.71 | tonne | 5959.84 | 2199.2 | 1.4 | 2909.52 | 2078.2286 | 2.71 | 5959.8388 | 1.4 | 2909.52 | 5959.8388 | 2012-02-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2012-02-01 | 0 | 5959.84 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 59.48 | m | 39512.16 | 664.29 | 59.48 | 20610 | 346.503 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 59.48 | m | 39512.16 | 664.29 | 59.48 | 20610 | 346.503 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-11-01 | 2011-11-01 | 59.48 | 39512.16 | 59.48 | 20610 | 39512.1568 | november | 13330.1 | 24389.43 | 26555.38 | 20032.19 | both | TRUE
swp | RCP | 12.2 | m | 6677.45 | 547.33 | 10.98 | 10500.25 | 956.3069 | 12.2 | 6677.4459 | 9.76 | 9270.25 | 5935.5075 | 2011-10-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 12.2 | m | 6677.45 | 547.33 | 10.98 | 10500.25 | 956.3069 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 2011-11-01 | P020 - P03 Regional Bypass Road | 2011-10-01 | 2011-11-01 | 0 | 0 | 1.22 | 1230 | 741.9384 | november | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 0 | 0 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 0.65 | 3340 | 0 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2011-09-01 | 0 | 0 | 0.65 | 3340 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 0.85 | 4150 | 0 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2011-09-01 | 0 | 0 | 0.2 | 810 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 0.95 | 4750 | 0 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2011-09-01 | 0 | 0 | 0.1 | 600 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 1 | 4750 | 0 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2011-09-01 | 0 | 0 | 0.05 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4750 | 4750 | 0 | 0 | 1 | 4750 | 0 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2011-09-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Purchase Water - IRC | 0 | item | 0 | 0 | 1 | 420 | 420 | 0 | 0 | 0 | 0 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2012-09-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Purchase Water - IRC | 0 | item | 0 | 0 | 1 | 420 | 420 | 0 | 0 | 0 | 420 | 0 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2012-09-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 4250 | 14560.069 | 0 | 0 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 8500 | 29120.138 | 530 | 6043.09 | 1815.7263 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4250 | 14560.07 | 530 | 6043.09 | 1815.7263 | june | 36434.42 | 35157.01 | 39678.22 | 33557.26 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 12750 | 43680.207 | 9695 | 51022.95 | 33214.0868 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4250 | 14560.07 | 9165 | 44979.86 | 31398.3606 | july | 36434.42 | 35688.72 | 40316.12 | 33657.39 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 17000 | 58240.276 | 9695 | 58886.44 | 33214.0868 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4250 | 14560.07 | 0 | 7863.49 | 0 | august | 36434.42 | 22588.94 | 19362.81 | 25315.42 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 21280 | 72903.1219 | 17000 | 92080.09 | 58240.276 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4280 | 14662.85 | 7305 | 33193.65 | 25026.1892 | september | 36434.42 | 35001.57 | 37737.27 | 33193.55 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 26280 | 90032.6149 | 26280 | 139834.145 | 90032.6149 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 5000 | 17129.49 | 9280 | 47754.05 | 31792.3389 | october | 70121.96 | 42446.38 | 42797.29 | 48833.07 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 26280 | m2 | 3.43 | 90032.61 | 26280 | 118730 | 4.5179 | 26280 | 90032.6149 | 26280 | 145851.255 | 90032.6149 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 4250 | 70964.1579 | 1875 | 22621.735 | 31307.7167 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 8500 | 141928.3157 | 5074 | 61006.81 | 84722.8558 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 4250 | 70964.16 | 3199 | 38385.07 | 53415.1391 | june | 34485.97 | 36824.96 | 37942.71 | 35389.08 | both | TRUE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 12750 | 212892.4736 | 9695 | 94361.75 | 161881.7672 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 4250 | 70964.16 | 4621 | 33354.94 | 77158.9114 | july | 34485.97 | 34056.06 | 33351.16 | 33355.04 | both | TRUE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 17000 | 283856.6314 | 14500 | 128050.49 | 242113.0092 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 4250 | 70964.16 | 4805 | 33688.74 | 80231.242 | august | 34485.97 | 34542.14 | 33923.12 | 33797.63 | both | TRUE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 21280 | 355321.7128 | 21280 | 183805.215 | 355321.7128 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 4280 | 71465.08 | 6780 | 55754.72 | 113208.7036 | september | 34485.97 | 35290.56 | 33771.02 | 34141.66 | both | TRUE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 26280 | 438808.9573 | 26280 | 223781.7 | 438808.9573 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 5000 | 83487.24 | 5000 | 39976.48 | 83487.2445 | october | 34485.97 | 34908.07 | 33123 | 34375.49 | both | TRUE
68 | Insitu Stabilisation | 26280 | m2 | 16.7 | 438808.96 | 26280 | 223782 | 8.5153 | 26280 | 438808.9573 | 26280 | 223781.7 | 438808.9573 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 4 | 6494.5455 | 1.2 | 4751.28 | 1948.3636 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 8 | 12989.0909 | 3 | 6267.435 | 4870.9091 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4 | 6494.55 | 1.8 | 1516.16 | 2922.5455 | june | 5324.28 | 8253.12 | 7131.71 | 6799.77 | both | TRUE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 12 | 19483.6364 | 14 | 25325.07 | 22730.9091 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4 | 6494.55 | 11 | 19057.64 | 17860 | july | 22309.49 | 18724.72 | 19587.47 | 18638.68 | both | TRUE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 16 | 25978.1818 | 20 | 60299.05 | 32472.7273 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4 | 6494.55 | 6 | 34973.98 | 9741.8182 | august | 22309.49 | 25004.41 | 29338.77 | 22827.4 | both | TRUE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 20 | 32472.7273 | 22.5 | 66781.515 | 36531.8182 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4 | 6494.55 | 2.5 | 6482.46 | 4059.0909 | september | 5324.28 | 8166.9 | 5320.73 | 6482.57 | both | TRUE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 24 | 38967.2727 | 26 | 90202.42 | 42214.5455 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 4 | 6494.55 | 3.5 | 23420.91 | 5682.7273 | october | 5324.28 | 8237.7 | 6980.68 | 6861.26 | both | TRUE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 27.5 | 44650 | 27.5 | 91621.18 | 44650 | 2011-11-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 3.5 | 5682.73 | 1.5 | 1418.76 | 2435.4545 | november | 5324.28 | 5553.61 | 2071.07 | 5066.91 | both | TRUE
191 | Dayworks - Cleaning Drains | 27.5 | days | 1623.64 | 44650 | 27.5 | 92723 | 3371.7455 | 27.5 | 44650 | 27.5 | 94517.63 | 44650 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 8 | 6342.9301 | 18 | 11964.15 | 5441.6865 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 16 | 12685.8603 | 35 | 23843.9 | 10581.057 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 8 | 6342.93 | 17 | 11879.75 | 5139.3706 | june | 5324.28 | 12380.08 | 13966.92 | 9917.88 | both | TRUE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 24 | 19028.7904 | 72 | 48482.1 | 21766.7459 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 8 | 6342.93 | 37 | 24638.2 | 11185.6889 | july | 22309.49 | 20514.55 | 22719.75 | 20245.61 | both | TRUE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 32 | 25371.7206 | 87 | 59050.25 | 26301.4846 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 8 | 6342.93 | 15 | 10568.15 | 4534.7387 | august | 22309.49 | 12860.1 | 10393.97 | 15424.56 | both | TRUE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 40 | 31714.6507 | 117 | 78901.65 | 35370.9621 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 8 | 6342.93 | 30 | 19851.4 | 9069.4775 | september | 5324.28 | 11332.76 | 10633.18 | 8979.23 | both | TRUE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 48 | 38057.5809 | 134 | 90848.15 | 40510.3326 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 8 | 6342.93 | 17 | 11946.5 | 5139.3706 | october | 5324.28 | 11931.36 | 13129.35 | 9699.2 | both | TRUE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 53 | 42021.9122 | 139 | 90848.15 | 42021.9122 | 2011-11-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 5 | 3964.33 | 5 | 0 | 1511.5796 | november | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 53 | days | 792.87 | 42021.91 | 139 | 93792 | 674.7626 | 53 | 42021.9122 | 139 | 93792.495 | 42021.9122 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 0.05 | 359.35 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 0.15 | 826.85 | 0 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0.1 | 467.5 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 0.75 | 5140.48 | 0 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0.6 | 4313.63 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 0.9 | 5259.45 | 0 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0.15 | 118.97 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 1 | 5697.75 | 0 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0.1 | 438.3 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 5698 | 5698 | 0 | 0 | 1 | 5697.75 | 0 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 0 | 0 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 1 | 6991.78 | 0 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 1 | 6991.78 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 2 | 15375.72 | 0 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 1 | 8383.94 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 3 | 22977.305 | 0 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 1 | 7601.59 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 4 | 28856.15 | 0 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 1 | 5878.84 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 5 | 36682.5 | 0 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 1 | 7826.35 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 6 | 36682.5 | 0 | 2011-11-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 1 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Relocations (Along Road) | 0 | month | 0 | 0 | 6 | 39399 | 6566.5 | 0 | 0 | 6 | 39398.615 | 0 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-06-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 41 | 4259.2362 | 67 | 9078.12 | 8090.0298 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 124 | 12881.5925 | 164 | 22107.29 | 19802.4611 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 83 | 8622.36 | 97 | 13029.17 | 11712.4313 | june | 9322.64 | 14552.62 | 16595.03 | 11704.12 | both | TRUE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 207 | 21503.9488 | 359 | 48479.02 | 43348.0703 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 83 | 8622.36 | 195 | 26371.73 | 23545.6092 | july | 8981.05 | 21908.42 | 28123.98 | 16109.86 | both | TRUE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 290 | 30126.3051 | 378 | 50970 | 45642.2579 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 83 | 8622.36 | 19 | 2490.98 | 2294.1876 | august | 8981.05 | 8522.7 | 6717.64 | 7583 | both | TRUE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 373 | 38748.6614 | 455 | 60399.53 | 54939.7548 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 83 | 8622.36 | 77 | 9429.53 | 9297.497 | september | 9322.64 | 12229.51 | 11239.96 | 9940.56 | both | TRUE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 456 | 47371.0177 | 499 | 67366.89 | 60252.6103 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 83 | 8622.36 | 44 | 6967.36 | 5312.8554 | october | 9322.64 | 12509.48 | 13231.29 | 10454.5 | both | TRUE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 580 | 60252.6103 | 499 | 67366.89 | 60252.6103 | 2011-11-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 124 | 12881.59 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 580 | nights | 103.88 | 60252.61 | 499 | 67367 | 135.004 | 580 | 60252.6103 | 499 | 67366.89 | 60252.6103 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 54.1762 | 19168.2714 | 41 | 13825 | 14952.7088 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 108.3524 | 38336.5428 | 123 | 41195 | 44858.1265 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 54.18 | 19168.27 | 82 | 27370 | 29905.4177 | june | 29799.52 | 24720.91 | 27709.42 | 25719.54 | both | TRUE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 162.5285 | 57504.8142 | 202 | 68055 | 73669.4435 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 54.18 | 19168.27 | 79 | 26860 | 28811.317 | july | 29799.52 | 25217.34 | 28291.4 | 25796.85 | both | TRUE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 216.7047 | 76673.0856 | 202 | 68055 | 73669.4435 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 54.18 | 19168.27 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 271.2633 | 95976.6625 | 284 | 95705 | 103574.8612 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 54.56 | 19303.58 | 82 | 27650 | 29905.4177 | september | 29799.52 | 19768.61 | 18172.96 | 22258.59 | both | TRUE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 335 | 118527.57 | 325 | 109135 | 118527.57 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 63.74 | 22550.91 | 41 | 13430 | 14952.7088 | october | 29799.52 | 17335.96 | 15489.17 | 21082.08 | both | TRUE
csa | Cement Powder (Stabilising) | 335 | tonne | 353.81 | 118527.57 | 325 | 109135 | 335.8 | 335 | 118527.57 | 325 | 109135 | 118527.57 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 25 | 754.9157 | 0 | 0 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 50 | 1509.8315 | 72.58 | 1033.29 | 1878.7262 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 25 | 754.92 | 72.58 | 1033.29 | 1878.7262 | june | 1153.96 | 1318.35 | -457.48 | 1033.19 | both | TRUE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 75 | 2264.7472 | 121.65 | 3163.725 | 3148.8984 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 25 | 754.92 | 49.07 | 2130.44 | 1270.1722 | july | 958.97 | 1917.82 | 332.88 | 1116.15 | both | TRUE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 100 | 3019.6629 | 172.29 | 3400.01 | 4459.7098 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 25 | 754.92 | 50.64 | 236.28 | 1310.8115 | august | 1824.94 | 2688.43 | 1155.26 | 2013.52 | both | TRUE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 125 | 3774.5787 | 207.65 | 3400.01 | 5375 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 25 | 754.92 | 35.36 | 0 | 915.2902 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 150 | 4529.4944 | 207.65 | 3838.46 | 5375 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 25 | 754.92 | 0 | 438.45 | 0 | october | 1153.96 | 1566.84 | -190.4 | 1265.32 | both | TRUE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 178 | 5375 | 207.65 | 3838.46 | 5375 | 2011-11-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 28 | 845.51 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | Road Base | 178 | tonne | 30.2 | 5375 | 207.65 | 3838 | 18.483 | 178 | 5375 | 207.65 | 3838.46 | 5375 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 208.6187 | 1083.5236 | 0 | 0 | 0 | 2011-05-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 417.2374 | 2167.0472 | 89 | 0 | 462.2481 | 2011-06-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 208.62 | 1083.52 | 89 | 0 | 462.2481 | june | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 625.8562 | 3250.5708 | 237 | 0 | 1230.9302 | 2011-07-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 208.62 | 1083.52 | 148 | 0 | 768.6822 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 834.4749 | 4334.0944 | 317 | 0 | 1646.4341 | 2011-08-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 208.62 | 1083.52 | 80 | 0 | 415.5039 | august | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 1044.5662 | 5425.2664 | 586 | 6462.59 | 3043.5659 | 2011-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 210.09 | 1091.17 | 269 | 6462.59 | 1397.1318 | september | 12590.7 | 8882.52 | 7412.17 | 9233.2 | both | TRUE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 1290 | 6700 | 1290 | 26038.82 | 6700 | 2011-10-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 245.43 | 1274.73 | 704 | 19576.23 | 3656.4341 | october | 12590.7 | 13126.61 | 15653.09 | 12309.5 | both | TRUE
qmr | Sealing Aggregate (10/7) | 1290 | tonne | 5.19 | 6700 | 1290 | 52649 | 40.8132 | 1290 | 6700 | 1290 | 26038.82 | 6700 | 2012-09-01 | P021 - P04 Regional Arterial Pavement Repairs | 2011-05-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 12 | 2220 | 0 | 720 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 24 | 4440 | 38 | 7669.1 | 7030 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 12 | 2220 | 38 | 6949.1 | 7030 | october | 3058.72 | 5781.39 | 7514.86 | 4944.88 | both | TRUE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 56 | 10360 | 62 | 12165 | 11470 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 32 | 5920 | 24 | 4495.9 | 4440 | november | 4719.61 | 5437.2 | 5401.81 | 5270.17 | both | TRUE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 68 | 12580 | 70 | 13592.52 | 12950 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 12 | 2220 | 8 | 1427.52 | 1480 | december | 3058.72 | 1792.31 | 1206.78 | 2065.11 | both | TRUE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 84 | 15540 | 70 | 13592.52 | 12950 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 16 | 2960 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 96 | 17760 | 81 | 15710.37 | 14985 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 12 | 2220 | 11 | 2117.85 | 2035 | february | 3058.72 | 2222.76 | 1865.57 | 2540.21 | both | TRUE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 104 | 19240 | 100 | 19270.52 | 18500 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 8 | 1480 | 19 | 3560.15 | 3515 | march | 2954.94 | 3191.99 | 3883.65 | 2892.45 | both | TRUE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 124 | 22940 | 121 | 20342.92 | 22385 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 20 | 3700 | 21 | 1072.4 | 3885 | april | 3058.72 | 1686.03 | -292.8 | 2286.96 | both | TRUE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 124 | 22940 | 121 | 20567.32 | 22385 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 224.4 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 124 | 22940 | 121 | 23188.92 | 22385 | 2012-06-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 2621.6 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 124 | 22940 | 121 | 23188.92 | 22940 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 555 | august | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.1 | 3346 | 0.1 | 0 | 3346 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.2 | 6692 | 0.25 | 1600 | 8365 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.1 | 3346 | 0.15 | 1600 | 5019 | october | 1393.55 | 2977.37 | 3509.82 | 2334.29 | both | TRUE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.4 | 13384 | 0.4 | 2769.54 | 13384 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.2 | 6692 | 0.15 | 1169.54 | 5019 | november | 4719.61 | 6239.99 | 6772.43 | 5507.94 | both | TRUE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.6 | 20076 | 0.4 | 2769.54 | 13384 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.2 | 6692 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.7 | 23422 | 0.75 | 4151.44 | 25095 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.1 | 3346 | 0.35 | 1381.9 | 11711 | january | 1393.55 | 1108.27 | 285.34 | 873.5 | both | TRUE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.9 | 30114 | 0.75 | 4151.44 | 25095 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.2 | 6692 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 1 | 33460 | 1 | 5728.34 | 33460 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.1 | 3346 | 0.25 | 1576.9 | 8365 | march | 1393.55 | 1943.67 | 2232.9 | 1334.46 | both | TRUE
15 | Service Locations | 18 | hrs | 4455 | 247.5 | 3.5 | 857.5 | 245.1429 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 18 | hrs | 4455 | 247.5 | 3.5 | 857.5 | 245.1429 | 0 | 0 | 0 | 130 | 0 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0 | 130 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 18 | hrs | 4455 | 247.5 | 3.5 | 857.5 | 245.1429 | 18 | 4455 | 0 | 130 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 18 | 4455 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 18 | hrs | 4455 | 247.5 | 3.5 | 857.5 | 245.1429 | 18 | 4455 | 3.5 | 857.5 | 866.25 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 3.5 | 727.5 | 866.25 | april | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 18 | hrs | 4455 | 247.5 | 3.5 | 857.5 | 245.1429 | 18 | 4455 | 3.5 | 857.5 | 4455 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 3588.75 | august | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 0.5 | 10375 | 0.25 | 3641.75 | 5187.5 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0.5 | 10375 | 0.25 | 3641.75 | 5187.5 | october | 4719.61 | 4245.67 | 4642.55 | 4195.02 | both | TRUE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 1 | 20750 | 1 | 13933.58 | 20750 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0.5 | 10375 | 0.75 | 10291.83 | 15562.5 | november | 4719.61 | 7653.01 | 9290.31 | 6355.47 | both | TRUE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 1 | 20750 | 0 | 13933.58 | 0 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0 | 0 | 0 | 0 | -20750 | december | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 1 | 20750 | 0 | 13933.58 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 1 | 20750 | 0 | 13933.58 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 1 | 20750 | 0 | 13933.58 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 1 | 20750 | 1 | 13933.58 | 20750 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 20750 | april | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 700 | 7758.1105 | 650 | 65243.68 | 7203.9597 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 700 | 7758.1105 | 700 | 70756.18 | 7758.1105 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 50 | 5512.5 | 554.1507 | october | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 700 | 7758.1105 | 720 | 71161.18 | 7979.7708 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 20 | 405 | 221.6603 | february | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 720 | 7979.7708 | 720 | 71161.18 | 7979.7708 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 20 | 221.66 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 720 | 7979.7708 | 730 | 71161.18 | 8090.6009 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 10 | 0 | 110.8301 | april | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 720 | 7979.7708 | 730 | 72746.43 | 8090.6009 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 1585.25 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.77 | 11.08 | 730 | 72746.43 | 99.6521 | 720 | 7979.7708 | 730 | 72746.43 | 7979.7708 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | -110.8301 | august | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 15900 | 15900 | 1 | 5217.475 | 5217 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 15900 | 15900 | 1 | 5217.475 | 5217 | 0.5 | 7950 | 0.5 | 2852.475 | 7950 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2011-11-01 | 0.5 | 7950 | 0.5 | 2852.48 | 7950 | october | 2514.97 | 3374.73 | 4622.27 | 2771.92 | both | TRUE
41 | Demolition works | 1 | item | 15900 | 15900 | 1 | 5217.475 | 5217 | 1 | 15900 | 1 | 5217.475 | 15900 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2011-11-01 | 0.5 | 7950 | 0.5 | 2365 | 7950 | november | 2514.97 | 4152.45 | 5103.68 | 3232.07 | both | TRUE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 200 | 5534.8896 | 60 | 1276.8 | 1660.4669 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 1800 | 49814.0065 | 1580 | 30926.475 | 43725.6279 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 1600 | 44279.12 | 1520 | 29649.68 | 42065.1611 | october | 20347.42 | 28600.78 | 30185.46 | 25782.35 | both | TRUE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 1800 | 49814.0065 | 1730 | 33731.475 | 47876.7952 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 0 | 0 | 150 | 2805 | 4151.1672 | november | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 2050 | 56732.6185 | 1980 | 38619.5897 | 54795.4072 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 250 | 6918.61 | 250 | 4888.11 | 6918.612 | january | 6137.31 | 6947.76 | 3594.85 | 6512.37 | both | TRUE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 2265 | 62682.6249 | 2060 | 40212.4897 | 57009.363 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 215 | 5950.01 | 80 | 1592.9 | 2213.9558 | february | 6137.31 | 6615.64 | 3442.33 | 6431.33 | both | TRUE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 2265 | 62682.6249 | 2060 | 40527.4897 | 57009.363 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 0 | 0 | 0 | 315 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 2265 | 62682.6249 | 2265 | 42327.4897 | 62682.6249 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 0 | 0 | 205 | 1800 | 5673.2619 | april | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 2265 | m3 | 62682.62 | 27.67 | 2265 | 43727.4897 | 19.3055 | 2265 | 62682.6249 | 2265 | 43727.4897 | 62682.6249 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-05-01 | 0 | 0 | 0 | 1400 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
55 | Place General Fill | 410 | m3 | 6310.53 | 15.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-02-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
55 | Place General Fill | 410 | m3 | 6310.53 | 15.39 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-02-01 | 2012-08-01 | 410 | 6310.53 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
55 | Place General Fill | 410 | m3 | 6310.53 | 15.39 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 6310.5311 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-02-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 6310.5311 | august | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 11813 | m2 | 13464 | 1.14 | 11813 | 26831.6 | 2.2714 | 4000 | 4559.0451 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 11813 | m2 | 13464 | 1.14 | 11813 | 26831.6 | 2.2714 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-10-01 | 7813 | 8904.95 | 11813 | 26831.6 | 13464 | october | 18318.04 | 25981.24 | 26627.15 | 21401.78 | both | TRUE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 1000 | 14564.9003 | 56 | 1127.92 | 815.6344 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 6196 | 90244.1224 | 6180 | 114398.01 | 90011.084 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 5196 | 75679.22 | 6124 | 113270.09 | 89195.4495 | october | 34485.97 | 22190.95 | 11743.6 | 24756.46 | both | TRUE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 6196 | 90244.1224 | 7370 | 134531.66 | 107343.3153 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 1190 | 20133.65 | 17332.2314 | november | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 6196 | 90244.1224 | 7580 | 138382.37 | 110401.9444 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 210 | 3850.71 | 3058.6291 | december | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 8000 | 116519.2025 | 8635 | 152631.495 | 125767.9142 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 1804 | 26275.08 | 1055 | 14249.12 | 15365.9698 | january | 5410.44 | 22120.09 | 24751.8 | 14811.49 | both | TRUE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 8796 | 128112.8632 | 8796 | 158813.52 | 128112.8632 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 796 | 11593.66 | 161 | 6182.02 | 2344.949 | february | 15290.35 | 9377.79 | 4506.29 | 9645.9 | both | TRUE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 8796 | 128112.8632 | 8796 | 158990.27 | 128112.8632 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 0 | 176.75 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 8796 | tonne | 128112.86 | 14.56 | 8796 | 159414.47 | 18.1235 | 8796 | 128112.8632 | 8796 | 159414.47 | 128112.8632 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 0 | 424.2 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 23626 | m2 | 10504.96 | 0.44 | 23626 | 7087.515 | 0.30001 | 4000 | 1778.5429 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 23626 | m2 | 10504.96 | 0.44 | 23626 | 7087.515 | 0.30001 | 18760 | 8341.3661 | 18760 | 3453.6 | 8341.3661 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 14760 | 6562.82 | 18760 | 3453.6 | 8341.3661 | october | 4191.71 | 9155.1 | 6473.58 | 5078.92 | both | TRUE
63 | Trim All Layers | 23626 | m2 | 10504.96 | 0.44 | 23626 | 7087.515 | 0.30001 | 21190 | 9421.8309 | 21190 | 5602.815 | 9421.8309 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 2430 | 1080.46 | 2430 | 2149.22 | 1080.4648 | january | 2852.72 | 3568.48 | 1769.89 | 2248.8 | both | TRUE
63 | Trim All Layers | 23626 | m2 | 10504.96 | 0.44 | 23626 | 7087.515 | 0.30001 | 23626 | 10504.9636 | 21190 | 5602.815 | 9421.8309 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 2436 | 1083.13 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 23626 | m2 | 10504.96 | 0.44 | 23626 | 7087.515 | 0.30001 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 2436 | 1484.7 | 1083.1326 | march | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 9380 | 66920.9525 | 9380 | 69005.5 | 66920.9525 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 9380 | 66920.95 | 9380 | 69005.5 | 66920.9525 | october | 77534.32 | 62799.65 | 65471.8 | 64335.79 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 18760 | 133841.905 | 18760 | 125506.06 | 133841.905 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 9380 | 66920.95 | 9380 | 56500.56 | 66920.9525 | december | 77534.32 | 58614.41 | 58852.93 | 61329.18 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 18760 | 133841.905 | 0 | 125506.06 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 0 | 0 | 0 | 0 | -133841.905 | january | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 18760 | 133841.905 | 0 | 125506.06 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 20421 | 145692.1931 | 0 | 125506.06 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 1661 | 11850.29 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 20421 | 145692.1931 | 20421 | 125506.06 | 145692.1931 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 0 | 0 | 0 | 0 | 145692.1931 | april | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.19 | 7.13 | 20421 | 131081.82 | 6.419 | 20421 | 145692.1931 | 20421 | 131081.82 | 145692.1931 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-05-01 | 0 | 0 | 0 | 5575.76 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 195 | tonne | 58305 | 299 | 267.4 | 80088.974 | 299.5101 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 195 | tonne | 58305 | 299 | 267.4 | 80088.974 | 299.5101 | 195 | 58305 | 267.4 | 0 | 79952.6 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 195 | 58305 | 267.4 | 0 | 79952.6 | april | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 195 | tonne | 58305 | 299 | 267.4 | 80088.974 | 299.5101 | 195 | 58305 | 267.4 | 80088.974 | 79952.6 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 0 | 0 | 0 | 80088.97 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 195 | tonne | 58305 | 299 | 267.4 | 80088.974 | 299.5101 | 195 | 58305 | 267.4 | 80088.974 | 58305 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 0 | 0 | 0 | 0 | -21647.6 | august | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 8808 | 8808 | 1 | 2580 | 2580 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 8808 | 8808 | 1 | 2580 | 2580 | 1 | 8808 | 0 | 0 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 1 | 8808 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 8808 | 8808 | 1 | 2580 | 2580 | 1 | 8808 | 1 | 2580 | 8808 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 0 | 0 | 1 | 2580 | 8808 | february | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 0.5 | 5614.75 | 0.5 | 0 | 5614.75 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 0.5 | 5614.75 | 0.55 | 0 | 6176.225 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0.05 | 0 | 561.475 | october | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 0.5 | 5614.75 | 0.55 | 810 | 6176.225 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0 | 810 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 1 | 11229.5 | 0.75 | 4862.5 | 8422.125 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0.5 | 5614.75 | 0.2 | 4052.5 | 2245.9 | december | 1899.18 | 3861.35 | 4344.59 | 2714.59 | both | TRUE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 1 | 11229.5 | 1 | 6261.1 | 11229.5 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0.25 | 1398.6 | 2807.375 | january | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 1 | 11229.5 | 1 | 6826.7 | 11229.5 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0 | 565.6 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 1 | 11229.5 | 1 | 6897.4 | 11229.5 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-03-01 | 0 | 0 | 0 | 70.7 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation of Subgrade | 1893 | m2 | 30573.16 | 16.15 | 1893 | 47892.13 | 25.2995 | 0 | 0 | 0 | 225 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation of Subgrade | 1893 | m2 | 30573.16 | 16.15 | 1893 | 47892.13 | 25.2995 | 350 | 5652.7229 | 655 | 16695.645 | 10578.6671 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 350 | 5652.72 | 655 | 16470.64 | 10578.6671 | october | 14835.1 | 14180.57 | 18661.64 | 14477.13 | both | TRUE
68 | Insitu Stabilisation of Subgrade | 1893 | m2 | 30573.16 | 16.15 | 1893 | 47892.13 | 25.2995 | 1893 | 30573.1555 | 1893 | 47297.13 | 30573.1555 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 1543 | 24920.43 | 1238 | 30601.49 | 19994.4884 | november | 13330.1 | 24328.12 | 31777.95 | 20757.75 | both | TRUE
68 | Insitu Stabilisation of Subgrade | 1893 | m2 | 30573.16 | 16.15 | 1893 | 47892.13 | 25.2995 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 595 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation of Subgrade | 1893 | m2 | 30573.16 | 16.15 | 1893 | 47892.13 | 25.2995 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 3.638e-12 | august | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 0 | 0 | 0 | 400 | 0 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 0 | 400 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 48 | 2691.5265 | 48 | 3520 | 2691.5265 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 48 | 2691.53 | 48 | 3120 | 2691.5265 | november | 3058.72 | 3042.42 | 1367.35 | 1943.7 | both | TRUE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 233 | 13065.1183 | 48 | 3520 | 2691.5265 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 185 | 10373.59 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 418 | 23438.71 | 48 | 4081.25 | 2691.5265 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 185 | 10373.59 | 0 | 561.25 | 0 | january | 5114.24 | 2869.42 | 180.29 | 2400.8 | both | TRUE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 418 | 23438.71 | 86 | 6346.95 | 4822.3183 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 38 | 2265.7 | 2130.7918 | february | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.07 | 418 | 30901.95 | 73.9282 | 418 | 23438.71 | 418 | 30901.95 | 23438.71 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 332 | 24555 | 18616.3917 | march | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 35 | m3 | 21000 | 600 | 35 | 6696.985 | 191.3429 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 35 | m3 | 21000 | 600 | 35 | 6696.985 | 191.3429 | 20 | 12000 | 18 | 3440.325 | 10800 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 20 | 12000 | 18 | 3440.32 | 10800 | november | 4719.61 | 5441.16 | 2950.25 | 4833.2 | both | TRUE
72 | Form & Pour Headwalls | 35 | m3 | 21000 | 600 | 35 | 6696.985 | 191.3429 | 35 | 21000 | 25 | 4851.985 | 15000 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 15 | 9000 | 7 | 1411.66 | 4200 | december | 1849.43 | 2775.21 | 501.11 | 1894.98 | both | TRUE
72 | Form & Pour Headwalls | 35 | m3 | 21000 | 600 | 35 | 6696.985 | 191.3429 | 35 | 21000 | 35 | 4851.985 | 21000 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 0 | 0 | 10 | 0 | 6000 | april | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 35 | m3 | 21000 | 600 | 35 | 6696.985 | 191.3429 | 35 | 21000 | 35 | 6696.985 | 21000 | 2012-06-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 0 | 0 | 0 | 1845 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 517 | m2 | 15824.81 | 30.61 | 517 | 11570 | 22.3791 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-03-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 517 | m2 | 15824.81 | 30.61 | 517 | 11570 | 22.3791 | 0 | 0 | 0 | 0 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-03-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 517 | m2 | 15824.81 | 30.61 | 517 | 11570 | 22.3791 | 517 | 15824.8109 | 160 | 3600 | 4897.427 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-03-01 | 2012-04-01 | 517 | 15824.81 | 0 | 3600 | 4897.427 | march | 1628.04 | 3876.97 | 3111.38 | 3484.86 | both | TRUE
73 | Form & Place Footpath | 517 | m2 | 15824.81 | 30.61 | 517 | 11570 | 22.3791 | 517 | 15824.8109 | 517 | 11570 | 15824.8109 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-03-01 | 2012-04-01 | 0 | 0 | 357 | 7970 | 10927.3839 | april | 0 | 0 | 0 | 0 | left_only | FALSE
75 | Saw Cutting/Joint sealing | 83 | m | 3526 | 42.48 | 83 | 4008.49 | 48.2892 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
75 | Saw Cutting/Joint sealing | 83 | m | 3526 | 42.48 | 83 | 4008.49 | 48.2892 | 6 | 254.8916 | 6 | 269.28 | 254.8916 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-02-01 | 6 | 254.89 | 6 | 269.28 | 254.8916 | november | 1153.96 | 1722.17 | 1255.91 | 1034.98 | both | TRUE
75 | Saw Cutting/Joint sealing | 83 | m | 3526 | 42.48 | 83 | 4008.49 | 48.2892 | 83 | 3526 | 15 | 711.18 | 637.2289 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-02-01 | 77 | 3271.11 | 9 | 441.9 | 382.3373 | january | 5795.74 | 1034.23 | -788.58 | 1883.34 | both | TRUE
75 | Saw Cutting/Joint sealing | 83 | m | 3526 | 42.48 | 83 | 4008.49 | 48.2892 | 83 | 3526 | 83 | 4008.49 | 3526 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-11-01 | 2012-02-01 | 0 | 0 | 68 | 3297.31 | 2888.7711 | february | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 102.48 | m | 41052.64 | 400.59 | 102 | 34010.8 | 327.8529 | 50 | 20029.5884 | 43.92 | 14553.385 | 17593.9904 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 102.48 | m | 41052.64 | 400.59 | 102 | 34010.8 | 327.8529 | 102.48 | 41052.6443 | 102.48 | 32464.275 | 41052.6443 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 52.48 | 21023.06 | 58.56 | 17910.89 | 23458.6539 | october | 19644.48 | 15867.29 | 17990.31 | 16365.26 | both | TRUE
81 | > 450 | 102.48 | m | 41052.64 | 400.59 | 102 | 34010.8 | 327.8529 | 102.48 | 41052.6443 | 102.48 | 33440.8 | 41052.6443 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 976.53 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 102.48 | m | 41052.64 | 400.59 | 102 | 34010.8 | 327.8529 | 102.48 | 41052.6443 | 102 | 33440.8 | 40860.3603 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | -0.48 | 0 | -192.284 | april | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 102.48 | m | 41052.64 | 400.59 | 102 | 34010.8 | 327.8529 | 102.48 | 41052.6443 | 102 | 34010.8 | 41052.6443 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 570 | 192.284 | august | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 500 | 17920.1291 | 875 | 9624.465 | 31360.226 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 500 | 17920.13 | 875 | 9624.46 | 31360.226 | october | 14917.02 | 8626.87 | 7161.99 | 9171.4 | both | TRUE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 1410 | 50534.7642 | 930 | 10214.465 | 33331.4402 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 910 | 32614.64 | 55 | 590 | 1971.2142 | november | 5841.9 | 3760.19 | -1010.22 | 3384.64 | both | TRUE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 1780 | 63795.6598 | 930 | 10214.465 | 33331.4402 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 370 | 13260.9 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 1780 | 63795.6598 | 1660 | 18262.525 | 59494.8288 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 730 | 8048.06 | 26163.3886 | january | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 120 | 1028.5 | 4300.831 | march | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.66 | 35.84 | 1780 | 19291.025 | 10.8376 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 7.276e-12 | august | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-Contractor | 1 | item | 13500 | 13500 | 1 | 13840 | 13840 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-12-01 | 2011-12-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-Contractor | 1 | item | 13500 | 13500 | 1 | 13840 | 13840 | 1 | 13500 | 1 | 13840 | 13500 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-12-01 | 2011-12-01 | 1 | 13500 | 1 | 13840 | 13500 | december | 29799.52 | 11697.75 | 7401.59 | 16552.88 | both | TRUE
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.7 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 10200 | 27489 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.7 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.7 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.7 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 27489 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 27489 | august | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 200 | 5992.1855 | 45 | 7903.41 | 1348.2417 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 400 | 11984.371 | 72 | 15179.52 | 2157.1868 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 200 | 5992.19 | 27 | 7276.11 | 808.945 | october | 5114.24 | 8639.49 | 11325.91 | 7761.99 | both | TRUE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 600 | 17976.5566 | 76 | 15497.67 | 2277.0305 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 200 | 5992.19 | 4 | 318.15 | 119.8437 | november | 5114.24 | 8483.23 | 10327.54 | 7618.23 | both | TRUE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 800 | 23968.7421 | 76 | 15497.67 | 2277.0305 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 200 | 5992.19 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 840 | 25167.1792 | 100 | 19127.455 | 2996.0928 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 40 | 1198.44 | 24 | 3629.79 | 719.0623 | january | 958.97 | 2284.9 | 2554.46 | 2026.23 | both | TRUE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 880 | 26365.6163 | 110 | 21548.605 | 3295.702 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 40 | 1198.44 | 10 | 2421.15 | 299.6093 | february | 1824.94 | 2417.02 | 2815.44 | 2531.03 | both | TRUE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 920 | 27564.0534 | 110 | 21548.605 | 3295.702 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 40 | 1198.44 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 933 | 27953.5455 | 110 | 21548.605 | 3295.702 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 13 | 389.49 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 933 | hrs | 27953.55 | 29.96 | 110 | 21548.605 | 56.8636 | 933 | 27953.5455 | 110 | 21548.605 | 27953.5455 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 24657.8434 | august | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 560 | m | 16000 | 28.57 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 560 | m | 16000 | 28.57 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 560 | m | 16000 | 28.57 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 560 | m | 16000 | 28.57 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 16000 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 16000 | august | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Supply & Place Box Culverts | 214 | m | 64479.51 | 301.31 | 214 | 59053.1702 | 275.9486 | 70 | 21091.4297 | 70 | 19480.19 | 21091.4297 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Supply & Place Box Culverts | 214 | m | 64479.51 | 301.31 | 214 | 59053.1702 | 275.9486 | 160 | 48208.9822 | 135 | 38187.17 | 40676.3288 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 90 | 27117.55 | 65 | 18706.98 | 19584.899 | october | 22048.5 | 17001.5 | 17674.45 | 17572.88 | both | TRUE
181 | Supply & Place Box Culverts | 214 | m | 64479.51 | 301.31 | 214 | 59053.1702 | 275.9486 | 214 | 64479.5137 | 154 | 42587.17 | 46401.1454 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 54 | 16270.53 | 19 | 4400 | 5724.8166 | november | 6137.31 | 12062.62 | 14042.53 | 9149.38 | both | TRUE
181 | Supply & Place Box Culverts | 214 | m | 64479.51 | 301.31 | 214 | 59053.1702 | 275.9486 | 214 | 64479.5137 | 206 | 56447.17 | 62069.0646 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 52 | 13860 | 15667.9192 | december | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Supply & Place Box Culverts | 214 | m | 64479.51 | 301.31 | 214 | 59053.1702 | 275.9486 | 214 | 64479.5137 | 214 | 56447.17 | 64479.5137 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 8 | 0 | 2410.4491 | april | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Supply & Place Box Culverts | 214 | m | 64479.51 | 301.31 | 214 | 59053.1702 | 275.9486 | 214 | 64479.5137 | 214 | 59053.1702 | 64479.5137 | 2012-07-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 2606 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
182 | Supply Base Slabs | 57 | m3 | 9379.8 | 164.56 | 57 | 11490 | 338.0351 | 28 | 4607.6211 | 23 | 0 | 3784.8316 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
182 | Supply Base Slabs | 57 | m3 | 9379.8 | 164.56 | 57 | 11490 | 338.0351 | 53 | 8721.5684 | 53 | 0 | 8721.5684 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 25 | 4113.95 | 30 | 0 | 4936.7368 | october | 0 | 0 | 0 | 0 | left_only | FALSE
182 | Supply Base Slabs | 57 | m3 | 9379.8 | 164.56 | 57 | 11490 | 338.0351 | 53 | 8721.5684 | 53 | 11490 | 8721.5684 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 0 | 0 | 0 | 11490 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
182 | Supply Base Slabs | 57 | m3 | 9379.8 | 164.56 | 57 | 11490 | 338.0351 | 57 | 9379.8 | 57 | 11490 | 9379.8 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-04-01 | 4 | 658.23 | 4 | 0 | 658.2316 | april | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 4 | 8497.6923 | 4.4 | 12970.12 | 9347.4615 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 12 | 25493.0769 | 12.2 | 35735.185 | 25917.9615 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 8 | 16995.38 | 7.8 | 22765.07 | 16570.5 | october | 14917.02 | 17191.33 | 19710.78 | 16349.02 | both | TRUE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 15 | 31866.3462 | 13.52 | 39554.665 | 28722.2 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 3 | 6373.27 | 1.32 | 3819.48 | 2804.2385 | november | 6137.31 | 7651.19 | 7103.61 | 7181.09 | both | TRUE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 17 | 36115.1923 | 13.5 | 39899.615 | 28679.7115 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 2 | 4248.85 | -0.02 | 344.95 | -42.4885 | december | 3058.72 | 4286.63 | 3493.68 | 3742.92 | both | TRUE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 19 | 40364.0385 | 14.7 | 43042.1095 | 31229.0192 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 2 | 4248.85 | 1.2 | 3142.49 | 2549.3077 | january | 3058.72 | 3088.61 | 1320.29 | 3016.5 | both | TRUE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 22 | 46737.3077 | 16 | 46146.6595 | 33990.7692 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 3 | 6373.27 | 1.3 | 3104.55 | 2761.75 | february | 6137.31 | 4107.56 | 2228.89 | 4828.85 | both | TRUE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 26 | 55235 | 16.5 | 47158.2945 | 35052.9808 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 4 | 8497.69 | 0.5 | 1011.63 | 1062.2115 | march | 6137.31 | 4614.45 | 3158.49 | 4971.03 | both | TRUE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 26 | 55235 | 17 | 47409.6295 | 36115.1923 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0.5 | 251.33 | 1062.2115 | april | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 26 | 55235 | 17 | 47625.0595 | 36115.1923 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 215.43 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 26 | 55235 | 17 | 48774.0195 | 36115.1923 | 2012-07-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 1148.96 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 26 | weeks | 55235 | 2124.42 | 17 | 49348.4995 | 2869.0588 | 26 | 55235 | 17 | 49348.4995 | 55235 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 574.48 | 19119.8077 | august | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 2 | 2500 | 2 | 729.39 | 2500 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 6 | 7500 | 6 | 4316.95 | 7500 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 4 | 5000 | 4 | 3587.56 | 5000 | october | 5051.4 | 3212.07 | 3213.59 | 3663.64 | both | TRUE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 12 | 15000 | 10 | 9551.79 | 12500 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 6 | 7500 | 4 | 5234.84 | 5000 | november | 2514.97 | 5384.31 | 6202.43 | 4281.82 | both | TRUE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 13 | 16250 | 10 | 9892.69 | 12500 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 1 | 1250 | 0 | 340.9 | 0 | december | 645.88 | 783.71 | 831.4 | 341 | both | TRUE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 13 | 16250 | 10 | 10745.11 | 12500 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 852.42 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 13 | 16250 | 10 | 11027.91 | 12500 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 282.8 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 13 | 16250 | 10 | 11133.96 | 12500 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 106.05 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 13 | 16250 | 13 | 11133.96 | 16250 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 3 | 0 | 3750 | april | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 13 | weeks | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 13 | 16250 | 13 | 11252.71 | 16250 | 2012-07-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 118.75 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 25500 | 25500 | 1 | 5722.72 | 5723 | 0.5 | 12750 | 0.75 | 3922 | 19125 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-10-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 25500 | 25500 | 1 | 5722.72 | 5723 | 1 | 25500 | 1 | 5722.72 | 25500 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-10-01 | 0.5 | 12750 | 0.25 | 1800.72 | 6375 | october | 4719.61 | 3702.31 | 3334.08 | 3870.69 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.2 | 0 | 0.2 | 3377.058 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.3 | 0 | 0.3 | 3810.448 | 0 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0.1 | 0 | 0.1 | 433.39 | 0 | october | 609.44 | 1058.23 | 1723.95 | 843.71 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.4 | 0 | 0.4 | 4399.798 | 0 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0.1 | 0 | 0.1 | 589.35 | 0 | november | 609.44 | 927.46 | 765.97 | 716.43 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.5 | 0 | 0.5 | 4469.298 | 0 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0.1 | 0 | 0.1 | 69.5 | 0 | december | 303.01 | 491.06 | 908.42 | 80.71 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.7 | 0 | 0.7 | 5479.218 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0.2 | 0 | 0.2 | 1009.92 | 0 | january | 1158.64 | 843.26 | 993.12 | 624.21 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.9 | 0 | 0.9 | 5744.188 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0.2 | 0 | 0.2 | 264.97 | 0 | february | 303.01 | 498.23 | 896.55 | 282.11 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 1 | 0 | 1 | 5837.818 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0.1 | 0 | 0.1 | 93.63 | 0 | march | 1158.64 | 432.91 | 966.97 | 279.69 | both | TRUE
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 1 | 0 | 1 | 5849.178 | 0 | 2012-07-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-07-01 | 0 | 0 | 0 | 11.36 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 0.5 | 6900 | 0.5 | 5153.88 | 6900 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 1 | 13800 | 0.9 | 9205.99 | 12420 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0.5 | 6900 | 0.4 | 4052.11 | 5520 | october | 2514.97 | 4144.12 | 5174.7 | 3595.88 | both | TRUE
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 1 | 13800 | 0.95 | 10026.46 | 13110 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 0.05 | 820.47 | 690 | november | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 1 | 13800 | 1 | 10026.46 | 13800 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 0.05 | 0 | 690 | december | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 1 | 13800 | 1 | 10401.46 | 13800 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 0 | 375 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 1 | 13800 | 1 | 10703.96 | 13800 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 0 | 302.5 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 50 | 8210.6142 | 7 | 1214.48 | 1149.486 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 50 | 8210.61 | 7 | 1214.48 | 1149.486 | october | 13406.07 | 5815.02 | 4133.29 | 7872.29 | both | TRUE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 80 | 13136.9827 | 9.6 | 1649.48 | 1576.4379 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 30 | 4926.37 | 2.6 | 435 | 426.9519 | november | 3058.72 | 2027.09 | 160.16 | 2081.55 | both | TRUE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 80 | 13136.9827 | 11 | 1649.48 | 1806.3351 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 1.4 | 0 | 229.8972 | january | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 80 | 13136.9827 | 16 | 2623.88 | 2627.3965 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 5 | 974.4 | 821.0614 | february | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 100 | 16421.2284 | 24 | 2623.88 | 3941.0948 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 20 | 3284.25 | 8 | 0 | 1313.6983 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 100 | 16421.2284 | 24 | 3904.88 | 3941.0948 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 1281 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 100 | m3 | 16421.23 | 164.21 | 24 | 3904.88 | 171.625 | 100 | 16421.2284 | 24 | 3904.88 | 16421.2284 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 12480.1336 | august | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 40 | 8704.1064 | 23.5 | 4207.2 | 5113.6625 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 80 | 17408.2128 | 115 | 20954.32 | 25024.3059 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 40 | 8704.11 | 91.5 | 16747.12 | 19910.6434 | october | 13406.07 | 12592.42 | 14843.96 | 12880.02 | both | TRUE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 80 | 17408.2128 | 136 | 24312.4 | 29593.9618 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 21 | 3358.08 | 4569.6559 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 80 | 17408.2128 | 139 | 24869.2 | 30246.7697 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 3 | 556.8 | 652.808 | december | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 80 | 17408.2128 | 166 | 29756.4 | 36122.0416 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 27 | 4887.2 | 5875.2718 | january | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 80 | 17408.2128 | 249 | 44698.4 | 54183.0623 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 83 | 14942 | 18061.0208 | february | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 117 | 25459.5112 | 254 | 45508 | 55271.0756 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 37 | 8051.3 | 5 | 809.6 | 1088.0133 | march | 1849.43 | 3267.21 | 3180.73 | 2892.27 | both | TRUE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 120 | 26112.3192 | 259 | 45508 | 56359.0889 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 3 | 652.81 | 5 | 0 | 1088.0133 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 120 | 26112.3192 | 259 | 45666 | 56359.0889 | 2012-06-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 158 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 120 | 26112.3192 | 259 | 46335.42 | 56359.0889 | 2012-07-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 669.42 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 120 | m3 | 26112.32 | 217.6 | 259 | 46335.42 | 178.0734 | 120 | 26112.3192 | 259 | 46335.42 | 26112.3192 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | -30246.7697 | august | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 43 | m3 | 8427.72 | 195.99 | 30 | 5390.78 | 179.7 | 0 | 0 | 0 | 31.28 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 43 | m3 | 8427.72 | 195.99 | 30 | 5390.78 | 179.7 | 4.8 | 940.7693 | 0 | 31.28 | 0 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 4.8 | 940.77 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 43 | m3 | 8427.72 | 195.99 | 30 | 5390.78 | 179.7 | 25 | 4899.84 | 0 | 31.28 | 0 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 20.2 | 3959.07 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 43 | m3 | 8427.72 | 195.99 | 30 | 5390.78 | 179.7 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 18 | 3527.88 | 30 | 5359.5 | 5879.808 | january | 3057.01 | 4401.84 | 2831.99 | 3487.83 | both | TRUE
ckm | Kerb Mix | 43 | m3 | 8427.72 | 195.99 | 30 | 5390.78 | 179.7 | 43 | 8427.7248 | 30 | 5390.78 | 8427.7248 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 2547.9168 | august | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 34 | tonne | 22220.82 | 653.55 | 37 | 12410 | 335.4054 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 34 | tonne | 22220.82 | 653.55 | 37 | 12410 | 335.4054 | 12 | 7842.6432 | 37 | 12410 | 24181.4832 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 12 | 7842.64 | 37 | 12410 | 24181.4832 | october | 4719.61 | 10126.88 | 13134.23 | 8305.24 | both | TRUE
csa | Cement Powder (Stabilising) | 34 | tonne | 22220.82 | 653.55 | 37 | 12410 | 335.4054 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 22 | 14378.18 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder (Stabilising) | 34 | tonne | 22220.82 | 653.55 | 37 | 12410 | 335.4054 | 34 | 22220.8224 | 37 | 12410 | 22220.8224 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | -1960.6608 | august | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 100 | tonne | 0 | 0 | 80.66 | 3182.03 | 39.4495 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 100 | tonne | 0 | 0 | 80.66 | 3182.03 | 39.4495 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 100 | tonne | 0 | 0 | 80.66 | 3182.03 | 39.4495 | 0 | 0 | 0 | 0 | 0 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 100 | tonne | 0 | 0 | 80.66 | 3182.03 | 39.4495 | 100 | 0 | 0 | 0 | 0 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 100 | 0 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 100 | tonne | 0 | 0 | 80.66 | 3182.03 | 39.4495 | 100 | 0 | 80.66 | 3182.03 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-01-01 | 2012-02-01 | 0 | 0 | 80.66 | 3182.03 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 455 | m3 | 11300.58 | 24.84 | 375 | 4651.9454 | 24.8827 | 250 | 6209.1082 | 188 | 0 | 4669.2493 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 455 | m3 | 11300.58 | 24.84 | 375 | 4651.9454 | 24.8827 | 380 | 9437.8444 | 295 | 2674.7594 | 7326.7476 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 130 | 3228.74 | 107 | 2674.76 | 2657.4983 | october | 1899.18 | 3706.96 | 6419.38 | 3035.49 | both | TRUE
qms | Sand | 455 | m3 | 11300.58 | 24.84 | 375 | 4651.9454 | 24.8827 | 380 | 9437.8444 | 330 | 3589.7194 | 8196.0228 | 2011-12-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 35 | 914.96 | 869.2751 | december | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 455 | m3 | 11300.58 | 24.84 | 375 | 4651.9454 | 24.8827 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 75 | 1862.73 | 45 | 1062.23 | 1117.6395 | january | 958.97 | 1354.37 | 2819.55 | 947.81 | both | TRUE
qms | Sand | 455 | m3 | 11300.58 | 24.84 | 375 | 4651.9454 | 24.8827 | 455 | 11300.5768 | 375 | 4651.9454 | 11300.5768 | 2012-08-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 1986.9146 | august | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1032 | m2 | 10988.85 | 10.65 | 1032 | 15444.99 | 7.4293 | 600 | 6388.869 | 440 | 11024.79 | 4685.1706 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1032 | m2 | 10988.85 | 10.65 | 1032 | 15444.99 | 7.4293 | 600 | 6388.869 | 512 | 11604.79 | 5451.8349 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 72 | 580 | 766.6643 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1032 | m2 | 10988.85 | 10.65 | 1032 | 15444.99 | 7.4293 | 1032 | 10988.8547 | 748 | 13347.29 | 7964.79 | 2012-01-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 432 | 4599.99 | 236 | 1742.5 | 2512.9551 | january | 2472.03 | 3682.83 | 4108.89 | 2700.86 | both | TRUE
rsm | Mesh | 1032 | m2 | 10988.85 | 10.65 | 1032 | 15444.99 | 7.4293 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2012-02-01 | 0 | 0 | 284 | 2097.7 | 3024.0647 | february | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 2 | each | 6535 | 3267.5 | 2 | 920 | 460 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 2 | each | 6535 | 3267.5 | 2 | 920 | 460 | 0 | 0 | 0 | 0 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 2 | each | 6535 | 3267.5 | 2 | 920 | 460 | 0 | 0 | 0 | 0 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 2 | each | 6535 | 3267.5 | 2 | 920 | 460 | 2 | 6535 | 2 | 0 | 6535 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-07-01 | 2 | 6535 | 2 | 0 | 6535 | april | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 2 | each | 6535 | 3267.5 | 2 | 920 | 460 | 2 | 6535 | 2 | 920 | 6535 | 2012-07-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-07-01 | 0 | 0 | 0 | 920 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 0 | 0 | 0 | 0 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 0 | 0 | 0 | 0 | 0 | 2012-02-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 0 | 0 | 0 | 0 | 0 | 2012-03-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 2 | 1250 | 2 | 0 | 1250 | 2012-04-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 2 | 1250 | 2 | 0 | 1250 | april | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 2 | 1250 | 2 | 551.81 | 1250 | 2012-05-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0 | 551.81 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
swh | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 2 | 1250 | 2 | 1141.81 | 1250 | 2012-06-01 | P022 - P05 Semi-Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0 | 590 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 2 | each | 49.39 | 24.7 | 2 | 5576.5 | 448.5 | 0 | 0 | 0 | 4679.5 | 0 | 2011-09-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-11-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 2 | each | 49.39 | 24.7 | 2 | 5576.5 | 448.5 | 2 | 49.392 | 1 | 5159.5 | 24.696 | 2011-10-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-11-01 | 2 | 49.39 | 1 | 480 | 24.696 | october | 609.44 | 909.76 | 1266.61 | 479.9 | both | TRUE
swp | RCP | 2 | each | 49.39 | 24.7 | 2 | 5576.5 | 448.5 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2011-11-01 | P022 - P05 Semi-Urban Road Reconstruction | 2011-09-01 | 2011-11-01 | 0 | 0 | 1 | 417 | 24.696 | november | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 30 | 7283.3333 | 14.5 | 2701.68 | 1963.7913 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 30 | 7283.33 | 14.5 | 2701.68 | 1963.7913 | november | 4719.61 | 6019.63 | 6062.14 | 5635.11 | both | TRUE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 45 | 10925 | 14.5 | 2701.68 | 1963.7913 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 60 | 14566.6667 | 20.5 | 3812.38 | 2776.3946 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 6 | 1110.7 | 812.6033 | january | 3058.72 | 1857.07 | 763.51 | 2144.06 | both | TRUE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 75 | 18208.3333 | 41.5 | 7648.38 | 5620.5062 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 21 | 3836 | 2844.1116 | february | 3058.72 | 3417.22 | 3487.46 | 3301.41 | both | TRUE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 90 | 21850 | 49 | 9078.38 | 6636.2603 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 7.5 | 1430 | 1015.7541 | march | 3058.72 | 4249.96 | 5178.75 | 3612.09 | both | TRUE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 105 | 25491.6667 | 64 | 11980.48 | 8667.7686 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 15 | 2902.1 | 2031.5083 | april | 3058.72 | 2923.33 | 1569.98 | 3047.39 | both | TRUE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 120 | 29133.3333 | 119 | 21999.28 | 16116.6322 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 55 | 10018.8 | 7448.8636 | may | 3058.72 | 7607.48 | 9671.85 | 6429.61 | both | TRUE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 135 | 32775 | 119 | 21999.28 | 16116.6322 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 15 | 3641.67 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 135 | 32775 | 169 | 31311.88 | 22888.3264 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 50 | 9312.6 | 6771.6942 | july | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 135 | 32775 | 188 | 34782.13 | 25461.5702 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 19 | 3470.25 | 2573.2438 | august | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 135 | 32775 | 230 | 42620.43 | 31149.7934 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 42 | 7838.3 | 5688.2231 | september | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 135 | hrs | 32775 | 242.78 | 242 | 44729.58 | 184.8347 | 135 | 32775 | 242 | 44729.58 | 32775 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 12 | 2109.15 | 1625.2066 | october | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 15 | 2084.3023 | 0 | 0 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 15 | 2084.3 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 30 | 4168.6047 | 0 | 0 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 15 | 2084.3 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 45 | 6252.907 | 9 | 1634.92 | 2172.7273 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 15 | 2084.3 | 9 | 1634.92 | 2172.7273 | march | 3058.72 | 2909.5 | 3048.17 | 2655.96 | both | TRUE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 60 | 8337.2093 | 9 | 1634.92 | 2172.7273 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 15 | 2084.3 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 75 | 10421.5116 | 9 | 1634.92 | 2172.7273 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 15 | 2084.3 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 90 | 12505.814 | 43 | 7912.42 | 10380.8081 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 15 | 2084.3 | 34 | 6277.5 | 8208.0808 | june | 3058.72 | 4704.22 | 5657.43 | 4076.4 | both | TRUE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 145 | 20148.2558 | 54.5 | 10091.92 | 13157.0707 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 55 | 7642.44 | 11.5 | 2179.5 | 2776.2626 | july | 5114.24 | 6497.63 | 7166.06 | 5740.8 | both | TRUE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 172 | 23900 | 59.5 | 11058.92 | 14364.1414 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 27 | 3751.74 | 5 | 967 | 1207.0707 | august | 3058.72 | 1620.93 | 173.82 | 1999.07 | both | TRUE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 172 | 23900 | 65 | 12071.02 | 15691.9192 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 0 | 0 | 5.5 | 1012.1 | 1327.7778 | september | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 172 | 23900 | 69.5 | 12825.67 | 16778.2828 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 0 | 0 | 4.5 | 754.65 | 1086.3636 | october | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 172 | hrs | 23900 | 138.95 | 99 | 18263.07 | 184.4747 | 172 | 23900 | 99 | 18263.07 | 23900 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 0 | 0 | 29.5 | 5437.4 | 7121.7172 | november | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.1 | 2542.5 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.2 | 5085 | 0.05 | 1591.54 | 1271.25 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.05 | 1591.54 | 1271.25 | november | 2096.28 | 2065.71 | 1455.68 | 1944.12 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.3 | 7627.5 | 0.08 | 2350.81 | 2034 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.03 | 759.27 | 762.75 | december | 2096.28 | 1352.81 | 1089.13 | 1225.44 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.4 | 10170 | 0.1 | 2670.9 | 2542.5 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.02 | 320.09 | 508.5 | january | 2096.28 | 779.44 | -94.58 | 902.91 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.5 | 12712.5 | 0.15 | 4611.7 | 3813.75 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.05 | 1940.8 | 1271.25 | february | 2096.28 | 1818.92 | 1804.44 | 1723.6 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.6 | 15255 | 0.15 | 4611.7 | 3813.75 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.7 | 17797.5 | 0.35 | 9695.78 | 8898.75 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.2 | 5084.08 | 5085 | april | 2096.28 | 3750.99 | 3730.62 | 3038.2 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.8 | 20340 | 0.45 | 12901.68 | 11441.25 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.1 | 3205.9 | 2542.5 | may | 2096.28 | 2764.78 | 2848.43 | 2753.99 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 0.9 | 22882.5 | 0.5 | 14673.95 | 12712.5 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0.05 | 1772.27 | 1271.25 | june | 2096.28 | 1583.33 | 1568.79 | 1603.48 | both | TRUE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 1 | 25425 | 0.5 | 14673.95 | 12712.5 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 2542.5 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 1 | 25425 | 0.85 | 25104.7 | 21611.25 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0.35 | 10430.75 | 8898.75 | august | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 1 | 25425 | 0.95 | 27744.07 | 24153.75 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0.1 | 2639.37 | 2542.5 | september | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 25425 | 25425 | 1 | 27869.52 | 27870 | 1 | 25425 | 1 | 27869.52 | 25425 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0.05 | 125.45 | 1271.25 | october | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 1.2 | 195 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 1.2 | 195 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 9 | 1480 | 0 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 7.8 | 1285 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 14 | 2282.5 | 0 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 5 | 802.5 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 17.25 | 2860 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 3.25 | 577.5 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 18.75 | 3107.5 | 0 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 1.5 | 247.5 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 0 | hrs | 0 | 0 | 24.5 | 4054.9 | 165.5102 | 0 | 0 | 24.5 | 4054.9 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-08-01 | 0 | 0 | 5.75 | 947.4 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 1 | 3115 | 0.75 | 1933.19 | 2336.25 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 1 | 3115 | 0.75 | 1933.19 | 2336.25 | may | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 1 | 3115 | 0.75 | 1959.34 | 2336.25 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0 | 26.15 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 1 | 3115 | 0.75 | 1987.65 | 2336.25 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0 | 28.31 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 1 | 3115 | 0.75 | 1997.09 | 2336.25 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0 | 9.44 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 1 | 3115 | 0.9 | 2350.36 | 2803.5 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0.15 | 353.27 | 467.25 | september | 0 | 0 | 0 | 0 | left_only | FALSE
32 | Disposal offsite - Clearing waste | 1 | item | 3115 | 3115 | 1 | 2535.32 | 2535 | 1 | 3115 | 1 | 2535.32 | 3115 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0.1 | 184.96 | 311.5 | october | 0 | 0 | 0 | 0 | left_only | FALSE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 40 | 1524.7102 | 20 | 2940.25 | 762.3551 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 40 | 1524.71 | 20 | 2940.25 | 762.3551 | december | 1824.94 | 1772.71 | 1210.51 | 1462.72 | both | TRUE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 80 | 3049.4205 | 30 | 4770.45 | 1143.5327 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 40 | 1524.71 | 10 | 1830.2 | 381.1776 | march | 2954.94 | 1720.02 | 1214.23 | 1751.04 | both | TRUE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 160 | 6098.8409 | 50 | 7250.785 | 1905.8878 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 80 | 3049.42 | 20 | 2480.34 | 762.3551 | april | 1899.18 | 2454.28 | 927.86 | 2214.05 | both | TRUE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 240 | 9148.2614 | 60 | 8553.17 | 2287.0653 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 80 | 3049.42 | 10 | 1302.39 | 381.1776 | may | 1899.18 | 2335.19 | 1419.53 | 2490.51 | both | TRUE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 240 | 9148.2614 | 80 | 11683.645 | 3049.4205 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 20 | 3130.48 | 762.3551 | august | 0 | 0 | 0 | 0 | left_only | FALSE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 240 | 9148.2614 | 150 | 15479.395 | 5717.6633 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 70 | 3795.75 | 2668.2429 | september | 0 | 0 | 0 | 0 | left_only | FALSE
33 | Re-spread topsoil | 240 | m3 | 9148.26 | 38.12 | 240 | 25138.27 | 104.7417 | 240 | 9148.2614 | 240 | 25138.27 | 9148.2614 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 90 | 9658.87 | 3430.598 | october | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 0 | 0 | 0 | 330 | 0 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0 | 330 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 0.25 | 19711.2769 | 0.1 | 1352.8 | 7884.5108 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0.25 | 19711.28 | 0.1 | 1022.8 | 7884.5108 | february | 1405.82 | 3297.72 | 1735.96 | 2206.04 | both | TRUE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 0.5 | 39422.5538 | 0.15 | 2167.925 | 11826.7661 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0.25 | 19711.28 | 0.05 | 815.12 | 3942.2554 | march | 1405.82 | 2146.84 | 284.42 | 1234.11 | both | TRUE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 0.75 | 59133.8307 | 0.15 | 2167.925 | 11826.7661 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0.25 | 19711.28 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 1 | 78845.1076 | 0.55 | 7077.435 | 43364.8092 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0.25 | 19711.28 | 0.4 | 4909.51 | 31538.0431 | may | 5554.16 | 4824.93 | 2741.03 | 4909.61 | both | TRUE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 1 | 78845.1076 | 0.9 | 11067.78 | 70960.5969 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0.35 | 3990.34 | 27595.7877 | july | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 1 | item | 78845.11 | 78845.11 | 1 | 12448.88 | 12449 | 1 | 78845.1076 | 1 | 12448.88 | 78845.1076 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-08-01 | 0 | 0 | 0.1 | 1381.1 | 7884.5108 | august | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 0 | m3 | 0 | 0 | 10 | 193.5 | 19.35 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-05-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 0 | m3 | 0 | 0 | 10 | 193.5 | 19.35 | 0 | 0 | 10 | 193.5 | 0 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-05-01 | 0 | 0 | 10 | 193.5 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 120 | 1984.6873 | 384 | 18346.464 | 6350.9993 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 895 | 14802.4593 | 384 | 37000.539 | 6350.9993 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 775 | 12817.77 | 0 | 18654.08 | 0 | november | 15290.35 | 17457.16 | 16756.1 | 16081.54 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 895 | 14802.4593 | 384 | 40441.939 | 6350.9993 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 3441.4 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 2325 | 38453.3161 | 1257 | 71961.764 | 20789.5993 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1430 | 23650.86 | 873 | 31519.82 | 14438.6 | january | 36035.78 | 29786.15 | 30542.47 | 30464.3 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 3323 | 54959.2987 | 1908 | 97868.889 | 31556.5278 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 998 | 16505.98 | 651 | 25907.12 | 10766.9285 | february | 15290.35 | 25171.73 | 29230.42 | 21054.01 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 4192 | 69331.7425 | 3134 | 114354.864 | 51833.4162 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 869 | 14372.44 | 1226 | 16485.97 | 20276.8884 | march | 15290.35 | 15771.31 | 14990.89 | 14721.81 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 5892 | 97448.1457 | 3134 | 164115.944 | 51833.4162 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1700 | 28116.4 | 0 | 49761.08 | 0 | april | 36035.78 | 28279.79 | 26681.69 | 29758.93 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 6335 | 104774.9496 | 5721 | 188753.5315 | 94619.9663 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 443 | 7326.8 | 2587 | 24637.59 | 42786.55 | may | 27472.44 | 21208.65 | 20892.84 | 22607.42 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 6987 | 115558.4171 | 6519 | 230001.577 | 107818.1367 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 652 | 10783.47 | 798 | 41248.05 | 13198.1704 | june | 15290.35 | 19066.55 | 20452.73 | 17068.49 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 7825 | 129418.15 | 6780 | 238750.477 | 112134.8316 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 838 | 13859.73 | 261 | 8748.9 | 4316.6948 | july | 15290.35 | 15469.14 | 14141.21 | 14536.45 | both | TRUE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 7825 | 129418.15 | 7378 | 274349.877 | 122025.1899 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 598 | 35599.4 | 9890.3583 | august | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 7825 | 129418.15 | 7649 | 305562.633 | 126507.2753 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 271 | 31212.76 | 4482.0855 | september | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 7825 | m3 | 129418.15 | 16.54 | 7825 | 308767.983 | 39.4592 | 7825 | 129418.15 | 7825 | 308767.983 | 129418.15 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 176 | 3205.35 | 2910.8747 | october | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 20 | 1059.6278 | 20 | 0 | 1059.6278 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 20 | 1059.63 | 20 | 0 | 1059.6278 | february | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 960 | 50862.1331 | 960 | 42660.3837 | 50862.1331 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 940 | 49802.51 | 940 | 42660.38 | 49802.5054 | april | 46217.61 | 46296.34 | 50846.74 | 44666.89 | both | TRUE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 1795 | 95101.5927 | 1795 | 81882.5185 | 95101.5927 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 835 | 44239.46 | 835 | 39222.13 | 44239.4595 | may | 46217.61 | 42904.07 | 46823.87 | 42729.43 | both | TRUE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 1805 | 95631.4066 | 1805 | 81882.5185 | 95631.4066 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 10 | 529.81 | 10 | 0 | 529.8139 | june | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 2444 | 129486.5139 | 2444 | 146832.5735 | 129486.5139 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 639 | 33855.11 | 639 | 64950.06 | 33855.1074 | july | 62249.6 | 55788.07 | 65168.02 | 55261.5 | both | TRUE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 2605 | 138016.5175 | 2605 | 206533.272 | 138016.5175 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 161 | 8530 | 161 | 59700.7 | 8530.0036 | august | 36434.42 | 40404.41 | 49627.06 | 36925.84 | both | TRUE
57 | Remove & Replace unsuitable | 2605 | m3 | 138016.52 | 52.98 | 2605 | 215667.317 | 82.8641 | 2605 | 138016.5175 | 2605 | 215667.317 | 138016.5175 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-09-01 | 0 | 0 | 0 | 9134.05 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 200 | 363.0226 | 200 | 530.25 | 363.0226 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 935 | 1697.1308 | 935 | 2080.5 | 1697.1308 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 735 | 1334.11 | 735 | 1550.25 | 1334.1082 | november | 2852.72 | 5309.94 | -422.15 | 3849.73 | both | TRUE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 2935 | 5327.3571 | 3180 | 2080.5 | 5772.0598 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 2000 | 3630.23 | 2245 | 0 | 4074.929 | february | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 3725 | 6761.2965 | 5223.3333 | 3667.625 | 9480.941 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 790 | 1433.94 | 2043.3333 | 1587.13 | 3708.8812 | march | 2852.72 | 3023.95 | -2959.38 | 2077.92 | both | TRUE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 5000 | 9075.5658 | 5223.3333 | 3667.625 | 9480.941 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 1275 | 2314.27 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 6500 | 11798.2355 | 9535 | 3667.625 | 17307.1039 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 1500 | 2722.67 | 4311.6667 | 0 | 7826.1629 | may | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 9000 | 16336.0184 | 10865 | 3667.625 | 19721.2044 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 2500 | 4537.78 | 1330 | 0 | 2414.1005 | june | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 12767 | 23173.5496 | 11300 | 3667.625 | 20510.7786 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 3767 | 6837.53 | 435 | 0 | 789.5742 | july | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 12767 | m2 | 23173.55 | 1.82 | 12767 | 4390.425 | 0.34386 | 12767 | 23173.5496 | 12767 | 4390.425 | 23173.5496 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 1467 | 722.8 | 2662.771 | august | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 500 | 12263.0927 | 400 | 3990.07 | 9607.4547 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 1000 | 24526.1855 | 800 | 29107.38 | 19214.9094 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 500 | 12263.09 | 400 | 25117.31 | 9607.4547 | november | 15290.35 | 22284.11 | 22879.31 | 17450.32 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 1200 | 29431.4226 | 1000 | 44215.21 | 24018.6368 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 200 | 4905.24 | 200 | 15107.83 | 4803.7274 | december | 9318.44 | 15599.46 | 15366.63 | 10894.21 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 2200 | 53957.608 | 1900 | 59531.29 | 45635.4099 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1000 | 24526.19 | 900 | 15316.08 | 21616.7731 | january | 26663.16 | 25388.72 | 24098.31 | 22985.7 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 3000 | 73578.5564 | 2700 | 76785.94 | 64850.3193 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 800 | 19620.95 | 800 | 17254.65 | 19214.9094 | february | 26663.16 | 20025.16 | 16474.68 | 19593.84 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 4000 | 98104.7419 | 3521 | 110169.115 | 84569.6201 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1000 | 24526.19 | 821 | 33383.18 | 19719.3008 | march | 26663.16 | 28000.58 | 28860.48 | 24595.32 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 5600 | 137346.6386 | 5100 | 152455.78 | 122495.0475 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1600 | 39241.9 | 1579 | 42286.67 | 37925.4275 | april | 26663.16 | 38334.9 | 41860.38 | 31787.65 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 8500 | 208472.5765 | 6810 | 194475.9775 | 163566.9164 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 2900 | 71125.94 | 1710 | 42020.2 | 41071.8689 | may | 54283.13 | 49116.75 | 49186.74 | 48220.44 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 9500 | 232998.762 | 7830 | 229892.6485 | 188065.9259 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1000 | 24526.19 | 1020 | 35416.67 | 24499.0095 | june | 26663.16 | 27050 | 27120.12 | 24240.66 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 11000 | 269788.0402 | 9070 | 260952.6235 | 217849.0355 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1500 | 36789.28 | 1240 | 31059.98 | 29783.1096 | july | 26663.16 | 37790.03 | 42376.28 | 31122.36 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 11525 | 282664.2876 | 10060 | 333157.8355 | 241627.4859 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 525 | 12876.25 | 990 | 72205.21 | 23778.4504 | august | 15290.35 | 19327.37 | 18591.58 | 15403.43 | both | TRUE
62 | Place & Compact Gravel | 11525 | tonne | 282664.29 | 24.53 | 11768.54 | 382852.6255 | 32.5319 | 11525 | 282664.2876 | 11768.54 | 382852.6255 | 282664.2876 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 1708.54 | 49694.79 | 41036.8017 | september | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 240 | 617.9828 | 240 | 0 | 617.9828 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 240 | 617.9828 | 240 | 4226.71 | 617.9828 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 4226.71 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 1122 | 2889.0698 | 1122 | 4226.71 | 2889.0698 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 882 | 2271.09 | 882 | 0 | 2271.0869 | december | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 1122 | 2889.0698 | 1122 | 7927.91 | 2889.0698 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 3701.2 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 3522 | 9068.8981 | 1122 | 14756.62 | 2889.0698 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 2400 | 6179.83 | 0 | 6828.71 | 0 | march | 6156.67 | 6735.18 | 4780.78 | 5363.55 | both | TRUE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 4467.6 | 11503.7505 | 1122 | 30773.57 | 2889.0698 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 945.6 | 2434.85 | 0 | 16016.95 | 0 | april | 6156.67 | 12832.36 | 13775.45 | 9708.76 | both | TRUE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 7800 | 20084.4422 | 7785.6 | 36702.47 | 20047.3633 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 3332.4 | 8580.69 | 6663.6 | 5928.9 | 17158.2935 | may | 10658.13 | 8943.24 | 5871.65 | 8775.24 | both | TRUE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 9000 | 23174.3564 | 9486 | 46879.845 | 24425.7717 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1200 | 3089.91 | 1700.4 | 10177.38 | 4378.4084 | june | 6156.67 | 8454.29 | 7964.34 | 6825.61 | both | TRUE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 10500 | 27036.7492 | 10465.2 | 47698.995 | 26947.1416 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1500 | 3862.39 | 979.2 | 819.15 | 2521.37 | july | 6156.67 | 4077.7 | 652.06 | 3729.42 | both | TRUE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 15532 | 39993.7893 | 12639.6 | 66733.096 | 32546.0662 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 5032 | 12957.04 | 2174.4 | 19034.1 | 5598.9245 | august | 18318.04 | 18300.97 | 18131.7 | 16591.2 | both | TRUE
63 | Trim All Layers | 15532 | m2 | 39993.79 | 2.57 | 15532 | 86275.348 | 5.5547 | 15532 | 39993.7893 | 15532 | 86275.348 | 39993.7893 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 2892.4 | 19542.25 | 7447.7232 | september | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 200 | 2383.6036 | 200 | 1377.5 | 2383.6036 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 935 | 11143.347 | 935 | 10775.265 | 11143.347 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 735 | 8759.74 | 735 | 9397.76 | 8759.7433 | december | 10658.13 | 11276.72 | 7486.49 | 9835.87 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 2935 | 34979.3832 | 935 | 10775.265 | 11143.347 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 2000 | 23836.04 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 3723 | 44370.7815 | 935 | 10775.265 | 11143.347 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 788 | 9391.4 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 6500 | 77467.1179 | 6488 | 72009.515 | 77324.1016 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 2777 | 33096.34 | 5553 | 61234.25 | 66180.7547 | may | 62249.6 | 50421.75 | 53707.59 | 52122.41 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 7500 | 89385.136 | 7905 | 79412.515 | 94211.9333 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1000 | 11918.02 | 1417 | 7403 | 16887.8317 | june | 10658.13 | 7899.08 | 1810.47 | 7910.22 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 8750 | 104282.6587 | 8721 | 86553.345 | 103937.0361 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1250 | 14897.52 | 816 | 7140.83 | 9725.1028 | july | 10658.13 | 10452.5 | 5237.41 | 9345.24 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 12767 | 152157.3375 | 10533 | 198423.965 | 125532.485 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4017 | 47874.68 | 1812 | 111870.62 | 21595.4489 | august | 77534.32 | 92071.34 | 114294.92 | 83468.06 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 12767 | 152157.3375 | 12767 | 274117.525 | 152157.3375 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 2234 | 75693.56 | 26624.8525 | september | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 12767 | m2 | 152157.34 | 11.92 | 12767 | 274290.025 | 10.0581 | 12767 | 152157.3375 | 12767 | 274290.025 | 152157.3375 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 172.5 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 1335.3 | tonne | 374978.97 | 280.82 | 1335.96 | 261664.129 | 305.056 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 1335.3 | tonne | 374978.97 | 280.82 | 1335.96 | 261664.129 | 305.056 | 400 | 112328.0063 | 355 | 108392.669 | 99641.8555 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 400 | 112328.01 | 355 | 108392.67 | 99641.8555 | may | 54283.13 | 58928.88 | 74647.95 | 55993.94 | both | TRUE
65 | Asphalt | 1335.3 | tonne | 374978.97 | 280.82 | 1335.96 | 261664.129 | 305.056 | 900 | 252738.0142 | 824 | 251275.169 | 231281.3773 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 500 | 140410.01 | 469 | 142882.5 | 131639.5218 | july | 112816.37 | 98422.61 | 120794.62 | 99751.65 | both | TRUE
65 | Asphalt | 1335.3 | tonne | 374978.97 | 280.82 | 1335.96 | 261664.129 | 305.056 | 1335.3 | 374978.967 | 1125 | 251275.169 | 315766.4435 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 435.3 | 122240.95 | 301 | 0 | 84485.0662 | august | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 1335.3 | tonne | 374978.97 | 280.82 | 1335.96 | 261664.129 | 305.056 | 1335.3 | 374978.967 | 1326 | 258529.919 | 372183.3814 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 201 | 7254.75 | 56416.9379 | september | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 1335.3 | tonne | 374978.97 | 280.82 | 1335.96 | 261664.129 | 305.056 | 1335.3 | 374978.967 | 1335.96 | 261664.129 | 374978.967 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2012-05-01 | 2012-10-01 | 0 | 0 | 9.96 | 3134.21 | 2795.5856 | october | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 20487.65 | 20487.65 | 1 | 4773.75 | 4774 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 20487.65 | 20487.65 | 1 | 4773.75 | 4774 | 1 | 20487.6543 | 0 | 0 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 1 | 20487.65 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 20487.65 | 20487.65 | 1 | 4773.75 | 4774 | 1 | 20487.6543 | 0.45 | 2153 | 9219.4444 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0.45 | 2153 | 9219.4444 | september | 0 | 0 | 0 | 0 | left_only | FALSE
66 | Linemarking | 1 | item | 20487.65 | 20487.65 | 1 | 4773.75 | 4774 | 1 | 20487.6543 | 1 | 4773.75 | 20487.6543 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0.55 | 2620.75 | 11268.2099 | november | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 0.5 | 4105 | 0.1 | 415.45 | 821 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0.5 | 4105 | 0.1 | 415.45 | 821 | april | 3057.01 | 1243.56 | -975.61 | 1630.43 | both | TRUE
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 0.5 | 4105 | 0.25 | 945.7 | 2052.5 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0.15 | 530.25 | 1231.5 | june | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 0.5 | 4105 | 0.5 | 1563.2 | 4105 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0.25 | 617.5 | 2052.5 | july | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 1 | 8210 | 0.5 | 1563.2 | 4105 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0.5 | 4105 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Install Road Furniture | 1 | item | 8210 | 8210 | 1 | 2520.95 | 2521 | 1 | 8210 | 1 | 2520.95 | 8210 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0.5 | 957.75 | 4105 | september | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation | 3335 | m2 | 47402.51 | 14.21 | 3335 | 46094.08 | 13.8213 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
68 | Insitu Stabilisation | 3335 | m2 | 47402.51 | 14.21 | 3335 | 46094.08 | 13.8213 | 985 | 14000.4421 | 985 | 13611.895 | 14000.4421 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 985 | 14000.44 | 985 | 13611.9 | 14000.4421 | april | 10658.13 | 13475.75 | 16214.53 | 12674 | both | TRUE
68 | Insitu Stabilisation | 3335 | m2 | 47402.51 | 14.21 | 3335 | 46094.08 | 13.8213 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 2350 | 33402.07 | 2350 | 32482.18 | 33402.07 | june | 25708.8 | 30037.94 | 37622.29 | 28270.14 | both | TRUE
68 | Insitu Stabilisation | 3335 | m2 | 47402.51 | 14.21 | 3335 | 46094.08 | 13.8213 | 3335 | 47402.5122 | 3335 | 46094.08 | 47402.5122 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-08-01 | 0 | 47402.51 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 250 | 11476.5781 | 250 | 3547.1 | 11476.5781 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 250 | 11476.58 | 250 | 3547.1 | 11476.5781 | november | 6137.31 | 5465.57 | 2770.46 | 4273.52 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 542 | 24881.2214 | 250 | 3711.73 | 11476.5781 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 292 | 13404.64 | 0 | 164.63 | 0 | february | 6137.31 | 2820.71 | -914.55 | 2535.5 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 618 | 28370.1012 | 618 | 24033.01 | 28370.1012 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 76 | 3488.88 | 368 | 20321.28 | 16893.523 | march | 3058.72 | 3322.5 | 2169.77 | 1499.3 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 1124 | 51598.6953 | 900 | 35554.82 | 41315.6813 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 506 | 23228.59 | 282 | 11521.81 | 12945.5801 | april | 6137.31 | 10189.57 | 8431.85 | 7534.07 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 1180 | 54169.4488 | 618 | 39508.57 | 28370.1012 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 56 | 2570.75 | -282 | 3953.75 | -12945.5801 | may | 3058.72 | 3930.97 | 2418.88 | 2523.54 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 1519 | 69731.6888 | 1100 | 44816.72 | 50496.9438 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 339 | 15562.24 | 482 | 5308.15 | 22126.8427 | june | 6137.31 | 4835.28 | 2152.76 | 3907.35 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 2278 | 104574.58 | 1400 | 54736.045 | 64268.8376 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 759 | 34842.89 | 300 | 9919.33 | 13771.8938 | july | 5841.9 | 18370.69 | 21119.02 | 12654.07 | both | TRUE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 2278 | 104574.58 | 1600 | 62825.1593 | 73450.1001 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 200 | 8089.11 | 9181.2625 | august | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 2278 | 104574.58 | 1700 | 69605.6343 | 78040.7313 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 100 | 6780.48 | 4590.6313 | september | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 2278 | 104574.58 | 2100 | 86079.5843 | 96403.2564 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 400 | 16473.95 | 18362.525 | october | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 2278 | m | 104574.58 | 45.91 | 2278 | 86929.5843 | 38.1607 | 2278 | 104574.58 | 2278 | 86929.5843 | 104574.58 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 178 | 850 | 8171.3236 | november | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 5.63 | m3 | 5599.75 | 994.63 | 5.63 | 13301.4 | 2362.5222 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 5.63 | m3 | 5599.75 | 994.63 | 5.63 | 13301.4 | 2362.5222 | 0 | 0 | 0 | 141.4 | 0 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-01-01 | 0 | 0 | 0 | 141.4 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 5.63 | m3 | 5599.75 | 994.63 | 5.63 | 13301.4 | 2362.5222 | 5.63 | 5599.75 | 1.75 | 4001.4 | 1740.5972 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-01-01 | 5.63 | 5599.75 | 1.75 | 3860 | 1740.5972 | december | 5795.74 | 4854.38 | 3433.62 | 4467.91 | both | TRUE
72 | Form & Pour Headwalls | 5.63 | m3 | 5599.75 | 994.63 | 5.63 | 13301.4 | 2362.5222 | 5.63 | 5599.75 | 5.63 | 13301.4 | 5599.75 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-01-01 | 0 | 0 | 3.88 | 9300 | 3859.1528 | january | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 0 | 0 | 0 | 360 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 0 | 0 | 0 | 360 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 120 | 1281.6976 | 90 | 4660 | 961.2732 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 120 | 1281.7 | 90 | 4300 | 961.2732 | february | 1824.94 | 4555.49 | 5672.57 | 3982.5 | both | TRUE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 120 | 1281.6976 | 100 | 5212.8 | 1068.0813 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 0 | 0 | 10 | 552.8 | 106.8081 | march | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 120 | 1281.6976 | 120 | 6172.3 | 1281.6976 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 0 | 0 | 20 | 959.5 | 213.6163 | april | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 260 | 2777.0114 | 260 | 13640.675 | 2777.0114 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 140 | 1495.31 | 140 | 7468.37 | 1495.3138 | may | 6869.26 | 6994.81 | 7885.16 | 7557.76 | both | TRUE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 400 | 4272.3252 | 400 | 20798.85 | 4272.3252 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 140 | 1495.31 | 140 | 7158.17 | 1495.3138 | june | 6869.26 | 6048.26 | 6977.7 | 6559.14 | both | TRUE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 750 | 8010.6097 | 485 | 25310.23 | 5180.1943 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 350 | 3738.28 | 85 | 4511.38 | 907.8691 | july | 2472.03 | 4199.89 | 4544.35 | 3763.25 | both | TRUE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 1069 | 11417.789 | 575 | 29815.23 | 6141.4674 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 319 | 3407.18 | 90 | 4505 | 961.2732 | august | 2472.03 | 4806.61 | 5354.39 | 4281.19 | both | TRUE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 1069 | 11417.789 | 750 | 39114.5 | 8010.6097 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 0 | 0 | 175 | 9299.27 | 1869.1423 | september | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 1069 | m2 | 11417.79 | 10.68 | 1069 | 55980.8 | 52.3676 | 1069 | 11417.789 | 1069 | 55980.8 | 11417.789 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-10-01 | 0 | 0 | 319 | 16866.3 | 3407.1793 | october | 0 | 0 | 0 | 0 | left_only | FALSE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 90 | 900 | 90 | 2715.72 | 900 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 90 | 900 | 90 | 2715.72 | 900 | november | 1153.96 | 3049.26 | 3292.6 | 1894.06 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 120 | 1200 | 120 | 3652.495 | 1200 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 30 | 300 | 30 | 936.78 | 300 | january | 958.97 | 962.7 | 605.59 | 270.05 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 140 | 1400 | 140 | 4218.095 | 1400 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 20 | 200 | 20 | 565.6 | 200 | february | 1103.31 | 807.32 | 592.42 | 362.56 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 150 | 1500 | 150 | 4530.695 | 1500 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 10 | 100 | 10 | 312.6 | 100 | march | 1153.96 | 1190.77 | 1574.5 | 397.85 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 177 | 1770 | 156 | 4684.745 | 1560 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 27 | 270 | 6 | 154.05 | 60 | may | 1153.96 | 1368.98 | 1005.95 | 1160.88 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 177 | 1770 | 160 | 4826.145 | 1600 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 4 | 141.4 | 40 | june | 0 | 0 | 0 | 0 | left_only | FALSE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 248 | 2480 | 177 | 5321.045 | 1770 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 71 | 710 | 17 | 494.9 | 170 | july | 958.97 | 1081.58 | 920.27 | 286.99 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 300 | 3000 | 248 | 7397.32 | 2480 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 52 | 520 | 71 | 2076.28 | 710 | august | 1824.94 | 1843.39 | 1755.96 | 1177.3 | both | TRUE
75 | Saw Cutting | 300 | m | 3000 | 10 | 300 | 8705.77 | 29.02 | 300 | 3000 | 300 | 8705.77 | 3000 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 52 | 1308.45 | 520 | september | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 0 | 0 | 0 | 300.475 | 0 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 0 | 300.48 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 30.42 | 13488.0193 | 30.42 | 8879.99 | 13488.0193 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 30.42 | 13488.02 | 30.42 | 8579.52 | 13488.0193 | january | 5629.51 | 7465.24 | 8653.55 | 6196.21 | both | TRUE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 51.48 | 22825.8787 | 51.48 | 15528.44 | 22825.8787 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 21.06 | 9337.86 | 21.06 | 6648.45 | 9337.8595 | march | 5629.51 | 6209.46 | 7769.41 | 5223.55 | both | TRUE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 66.6 | 29529.983 | 51.48 | 15528.44 | 22825.8787 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 15.12 | 6704.1 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 66.6 | 29529.983 | 58.5 | 17758.585 | 25938.4986 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 7.02 | 2230.15 | 3112.6198 | july | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 66.6 | 29529.983 | 66.6 | 19882.545 | 29529.983 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 8.1 | 2123.96 | 3591.4844 | august | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 66.6 | m | 29529.98 | 443.39 | 66.6 | 19984.005 | 300.0601 | 66.6 | 29529.983 | 66.6 | 19984.005 | 29529.983 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 0 | 101.46 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 0 | 0 | 0 | 70.7 | 0 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 0 | 70.7 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 2 | 7695.7895 | 2 | 2064.225 | 7695.7895 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 2 | 7695.79 | 2 | 1993.52 | 7695.7895 | january | 1405.82 | 3774.61 | 3114.31 | 2016.56 | both | TRUE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 5 | 19239.4737 | 3 | 2970.525 | 11543.6842 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 3 | 11543.68 | 1 | 906.3 | 3847.8947 | march | 1405.82 | 3191.65 | 2370.36 | 1636.94 | both | TRUE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 6 | 23087.3684 | 6 | 5692.925 | 23087.3684 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 1 | 3847.89 | 3 | 2722.4 | 11543.6842 | april | 3058.72 | 4199.1 | 2965.75 | 2945.32 | both | TRUE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 12 | 46174.7368 | 11 | 9640.315 | 42326.8421 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 6 | 23087.37 | 5 | 3947.39 | 19239.4737 | may | 5554.16 | 7410.19 | 5934.79 | 6538.04 | both | TRUE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 14 | 53870.5263 | 11 | 9640.315 | 42326.8421 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 2 | 7695.79 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 19 | 73110 | 12 | 9923.115 | 46174.7368 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 5 | 19239.47 | 1 | 282.8 | 3847.8947 | july | 1405.82 | 4355.6 | 2887.13 | 2558.89 | both | TRUE
85 | Install SW Pits & Chambers | 19 | each | 73110 | 3847.89 | 19 | 16398.015 | 863.0526 | 19 | 73110 | 19 | 16398.015 | 73110 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-10-01 | 0 | 0 | 7 | 6474.9 | 26935.2632 | october | 0 | 0 | 0 | 0 | left_only | FALSE
86 | SW Sub-Contract Works | 1 | item | 17380 | 17380 | 1 | 41911.81 | 41912 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
86 | SW Sub-Contract Works | 1 | item | 17380 | 17380 | 1 | 41911.81 | 41912 | 0 | 0 | 0 | 71.81 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 71.81 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
86 | SW Sub-Contract Works | 1 | item | 17380 | 17380 | 1 | 41911.81 | 41912 | 1 | 17380 | 1 | 41911.81 | 17380 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1 | 17380 | 1 | 41840 | 17380 | september | 2514.97 | 2250.78 | -4425.17 | 2038.3 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 500 | 20262.079 | 487 | 11174.725 | 19735.265 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 500 | 20262.08 | 487 | 11174.72 | 19735.265 | november | 25708.8 | 13798.39 | 11422.05 | 15681.62 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 500 | 20262.079 | 487 | 11892.875 | 19735.265 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 718.15 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 500 | 20262.079 | 523 | 14670.175 | 21194.1347 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 36 | 2777.3 | 1458.8697 | january | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 1000 | 40524.158 | 973 | 25627 | 39430.0058 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 500 | 20262.08 | 450 | 10956.82 | 18235.8711 | february | 25708.8 | 11284.71 | 8179.16 | 13995.34 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 1400 | 56733.8213 | 1269 | 30238.4 | 51425.1566 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 400 | 16209.66 | 296 | 4611.4 | 11995.1508 | march | 1449.61 | 5123.36 | 4898.96 | 2129.17 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 1400 | 56733.8213 | 1331 | 30238.4 | 53937.6544 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 62 | 0 | 2512.4978 | april | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 1800 | 72943.4845 | 1600 | 33913.3 | 64838.6529 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 400 | 16209.66 | 269 | 3674.9 | 10900.9985 | may | 1449.61 | 5887.67 | 5283.42 | 3269.94 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 2400 | 97257.9793 | 2118 | 45796.425 | 85830.1667 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 600 | 24314.49 | 518 | 11883.13 | 20991.5139 | june | 25708.8 | 13560.2 | 11426.32 | 15566.92 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 2803 | 113589.215 | 2200 | 46263.925 | 89153.1477 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 403 | 16331.24 | 82 | 467.5 | 3322.981 | july | 1449.61 | 3708.36 | 2203.37 | 1232.59 | both | TRUE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 2803 | 113589.215 | 2803 | 58565.375 | 113589.215 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 603 | 12301.45 | 24436.0673 | august | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 2803 | m | 113589.22 | 40.52 | 2803 | 58724.45 | 20.9504 | 2803 | 113589.215 | 2803 | 58724.45 | 113589.215 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 159.07 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0 | 0 | 0 | 920 | 0 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0 | 0 | 0 | 920 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0.15 | 42345.36 | 0.13 | 43097.1 | 36699.312 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0.15 | 42345.36 | 0.13 | 42177.1 | 36699.312 | march | 54283.13 | 46336.14 | 46578.1 | 45869.7 | both | TRUE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0.25 | 70575.6 | 0.22 | 73213.5 | 62106.528 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0.1 | 28230.24 | 0.09 | 30116.4 | 25407.216 | april | 14412.59 | 20417.02 | 14860.99 | 16653.94 | both | TRUE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0.5 | 141151.2 | 0.46 | 151583.5 | 129859.104 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0.25 | 70575.6 | 0.24 | 78370 | 67752.576 | may | 54283.13 | 71698.93 | 82678.6 | 63478.05 | both | TRUE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0.6 | 169381.44 | 0.6 | 196911.5 | 169381.44 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0.1 | 28230.24 | 0.14 | 45328 | 39522.336 | june | 14412.59 | 31287.43 | 33356.53 | 23649.58 | both | TRUE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 0.7 | 197611.68 | 0.63 | 207821.5 | 177850.512 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0.1 | 28230.24 | 0.03 | 10910 | 8469.072 | july | 14412.59 | 19800.09 | 14951.59 | 15978.24 | both | TRUE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 1 | 282302.4 | 0.85 | 280837.5 | 239957.04 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0.3 | 84690.72 | 0.22 | 73016 | 62106.528 | august | 54283.13 | 69744.18 | 78142.3 | 61993.3 | both | TRUE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 1 | 282302.4 | 0.98 | 280837.5 | 276656.352 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0 | 0 | 0.13 | 0 | 36699.312 | september | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 1 | item | 282302.4 | 282302.4 | 1 | 287637.5 | 329550 | 1 | 282302.4 | 1 | 287637.5 | 282302.4 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-11-01 | 0 | 0 | 0.02 | 6800 | 5646.048 | november | 0 | 0 | 0 | 0 | left_only | FALSE
110 | Electrical & Telecom | 0 | item | 0 | 0 | 1 | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-06-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
110 | Electrical & Telecom | 0 | item | 0 | 0 | 1 | 110 | 110 | 0 | 0 | 1 | 110 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-06-01 | 2012-06-01 | 0 | 0 | 1 | 110 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
120 | Landscaping Sub-contractors | 0 | item | 0 | 0 | 1 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
120 | Landscaping Sub-contractors | 0 | item | 0 | 0 | 1 | 350 | 350 | 0 | 0 | 1 | 350 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-08-01 | 0 | 0 | 1 | 350 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 3005 | m2 | 14478.48 | 4.82 | 3005 | 5977.08 | 2.1055 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 3005 | m2 | 14478.48 | 4.82 | 3005 | 5977.08 | 2.1055 | 3005 | 14478.475 | 350 | 388.85 | 1686.3448 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 3005 | 14478.48 | 350 | 388.85 | 1686.3448 | august | 2852.72 | 8226.9 | -193.62 | 5750.16 | both | TRUE
121 | Landscaping Sub-contractors | 3005 | m2 | 14478.48 | 4.82 | 3005 | 5977.08 | 2.1055 | 3005 | 14478.475 | 2085 | 4027.08 | 10045.7971 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 1735 | 3638.23 | 8359.4523 | october | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 3005 | m2 | 14478.48 | 4.82 | 3005 | 5977.08 | 2.1055 | 3005 | 14478.475 | 3005 | 5977.08 | 14478.475 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 920 | 1950 | 4432.6779 | november | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 150 | 13200.4709 | 4 | 392.1 | 2081.0982 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 370 | 32561.1616 | 11.5 | 1169.8 | 5983.1574 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 7.5 | 777.7 | 3902.0592 | november | 6137.31 | 3217.97 | -1450.91 | 4117.25 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 590 | 51921.8522 | 14 | 1452.6 | 7283.8438 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 2.5 | 282.8 | 1300.6864 | december | 6137.31 | 5226.08 | 2493.68 | 5157.96 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 810 | 71282.5429 | 14 | 1452.6 | 7283.8438 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 1030 | 90643.2336 | 24 | 2477.75 | 12486.5894 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 10 | 1025.15 | 5202.7456 | february | 6137.31 | 5229.95 | 2476.61 | 5357.24 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 1250 | 110003.9242 | 34.5 | 3511.725 | 17949.4723 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 10.5 | 1033.97 | 5462.8829 | march | 6137.31 | 3101.9 | -523.15 | 3753.48 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 1470 | 129364.6149 | 63.5 | 6481.875 | 33037.4346 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 29 | 2970.15 | 15087.9622 | april | 6137.31 | 5302.41 | 1456.45 | 5469.42 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 1690 | 148725.3055 | 154 | 15744.025 | 80122.2822 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 90.5 | 9262.15 | 47084.8477 | may | 6137.31 | 6596.47 | 4187.1 | 6659.62 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 1910 | 168085.9962 | 161 | 16434.625 | 83764.2042 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 7 | 690.6 | 3641.9219 | june | 6137.31 | 2806.84 | -1224.91 | 3822.68 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 2130 | 187446.6869 | 223 | 22795.575 | 116021.2269 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 220 | 19360.69 | 62 | 6360.95 | 32257.0227 | july | 6137.31 | 5097.7 | 2200.17 | 5060.27 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 2217 | 195102.96 | 298 | 30373.01 | 155041.8189 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 87 | 7656.27 | 75 | 7577.44 | 39020.592 | august | 6137.31 | 8300.85 | 8465 | 7043.41 | both | TRUE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 2217 | 195102.96 | 367 | 37429.48 | 190940.7635 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 69 | 7056.47 | 35898.9446 | september | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 2217 | 195102.96 | 373 | 38098.98 | 194062.4109 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 6 | 669.5 | 3121.6474 | october | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2217 | hrs | 195102.96 | 88 | 375 | 38275.73 | 102.0693 | 2217 | 195102.96 | 375 | 38275.73 | 195102.96 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 2 | 176.75 | 1040.5491 | november | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 2000 | 10000 | 450 | 1843.575 | 20718.75 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 2000 | 10000 | 500 | 2002.65 | 23020.8333 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 50 | 159.08 | 2302.0833 | november | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 2000 | 10000 | 600 | 2374.39 | 27625 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 100 | 371.74 | 4604.1667 | january | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 3000 | 15000 | 600 | 2374.39 | 27625 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1000 | 5000 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 3000 | 15000 | 750 | 2957.665 | 34531.25 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 150 | 583.28 | 6906.25 | march | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 4000 | 20000 | 750 | 2957.665 | 34531.25 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1000 | 5000 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 5000 | 25000 | 1100 | 4411.67 | 50645.8333 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 1000 | 5000 | 350 | 1454 | 16114.5833 | may | 1449.61 | 3383.65 | 213.99 | 1455.43 | both | TRUE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 7000 | 35000 | 1100 | 4411.67 | 50645.8333 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 2000 | 10000 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 9000 | 45000 | 1150 | 4613.72 | 52947.9167 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 2000 | 10000 | 50 | 202.05 | 2302.0833 | july | 1449.61 | 6943.79 | 5384.1 | 3100.02 | both | TRUE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 11050 | 55250 | 1150 | 4613.72 | 52947.9167 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 2050 | 10250 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences | 11050 | m | 55250 | 5 | 1200 | 4825.82 | 4.0217 | 11050 | 55250 | 1200 | 4825.82 | 55250 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 50 | 212.1 | 2302.0833 | october | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 25.2 | 5582.4931 | 12 | 9003.025 | 2658.33 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 25.2 | 5582.4931 | 18.6 | 12534.825 | 4120.4116 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 6.6 | 3531.8 | 1462.0815 | november | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 25.2 | 5582.4931 | 25.2 | 14467.875 | 5582.4931 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 6.6 | 1933.05 | 1462.0815 | december | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 64.8 | 14354.9822 | 64.8 | 20079.275 | 14354.9822 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 39.6 | 8772.49 | 39.6 | 5611.4 | 8772.4891 | february | 11719.06 | 7242.95 | 6935.38 | 7647.92 | both | TRUE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 64.8 | 14354.9822 | 64.8 | 20471.375 | 14354.9822 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 392.1 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 202.4 | 44837.1667 | 64.8 | 20471.375 | 14354.9822 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 137.6 | 30482.18 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 202.4 | 44837.1667 | 202.4 | 64546.375 | 44837.1667 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 137.6 | 44075 | 30482.1845 | july | 0 | 0 | 0 | 0 | left_only | FALSE
181 | Place Box Culverts | 202.4 | m | 44837.17 | 221.53 | 202.4 | 65321.65 | 325.5534 | 202.4 | 44837.1667 | 202.4 | 65321.65 | 44837.1667 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 775.28 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
182 | Supply Base Slabs | 0 | item | 0 | 0 | 1 | 570 | 570 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-01-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
182 | Supply Base Slabs | 0 | item | 0 | 0 | 1 | 570 | 570 | 0 | 0 | 1 | 570 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-01-01 | 0 | 0 | 1 | 570 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
201 | Non Conformance | 0 | item | 0 | 0 | 1 | 13650.62 | 13651 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
201 | Non Conformance | 0 | item | 0 | 0 | 1 | 13650.62 | 13651 | 0 | 0 | 1 | 13650.62 | 0 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-11-01 | 0 | 0 | 1 | 13650.62 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
220 | Protective Work | 0 | item | 0 | 0 | 1 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-06-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
220 | Protective Work | 0 | item | 0 | 0 | 1 | 1500 | 1500 | 0 | 0 | 1 | 1500 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-06-01 | 2012-06-01 | 0 | 0 | 1 | 1500 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 0 | 0 | 0 | 420 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 0 | 0 | 0 | 420 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 1500 | 23653.8462 | 1475 | 31753.728 | 23259.6154 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 1500 | 23653.85 | 1475 | 31333.73 | 23259.6154 | april | 22048.5 | 26020.57 | 31128.89 | 23731.72 | both | TRUE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 1800 | 28384.6154 | 1761 | 31753.728 | 27769.6154 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 300 | 4730.77 | 286 | 0 | 4510 | may | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 1800 | 28384.6154 | 1802 | 31753.728 | 28416.1538 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 0 | 0 | 41 | 0 | 646.5385 | june | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 1885 | 29725 | 1802 | 31753.728 | 28416.1538 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 85 | 1340.38 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Stone / Rock | 1885 | tonne | 29725 | 15.77 | 1885 | 31753.728 | 17.6414 | 1885 | 29725 | 1885 | 31753.728 | 29725 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-09-01 | 0 | 0 | 83 | 0 | 1308.8462 | september | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 1800 | 6604.258 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 1800 | 6604.258 | 1652 | 11551.5 | 6061.2412 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 1652 | 11551.5 | 6061.2412 | november | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 4000 | 14676.1289 | 3812 | 23754.8 | 13986.3508 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 2200 | 8071.87 | 2160 | 12203.3 | 7925.1096 | january | 10658.13 | 11660.69 | 8976.11 | 9027.23 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 7500 | 27517.7417 | 7138 | 43750.6 | 26189.552 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 3500 | 12841.61 | 3326 | 19995.8 | 12203.2012 | february | 10658.13 | 13789.6 | 11685.16 | 10482.62 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 10000 | 36690.3222 | 19400 | 62671.85 | 71179.2251 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 2500 | 9172.58 | 12262 | 18921.25 | 44989.6731 | march | 10658.13 | 15773.6 | 15905.14 | 11591.33 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 27000 | 99063.87 | 24500 | 80452.86 | 89891.2894 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 17000 | 62373.55 | 5100 | 17781.01 | 18712.0643 | april | 50751.9 | 37394.84 | 29158.6 | 37625.36 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 34000 | 124747.0955 | 30000 | 99607.46 | 110070.9666 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 7000 | 25683.23 | 5500 | 19154.6 | 20179.6772 | may | 36035.78 | 26611.04 | 23205.42 | 26940.23 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 38580 | 141551.2631 | 38580 | 123613.56 | 141551.2631 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 4580 | 16804.17 | 8580 | 24006.1 | 31480.2965 | june | 4191.71 | 21013.07 | 24003.01 | 13105.37 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 38580 | 141551.2631 | 38580 | 126686.96 | 141551.2631 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 3073.4 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 40080 | 147054.8114 | 38580 | 128160.96 | 141551.2631 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 1500 | 5503.55 | 0 | 1474 | 0 | august | 6156.67 | 4529.58 | -800.33 | 3111.49 | both | TRUE
222 | Supply & Place Geofabrics | 40080 | m2 | 147054.81 | 3.67 | 40080 | 129487.46 | 3.2307 | 40080 | 147054.8114 | 40080 | 129487.46 | 147054.8114 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 1500 | 1326.5 | 5503.5483 | september | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 2 | 3850.3571 | 2 | 405 | 3369.0625 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 6 | 11551.0714 | 6 | 405 | 10107.1875 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | november | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 10 | 19251.7857 | 10 | 405 | 16845.3125 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | december | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 14 | 26952.5 | 14 | 405 | 23583.4375 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | january | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 18 | 34653.2143 | 18 | 405 | 30321.5625 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | february | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 22 | 42353.9286 | 22 | 405 | 37059.6875 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | march | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 26 | 50054.6429 | 26 | 405 | 43797.8125 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | april | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 30 | 57755.3571 | 30 | 405 | 50535.9375 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | may | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 34 | 65456.0714 | 34 | 405 | 57274.0625 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | june | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 38 | 73156.7857 | 38 | 405 | 64012.1875 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | july | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 42 | 80857.5 | 42 | 405 | 70750.3125 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 7700.71 | 4 | 0 | 6738.125 | august | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 42 | 80857.5 | 44 | 405 | 74119.375 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 2 | 0 | 3369.0625 | september | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 42 | 80857.5 | 46 | 405 | 77488.4375 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 2 | 0 | 3369.0625 | october | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 42 | weeks | 80857.5 | 1925.18 | 48 | 658 | 0 | 42 | 80857.5 | 48 | 658 | 80857.5 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 2 | 253 | 3369.0625 | november | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 2 | 5727.7249 | 5.2 | 13526.855 | 11169.0635 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 6 | 17183.1746 | 8.5 | 22713.005 | 18257.123 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 3.3 | 9186.15 | 7088.0595 | november | 11320.57 | 11366.35 | 10492.12 | 11047.49 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 10 | 28638.6243 | 10.1 | 27021.605 | 21693.7579 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 1.6 | 4308.6 | 3436.6349 | december | 11320.57 | 7907.82 | 5775.44 | 8553.5 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 14 | 40094.0741 | 12.5 | 33520.41 | 26848.7103 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 2.4 | 6498.81 | 5154.9524 | january | 11320.57 | 8286.36 | 6099.91 | 8846.47 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 18 | 51549.5238 | 16 | 42783.9 | 34366.3492 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 3.5 | 9263.49 | 7517.6389 | february | 11320.57 | 8840 | 7229.16 | 9353.02 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 22 | 63004.9735 | 21.1 | 56715.04 | 45320.623 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 5.1 | 13931.14 | 10954.2738 | march | 11320.57 | 13052.97 | 14276.05 | 11849.34 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 26 | 74460.4233 | 26 | 69999.89 | 55845.3175 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 4.9 | 13284.85 | 10524.6944 | april | 11320.57 | 12820.01 | 12400.08 | 11991.81 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 30 | 85915.873 | 31.2 | 84074.65 | 67014.381 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 5.2 | 14074.76 | 11169.0635 | may | 11320.57 | 11804.35 | 11471.25 | 11688.55 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 34 | 97371.3228 | 36.2 | 97646.74 | 77753.8651 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 5 | 13572.09 | 10739.4841 | june | 11320.57 | 12996.3 | 13951.99 | 12072.68 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 38 | 108826.7725 | 41.8 | 112695.3154 | 89782.0873 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 5.6 | 15048.58 | 12028.2222 | july | 11320.57 | 12635.26 | 13175.41 | 11595.55 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 42 | 120282.2222 | 47.9 | 129067.9954 | 102884.2579 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 4 | 11455.45 | 6.1 | 16372.68 | 13102.1706 | august | 11320.57 | 13648.73 | 14582.97 | 12379.15 | both | TRUE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 42 | 120282.2222 | 53 | 142999.1354 | 113838.5317 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 5.1 | 13931.14 | 10954.2738 | september | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 42 | 120282.2222 | 55.9 | 150862.3304 | 120067.4325 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 2.9 | 7863.2 | 6228.9008 | october | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 42 | weeks | 120282.22 | 2863.86 | 56 | 150862.3304 | 2705.7143 | 42 | 120282.2222 | 56 | 150862.3304 | 120282.2222 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-11-01 | 0 | 0 | 0.1 | 0 | 214.7897 | november | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 2 | 2500 | 2.9 | 750.58 | 2718.75 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 6 | 7500 | 6 | 2720.22 | 5625 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 3.1 | 1969.64 | 2906.25 | november | 3058.72 | 3147.45 | 2433.82 | 2812.3 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 10 | 12500 | 6 | 2720.22 | 5625 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 14 | 17500 | 16.8 | 4272.22 | 15750 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 10.8 | 1552 | 10125 | january | 3058.72 | 1513.6 | 332.87 | 1546.35 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 18 | 22500 | 22.9 | 5837.02 | 21468.75 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 6.1 | 1564.8 | 5718.75 | february | 3058.72 | 1616.22 | 747.53 | 1761.27 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 22 | 27500 | 22.9 | 5837.02 | 21468.75 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 0 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 26 | 32500 | 23.4 | 5962.02 | 21937.5 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 0.5 | 125 | 468.75 | april | 3058.72 | 1199.29 | -1048.01 | 1557.02 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 30 | 37500 | 29.1 | 7419.52 | 27281.25 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 5.7 | 1457.5 | 5343.75 | may | 3058.72 | 2248.2 | 1294.23 | 2588.7 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 34 | 42500 | 34.7 | 8856.72 | 32531.25 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 5.6 | 1437.2 | 5250 | june | 3058.72 | 1422.4 | 578.08 | 1668.16 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 38 | 47500 | 39.9 | 10176.72 | 37406.25 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 5.2 | 1320 | 4875 | july | 3058.72 | 1370.88 | 291.9 | 1391.16 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 42 | 52500 | 45.3 | 11540.72 | 42468.75 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 4 | 5000 | 5.4 | 1364 | 5062.5 | august | 3058.72 | 1580.52 | 425.89 | 1655.01 | both | TRUE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 42 | 52500 | 50.6 | 12906.52 | 47437.5 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 5.3 | 1365.8 | 4968.75 | september | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 42 | weeks | 52500 | 1250 | 56 | 14376.32 | 256.7143 | 42 | 52500 | 56 | 14376.32 | 52500 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 5.4 | 1469.8 | 5062.5 | october | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0.75 | 24375 | 0.6 | 18281.81 | 19500 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0.75 | 24375 | 0.6 | 18281.81 | 19500 | november | 29134.33 | 16056.66 | 14981.96 | 19649.5 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0.75 | 24375 | 0.6 | 18893.81 | 19500 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 612 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0.75 | 24375 | 0.7 | 20141.27 | 22750 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 1247.46 | 3250 | march | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0.75 | 24375 | 0.7 | 21581.27 | 22750 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 1440 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0.75 | 24375 | 0.7 | 21800.27 | 22750 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 219 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 0.75 | 24375 | 0.8 | 23436.11 | 26000 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 1635.84 | 3250 | june | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 1 | 32500 | 0.9 | 25093.55 | 29250 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0.25 | 8125 | 0.1 | 1657.44 | 3250 | july | 2795.89 | 3223.74 | 3293.01 | 2519.07 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 1 | 32500 | 0.9 | 28294.05 | 29250 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 3200.5 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 1 | 32500 | 0.9 | 29683.9 | 29250 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 1389.85 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 32500 | 32500 | 1 | 29769.1 | 29769 | 1 | 32500 | 1 | 29769.1 | 32500 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 85.2 | 3250 | october | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.1 | 695.05 | 0 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 695.05 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.2 | 1275.22 | 0 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 580.17 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.3 | 1850.066 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 574.85 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.4 | 2924.096 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 1074.03 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.5 | 4223.026 | 0 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 1298.93 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.6 | 7172.926 | 0 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 2949.9 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.7 | 8068.601 | 0 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 895.67 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.8 | 9756.451 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 1687.85 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.9 | 11068.731 | 0 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 1312.28 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.9 | 12303.091 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 1234.36 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 0.9 | 13382.734 | 0 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 1079.64 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 0 | item | 0 | 0 | 1 | 13752.069 | 13752 | 0 | 0 | 1 | 13752.069 | 0 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.1 | 369.34 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.1 | 1870 | 0.1 | 1141.72 | 1870 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.2 | 3740 | 0.1 | 1281.52 | 1870 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 1870 | 0 | 139.8 | 0 | november | 2681.29 | 803.51 | -455.54 | 1321.66 | both | TRUE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.3 | 5610 | 0.1 | 1560.94 | 1870 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 1870 | 0 | 279.42 | 0 | february | 633.01 | 790.79 | 738.08 | 611.95 | both | TRUE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.5 | 9350 | 0.4 | 4882.34 | 7480 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.2 | 3740 | 0.3 | 3321.4 | 5610 | march | 5051.4 | 3071 | 3484.4 | 3277.53 | both | TRUE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.5 | 9350 | 0.6 | 6852.34 | 11220 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0.2 | 1970 | 3740 | april | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.6 | 11220 | 0.8 | 9256.14 | 14960 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 1870 | 0.2 | 2403.8 | 3740 | may | 2681.29 | 1923.82 | 1604.62 | 2403.9 | both | TRUE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.7 | 13090 | 0.9 | 9949.14 | 16830 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.1 | 1870 | 0.1 | 693 | 1870 | june | 633.01 | 866.17 | 995.15 | 692.9 | both | TRUE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 0.7 | 13090 | 0.9 | 12285.79 | 16830 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 2336.65 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 1 | 18700 | 0.95 | 13626.15 | 17765 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0.3 | 5610 | 0.05 | 1340.36 | 935 | august | 5051.4 | 4486.28 | 4873.97 | 4374.48 | both | TRUE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 1 | 18700 | 1 | 14152.61 | 18700 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0.05 | 526.46 | 935 | september | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment / disestablishment | 1 | item | 18700 | 18700 | 1 | 14352.61 | 14353 | 1 | 18700 | 1 | 14352.61 | 18700 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 200 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
908 | Safety Work wear | 0 | item | 0 | 0 | 1 | 413.73 | 413.73 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
908 | Safety Work wear | 0 | item | 0 | 0 | 1 | 413.73 | 413.73 | 0 | 0 | 0.65683 | 271.75 | 0 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0.65683 | 271.75 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
908 | Safety Work wear | 0 | item | 0 | 0 | 1 | 413.73 | 413.73 | 0 | 0 | 1 | 413.73 | 0 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0.34317 | 141.98 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0.044859 | 117.84 | 0 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0.044859 | 117.84 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0.14731 | 386.96 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0.10245 | 269.12 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0.24476 | 642.95 | 0 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0.097449 | 255.99 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0.34221 | 898.94 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0.097449 | 255.99 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 0.41132 | 1080.5 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0.069116 | 181.56 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 0 | item | 0 | 0 | 1 | 2626.9 | 2626.9 | 0 | 0 | 1 | 2626.9 | 0 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-11-01 | 0 | 0 | 0.58868 | 1546.4 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0.032775 | 450.75 | 0 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0.032775 | 450.75 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0.12402 | 1705.675 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0.091249 | 1254.92 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0.50573 | 6955.15 | 0 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0.3817 | 5249.48 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0.60562 | 8328.95 | 0 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0.099893 | 1373.8 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 0.68669 | 9443.95 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0.081075 | 1115 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather Stand Down | 0 | hrs | 0 | 0 | 327 | 13752.765 | 42.0574 | 0 | 0 | 1 | 13752.765 | 0 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-01-01 | 2012-07-01 | 0 | 0 | 0.31331 | 4308.81 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
915 | Maintenance | 0 | item | 0 | 0 | 22 | 925.02 | 42.0464 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-11-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
915 | Maintenance | 0 | item | 0 | 0 | 22 | 925.02 | 42.0464 | 0 | 0 | 0.17197 | 159.075 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-11-01 | 0 | 0 | 0.17197 | 159.07 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
915 | Maintenance | 0 | item | 0 | 0 | 22 | 925.02 | 42.0464 | 0 | 0 | 0.83812 | 775.275 | 0 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-11-01 | 0 | 0 | 0.66615 | 616.2 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
915 | Maintenance | 0 | item | 0 | 0 | 22 | 925.02 | 42.0464 | 0 | 0 | 1 | 925.02 | 0 | 2012-11-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-11-01 | 0 | 0 | 0.16188 | 149.74 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | 20 Mpa | 0 | m3 | 0 | 0 | 2.25 | 372.81 | 165.6933 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | 20 Mpa | 0 | m3 | 0 | 0 | 2.25 | 372.81 | 165.6933 | 0 | 0 | 0.68614 | 255.8 | 0 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0.68614 | 255.8 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | 20 Mpa | 0 | m3 | 0 | 0 | 2.25 | 372.81 | 165.6933 | 0 | 0 | 1 | 372.81 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-06-01 | 0 | 0 | 0.31386 | 117.01 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 0 | 0 | 3.7 | 639.16 | 1219.3814 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 3.7 | 639.16 | 1219.3814 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 0 | 0 | 4.5 | 786.11 | 1483.0315 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 0.8 | 146.95 | 263.65 | december | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 0 | 0 | 11.4 | 1973.59 | 3757.013 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 6.9 | 1187.48 | 2273.9816 | january | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 6 | 3004.0285 | 11.4 | 1973.59 | 3757.013 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 6 | 3004.03 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 6 | 3004.0285 | 25 | 4072.69 | 8239.0637 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 13.6 | 2099.1 | 4482.0506 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 13 | 6508.7285 | 25 | 4072.69 | 8239.0637 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 7 | 3504.7 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 20 | 10013.4284 | 29.3 | 4703.09 | 9656.1826 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 7 | 3504.7 | 4.3 | 630.4 | 1417.1189 | june | 3058.72 | 1694.79 | 577.45 | 1779.01 | both | TRUE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 37.5 | 18775.1783 | 42.3 | 6955.89 | 13940.4957 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 17.5 | 8761.75 | 13 | 2252.8 | 4284.3131 | july | 1849.43 | 2341.57 | 1067.97 | 1678.76 | both | TRUE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 50 | 25033.571 | 46.8 | 7725.89 | 15423.5272 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 12.5 | 6258.39 | 4.5 | 770 | 1483.0315 | august | 589.26 | 1482.47 | 90.55 | 808.24 | both | TRUE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 50 | 25033.571 | 72.4 | 12163.27 | 23860.3283 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 25.6 | 4437.38 | 8436.8012 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 50 | m3 | 25033.57 | 500.67 | 75.96 | 12777.37 | 173.1174 | 50 | 25033.571 | 75.96 | 12777.37 | 25033.571 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-10-01 | 0 | 0 | 3.56 | 614.1 | 1173.2427 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 0 | 0 | 0 | 1027.52 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 42.75 | 3370.5301 | 39.6 | 3727.95 | 2957.1013 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 42.75 | 3370.53 | 39.6 | 2700.43 | 2957.1013 | november | 3058.72 | 5565.33 | 5934.47 | 4920.43 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 48.38 | 3814.4152 | 47.4 | 5156.11 | 3539.5606 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 5.63 | 443.89 | 7.8 | 1428.16 | 582.4593 | december | 1103.31 | 2604.1 | 2806.37 | 2082.89 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 48.38 | 3814.4152 | 45.4 | 5156.11 | 3390.2121 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | -2 | 0 | -149.3486 | january | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 84.88 | 6692.1777 | 90.7 | 5156.11 | 6772.9568 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 36.5 | 2877.76 | 45.3 | 0 | 3382.7447 | february | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 94.38 | 7441.1844 | 134.6 | 13190.41 | 10051.1575 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 9.5 | 749.01 | 43.9 | 8034.3 | 3278.2007 | march | 2954.94 | 5547.72 | 7354.1 | 4539.87 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 205 | 16162.7761 | 217.2 | 19988.21 | 16219.2526 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 110.62 | 8721.59 | 82.6 | 6797.8 | 6168.0951 | april | 5114.24 | 6820.32 | 6415.44 | 6477.09 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 260 | 20499.1307 | 247.6 | 25554.208 | 18489.3506 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 55 | 4336.35 | 30.4 | 5566 | 2270.098 | may | 3058.72 | 5772.38 | 6432.79 | 5429.84 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 321 | 25308.5421 | 301 | 35339.828 | 22476.9569 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 61 | 4809.41 | 53.4 | 9785.62 | 3987.6063 | june | 3058.72 | 7550.1 | 9785.35 | 6201.39 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 415.6 | 32767.072 | 347.4 | 42843.938 | 25941.8432 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 94.6 | 7458.53 | 46.4 | 7504.11 | 3464.8864 | july | 5114.24 | 7746.62 | 9101.35 | 6776.1 | both | TRUE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 415.6 | 32767.072 | 409.6 | 54234.838 | 30586.5832 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 62.2 | 11390.9 | 4644.7399 | august | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 415.6 | 32767.072 | 433.6 | 58636.468 | 32378.7658 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 24 | 4401.63 | 1792.1826 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 415.6 | m3 | 32767.07 | 78.84 | 438.8 | 59600.368 | 183.2748 | 415.6 | 32767.072 | 438.8 | 59600.368 | 32767.072 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 5.2 | 963.9 | 388.3062 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c40 | 40 Mpa | 0 | m3 | 0 | 0 | 7.8 | 1518.62 | 194.6949 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-07-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c40 | 40 Mpa | 0 | m3 | 0 | 0 | 7.8 | 1518.62 | 194.6949 | 0 | 0 | 2.6421 | 514.4 | 0 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-07-01 | 0 | 0 | 2.6421 | 514.4 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c40 | 40 Mpa | 0 | m3 | 0 | 0 | 7.8 | 1518.62 | 194.6949 | 0 | 0 | 7.8 | 1518.62 | 0 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-07-01 | 0 | 0 | 5.1579 | 1004.22 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 21 | 4052.5437 | 21 | 4036.36 | 9989.6872 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 21 | 4052.54 | 21 | 4036.36 | 9989.6872 | november | 3058.72 | 4805.87 | 2468.67 | 3789.25 | both | TRUE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 65 | 12543.5875 | 65 | 12347.88 | 30920.4605 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 44 | 8491.04 | 44 | 8311.52 | 20930.7732 | february | 11719.06 | 7573.46 | 5070.55 | 8311.62 | both | TRUE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 100 | 19297.827 | 111.56 | 20965.02 | 53069.0241 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 35 | 6754.24 | 46.56 | 8617.14 | 22148.5637 | april | 7116.63 | 8061.17 | 5976.36 | 7219.56 | both | TRUE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 100 | 19297.827 | 111.56 | 20983.15 | 53069.0241 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 18.13 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 275 | 53069.0241 | 111.56 | 21255.195 | 53069.0241 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 175 | 33771.2 | 0 | 272.04 | 0 | june | 2744.08 | 12731.06 | 12502.94 | 9358.98 | both | TRUE
ckm | Concrete - Keb Mix | 275 | m3 | 53069.02 | 192.98 | 111.56 | 21753.955 | 194.9978 | 275 | 53069.0241 | 111.56 | 21753.955 | 53069.0241 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 498.76 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 5 | 3767.8913 | 5 | 0 | 1762.7561 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 8 | 6028.626 | 7 | 0 | 2467.8586 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 3 | 2260.73 | 2 | 0 | 705.1025 | january | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 30 | 22607.3475 | 39 | 6089.32 | 13749.4979 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 22 | 16578.72 | 32 | 6089.32 | 11281.6393 | april | 1849.43 | 8601.08 | 9137.82 | 6524.02 | both | TRUE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 40 | 30143.13 | 66.5 | 11409.9715 | 23444.6567 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 10 | 7535.78 | 27.5 | 5320.65 | 9695.1588 | may | 4719.61 | 5835 | 5818.24 | 5807.92 | both | TRUE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 40 | 30143.13 | 69.5 | 11772.6965 | 24502.3104 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 3 | 362.73 | 1057.6537 | june | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 40 | 30143.13 | 73 | 12407.4665 | 25736.2396 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 3.5 | 634.77 | 1233.9293 | august | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 40 | 30143.13 | 75.5 | 12407.4665 | 26617.6177 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 2.5 | 0 | 881.3781 | september | 0 | 0 | 0 | 0 | left_only | FALSE
csa | Cement Powder | 40 | tonne | 30143.13 | 753.58 | 85.5 | 14398.4665 | 197.0724 | 40 | 30143.13 | 85.5 | 14398.4665 | 30143.13 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-10-01 | 0 | 0 | 10 | 1991 | 3525.5123 | october | 0 | 0 | 0 | 0 | left_only | FALSE
css | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
css | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 3 | 0 | 21 | 3249 | 0 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 3 | 0 | 21 | 3249 | 0 | november | 5326.7 | 2538.7 | 1888.84 | 3249.1 | both | TRUE
css | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 4 | 0 | 25 | 3929.94 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 1 | 0 | 4 | 680.94 | 0 | february | 645.88 | 924.47 | 1154.83 | 680.84 | both | TRUE
css | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 6 | 0 | 27 | 4110.94 | 0 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 2 | 0 | 2 | 181 | 0 | march | 1158.64 | 708.77 | 1066.05 | 473.83 | both | TRUE
css | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 0 | 0 | 27 | 4110.94 | 0 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
css | Stabilised Sand | 6 | m3 | 0 | 0 | 27 | 4110.94 | 152.2593 | 6 | 0 | 27 | 4110.94 | 0 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-06-01 | 0 | 0 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 1500 | 55089.4138 | 1475 | 53387.92 | 54171.2569 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 1500 | 55089.41 | 1475 | 53387.92 | 54171.2569 | april | 46217.61 | 45029.25 | 50135.85 | 44051 | both | TRUE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 1800 | 66107.2966 | 1761 | 63646.936 | 64674.9718 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 300 | 11017.88 | 286 | 10259.02 | 10503.7149 | may | 6137.31 | 13433.36 | 15454.47 | 10714.77 | both | TRUE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 1800 | 66107.2966 | 1802 | 65146.936 | 66180.7491 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 41 | 1500 | 1505.7773 | june | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 1800 | 66107.2966 | 1802 | 65308.4336 | 66180.7491 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 0 | 161.5 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 1885 | 69229.03 | 1802 | 65308.4336 | 66180.7491 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 85 | 3121.73 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Rock | 1885 | tonne | 69229.03 | 36.73 | 1885 | 68183.8936 | 36.1719 | 1885 | 69229.03 | 1885 | 68183.8936 | 69229.03 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2012-04-01 | 2012-09-01 | 0 | 0 | 83 | 2875.46 | 3048.2809 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 50 | 759.0141 | 32 | 431.68 | 489.3061 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 150 | 2277.0422 | 141 | 1900.5 | 2156.0052 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 100 | 1518.03 | 109 | 1468.82 | 1666.6991 | november | 2954.94 | 2249.24 | 1029.27 | 2212.9 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 200 | 3036.0562 | 199 | 2681.4017 | 3042.8726 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 50 | 759.01 | 58 | 780.9 | 886.8674 | january | 958.97 | 1132.99 | 311.93 | 648.65 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 300 | 4554.0843 | 296 | 3998.0249 | 4526.0819 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 100 | 1518.03 | 97 | 1316.62 | 1483.2093 | february | 1824.94 | 1462.55 | 784.11 | 1289.9 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 430 | 6527.5209 | 427 | 5767.2079 | 6529.1789 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 130 | 1973.44 | 131 | 1769.18 | 2003.097 | march | 2954.94 | 2001.53 | 1687.46 | 1769.28 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 580 | 8804.5631 | 570 | 7702.1241 | 8715.7658 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 150 | 2277.04 | 143 | 1934.92 | 2186.5869 | april | 1899.18 | 2671.55 | 1445.84 | 2168.97 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 700 | 10626.1968 | 680 | 9183.4229 | 10397.7557 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 120 | 1821.63 | 110 | 1481.3 | 1681.9899 | may | 2954.94 | 2282.51 | 1326.47 | 2595.77 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 830 | 12599.6333 | 833 | 11252.638 | 12737.2507 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 130 | 1973.44 | 153 | 2069.22 | 2339.495 | june | 2954.94 | 1943.51 | 1361.28 | 1991.75 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 988.8 | 15010.262 | 857 | 11569.6751 | 13104.2303 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 158.8 | 2410.63 | 24 | 317.04 | 366.9796 | july | 1899.18 | 2714.91 | 2564.71 | 1921.76 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 996 | 15119.56 | 988.8 | 13264.1642 | 15119.56 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 7.2 | 109.3 | 131.8 | 1694.49 | 2015.3297 | august | 1103.31 | 1895.26 | 1560.26 | 1244.55 | both | TRUE
qms | Sand | 996 | tonne | 15119.56 | 15.18 | 988.8 | 13323.9074 | 13.4749 | 996 | 15119.56 | 988.8 | 13323.9074 | 15119.56 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 59.74 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | each | 4620 | 4620 | 1 | 959.07 | 959 | 0.5 | 2310 | 0.4 | 445.2 | 1848 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | each | 4620 | 4620 | 1 | 959.07 | 959 | 0.5 | 2310 | 0.6 | 578.95 | 2772 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 0.2 | 133.75 | 924 | november | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | each | 4620 | 4620 | 1 | 959.07 | 959 | 0.5 | 2310 | 0.9 | 870.43 | 4158 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 0.3 | 291.48 | 1386 | december | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | each | 4620 | 4620 | 1 | 959.07 | 959 | 1 | 4620 | 0.9 | 870.43 | 4158 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0.5 | 2310 | 0 | 0 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
rfs | Signs | 1 | each | 4620 | 4620 | 1 | 959.07 | 959 | 1 | 4620 | 1 | 959.07 | 4620 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-03-01 | 0 | 0 | 0.1 | 88.64 | 462 | march | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 432 | 4471.8065 | 403.2 | 4350 | 4173.686 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 864 | 8943.6129 | 720 | 8180.2 | 7453.0108 | 2011-11-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 432 | 4471.81 | 316.8 | 3830.2 | 3279.3247 | november | 7179.81 | 3773.92 | 2696.53 | 4422.89 | both | TRUE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 864 | 8943.6129 | 806.4 | 8558.1 | 8347.3721 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 86.4 | 377.9 | 894.3613 | december | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 1123.2 | 11626.6968 | 1022.4 | 11001.6 | 10583.2753 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 259.2 | 2683.08 | 216 | 2443.5 | 2235.9032 | april | 12590.7 | 4063.13 | 1762.36 | 6292.66 | both | TRUE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 1339.2 | 13862.6 | 1022.4 | 11001.6 | 10583.2753 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 216 | 2235.9 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 1339.2 | 13862.6 | 1195.2 | 12814.358 | 12371.9979 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 172.8 | 1812.76 | 1788.7226 | july | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 1339.2 | 13862.6 | 1267.2 | 13600.358 | 13117.299 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 72 | 786 | 745.3011 | august | 0 | 0 | 0 | 0 | left_only | FALSE
rsm | Mesh | 1339.2 | m2 | 13862.6 | 10.35 | 1339.2 | 14373.948 | 10.7333 | 1339.2 | 13862.6 | 1339.2 | 14373.948 | 13862.6 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 72 | 773.59 | 745.3011 | september | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 202.4 | m | 68168.09 | 336.8 | 202.4 | 67270 | 332.3617 | 25.2 | 8487.3311 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 202.4 | m | 68168.09 | 336.8 | 202.4 | 67270 | 332.3617 | 43.2 | 14549.7105 | 33.6 | 11100 | 11316.4415 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 18 | 6062.38 | 33.6 | 11100 | 11316.4415 | february | 6137.31 | 4775.04 | 1467.19 | 4263.11 | both | TRUE
swc | RCBC | 202.4 | m | 68168.09 | 336.8 | 202.4 | 67270 | 332.3617 | 43.2 | 14549.7105 | 43.2 | 14604 | 14549.7105 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 9.6 | 3504 | 3233.269 | march | 0 | 0 | 0 | 0 | left_only | FALSE
swc | RCBC | 202.4 | m | 68168.09 | 336.8 | 202.4 | 67270 | 332.3617 | 202.4 | 68168.088 | 194.4 | 64204 | 65473.6972 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 159.2 | 53618.38 | 151.2 | 49600 | 50923.9867 | july | 46217.61 | 40787.23 | 43654.93 | 40800.47 | both | TRUE
swc | RCBC | 202.4 | m | 68168.09 | 336.8 | 202.4 | 67270 | 332.3617 | 202.4 | 68168.088 | 202.4 | 67270 | 68168.088 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-10-01 | 2012-09-01 | 0 | 0 | 8 | 3066 | 2694.3908 | september | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 17 | 2684.2105 | 0 | 0 | 0 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 17 | 2684.21 | 0 | 0 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 17 | 2684.2105 | 5 | 2320 | 789.4737 | 2012-04-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 0 | 0 | 5 | 2320 | 789.4737 | april | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 17 | 2684.2105 | 11 | 5253.5 | 1736.8421 | 2012-05-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 0 | 0 | 6 | 2933.5 | 947.3684 | may | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 17 | 2684.2105 | 13 | 5849.5 | 2052.6316 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 0 | 0 | 2 | 596 | 315.7895 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 19 | 3000 | 13 | 6128.5 | 2052.6316 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 2 | 315.79 | 0 | 279 | 0 | august | 645.88 | 930.3 | 78.51 | 278.9 | both | TRUE
swl | Grates, Frames & Lids | 19 | each | 3000 | 157.89 | 19 | 8583.04 | 451.7368 | 19 | 3000 | 19 | 8583.04 | 3000 | 2012-10-01 | P024 - P06 Urban Road Reconstruction | 2012-02-01 | 2012-10-01 | 0 | 0 | 6 | 2454.54 | 947.3684 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 11.7 | 5592.0552 | 28.08 | 1778 | 13420.9324 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 11.7 | 5592.06 | 28.08 | 1778 | 13420.9324 | december | 3058.72 | 2812.24 | -482.61 | 1741.84 | both | TRUE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 11.7 | 5592.0552 | 11.7 | 1778 | 5592.0552 | 2012-01-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 0 | 0 | -16.38 | 0 | -7828.8772 | january | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 49.14 | 23486.6317 | 49.14 | 7592 | 23486.6317 | 2012-03-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 37.44 | 17894.58 | 37.44 | 5814 | 17894.5766 | march | 13406.07 | 7002.55 | 2683.74 | 7897.95 | both | TRUE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 67.86 | 32433.92 | 49.14 | 7592 | 23486.6317 | 2012-06-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 18.72 | 8947.29 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 67.86 | 32433.92 | 56.16 | 8731.999 | 26841.8648 | 2012-07-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 0 | 0 | 7.02 | 1140 | 3355.2331 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 67.86 | m | 32433.92 | 477.95 | 67.86 | 10551.499 | 155.4819 | 67.86 | 32433.92 | 67.86 | 10551.499 | 32433.92 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-08-01 | 0 | 0 | 11.7 | 1819.5 | 5592.0552 | august | 0 | 0 | 0 | 0 | left_only | FALSE
swpc | Pre-cast Pit Tops / backstones | 19 | each | 25742.7 | 1354.88 | 19 | 13460 | 708.4211 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swpc | Pre-cast Pit Tops / backstones | 19 | each | 25742.7 | 1354.88 | 19 | 13460 | 708.4211 | 0 | 0 | 1 | 511.67 | 1354.8789 | 2011-12-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 0 | 0 | 1 | 511.67 | 1354.8789 | december | 0 | 0 | 0 | 0 | left_only | FALSE
swpc | Pre-cast Pit Tops / backstones | 19 | each | 25742.7 | 1354.88 | 19 | 13460 | 708.4211 | 17 | 23032.9421 | 17 | 12001.7 | 23032.9421 | 2012-02-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 17 | 23032.94 | 16 | 11490.03 | 21678.0632 | february | 2795.89 | 8831.31 | 12921.3 | 6562.26 | both | TRUE
swpc | Pre-cast Pit Tops / backstones | 19 | each | 25742.7 | 1354.88 | 19 | 13460 | 708.4211 | 19 | 25742.7 | 19 | 13460 | 25742.7 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-12-01 | 2012-09-01 | 2 | 2709.76 | 2 | 1458.3 | 2709.7579 | september | 11114.42 | 3851.87 | 3919.38 | 5311.82 | both | TRUE
wmf | Watermain Fittings | 0 | item | 0 | 0 | 1 | 134.4 | 134 | 0 | 0 | 0 | 0 | 0 | 2011-10-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
wmf | Watermain Fittings | 0 | item | 0 | 0 | 1 | 134.4 | 134 | 0 | 0 | 0 | 0 | 0 | 2012-08-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
wmf | Watermain Fittings | 0 | item | 0 | 0 | 1 | 134.4 | 134 | 0 | 0 | 1 | 134.4 | 0 | 2012-09-01 | P024 - P06 Urban Road Reconstruction | 2011-11-01 | 2012-09-01 | 0 | 0 | 0 | 134.4 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 100 | hrs | 15945 | 312.65 | 51 | 8207.5 | 160.9314 | 10 | 1594.5 | 4.5 | 697.5 | 1406.9118 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 100 | hrs | 15945 | 312.65 | 51 | 8207.5 | 160.9314 | 45 | 7175.25 | 0 | 4707.5 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-09-01 | 35 | 5580.75 | -4.5 | 4010 | -1406.9118 | may | 3058.72 | 5421.01 | 6154.63 | 5118.92 | both | TRUE
11 | Survey - Construction | 100 | hrs | 15945 | 312.65 | 51 | 8207.5 | 160.9314 | 60 | 9567 | 29.5 | 4707.5 | 9223.0882 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-09-01 | 15 | 2391.75 | 29.5 | 0 | 9223.0882 | june | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 100 | hrs | 15945 | 312.65 | 51 | 8207.5 | 160.9314 | 80 | 12756 | 45 | 7152.5 | 14069.1176 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-09-01 | 20 | 3189 | 15.5 | 2445 | 4846.0294 | july | 3058.72 | 2330.96 | 1926.69 | 2444.9 | both | TRUE
11 | Survey - Construction | 100 | hrs | 15945 | 312.65 | 51 | 8207.5 | 160.9314 | 95 | 15147.75 | 48.5 | 7752.5 | 15163.3824 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-09-01 | 15 | 2391.75 | 3.5 | 600 | 1094.2647 | august | 3058.72 | 1256.69 | 119.85 | 1863.32 | both | TRUE
11 | Survey - Construction | 100 | hrs | 15945 | 312.65 | 51 | 8207.5 | 160.9314 | 100 | 15945 | 51 | 8207.5 | 15945 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-09-01 | 5 | 797.25 | 2.5 | 455 | 781.6176 | september | 2954.94 | 1615.59 | -372.35 | 1886.37 | both | TRUE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 10 | 1606.5217 | 0 | 0 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 10 | 1606.52 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 20 | 3213.0435 | 4.5 | 725 | 242.7372 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 10 | 1606.52 | 4.5 | 725 | 242.7372 | august | 1103.31 | 1714.49 | 1289.96 | 1133.67 | both | TRUE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 20 | 3213.0435 | 14 | 2207.5 | 755.1825 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 0 | 0 | 9.5 | 1482.5 | 512.4453 | september | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 30 | 4819.5652 | 51 | 8180 | 2751.0219 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 10 | 1606.52 | 37 | 5972.5 | 1995.8394 | october | 2954.94 | 4440.58 | 5456.74 | 3662.24 | both | TRUE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 46 | 7390 | 73 | 11657.5 | 3937.7372 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 16 | 2570.43 | 22 | 3477.5 | 1186.7153 | november | 3057.01 | 3720 | 3427.74 | 3203.96 | both | TRUE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 46 | 7390 | 103 | 16551 | 5555.9854 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 0 | 0 | 30 | 4893.5 | 1618.2482 | december | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 46 | 7390 | 125 | 19943.5 | 6742.7007 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 0 | 0 | 22 | 3392.5 | 1186.7153 | february | 0 | 0 | 0 | 0 | left_only | FALSE
12 | Survey - As Constructed | 46 | item | 7390 | 53.94 | 137 | 21901 | 159.8613 | 46 | 7390 | 137 | 21901 | 7390 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-03-01 | 0 | 0 | 12 | 1957.5 | 647.2993 | march | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0.1 | 2873.1 | 0.1 | 2239.93 | 2873.1 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.1 | 2873.1 | 0.1 | 2239.93 | 2873.1 | may | 1393.55 | 2142.49 | 1900.15 | 2122.69 | both | TRUE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0.2 | 5746.2 | 0.1 | 2239.93 | 2873.1 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.1 | 2873.1 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0.3 | 8619.3 | 0.1 | 2365.36 | 2873.1 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.1 | 2873.1 | 0 | 125.43 | 0 | july | 1393.55 | 502.14 | -311.1 | 431.78 | both | TRUE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0.6 | 17238.6 | 0.35 | 3685.15 | 10055.85 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.3 | 8619.3 | 0.25 | 1319.79 | 7182.75 | august | 5629.51 | 2326.82 | 738.32 | 3179.03 | both | TRUE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0.75 | 21548.25 | 0.5 | 5306.89 | 14365.5 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.15 | 4309.65 | 0.15 | 1621.74 | 4309.65 | september | 1654.63 | 2283.24 | 814.83 | 1675.92 | both | TRUE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0.9 | 25857.9 | 0.65 | 6595.4 | 18675.15 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.15 | 4309.65 | 0.15 | 1288.51 | 4309.65 | october | 1393.55 | 1472.25 | 1138.08 | 1402.8 | both | TRUE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 1 | 28731 | 0.85 | 8332.36 | 24421.35 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0.1 | 2873.1 | 0.2 | 1736.96 | 5746.2 | november | 1393.55 | 1767.29 | 1020.54 | 1522.24 | both | TRUE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 1 | 28731 | 0.95 | 9344.95 | 27294.45 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0.1 | 1012.59 | 2873.1 | december | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 1 | 28731 | 0.95 | 9470.38 | 27294.45 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 125.43 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 1 | 28731 | 1 | 9470.38 | 28731 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0.05 | 0 | 1436.55 | march | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 1 | item | 1998 | 0 | 0 | 0 | 0 | 1 | 1998 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 1 | item | 1998 | 0 | 0 | 0 | 0 | 1 | 1998 | 1 | 0 | 1998 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 1 | 0 | 1998 | may | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 1 | item | 1998 | 0 | 0 | 0 | 0 | 1 | 1998 | 1 | 0 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0 | 0 | -1998 | august | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 1 | item | 1998 | 0 | 0 | 0 | 0 | 1 | 1998 | 1 | 0 | 1998 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 1998 | september | 0 | 0 | 0 | 0 | left_only | FALSE
15 | Service Locations | 1 | item | 1998 | 0 | 0 | 0 | 0 | 1 | 1998 | 0 | 0 | 1998 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | -1 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 0 | item | 0 | 0 | 1 | 1682.9 | 1682.9 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-11-01 | 2014-11-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition works | 0 | item | 0 | 0 | 1 | 1682.9 | 1682.9 | 0 | 0 | 1 | 1682.9 | 0 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-11-01 | 2014-11-01 | 0 | 0 | 1 | 1682.9 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 677 | cum | 10200.13 | 15.07 | 677 | 14016.515 | 20.7039 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 677 | cum | 10200.13 | 15.07 | 677 | 14016.515 | 20.7039 | 200 | 3013.3333 | 0 | 0 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-09-01 | 200 | 3013.33 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 677 | cum | 10200.13 | 15.07 | 677 | 14016.515 | 20.7039 | 677 | 10200.1333 | 150 | 3376.775 | 2260 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-09-01 | 477 | 7186.8 | 150 | 3376.78 | 2260 | june | 9322.64 | 7065.3 | 5325.23 | 6958.57 | both | TRUE
52 | Stockpile to Fill | 677 | cum | 10200.13 | 15.07 | 677 | 14016.515 | 20.7039 | 677 | 10200.1333 | 480 | 9955.04 | 7232 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-09-01 | 0 | 0 | 330 | 6578.27 | 4972 | july | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 677 | cum | 10200.13 | 15.07 | 677 | 14016.515 | 20.7039 | 677 | 10200.1333 | 677 | 13641.515 | 10200.1333 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-09-01 | 0 | 0 | 197 | 3686.47 | 2968.1333 | august | 0 | 0 | 0 | 0 | left_only | FALSE
52 | Stockpile to Fill | 677 | cum | 10200.13 | 15.07 | 677 | 14016.515 | 20.7039 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-09-01 | 0 | 0 | 0 | 375 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 0 | cum | 1320.42 | 26.41 | 50 | 11469.48 | 229.3896 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 0 | cum | 1320.42 | 26.41 | 50 | 11469.48 | 229.3896 | 0 | 0 | 40 | 4498.07 | 1056.3326 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 0 | 0 | 40 | 4498.07 | 1056.3326 | august | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 0 | cum | 1320.42 | 26.41 | 50 | 11469.48 | 229.3896 | 0 | 1320.4158 | 40 | 10658.615 | 1056.3326 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 0 | 1320.42 | 0 | 6160.54 | 0 | september | 2681.29 | 5804.97 | 2488.27 | 4494.34 | both | TRUE
53 | Cut to Spoil | 0 | cum | 1320.42 | 26.41 | 50 | 11469.48 | 229.3896 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 0 | 0 | 10 | 810.86 | 264.0832 | october | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 350 | 3691.9355 | 0 | 0 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 350 | 3691.94 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 0 | 355.99 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 650 | 6856.45 | 0 | 355.99 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 50 | 1040.93 | 210.9677 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 50 | 684.94 | 210.9677 | july | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 1200 | 15035.49 | 5063.2258 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 1150 | 13994.56 | 4852.2581 | august | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 1400 | 20480.44 | 5907.0968 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 200 | 5444.95 | 843.871 | september | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 2400 | 35521.275 | 10126.4516 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 1000 | 15040.83 | 4219.3548 | october | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 2400 | 35806.275 | 10126.4516 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 285 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
54 | Cut to Stockpile | 1000 | cum | 10548.39 | 4.22 | 2500 | 36701.55 | 14.6806 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 100 | 895.28 | 421.9355 | december | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Cut to Fill | 0 | cum | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Cut to Fill | 0 | cum | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2014-10-01 | 0 | 0 | 0 | 220 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 2000 | 2205.7143 | 0 | 0 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 2000 | 2205.71 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 4000 | 4411.4286 | 2300 | 2803.89 | 2536.5714 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 2000 | 2205.71 | 2300 | 2803.89 | 2536.5714 | june | 9318.44 | 2925.6 | 4926.32 | 3754.27 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 6000 | 6617.1429 | 4500 | 5617.475 | 4962.8571 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 2000 | 2205.71 | 2200 | 2813.59 | 2426.2857 | july | 9318.44 | 2782.18 | 4494.55 | 3417.86 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 6000 | 6617.1429 | 4500 | 5725.525 | 4962.8571 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 0 | 108.05 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 60000 | 66171.4286 | 6900 | 8833.575 | 7609.7143 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 54000 | 59554.29 | 2400 | 3108.05 | 2646.8571 | september | 5183.5 | 12754.05 | -1463.5 | 3108.15 | both | TRUE
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.71 | 1.1 | 9000 | 10847.275 | 1.2053 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 100 | 283.68 | 110.2857 | november | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 0 | 0 | 0 | 236.21 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 0 | 236.21 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 380 | 3690.2222 | 0 | 236.21 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 380 | 3690.22 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 380 | 3690.2222 | 450 | 8828.555 | 1738.8482 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 450 | 8592.34 | 1738.8482 | august | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 380 | 3690.2222 | 750 | 9390.995 | 2898.0803 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 300 | 562.44 | 1159.2321 | september | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 380 | 3690.2222 | 850 | 10544.735 | 3284.491 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 100 | 1153.74 | 386.4107 | october | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 380 | 3690.2222 | 850 | 10873.895 | 3284.491 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 0 | 329.16 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 380 | sqm | 3690.22 | 3.86 | 955 | 12355.115 | 12.9373 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 105 | 1481.22 | 405.7312 | december | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 842.4 | tonne | 9049.19 | 5.16 | 1753 | 23084.9625 | 13.1688 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 842.4 | tonne | 9049.19 | 5.16 | 1753 | 23084.9625 | 13.1688 | 0 | 0 | 0 | 550 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-10-01 | 0 | 0 | 0 | 550 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 842.4 | tonne | 9049.19 | 5.16 | 1753 | 23084.9625 | 13.1688 | 842.4 | 9049.1915 | 0 | 550 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-10-01 | 842.4 | 9049.19 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 842.4 | tonne | 9049.19 | 5.16 | 1753 | 23084.9625 | 13.1688 | 842.4 | 9049.1915 | 0 | 1126.075 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-10-01 | 0 | 0 | 0 | 576.08 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 842.4 | tonne | 9049.19 | 5.16 | 1753 | 23084.9625 | 13.1688 | 842.4 | 9049.1915 | 1753 | 22163.3925 | 9049.1915 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-10-01 | 0 | 0 | 1753 | 21037.32 | 9049.1915 | september | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel | 842.4 | tonne | 9049.19 | 5.16 | 1753 | 23084.9625 | 13.1688 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-10-01 | 0 | 0 | 0 | 921.57 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 0 | 0 | 0 | 120 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 0 | 120 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 2339 | 8139.9895 | 0 | 120 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 2339 | 8139.99 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 2339 | 8139.9895 | 0 | 1685.67 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 0 | 1565.67 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 2339 | 8139.9895 | 2100 | 14302.925 | 5189.4287 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 2100 | 12617.26 | 5189.4287 | september | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 2339 | 8139.9895 | 3000 | 19887.195 | 7413.4695 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 900 | 5584.27 | 2224.0409 | october | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 2339 | 8139.9895 | 3200 | 21032.97 | 7907.7008 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 200 | 1145.77 | 494.2313 | november | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 2339 | sqm | 8139.99 | 2.47 | 3294 | 21526.71 | 6.5351 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-12-01 | 0 | 0 | 94 | 493.74 | 232.2887 | december | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 955 | sqm | 17548.12 | 18.38 | 955 | 6539.39 | 6.8475 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 955 | sqm | 17548.12 | 18.38 | 955 | 6539.39 | 6.8475 | 955 | 17548.125 | 0 | 0 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 955 | 17548.12 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 955 | sqm | 17548.12 | 18.38 | 955 | 6539.39 | 6.8475 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-10-01 | 0 | 0 | 955 | 6539.39 | 17548.125 | october | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 88 | tonne | 39160 | 454.29 | 86.2 | 34904.46 | 404.9241 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-01-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 88 | tonne | 39160 | 454.29 | 86.2 | 34904.46 | 404.9241 | 88 | 39160 | 0 | 0 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-01-01 | 88 | 39160 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 88 | tonne | 39160 | 454.29 | 86.2 | 34904.46 | 404.9241 | 88 | 39160 | 86.2 | 34298.94 | 39160 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-01-01 | 0 | 0 | 86.2 | 34298.94 | 39160 | october | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 88 | tonne | 39160 | 454.29 | 86.2 | 34904.46 | 404.9241 | 88 | 39160 | 86.2 | 34465.66 | 39160 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-01-01 | 0 | 0 | 0 | 166.72 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt | 88 | tonne | 39160 | 454.29 | 86.2 | 34904.46 | 404.9241 | 88 | 39160 | 86.2 | 34904.46 | 39160 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-01-01 | 0 | 0 | 0 | 438.8 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-01-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 443 | 16834 | 0 | 78.11 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-01-01 | 443 | 16834 | 0 | 78.11 | 0 | july | 1628.04 | 1321.84 | -2023.21 | 368.74 | both | TRUE
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 443 | 16834 | 443 | 14132.814 | 16834 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-01-01 | 0 | 0 | 443 | 14054.7 | 16834 | september | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 443 | 16834 | 443 | 14255.699 | 16834 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-01-01 | 0 | 0 | 0 | 122.89 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 443 | 16834 | 443 | 14450.204 | 16834 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-01-01 | 0 | 0 | 0 | 194.51 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 443 | 16834 | 443 | 14639.324 | 16834 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2015-01-01 | 0 | 0 | 0 | 189.12 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 1 | cum | 1900 | 1900 | 1 | 532.5 | 532.5 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-07-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
72 | Form & Pour Headwalls | 1 | cum | 1900 | 1900 | 1 | 532.5 | 532.5 | 1 | 1900 | 1 | 532.5 | 1900 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-07-01 | 1 | 1900 | 1 | 532.5 | 1900 | july | 409.36 | 3604.02 | 3143.7 | 1586.09 | both | TRUE
73 | Form & Place Footpath | 466.1 | sqm | 24991.5 | 44.94 | 556.1 | 38225.2775 | 68.7381 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 466.1 | sqm | 24991.5 | 44.94 | 556.1 | 38225.2775 | 68.7381 | 200 | 10723.6653 | 0 | 0 | 0 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 200 | 10723.67 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 466.1 | sqm | 24991.5 | 44.94 | 556.1 | 38225.2775 | 68.7381 | 466.1 | 24991.502 | 135 | 9330.355 | 6066.9893 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 266.1 | 14267.84 | 135 | 9330.36 | 6066.9893 | october | 14835.1 | 9353.49 | 14628.05 | 10742.31 | both | TRUE
73 | Form & Place Footpath | 466.1 | sqm | 24991.5 | 44.94 | 556.1 | 38225.2775 | 68.7381 | 466.1 | 24991.502 | 380 | 26282.4175 | 17077.4515 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 245 | 16952.06 | 11010.4621 | november | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 466.1 | sqm | 24991.5 | 44.94 | 556.1 | 38225.2775 | 68.7381 | 466.1 | 24991.502 | 540 | 37199.7975 | 24267.9573 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 160 | 10917.38 | 7190.5059 | december | 0 | 0 | 0 | 0 | left_only | FALSE
73 | Form & Place Footpath | 466.1 | sqm | 24991.5 | 44.94 | 556.1 | 38225.2775 | 68.7381 | 466.1 | 24991.502 | 556.1 | 38225.2775 | 24991.502 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 16.1 | 1025.48 | 723.5447 | march | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 405.2 | m | 18720.24 | 46.2 | 405.2 | 16600.83 | 40.9695 | 200 | 9240 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-05-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
81 | > 450 | 405.2 | m | 18720.24 | 46.2 | 405.2 | 16600.83 | 40.9695 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-05-01 | 205.2 | 9480.24 | 405.2 | 16600.83 | 18720.24 | may | 14835.1 | 11629.53 | 13495.05 | 12270.86 | both | TRUE
82 | 525 > 750 | 102.4 | m | 4730.88 | 46.2 | 102.4 | 10332.59 | 100.9042 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
82 | 525 > 750 | 102.4 | m | 4730.88 | 46.2 | 102.4 | 10332.59 | 100.9042 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | may | 0 | 0 | 0 | 0 | left_only | FALSE
82 | 525 > 750 | 102.4 | m | 4730.88 | 46.2 | 102.4 | 10332.59 | 100.9042 | 102.4 | 4730.88 | 102.4 | 10005.11 | 4730.88 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 7.4 | 109.16 | 341.88 | november | 0 | 0 | 0 | 0 | left_only | FALSE
82 | 525 > 750 | 102.4 | m | 4730.88 | 46.2 | 102.4 | 10332.59 | 100.9042 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 327.48 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 0 | 0 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 1 | 35388 | 0 | 0 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 0 | 97.3 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 97.3 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 0 | 914.245 | 35388 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 816.94 | 35388 | september | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 0.8 | 4894 | 35388 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0.8 | 3979.76 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 1 | 6064.855 | 35388 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0.2 | 1170.85 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 0 | 6064.855 | 0 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | -1 | 0 | -35388 | december | 0 | 0 | 0 | 0 | left_only | FALSE
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 1 | 35388 | 1 | 6064.855 | 35388 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 1 | 0 | 35388 | march | 0 | 0 | 0 | 0 | left_only | FALSE
86 | SW Sub-contractors | 11 | each | 6500 | 590.91 | 11 | 22752.36 | 2068.3964 | 2 | 1181.8182 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
86 | SW Sub-contractors | 11 | each | 6500 | 590.91 | 11 | 22752.36 | 2068.3964 | 6 | 3545.4545 | 2 | 5635.2 | 1181.8182 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 4 | 2363.64 | 2 | 5635.2 | 1181.8182 | may | 5795.74 | 4696.95 | 5329.55 | 4912.62 | both | TRUE
86 | SW Sub-contractors | 11 | each | 6500 | 590.91 | 11 | 22752.36 | 2068.3964 | 11 | 6500 | 3 | 8090.2 | 1772.7273 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 5 | 2954.55 | 1 | 2455 | 590.9091 | june | 5795.74 | 2744.98 | 2760.65 | 3275.55 | both | TRUE
86 | SW Sub-contractors | 11 | each | 6500 | 590.91 | 11 | 22752.36 | 2068.3964 | 11 | 6500 | 10.5 | 22643.2 | 6204.5455 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 7.5 | 14553 | 4431.8182 | september | 0 | 0 | 0 | 0 | left_only | FALSE
86 | SW Sub-contractors | 11 | each | 6500 | 590.91 | 11 | 22752.36 | 2068.3964 | 11 | 6500 | 11 | 22752.36 | 6500 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0.5 | 109.16 | 295.4545 | december | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 300 | 11967.0908 | 0 | 658 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 300 | 11967.09 | 0 | 658 | 0 | may | 11719.06 | 5182.17 | 2881.27 | 6269.37 | both | TRUE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 1017 | 40568.4377 | 265 | 4562.595 | 10570.9302 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 717 | 28601.35 | 265 | 3904.6 | 10570.9302 | june | 5841.9 | 6972.3 | 5633.18 | 5480.84 | both | TRUE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 1017 | 40568.4377 | 350 | 6164.32 | 13961.6059 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 85 | 1601.72 | 3390.6757 | july | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 1017 | 40568.4377 | 350 | 6440.79 | 13961.6059 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 0 | 276.47 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 1017 | 40568.4377 | 900 | 16574.48 | 35901.2723 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 550 | 10133.69 | 21939.6664 | september | 0 | 0 | 0 | 0 | left_only | FALSE
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.44 | 39.89 | 1017 | 17562.98 | 17.2694 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 117 | 988.5 | 4667.1654 | october | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 8 | 34933.95 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 9.5 | 52026.8 | 20533.698 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 8 | 34933.95 | 9.5 | 52026.8 | 20533.698 | may | 29134.33 | 40211.16 | 52398.34 | 35707.64 | both | TRUE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 15 | 79383 | 44843.0693 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 5.5 | 27356.2 | 24309.3712 | june | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 15 | 79383 | 49363.2783 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 4520.209 | july | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 15 | 79987.58 | 49600.9155 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 604.58 | 237.6372 | august | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 15 | 79987.58 | 50080.4291 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 479.5136 | september | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 15 | 82587.58 | 62689.847 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 2600 | 12609.4179 | october | 0 | 0 | 0 | 0 | left_only | FALSE
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.74 | 16 | 85835.88 | 5364.7425 | 16 | 69867.9 | 16 | 85835.88 | 69867.9 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 1 | 3248.3 | 7178.053 | december | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 0 | 0 | 0 | 213.6 | 31706.702 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 213.6 | 31706.702 | may | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 12 | 47948.9467 | 10 | 34703.604 | 69243.5347 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 12 | 47948.95 | 10 | 34490 | 37536.8328 | june | 20347.42 | 28731.57 | 31845.03 | 25159.17 | both | TRUE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 27 | 107885.13 | 13 | 46203.604 | 76223.3257 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 15 | 59936.18 | 3 | 11500 | 6979.791 | july | 20347.42 | 16990.21 | 11653.6 | 17561.98 | both | TRUE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 27 | 107885.13 | 13 | 46203.604 | 76590.2685 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 366.9428 | august | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 27 | 107885.13 | 13 | 47423.549 | 77330.6999 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 1219.95 | 740.4314 | september | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 27 | 107885.13 | 22 | 76903.549 | 96801.282 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 9 | 29480 | 19470.5821 | october | 0 | 0 | 0 | 0 | left_only | FALSE
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.75 | 27 | 93624.379 | 3467.5696 | 27 | 107885.13 | 27 | 93624.379 | 107885.13 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 5 | 16720.83 | 11083.848 | december | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 200 | 15114.577 | 135 | 17380 | 10202.3394 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 200 | 15114.58 | 135 | 17380 | 10202.3394 | may | 16429.38 | 16016.75 | 16656.88 | 15156.08 | both | TRUE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 135 | 17380 | 10202.3394 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 256 | 19346.66 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 365 | 46098.8175 | 27584.103 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 230 | 28718.82 | 17381.7635 | september | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 425 | 54113.9705 | 32118.476 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 60 | 8015.15 | 4534.3731 | october | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 430 | 54579.5805 | 32496.3405 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 5 | 465.61 | 377.8644 | november | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 435 | 55155.6105 | 32874.2049 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 5 | 576.03 | 377.8644 | december | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 456 | 56606.7105 | 34461.2355 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 21 | 1451.1 | 1587.0306 | march | 0 | 0 | 0 | 0 | left_only | FALSE
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.24 | 75.57 | 456 | 57698.3105 | 126.5314 | 456 | 34461.2355 | 456 | 57698.3105 | 34461.2355 | 2015-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 1091.6 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 0 | 0 | 0 | 0 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 0 | 0 | 0 | 0 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 0 | 0 | 0.85 | 86632.52 | 14353.6667 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 0.85 | 86632.52 | 14353.6667 | october | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 6 | 101320 | 0.85 | 86632.52 | 14353.6667 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 6 | 101320 | 0 | 0 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 6 | 101320 | 1 | 91396.68 | 16886.6667 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 0.15 | 4764.16 | 2533 | december | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 6 | 101320 | 6 | 91396.68 | 101320 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 5 | 0 | 84433.3333 | march | 0 | 0 | 0 | 0 | left_only | FALSE
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.67 | 6 | 91724.16 | 15287.36 | 6 | 101320 | 6 | 91724.16 | 101320 | 2015-05-01 | P038 - P17 Marina Sub-division | 2014-10-01 | 2015-05-01 | 0 | 0 | 0 | 327.48 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 0.1 | 40547.327 | 0.028751 | 9657.1439 | 11657.5875 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0.1 | 40547.33 | 0.028751 | 9657.14 | 11657.5875 | june | 14412.59 | 19089.77 | 13338.84 | 15321.2 | both | TRUE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 0.2 | 81094.654 | 0.028751 | 9657.1439 | 11657.5875 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0.1 | 40547.33 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 0.25 | 101368.3175 | 0.064312 | 21602.0339 | 26076.8198 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0.05 | 20273.66 | 0.035561 | 11944.89 | 14419.2323 | september | 5554.16 | 17836.13 | 14067.62 | 11075.06 | both | TRUE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 0.75 | 304104.9525 | 0.21642 | 72693.1618 | 87751.2966 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0.5 | 202736.64 | 0.1521 | 51091.13 | 61674.4769 | october | 112816.37 | 65885.53 | 45867.04 | 79654.5 | both | TRUE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 1 | 405473.27 | 0.76569 | 257190.633 | 310466.7752 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0.25 | 101368.32 | 0.54927 | 184497.47 | 222715.4785 | november | 54283.13 | 41950.15 | 32436.09 | 43811.34 | both | TRUE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 1 | 405473.27 | 0.90125 | 302723.3795 | 365431.4712 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0.13556 | 45532.75 | 54964.6961 | december | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 1 | 405473.27 | 0.971 | 326154.5772 | 393716.3598 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0.069758 | 23431.2 | 28284.8885 | january | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 1 | 405473.27 | 1 | 326154.5772 | 405473.27 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0.028996 | 0 | 11756.9102 | february | 0 | 0 | 0 | 0 | left_only | FALSE
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 1 | 405473.27 | 1 | 343303.69 | 405473.27 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 17149.11 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 0 | 0 | 0.017132 | 2895.45 | 2053.2658 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0.017132 | 2895.45 | 2053.2658 | august | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 0 | 0 | 0.30678 | 51850 | 36768.6653 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0.28965 | 48954.55 | 34715.3995 | september | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 0.35 | 41948.5796 | 0.3302 | 55808.35 | 39575.671 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0.35 | 41948.58 | 0.02342 | 3958.35 | 2807.0057 | october | 14412.59 | 12679.14 | 5141.3 | 12636.12 | both | TRUE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 1 | 119853.0845 | 0.36422 | 61558.35 | 43653.199 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0.65 | 77904.5 | 0.034021 | 5750 | 4077.528 | november | 20347.42 | 16275.93 | 4566.78 | 17491.2 | both | TRUE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 1 | 119853.0845 | 0.47269 | 79890.29 | 56653.0248 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0.10846 | 18331.94 | 12999.8258 | december | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 1 | 119853.0845 | 0.50852 | 85945.7 | 60947.1298 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0.035828 | 6055.41 | 4294.105 | january | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 1 | 119853.0845 | 0.54915 | 92812.7 | 65816.7619 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0.04063 | 6867 | 4869.6321 | february | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 1 | 119853.0845 | 1 | 92812.7 | 119853.0845 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0.45085 | 0 | 54036.3226 | march | 0 | 0 | 0 | 0 | left_only | FALSE
123 | Supply & Installation of Street Furniture | 1 | item | 119853.08 | 119853.08 | 1 | 109537.7 | 109537.7 | 1 | 119853.0845 | 1 | 109537.7 | 119853.0845 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 16725 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 0 | 0 | 0 | 194.6 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-02-01 | 0 | 0 | 0 | 194.6 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 0 | 0 | 0 | 303.76 | 0 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-02-01 | 0 | 0 | 0 | 109.16 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 1 | 21670 | 0 | 731.66 | 0 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-02-01 | 1 | 21670 | 0 | 427.9 | 0 | november | 10491.91 | 4995.35 | 488.77 | 6562.71 | both | TRUE
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 1 | 21670 | 0.1 | 1355.5 | 2167 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-02-01 | 0 | 0 | 0.1 | 623.84 | 2167 | december | 0 | 0 | 0 | 0 | left_only | FALSE
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 1 | 21670 | 1 | 18080.5 | 21670 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-02-01 | 0 | 0 | 0.9 | 16725 | 19503 | february | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 150 | 77330.8738 | 100 | 42453.6871 | 43249.0719 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 150 | 77330.87 | 100 | 42453.69 | 43249.0719 | may | 54283.13 | 50372.06 | 47834.91 | 49303.33 | both | TRUE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 325 | 167550.2265 | 325 | 122163.2821 | 140559.4837 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 175 | 90219.35 | 225 | 79709.6 | 97310.4118 | june | 54283.13 | 62496.52 | 66142.79 | 57009.93 | both | TRUE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 500 | 257769.5792 | 620 | 243242.2971 | 268144.2458 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 175 | 90219.35 | 295 | 121079.02 | 127584.7621 | july | 54283.13 | 61077.36 | 63689.74 | 55848.63 | both | TRUE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 675 | 265477.6521 | 291931.2354 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 177 | 91250.43 | 55 | 22235.35 | 23786.9895 | august | 54283.13 | 40279.6 | 30420.32 | 42549.46 | both | TRUE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 675 | 266128.9271 | 291931.2354 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 651.28 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 738 | 292216.0861 | 319178.1507 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 63 | 26087.16 | 27246.9153 | november | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 743 | 294585.2661 | 321340.6043 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 5 | 2369.18 | 2162.4536 | december | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 745 | 294803.5861 | 322205.5857 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 2 | 218.32 | 864.9814 | january | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 745 | 295560.0662 | 322205.5857 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 756.48 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.01 | 432.49 | 807 | 322580.1561 | 399.7276 | 677 | 349020.0103 | 807 | 322580.1561 | 349020.0103 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 62 | 27020.09 | 26814.4246 | march | 0 | 0 | 0 | 0 | left_only | FALSE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 50 | 4691.2656 | 20 | 2434.035 | 1876.5063 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 300 | 28147.5938 | 250 | 27212.315 | 23456.3282 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 250 | 23456.33 | 230 | 24778.28 | 21579.8219 | may | 22048.5 | 21154.62 | 23029.51 | 20415.66 | both | TRUE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 500 | 46912.6563 | 380 | 41215.715 | 35653.6188 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 200 | 18765.06 | 130 | 14003.4 | 12197.2906 | june | 11719.06 | 11851.67 | 11828.12 | 10696.44 | both | TRUE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 577 | 54137.2054 | 445 | 49041.35 | 41752.2641 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 77 | 7224.55 | 65 | 7825.64 | 6098.6453 | july | 11719.06 | 9696.24 | 9574.77 | 8844.78 | both | TRUE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 577 | 54137.2054 | 480 | 52921.38 | 45036.1501 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 0 | 0 | 35 | 3880.03 | 3283.8859 | august | 0 | 0 | 0 | 0 | left_only | FALSE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 577 | 54137.2054 | 480 | 53326.22 | 45036.1501 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 0 | 0 | 0 | 404.84 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 577 | 54137.2054 | 535 | 59107.16 | 50196.5423 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 0 | 0 | 55 | 5780.94 | 5160.3922 | october | 0 | 0 | 0 | 0 | left_only | FALSE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 577 | 54137.2054 | 535 | 59461.06 | 50196.5423 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 0 | 0 | 0 | 353.9 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.21 | 93.83 | 577 | 62335.54 | 108.0339 | 577 | 54137.2054 | 577 | 62335.54 | 54137.2054 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-01-01 | 0 | 0 | 42 | 2874.48 | 3940.6631 | january | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 0 | 106.12 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 50 | 1714.585 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 50 | 1608.46 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 0.6 | 1973.925 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | -49.4 | 259.34 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 0.75 | 2721.905 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0.15 | 747.98 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 1 | 3567.895 | 0 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0.25 | 845.99 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 100 | 3567.895 | 0 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 99 | 0 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
152 | Supply & Install safety devices | 0 | item | 0 | 0 | 1 | 875 | 875 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-07-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
152 | Supply & Install safety devices | 0 | item | 0 | 0 | 1 | 875 | 875 | 0 | 0 | 1 | 875 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-07-01 | 0 | 0 | 1 | 875 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geo-fabric | 2600 | sqm | 5804.95 | 0 | 0 | 76.9 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geo-fabric | 2600 | sqm | 5804.95 | 0 | 0 | 76.9 | 0 | 1000 | 2232.6742 | 0 | 76.9 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-09-01 | 1000 | 2232.67 | 0 | 76.9 | 0 | june | 2472.03 | 2457.22 | 846.04 | 1155.86 | both | TRUE
222 | Supply & Place Geo-fabric | 2600 | sqm | 5804.95 | 0 | 0 | 76.9 | 0 | 2600 | 5804.9529 | 0 | 76.9 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-09-01 | 1600 | 3572.28 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geo-fabric | 2600 | sqm | 5804.95 | 0 | 0 | 76.9 | 0 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 5804.9529 | september | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 2 | 8742.8571 | 0.25 | 1245.875 | 2385.1915 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 4 | 17485.7143 | 0.75 | 3775.875 | 7155.5745 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8742.86 | 0.5 | 2530 | 4770.383 | may | 5554.16 | 3563.14 | 583.75 | 4214.81 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 6 | 26228.5714 | 1.3 | 6811.875 | 12402.9959 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8742.86 | 0.55 | 3036 | 5247.4213 | june | 1405.82 | 3008.94 | 1257.94 | 2172.6 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 8 | 34971.4286 | 1.5 | 7892.875 | 14311.1491 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8742.86 | 0.2 | 1081 | 1908.1532 | july | 1405.82 | 2527.03 | 289.86 | 1617.32 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 10 | 43714.2857 | 1.8 | 9732.875 | 17173.3789 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8742.86 | 0.3 | 1840 | 2862.2298 | august | 1405.82 | 3891.18 | 2253.04 | 2627.67 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 12 | 52457.1429 | 2.7 | 14171.875 | 25760.0684 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8742.86 | 0.9 | 4439 | 8586.6895 | september | 5554.16 | 7046.07 | 5019.93 | 5818.82 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 13 | 56828.5714 | 3.1 | 16563.875 | 29576.3748 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 1 | 4371.43 | 0.4 | 2392 | 3816.3064 | october | 5051.4 | 4367.28 | 2944.49 | 4175.47 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 4.4 | 23325.875 | 41979.3707 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 1 | 4371.43 | 1.3 | 6762 | 12402.9959 | november | 5051.4 | 4446.15 | 2318.67 | 4183.74 | both | TRUE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 5 | 26338.875 | 47703.8303 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0.6 | 3013 | 5724.4596 | december | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 5.1 | 26568.875 | 48657.9069 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0.1 | 230 | 954.0766 | january | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 5.2 | 27212.875 | 49611.9835 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0.1 | 644 | 954.0766 | february | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 6.4146 | 27971.875 | 61200 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 1.2146 | 759 | 11588.0165 | march | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 6.3988 | 27971.875 | 61200 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | -0.015784 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 61200 | 9540.77 | 6.4146 | 28040.875 | 4371.4286 | 14 | 61200 | 6.3988 | 28040.875 | 61200 | 2015-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0 | 69 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 2 | 8290 | 0.2 | 789.8 | 491.8069 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 4 | 16580 | 2.2 | 9080.68 | 5409.8754 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 2 | 8290.88 | 4918.0685 | may | 11320.57 | 10444.52 | 10268.07 | 10960.43 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 6 | 24870 | 3.7 | 15596.23 | 9098.4268 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 1.5 | 6515.55 | 3688.5514 | june | 11320.57 | 9746.87 | 9754.97 | 10122.74 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 8 | 33160 | 5 | 20920.63 | 12295.1713 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 1.3 | 5324.4 | 3196.7446 | july | 11320.57 | 10153.83 | 10195.2 | 10142.21 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 10 | 41450 | 7.1 | 29528.41 | 17459.1433 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 2.1 | 8607.78 | 5163.972 | august | 11320.57 | 9570.6 | 9072.97 | 9893.39 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 12 | 49740 | 11.5 | 47853.22 | 28278.8941 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 4.4 | 18324.81 | 10819.7508 | september | 14917.02 | 17700.25 | 19849.53 | 16128.61 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 14 | 58030 | 15.8 | 65823.07 | 38852.7415 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 4.3 | 17969.85 | 10573.8474 | october | 14917.02 | 17019.11 | 20318.1 | 16021.1 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 20 | 83304.85 | 49180.6854 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 2 | 8290 | 4.2 | 17481.78 | 10327.9439 | november | 11320.57 | 15998.76 | 18782.99 | 14193.93 | both | TRUE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 23 | 95684.08 | 56557.7882 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 3 | 12379.23 | 7377.1028 | december | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 25.5 | 105844.81 | 62705.3739 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 2.5 | 10160.73 | 6147.5857 | january | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 26 | 107841.46 | 63934.891 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0.5 | 1996.65 | 1229.5171 | february | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 26.9699 | 109483.15 | 66320 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0.96994 | 1641.69 | 2385.109 | march | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 26.4133 | 109483.15 | 66320 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | -0.55663 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 16 | weeks | 66320 | 2459.03 | 26.9699 | 111790.39 | 4145 | 16 | 66320 | 26.4133 | 111790.39 | 66320 | 2015-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-05-01 | 0 | 0 | 0 | 2307.24 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 2 | 1600 | 3.4 | 3027.55 | 2841.5588 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 4 | 3200 | 3.4 | 3050.08 | 2841.5588 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 0 | 22.53 | 0 | may | 1856.64 | 1821.34 | 1720.72 | 2026.9 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 6 | 4800 | 4.8 | 4334.58 | 4011.6124 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 1.4 | 1284.5 | 1170.0536 | june | 633.01 | 1155.68 | 1541.47 | 827.24 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 8 | 6400 | 5.2 | 4658.46 | 4345.9134 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 0.4 | 323.88 | 334.301 | july | 633.01 | 754.22 | 700.86 | 323.98 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 10 | 8000 | 6.6 | 5894.21 | 5515.967 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 1.4 | 1235.75 | 1170.0536 | august | 633.01 | 1155.11 | 1137.86 | 711.49 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 12 | 9600 | 7.1 | 6364.21 | 5933.8433 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 0.5 | 470 | 417.8763 | september | 1856.64 | 2242.87 | 1306.45 | 1651.41 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 14 | 11200 | 9.2 | 8193.22 | 7688.9237 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 2.1 | 1829.01 | 1755.0804 | october | 1856.64 | 1539.72 | 1740.15 | 1529.67 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 16 | 12800 | 11.4 | 10188.99 | 9527.5794 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 2 | 1600 | 2.2 | 1995.77 | 1838.6557 | november | 1856.64 | 1685.15 | 1219.8 | 1580.99 | both | TRUE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 16 | 12800 | 12.9 | 11540.66 | 10781.2083 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 0 | 0 | 1.5 | 1351.67 | 1253.6289 | december | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 16 | 12800 | 13.4 | 11979.7 | 11199.0846 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 0 | 0 | 0.5 | 439.04 | 417.8763 | january | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 16 | 12800 | 15.3155 | 11979.7 | 12800 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 0 | 0 | 1.9155 | 0 | 1600.9154 | march | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 16 | weeks | 12800 | 835.75 | 15.3155 | 12252.43 | 800 | 16 | 12800 | 14.9746 | 12252.43 | 12800 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-04-01 | 0 | 0 | -0.34091 | 272.73 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 0.75 | 17775 | 0.8 | 8405.25 | 18960 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 0.8 | 18960 | 0.85 | 8649.57 | 20145 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0.05 | 1185 | 0.05 | 244.32 | 1185 | may | 327.58 | 858.52 | 761.06 | 751.81 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 0.85 | 20145 | 0.85 | 8699.97 | 20145 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0.05 | 1185 | 0 | 50.4 | 0 | june | 327.58 | 371.48 | 581.64 | 50.3 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 0.9 | 21330 | 0.85 | 8699.97 | 20145 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0.05 | 1185 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 0.95 | 22515 | 0.9 | 8836 | 21330 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0.05 | 1185 | 0.05 | 136.03 | 1185 | august | 327.58 | 640.88 | 605.75 | 109.11 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 1 | 23700 | 0.95 | 9497.2 | 22515 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0.05 | 1185 | 0.05 | 661.2 | 1185 | september | 327.58 | 813.73 | -392.04 | 74.8 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 1 | 23700 | 0.95 | 9712.97 | 22515 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 215.77 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 1 | 23700 | 0.95 | 9749.63 | 22515 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 36.66 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 1 | 23700 | 1 | 9907.84 | 23700 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0.05 | 158.21 | 1185 | december | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 0.2 | 1000 | 0.6 | 3039.66 | 3000 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0.2 | 1000 | 0.6 | 3039.66 | 3000 | may | 1158.64 | 2168.08 | 2642.94 | 2044.3 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 0.4 | 2000 | 0.66 | 3277.71 | 3300 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0.2 | 1000 | 0.06 | 238.05 | 300 | june | 1158.64 | 724.56 | 948.08 | 724.34 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 0.6 | 3000 | 0.65554 | 3277.71 | 3277.71 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0.2 | 1000 | -0.004458 | 0 | -22.29 | july | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 0.8 | 4000 | 0.65 | 3285.73 | 3250 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0.2 | 1000 | -0.005542 | 8.02 | -27.71 | august | 303.01 | 393.32 | 218.56 | 127.2 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 1 | 5000 | 0.7 | 3397.46 | 3500 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0.2 | 1000 | 0.05 | 111.73 | 250 | september | 609.44 | 446.94 | -1039.04 | 111.63 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 1 | 5000 | 0.7 | 3408.78 | 3500 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0 | 0 | 0 | 11.32 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 1 | 5000 | 0.8 | 3960.37 | 4000 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0 | 0 | 0.1 | 551.59 | 500 | december | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 1 | 5000 | 1 | 3960.37 | 5000 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-02-01 | 0 | 0 | 0.2 | 0 | 1000 | february | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0.2 | 0 | 0 | 0 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.2 | 0 | 0 | 0 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0.3 | 0 | 0 | 1800 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.1 | 0 | 0 | 1800 | 0 | june | 1158.64 | 1283.61 | 1664.65 | 1186.94 | both | TRUE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0.5 | 0 | 0 | 1800 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.2 | 0 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0.6 | 0 | 0 | 1800 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.1 | 0 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0.75 | 0 | 0 | 1800 | 0 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.15 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0.9 | 0 | 0 | 3779.535 | 0 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.15 | 0 | 0 | 1979.54 | 0 | october | 609.44 | 1567.58 | 2115.03 | 1270.26 | both | TRUE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 0 | 8850.655 | 0 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0.1 | 0 | 0 | 5071.12 | 0 | november | 609.44 | 1395.09 | 1090.96 | 1116.01 | both | TRUE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 0 | 9703.155 | 0 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 852.5 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 0 | 13061.915 | 0 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 3358.76 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 0 | 17165.1686 | 0 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 4103.25 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 1 | 19871.0114 | 0 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 1 | 2705.84 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 1 | 22192.6162 | 0 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 2321.6 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 1 | 0 | 1 | 24005.0022 | 0 | 2015-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-05-01 | 0 | 0 | 0 | 1812.39 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 0 | 252.175 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 252.18 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 0 | 3501.09 | 0 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 3248.92 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 0 | 5430.585 | 0 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 1929.49 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 0 | 6330.005 | 0 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 899.42 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 1 | 7301.655 | 0 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 1 | 971.65 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 1 | 8179.135 | 0 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-04-01 | 0 | 0 | 0 | 877.48 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather (Labour) | 0 | hrs | 0 | 0 | 97 | 5482.79 | 56.5236 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-01-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather (Labour) | 0 | hrs | 0 | 0 | 97 | 5482.79 | 56.5236 | 0 | 0 | 32 | 1529.975 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-01-01 | 0 | 0 | 32 | 1529.98 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather (Labour) | 0 | hrs | 0 | 0 | 97 | 5482.79 | 56.5236 | 0 | 0 | 64 | 3103.6 | 0 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-01-01 | 0 | 0 | 32 | 1573.63 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather (Labour) | 0 | hrs | 0 | 0 | 97 | 5482.79 | 56.5236 | 0 | 0 | 72 | 3463.6 | 0 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-01-01 | 0 | 0 | 8 | 360 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
913 | Wet Weather (Labour) | 0 | hrs | 0 | 0 | 97 | 5482.79 | 56.5236 | 0 | 0 | 97 | 5482.79 | 0 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-01-01 | 0 | 0 | 25 | 2019.19 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
914 | Training | 0 | hrs | 0 | 0 | 4.5 | 207.5 | 46.1111 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-08-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
914 | Training | 0 | hrs | 0 | 0 | 4.5 | 207.5 | 46.1111 | 0 | 0 | 4.5 | 207.5 | 0 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2014-08-01 | 0 | 0 | 4.5 | 207.5 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 50 | 2400 | 9 | 448.56 | 306.2066 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 150 | 7200 | 95.3 | 4575.71 | 3242.3877 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 100 | 4800 | 86.3 | 4127.15 | 2936.1811 | may | 3058.72 | 4526.55 | 3616.09 | 4365.58 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 250 | 12000 | 162 | 7779.71 | 5511.7189 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 100 | 4800 | 66.7 | 3204 | 2269.3312 | june | 3058.72 | 3641.83 | 2806.59 | 3406.94 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 350 | 16800 | 206.1 | 9894.35 | 7012.1313 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 100 | 4800 | 44.1 | 2114.64 | 1500.4124 | july | 3058.72 | 3557.19 | 2467.94 | 3108.54 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 450 | 21600 | 289.7 | 13910.03 | 9856.4504 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 100 | 4800 | 83.6 | 4015.68 | 2844.3191 | august | 3058.72 | 4271.25 | 3401.12 | 3698.54 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 500 | 24000 | 453.5 | 21770.51 | 15429.4106 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 50 | 2400 | 163.8 | 7860.48 | 5572.9602 | september | 11114.42 | 6843.31 | 4631.33 | 7693.3 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 550 | 26400 | 611 | 29331.95 | 20788.0262 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 50 | 2400 | 157.5 | 7561.44 | 5358.6156 | october | 3058.72 | 6296.07 | 7176.33 | 5153.15 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 600 | 28800 | 728.5 | 34970.99 | 24785.7236 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 50 | 2400 | 117.5 | 5639.04 | 3997.6973 | november | 3058.72 | 5418.96 | 5035.86 | 4543.29 | both | TRUE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 600 | 28800 | 758.3 | 36402.11 | 25799.6076 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 29.8 | 1431.12 | 1013.8841 | december | 0 | 0 | 0 | 0 | left_only | FALSE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 600 | 28800 | 838.9 | 40268.27 | 28541.8579 | 2015-01-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 80.6 | 3866.16 | 2742.2503 | january | 0 | 0 | 0 | 0 | left_only | FALSE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 600 | 28800 | 846.4 | 40631.39 | 28797.0301 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 7.5 | 363.12 | 255.1722 | february | 0 | 0 | 0 | 0 | left_only | FALSE
916 | Site Administration | 600 | hrs | 28800 | 34.02 | 846.4873 | 40631.39 | 48 | 600 | 28800 | 846.4873 | 40631.39 | 28800 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2015-03-01 | 0 | 0 | 0.087292 | 0 | 2.9699 | march | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | 20 MPa Concrete | 235 | cum | 46527.59 | 278.04 | 167.3434 | 33134 | 198 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c20 | 20 MPa Concrete | 235 | cum | 46527.59 | 278.04 | 167.3434 | 33134 | 198 | 52 | 10295.4677 | 85 | 16770.6 | 23633.1085 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 52 | 10295.47 | 85 | 16770.6 | 23633.1085 | may | 11719.06 | 13222.52 | 15528.1 | 12054.63 | both | TRUE
c20 | 20 MPa Concrete | 235 | cum | 46527.59 | 278.04 | 167.3434 | 33134 | 198 | 113 | 22372.8434 | 97 | 19219.8 | 26969.5473 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 61 | 12077.38 | 12 | 2449.2 | 3336.4388 | june | 11719.06 | 5014.59 | 2907.65 | 6395.18 | both | TRUE
c20 | 20 MPa Concrete | 235 | cum | 46527.59 | 278.04 | 167.3434 | 33134 | 198 | 170 | 33658.2599 | 160 | 31487 | 44485.8513 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 57 | 11285.42 | 63 | 12267.2 | 17516.3039 | july | 11719.06 | 6123.32 | 4552.27 | 6853.14 | both | TRUE
c20 | 20 MPa Concrete | 235 | cum | 46527.59 | 278.04 | 167.3434 | 33134 | 198 | 235 | 46527.5946 | 163 | 32342 | 45319.961 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 65 | 12869.33 | 3 | 855 | 834.1097 | august | 7116.63 | 3420.22 | 951.43 | 3824.86 | both | TRUE
c20 | 20 MPa Concrete | 235 | cum | 46527.59 | 278.04 | 167.3434 | 33134 | 198 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 4.3434 | 792 | 1207.6336 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 10 | 2768.127 | 12 | 19068.2 | 486.8529 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 10 | 2768.13 | 12 | 19068.2 | 486.8529 | june | 5795.74 | 13408.52 | 18868.38 | 9951.37 | both | TRUE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 12 | 22522.4 | 486.8529 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 14.87 | 4116.48 | 0 | 3454.2 | 0 | july | 5795.74 | 12636.15 | 17283.16 | 9234.53 | both | TRUE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 12 | 23822 | 486.8529 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 0 | 1299.6 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 13.4 | 24125.2 | 543.6524 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 1.4 | 303.2 | 56.7995 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 37.5 | 28928 | 1521.4152 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 24.1 | 4802.8 | 977.7628 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 55.5 | 32468.8 | 2251.6945 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 18 | 3540.8 | 730.2793 | november | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 61.26 | 33596 | 2485.3839 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 5.76 | 1127.2 | 233.6894 | december | 0 | 0 | 0 | 0 | left_only | FALSE
c25 | 25 Mpa | 24.87 | cum | 6884.61 | 40.57 | 169.6925 | 33596 | 197.9816 | 24.871 | 6884.6088 | 169.6925 | 33596 | 6884.6088 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-06-01 | 2015-03-01 | 0 | 0 | 108.4325 | 0 | 4399.2249 | march | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 11 | cum | 1980 | 313.6 | 6.3139 | 1359.2 | 215.2727 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 11 | cum | 1980 | 313.6 | 6.3139 | 1359.2 | 215.2727 | 0 | 0 | 1.6 | 351.4 | 501.754 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-03-01 | 0 | 0 | 1.6 | 351.4 | 501.754 | august | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 11 | cum | 1980 | 313.6 | 6.3139 | 1359.2 | 215.2727 | 11 | 1980 | 1.6 | 351.4 | 501.754 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-03-01 | 11 | 1980 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 11 | cum | 1980 | 313.6 | 6.3139 | 1359.2 | 215.2727 | 11 | 1980 | 6.31 | 1359.2 | 1978.7922 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-03-01 | 0 | 0 | 4.71 | 1007.8 | 1477.0383 | october | 0 | 0 | 0 | 0 | left_only | FALSE
c32 | 32 Mpa | 11 | cum | 1980 | 313.6 | 6.3139 | 1359.2 | 215.2727 | 11 | 1980 | 6.3139 | 1359.2 | 1980 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-08-01 | 2015-03-01 | 0 | 0 | 0.0038514 | 0 | 1.2078 | march | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 31.54 | cum | 6371.05 | 242.32 | 26.2916 | 5311 | 202.0036 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 31.54 | cum | 6371.05 | 242.32 | 26.2916 | 5311 | 202.0036 | 31.544 | 6371.0547 | 0 | 0 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 31.54 | 6371.05 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
ckm | Kerb Mix | 31.54 | cum | 6371.05 | 242.32 | 26.2916 | 5311 | 202.0036 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 0 | 0 | 26.2916 | 5311 | 6371.0547 | september | 0 | 0 | 0 | 0 | left_only | FALSE
e32 | Exposed Aggregate Concrete | 44.88 | cum | 14001.5 | 313.41 | 44.6749 | 13939 | 312.0098 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
e32 | Exposed Aggregate Concrete | 44.88 | cum | 14001.5 | 313.41 | 44.6749 | 13939 | 312.0098 | 44.88 | 14001.4959 | 0 | 0 | 0 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 44.88 | 14001.5 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
e32 | Exposed Aggregate Concrete | 44.88 | cum | 14001.5 | 313.41 | 44.6749 | 13939 | 312.0098 | 44.88 | 14001.4959 | 29.9 | 9323 | 9370.9204 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 29.9 | 9323 | 9370.9204 | november | 0 | 0 | 0 | 0 | left_only | FALSE
e32 | Exposed Aggregate Concrete | 44.88 | cum | 14001.5 | 313.41 | 44.6749 | 13939 | 312.0098 | 44.88 | 14001.4959 | 44.67 | 13939 | 13999.967 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 14.77 | 4616 | 4629.0466 | december | 0 | 0 | 0 | 0 | left_only | FALSE
e32 | Exposed Aggregate Concrete | 44.88 | cum | 14001.5 | 313.41 | 44.6749 | 13939 | 312.0098 | 44.88 | 14001.4959 | 44.6749 | 13939 | 14001.4959 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2015-03-01 | 0 | 0 | 0.0048782 | 0 | 1.5289 | march | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 1000 | 5366.3142 | 900 | 6187.74 | 4829.6828 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 1000 | 5366.31 | 900 | 6187.74 | 4829.6828 | may | 7179.81 | 7154.44 | 7289.1 | 6238.08 | both | TRUE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 1170 | 6278.5876 | 900 | 6187.74 | 4829.6828 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 170 | 912.27 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 1170 | 6278.5876 | 900 | 6989.59 | 4829.6828 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 0 | 0 | 0 | 801.85 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 1170 | 6278.5876 | 1170 | 8507.09 | 6278.5876 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 0 | 0 | 270 | 1517.5 | 1448.9048 | october | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 1170 | 6278.5876 | 1170 | 8552.194 | 6278.5876 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 0 | 0 | 0 | 45.1 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
etc | Conduits | 1170 | m | 6278.59 | 5.37 | 1170 | 8596.694 | 7.3476 | 1170 | 6278.5876 | 1170 | 8596.694 | 6278.5876 | 2015-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-04-01 | 0 | 0 | 0 | 44.5 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.94 | 2637.16 | 6 | 12952.31 | 2158.7183 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.94 | 2637.16 | 6 | 12952.31 | 2158.7183 | 6 | 15822.945 | 0 | 174.68 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 6 | 15822.94 | 0 | 174.68 | 0 | may | 2514.97 | 1597.08 | 34.53 | 2050.06 | both | TRUE
etm | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.94 | 2637.16 | 6 | 12952.31 | 2158.7183 | 6 | 15822.945 | 3 | 7480.68 | 7911.4725 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 3 | 7306 | 7911.4725 | june | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.94 | 2637.16 | 6 | 12952.31 | 2158.7183 | 6 | 15822.945 | 3 | 7570 | 7911.4725 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 0 | 89.32 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.94 | 2637.16 | 6 | 12952.31 | 2158.7183 | 6 | 15822.945 | 6 | 12798.36 | 15822.945 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 3 | 5228.36 | 7911.4725 | october | 0 | 0 | 0 | 0 | left_only | FALSE
etm | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.94 | 2637.16 | 6 | 12952.31 | 2158.7183 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-11-01 | 0 | 0 | 0 | 153.95 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 23 | each | 29400 | 1278.26 | 23 | 1580 | 68.6957 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 23 | each | 29400 | 1278.26 | 23 | 1580 | 68.6957 | 0 | 0 | 0 | 1580 | 0 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 0 | 0 | 0 | 1580 | 0 | may | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 23 | each | 29400 | 1278.26 | 23 | 1580 | 68.6957 | 0 | 0 | 23 | 1580 | 29400 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 0 | 0 | 23 | 0 | 29400 | june | 0 | 0 | 0 | 0 | left_only | FALSE
etp | Pits & Lids | 23 | each | 29400 | 1278.26 | 23 | 1580 | 68.6957 | 23 | 29400 | 23 | 1580 | 29400 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 23 | 29400 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.1 | 2.1 | 300 | tonne | 10500 | 35.52 | 295.5914 | 10345.698 | 35 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.1 | 2.1 | 300 | tonne | 10500 | 35.52 | 295.5914 | 10345.698 | 35 | 300 | 10500 | 0 | 0 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 300 | 10500 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.1 | 2.1 | 300 | tonne | 10500 | 35.52 | 295.5914 | 10345.698 | 35 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 0 | 0 | 295.5914 | 10345.7 | 10500 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 542.4 | tonne | 18984 | 42.41 | 447.6711 | 15668.488 | 35 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 542.4 | tonne | 18984 | 42.41 | 447.6711 | 15668.488 | 35 | 542.4 | 18984 | 0 | 0 | 0 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 542.4 | 18984 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.3 | 2.3 | 542.4 | tonne | 18984 | 42.41 | 447.6711 | 15668.488 | 35 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-07-01 | 2014-09-01 | 0 | 0 | 447.6711 | 15668.49 | 18984 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.5 | 2.5 | 0 | tonne | 28444.98 | 31.21 | 911.3 | 14580.8 | 16 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2014-09-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
qm2.5 | 2.5 | 0 | tonne | 28444.98 | 31.21 | 911.3 | 14580.8 | 16 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-09-01 | 2014-09-01 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 177 | 9477.436 | 48 | 2131.18 | 1947.9387 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 177 | 9477.44 | 48 | 2131.18 | 1947.9387 | may | 11719.06 | 14180.87 | 15714.5 | 13049.5 | both | TRUE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 390 | 20882.4861 | 695 | 30507.62 | 28204.529 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 213 | 11405.05 | 647 | 28376.44 | 26256.5903 | june | 11719.06 | 21660.78 | 27925.27 | 17533.23 | both | TRUE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 600 | 32126.9017 | 995 | 43587.5848 | 40379.1458 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 210 | 11244.42 | 300 | 13079.96 | 12174.6168 | july | 11719.06 | 13759.95 | 15222.12 | 12178.09 | both | TRUE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 800 | 42835.8689 | 1010 | 44268.4948 | 40987.8767 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 200 | 10708.97 | 15 | 680.91 | 608.7308 | august | 7116.63 | 4464.33 | 1425.78 | 4847.18 | both | TRUE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 800 | 42835.8689 | 1055.5372 | 46189.1848 | 42835.8689 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 45.5372 | 1920.69 | 1847.9923 | november | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.87 | 40.58 | 1055.5372 | 46148.0854 | 43.72 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-12-01 | 0 | 0 | 0 | -41.1 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 200 | 2022.202 | 125 | 4314.14 | 1359.2672 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 200 | 2022.2 | 125 | 4314.14 | 1359.2672 | may | 3057.01 | 3905.14 | 3879.41 | 3707.77 | both | TRUE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 400 | 4044.404 | 180 | 6263.59 | 1957.3448 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 200 | 2022.2 | 55 | 1949.45 | 598.0776 | june | 3057.01 | 2299.66 | 1927.95 | 2283.09 | both | TRUE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 500 | 5055.505 | 200 | 7079.65 | 2174.8276 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 100 | 1011.1 | 20 | 816.06 | 217.4828 | july | 958.97 | 1917.23 | 1747.82 | 1128.56 | both | TRUE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 600 | 6066.606 | 200 | 7079.65 | 2174.8276 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 100 | 1011.1 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 687.161 | 6947.8917 | 560 | 19592.9867 | 6089.5172 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 87.16 | 881.29 | 360 | 12513.34 | 3914.6896 | september | 6869.26 | 9344.44 | 10696.4 | 7760.52 | both | TRUE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 687.161 | 6947.8917 | 585 | 20475.3448 | 6361.3706 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 25 | 882.36 | 271.8534 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 687.161 | 6947.8917 | 610 | 21398.7134 | 6633.224 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 25 | 923.37 | 271.8534 | november | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 687.161 | 6947.8917 | 610 | 21990.5944 | 6633.224 | 2015-02-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 0 | 591.88 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 687.16 | tonne | 6947.89 | 10.87 | 638.9373 | 22283.1785 | 34.8754 | 687.161 | 6947.8917 | 638.9373 | 22283.1785 | 6947.8917 | 2015-03-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2015-03-01 | 0 | 0 | 28.9373 | 292.58 | 314.6677 | march | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 6.89 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 2 | 6221.4509 | 2 | 5787.79 | 17152.8 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 6.89 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 2.5 | 7776.8136 | 2 | 5787.79 | 17152.8 | 2014-08-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0.5 | 1555.36 | 0 | 0 | 0 | august | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 6.89 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 6.893 | 21441 | 2 | 5787.79 | 17152.8 | 2014-09-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 4.39 | 13664.19 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 6.89 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 6.893 | 21441 | 2.3 | 6664.02 | 19725.72 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0.3 | 876.23 | 2572.92 | october | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 6.89 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 6.893 | 21441 | 2.5 | 7107.38 | 21441 | 2014-11-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0.2 | 443.36 | 1715.28 | november | 0 | 0 | 0 | 0 | left_only | FALSE
rsb | Straight / Bent Bar | 6.89 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 6.893 | 21441 | 2.5 | 7224.56 | 21441 | 2014-12-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-12-01 | 0 | 0 | 0 | 117.18 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 10 | each | 2500 | 250 | 10 | 5034 | 503.4 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 10 | each | 2500 | 250 | 10 | 5034 | 503.4 | 0 | 0 | 10 | 5034 | 2500 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 0 | 0 | 10 | 5034 | 2500 | may | 0 | 0 | 0 | 0 | left_only | FALSE
swl | Grates, Frames & Lids | 10 | each | 2500 | 250 | 10 | 5034 | 503.4 | 10 | 2500 | 10 | 5034 | 2500 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-07-01 | 10 | 2500 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 507.6 | m | 42802.17 | 84.32 | 507.6 | 11450.18 | 22.5575 | 0 | 0 | 0 | 0 | 0 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 507.6 | m | 42802.17 | 84.32 | 507.6 | 11450.18 | 22.5575 | 400 | 33729.0512 | 400 | 8953.67 | 33729.0512 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 400 | 33729.05 | 400 | 8953.67 | 33729.0512 | may | 5841.9 | 14535.48 | 13560.5 | 11271.85 | both | TRUE
swp | RCP | 507.6 | m | 42802.17 | 84.32 | 507.6 | 11450.18 | 22.5575 | 507.6 | 42802.166 | 400 | 8953.67 | 33729.0512 | 2014-07-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 107.6 | 9073.11 | 0 | 0 | 0 | july | 0 | 0 | 0 | 0 | left_only | FALSE
swp | RCP | 507.6 | m | 42802.17 | 84.32 | 507.6 | 11450.18 | 22.5575 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 2014-10-01 | P038 - P17 Marina Sub-division | 2014-05-01 | 2014-10-01 | 0 | 0 | 107.6 | 2496.51 | 9073.1148 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swpc | Pre-cast Pits | 2 | each | 26170 | 13085 | 2 | 29445 | 14722.5 | 0 | 0 | 0.54 | 7975 | 7065.9 | 2014-04-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-06-01 | 0 | 0 | 0 | 0 | 0 | april | 0 | 0 | 0 | 0 | left_only | FALSE
swpc | Pre-cast Pits | 2 | each | 26170 | 13085 | 2 | 29445 | 14722.5 | 2 | 26170 | 2 | 30945 | 26170 | 2014-05-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-06-01 | 2 | 26170 | 1.46 | 22970 | 19104.1 | may | 29134.33 | 18099.22 | 20509.51 | 21263.75 | both | TRUE
swpc | Pre-cast Pits | 2 | each | 26170 | 13085 | 2 | 29445 | 14722.5 | 2 | 26170 | 2 | 29445 | 26170 | 2014-06-01 | P038 - P17 Marina Sub-division | 2014-04-01 | 2014-06-01 | 0 | 0 | 0 | -1500 | 0 | june | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 180 | hrs | 33305.5 | 185.03 | 198 | 36667.3 | 185.1884 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
11 | Survey - Construction | 180 | hrs | 33305.5 | 185.03 | 198 | 36667.3 | 185.1884 | 100 | 18503.0556 | 108 | 20034.6 | 18166.6364 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 100 | 18503.06 | 108 | 20034.6 | 18166.6364 | october | 5114.24 | 13238.93 | 16846 | 10681.09 | both | TRUE
11 | Survey - Construction | 180 | hrs | 33305.5 | 185.03 | 198 | 36667.3 | 185.1884 | 150 | 27754.5833 | 164 | 30386.6 | 27586.3737 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 50 | 9251.53 | 56 | 10352 | 9419.7374 | january | 13406.07 | 10948.45 | 12116.56 | 11362.95 | both | TRUE
11 | Survey - Construction | 180 | hrs | 33305.5 | 185.03 | 198 | 36667.3 | 185.1884 | 165 | 30530.0417 | 182 | 33608.3 | 30614.1465 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 15 | 2775.46 | 18 | 3221.7 | 3027.7727 | february | 3058.72 | 3160.95 | 3181.93 | 3115.71 | both | TRUE
11 | Survey - Construction | 180 | hrs | 33305.5 | 185.03 | 198 | 36667.3 | 185.1884 | 180 | 33305.5 | 198 | 36667.3 | 33305.5 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 15 | 2775.46 | 16 | 3059 | 2691.3535 | march | 3058.72 | 3267.01 | 3721.86 | 2956.52 | both | TRUE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4536 | 4536 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2014-12-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4536 | 4536 | 0 | 0 | 0.5 | 2430 | 0 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2014-12-01 | 0 | 0 | 0.5 | 2430 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4536 | 4536 | 0 | 0 | 0.9 | 4239 | 0 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2014-12-01 | 0 | 0 | 0.4 | 1809 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
13 | QA Testing | 0 | item | 0 | 0 | 1 | 4536 | 4536 | 0 | 0 | 1 | 4536 | 0 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2014-12-01 | 0 | 0 | 0.1 | 297 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 1 | 1000 | 1 | 900 | 555.5556 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 1 | 1000 | 1 | 900 | 555.5556 | october | 609.44 | 962 | 738.46 | 900.1 | both | TRUE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 5 | 5000 | 5 | 4488 | 2777.7778 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 4 | 4000 | 4 | 3588 | 2222.2222 | november | 3057.01 | 3003.64 | 2308.98 | 3002.28 | both | TRUE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 8 | 8000 | 8 | 7314 | 4444.4444 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 3 | 3000 | 3 | 2826 | 1666.6667 | december | 3057.01 | 2877.43 | 2987.65 | 2643.16 | both | TRUE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 8 | 8000 | 11.3 | 10140 | 6277.7778 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 3.3 | 2826 | 1833.3333 | january | 0 | 0 | 0 | 0 | left_only | FALSE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 8 | 8000 | 13.6 | 12259.5 | 7555.5556 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 2.3 | 2119.5 | 1277.7778 | february | 0 | 0 | 0 | 0 | left_only | FALSE
16 | GPS Hire | 8 | weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 8 | 8000 | 14.4 | 12966 | 8000 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0.8 | 706.5 | 444.4444 | march | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition | 1 | item | 7626.23 | 7626.23 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
41 | Demolition | 1 | item | 7626.23 | 7626.23 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 7626.2264 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 7626.2264 | march | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 12149 | m3 | 236016.49 | 19.43 | 12149 | 359268.44 | 29.5719 | 1000 | 19426.8245 | 903 | 27908.58 | 17542.4225 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
53 | Cut to Spoil | 12149 | m3 | 236016.49 | 19.43 | 12149 | 359268.44 | 29.5719 | 4034 | 78367.8101 | 3747 | 124092.32 | 72792.3115 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 3034 | 58940.99 | 2844 | 96183.74 | 55249.8889 | october | 96278.32 | 85437.3 | 99880.2 | 85551.81 | both | TRUE
53 | Cut to Spoil | 12149 | m3 | 236016.49 | 19.43 | 12149 | 359268.44 | 29.5719 | 9615 | 186788.9178 | 8854 | 215681.595 | 172005.1043 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 5581 | 108421.11 | 5107 | 91589.28 | 99212.7928 | november | 96278.32 | 89413.43 | 99003.26 | 88742.9 | both | TRUE
53 | Cut to Spoil | 12149 | m3 | 236016.49 | 19.43 | 12149 | 359268.44 | 29.5719 | 10000 | 194268.2452 | 9946 | 252038.68 | 193219.1967 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 385 | 7479.33 | 1092 | 36357.09 | 21214.0924 | december | 27472.44 | 28015.17 | 31519.94 | 25915.73 | both | TRUE
53 | Cut to Spoil | 12149 | m3 | 236016.49 | 19.43 | 12149 | 359268.44 | 29.5719 | 11878 | 230751.8217 | 11000 | 319105.3 | 213695.0697 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 1878 | 36483.58 | 1054 | 67066.62 | 20475.873 | january | 62249.6 | 61594.48 | 72632.36 | 58940.43 | both | TRUE
53 | Cut to Spoil | 12149 | m3 | 236016.49 | 19.43 | 12149 | 359268.44 | 29.5719 | 12149 | 236016.4911 | 12149 | 359268.44 | 236016.4911 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 271 | 5264.67 | 1149 | 40163.14 | 22321.4214 | february | 27472.44 | 24746.68 | 26605.79 | 23969.44 | both | TRUE
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.63 | 68.54 | 2378 | 36487.555 | 15.3438 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.63 | 68.54 | 2378 | 36487.555 | 15.3438 | 34 | 2330.4244 | 34 | 521.85 | 2330.4244 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 34 | 2330.42 | 34 | 521.85 | 2330.4244 | october | 3058.72 | 4619.44 | 1383.97 | 3334.25 | both | TRUE
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.63 | 68.54 | 2378 | 36487.555 | 15.3438 | 1615 | 110695.1602 | 1613 | 23166.375 | 110558.0764 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 1581 | 108364.74 | 1579 | 22644.53 | 108227.652 | november | 77534.32 | 72513.73 | 78298.4 | 72398.15 | both | TRUE
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.63 | 68.54 | 2378 | 36487.555 | 15.3438 | 2000 | 137083.7897 | 2002 | 27665.145 | 137220.8735 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 385 | 26388.63 | 389 | 4498.77 | 26662.7971 | december | 2744.08 | 8285.15 | 4402.1 | 5740.39 | both | TRUE
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.63 | 68.54 | 2378 | 36487.555 | 15.3438 | 2378 | 162992.626 | 2100 | 28898.625 | 143937.9792 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 378 | 25908.84 | 98 | 1233.48 | 6717.1057 | january | 2744.08 | 7029.99 | 2195.49 | 4968.34 | both | TRUE
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.63 | 68.54 | 2378 | 36487.555 | 15.3438 | 2378 | 162992.626 | 2378 | 36487.555 | 162992.626 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 0 | 278 | 7588.93 | 19054.6468 | february | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 25482 | m2 | 131922.98 | 5.18 | 25482 | 3483.915 | 0.13672 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-01-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
61 | Subgrade Preparation | 25482 | m2 | 131922.98 | 5.18 | 25482 | 3483.915 | 0.13672 | 15000 | 77656.5688 | 17000 | 2508.3 | 88010.778 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-01-01 | 15000 | 77656.57 | 17000 | 2508.3 | 88010.778 | october | 5183.5 | 11450.71 | -2954.54 | 7679.76 | both | TRUE
61 | Subgrade Preparation | 25482 | m2 | 131922.98 | 5.18 | 25482 | 3483.915 | 0.13672 | 25482 | 131922.9791 | 23500 | 3236.39 | 121661.9578 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-01-01 | 10482 | 54266.41 | 6500 | 728.09 | 33651.1798 | november | 5183.5 | 10550.25 | -1162.18 | 7161.37 | both | TRUE
61 | Subgrade Preparation | 25482 | m2 | 131922.98 | 5.18 | 25482 | 3483.915 | 0.13672 | 25482 | 131922.9791 | 25482 | 3483.915 | 131922.9791 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-01-01 | 0 | 0 | 1982 | 247.53 | 10261.0213 | january | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 1100 | 18292.8452 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 6750 | 112251.5503 | 1250 | 16948.92 | 51928.1885 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 5650 | 93958.71 | 1250 | 16948.92 | 51928.1885 | october | 25441.84 | 22547.37 | 11021.67 | 21113.05 | both | TRUE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 15000 | 249447.8895 | 4500 | 57164.455 | 186941.4786 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 8250 | 137196.34 | 3250 | 40215.53 | 135013.2901 | november | 25441.84 | 51523.11 | 50459.2 | 40337.74 | both | TRUE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 19401 | 322635.9003 | 6000 | 72503.555 | 249255.3048 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4401 | 73188.01 | 1500 | 15339.1 | 62313.8262 | december | 25441.84 | 20239.3 | 10124.99 | 19064.74 | both | TRUE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 20401 | 339265.7596 | 7500 | 78440.565 | 311569.131 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 1000 | 16629.86 | 1500 | 5937.01 | 62313.8262 | january | 15290.35 | 11100.45 | 5202.36 | 9333.54 | both | TRUE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 24591 | 408944.87 | 9844 | 107704.35 | 408944.87 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4190 | 69679.11 | 2344 | 29263.79 | 97375.7391 | february | 25441.84 | 27083.32 | 21409.61 | 23643.68 | both | TRUE
62 | Place & Compact Gravel (CBR80) | 24591 | tonne | 408944.87 | 16.63 | 9844 | 112261.32 | 11.404 | 24591 | 408944.87 | 9844 | 112261.32 | 408944.87 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 4556.97 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 29554 | m2 | 64324.17 | 2.18 | 29554 | 31078.215 | 1.0516 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 29554 | m2 | 64324.17 | 2.18 | 29554 | 31078.215 | 1.0516 | 15000 | 32647.4433 | 15000 | 3857.2 | 32647.4433 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-02-01 | 15000 | 32647.44 | 15000 | 3857.2 | 32647.4433 | november | 5410.44 | 9928.75 | 3716.9 | 6103.06 | both | TRUE
63 | Trim All Layers | 29554 | m2 | 64324.17 | 2.18 | 29554 | 31078.215 | 1.0516 | 23650 | 51474.1356 | 20850 | 25586.235 | 45379.9462 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-02-01 | 8650 | 18826.69 | 5850 | 21729.04 | 12732.5029 | december | 70121.96 | 19114.18 | 7438.35 | 32550.8 | both | TRUE
63 | Trim All Layers | 29554 | m2 | 64324.17 | 2.18 | 29554 | 31078.215 | 1.0516 | 23650 | 51474.1356 | 20850 | 25856.235 | 45379.9462 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-02-01 | 0 | 0 | 0 | 270 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
63 | Trim All Layers | 29554 | m2 | 64324.17 | 2.18 | 29554 | 31078.215 | 1.0516 | 29554 | 64324.1693 | 29554 | 31078.215 | 64324.1693 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-02-01 | 5904 | 12850.03 | 8704 | 5221.98 | 18944.2231 | february | 4191.71 | 8077.02 | 6647.84 | 5221.88 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.69 | 7.3 | 59019 | 358171.698 | 6.0688 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.69 | 7.3 | 59019 | 358171.698 | 6.0688 | 27000 | 197141.6273 | 26911 | 144776.32 | 196491.7901 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 27000 | 197141.63 | 26911 | 144776.32 | 196491.7901 | november | 112816.37 | 114336.57 | 119763.6 | 107291.75 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.69 | 7.3 | 59019 | 358171.698 | 6.0688 | 43000 | 313966.2953 | 43316 | 238241.242 | 316273.5825 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 16000 | 116824.67 | 16405 | 93464.92 | 119781.7924 | december | 50751.9 | 61751.08 | 63935.73 | 53417.33 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.69 | 7.3 | 59019 | 358171.698 | 6.0688 | 48000 | 350474.0041 | 47300 | 260384.727 | 345362.9249 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 5000 | 36507.71 | 3984 | 22143.48 | 29089.3423 | january | 26663.16 | 32658.73 | 35503.43 | 26915.37 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.69 | 7.3 | 59019 | 358171.698 | 6.0688 | 59019 | 430929.6926 | 53800 | 309481.994 | 392822.9462 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 11019 | 80455.69 | 6500 | 49097.27 | 47460.0214 | february | 50751.9 | 50007.74 | 50904.2 | 45927.62 | both | TRUE
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.69 | 7.3 | 59019 | 358171.698 | 6.0688 | 59019 | 430929.6926 | 59019 | 358171.698 | 430929.6926 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 5219 | 48689.7 | 38106.7464 | march | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt (Cold MIx) | 20 | tonne | 25937.5 | 1296.88 | 2 | 500.6 | 250.3 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2015-02-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
65 | Asphalt (Cold MIx) | 20 | tonne | 25937.5 | 1296.88 | 2 | 500.6 | 250.3 | 20 | 25937.5 | 2 | 500.6 | 25937.5 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2015-02-01 | 2015-02-01 | 20 | 25937.5 | 2 | 500.6 | 25937.5 | february | 13330.1 | 4337.07 | 11754.7 | 7195.04 | both | TRUE
67 | Line Marking & Signs | 1 | item | 6094 | 6094 | 1 | 3719.88 | 3719.88 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
67 | Line Marking & Signs | 1 | item | 6094 | 6094 | 1 | 3719.88 | 3719.88 | 0.1 | 609.4 | 0.1 | 448.42 | 609.4 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0.1 | 609.4 | 0.1 | 448.42 | 609.4 | october | 327.58 | 523.44 | 120.11 | 290.09 | both | TRUE
67 | Line Marking & Signs | 1 | item | 6094 | 6094 | 1 | 3719.88 | 3719.88 | 0.2 | 1218.8 | 0.2 | 681.96 | 1218.8 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0.1 | 609.4 | 0.1 | 233.54 | 609.4 | november | 327.58 | 362 | -886.45 | 142.98 | both | TRUE
67 | Line Marking & Signs | 1 | item | 6094 | 6094 | 1 | 3719.88 | 3719.88 | 0.7 | 4265.8 | 0.7 | 2668.44 | 4265.8 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0.5 | 3047 | 0.5 | 1986.48 | 3047 | december | 5795.74 | 2300.67 | 1401.27 | 2897.33 | both | TRUE
67 | Line Marking & Signs | 1 | item | 6094 | 6094 | 1 | 3719.88 | 3719.88 | 1 | 6094 | 1 | 3719.88 | 6094 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 6094 | 0.3 | 995.39 | 1828.2 | february | 8981.05 | 3834.57 | 2719.76 | 5142.8 | both | TRUE
72 | 525 > 750 | 31.2 | m | 2200 | 70.51 | 31.2 | 12781.13 | 409.6516 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2015-02-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
72 | 525 > 750 | 31.2 | m | 2200 | 70.51 | 31.2 | 12781.13 | 409.6516 | 31.2 | 2200 | 31.2 | 12781.13 | 2200 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2015-02-01 | 2015-02-01 | 31.2 | 2200 | 31.2 | 12781.13 | 2200 | february | 5795.74 | 4171.71 | 1321.51 | 3451.06 | both | TRUE
81 | SW >450 | 1 | item | 4246.94 | 4246.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
81 | SW >450 | 1 | item | 4246.94 | 4246.94 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 0 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 1 | 4246.94 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
81 | SW >450 | 1 | item | 4246.94 | 4246.94 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 4246.9385 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 4246.9385 | march | 0 | 0 | 0 | 0 | left_only | FALSE
82 | SW<525 | 1 | item | 8332.29 | 8332.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
82 | SW<525 | 1 | item | 8332.29 | 8332.29 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 0 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 1 | 8332.29 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
82 | SW<525 | 1 | item | 8332.29 | 8332.29 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 8332.2857 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 8332.2857 | march | 0 | 0 | 0 | 0 | left_only | FALSE
88 | Clean & Trim Table Drains | 141 | m3 | 53447.89 | 379.06 | 141 | 11515.3925 | 81.6695 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
88 | Clean & Trim Table Drains | 141 | m3 | 53447.89 | 379.06 | 141 | 11515.3925 | 81.6695 | 65 | 24639.0992 | 40 | 3205.11 | 15162.5226 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 65 | 24639.1 | 40 | 3205.11 | 15162.5226 | november | 2744.08 | 7211.67 | 5194.47 | 5776.61 | both | TRUE
88 | Clean & Trim Table Drains | 141 | m3 | 53447.89 | 379.06 | 141 | 11515.3925 | 81.6695 | 65 | 24639.0992 | 55 | 4552.23 | 20848.4686 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 15 | 1347.12 | 5685.946 | december | 0 | 0 | 0 | 0 | left_only | FALSE
88 | Clean & Trim Table Drains | 141 | m3 | 53447.89 | 379.06 | 141 | 11515.3925 | 81.6695 | 65 | 24639.0992 | 65 | 5169.72 | 24639.0992 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 10 | 617.49 | 3790.6307 | january | 0 | 0 | 0 | 0 | left_only | FALSE
88 | Clean & Trim Table Drains | 141 | m3 | 53447.89 | 379.06 | 141 | 11515.3925 | 81.6695 | 141 | 53447.8922 | 141 | 11435.3925 | 53447.8922 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 76 | 28808.79 | 76 | 6265.67 | 28808.793 | february | 2744.08 | 6470.94 | 4276.4 | 5318.38 | both | TRUE
88 | Clean & Trim Table Drains | 141 | m3 | 53447.89 | 379.06 | 141 | 11515.3925 | 81.6695 | 141 | 53447.8922 | 141 | 11515.3925 | 53447.8922 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 80 | 0 | march | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 80 | 3840.1398 | 50 | 4305.04 | 3978.9636 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 485 | 23280.8475 | 290 | 18893.75 | 23077.9888 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 405 | 19440.71 | 240 | 14588.71 | 19099.0252 | october | 14917.02 | 13311.16 | 14066.33 | 13714.27 | both | TRUE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 1225 | 58802.1405 | 736 | 43252.38 | 58570.3439 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 740 | 35521.29 | 446 | 24358.63 | 35492.3551 | november | 13119.91 | 21195.93 | 24274.21 | 18485.66 | both | TRUE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 1475 | 70802.5773 | 884 | 51499.55 | 70348.0761 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 250 | 12000.44 | 148 | 8247.17 | 11777.7322 | december | 6137.31 | 8761.38 | 9803.84 | 7597.76 | both | TRUE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 1860 | 89283.2501 | 1114 | 63826.72 | 88651.3085 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 385 | 18480.67 | 230 | 12327.17 | 18303.2325 | january | 6137.31 | 11644.59 | 13310.96 | 9622.21 | both | TRUE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 2280 | 109443.9839 | 1368 | 76966.21 | 108864.4435 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 420 | 20160.73 | 254 | 13139.49 | 20213.135 | february | 6137.31 | 12398.93 | 14554.49 | 10287.56 | both | TRUE
141 | Traffic Controllers | 2442 | hrs | 117220.27 | 48 | 1473 | 82094.66 | 55.733 | 2442 | 117220.267 | 1473 | 82094.66 | 117220.267 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 162 | 7776.28 | 105 | 5128.45 | 8355.8235 | march | 6137.31 | 8182.45 | 9747.46 | 7119.44 | both | TRUE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 0.2 | 2960 | 0.2 | 969.36 | 2960 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 0.5 | 7400 | 0.45 | 1407.96 | 6660 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0.3 | 4440 | 0.25 | 438.6 | 3700 | october | 1899.18 | 1237.06 | -3820.73 | 877.79 | both | TRUE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 0.8 | 11840 | 0.65 | 1407.96 | 9620 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0.3 | 4440 | 0.2 | 0 | 2960 | november | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 0.8 | 11840 | 0.8 | 2544.92 | 11840 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0.15 | 1136.96 | 2220 | december | 0 | 0 | 0 | 0 | left_only | FALSE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 0.9 | 13320 | 0.9 | 3294.92 | 13320 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0.1 | 1480 | 0.1 | 750 | 1480 | january | 633.01 | 1047.4 | -3749.69 | 48.03 | both | TRUE
151 | Supply & Place Silt fences & protective devices | 1 | item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 1 | 14800 | 1 | 3294.92 | 14800 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0.1 | 1480 | 0.1 | 0 | 1480 | february | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Protection Rock | 28.64 | m3 | 6471.6 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-12-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Protection Rock | 28.64 | m3 | 6471.6 | 226 | 0 | 0 | 0 | 28.64 | 6472.64 | 0 | 0 | 0 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-12-01 | 2015-03-01 | 28.64 | 6472.64 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
221 | Place Protection Rock | 28.64 | m3 | 6471.6 | 226 | 0 | 0 | 0 | 28.64 | 6472.64 | 0 | 0 | 6471.6 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-12-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 6471.6 | march | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8 | 14642 | 37594.3225 | 2.5676 | 0 | 0 | 0 | 5312.5 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8 | 14642 | 37594.3225 | 2.5676 | 9250 | 16661.3714 | 9159 | 22060.235 | 16497.4595 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 9250 | 16661.37 | 9159 | 16747.74 | 16497.4595 | november | 18318.04 | 19595.32 | 14574.77 | 16907.91 | both | TRUE
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8 | 14642 | 37594.3225 | 2.5676 | 10500 | 18912.9081 | 10231 | 31275.655 | 18428.3774 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 1250 | 2251.54 | 1072 | 9215.42 | 1930.9179 | december | 2852.72 | 7553.02 | 3750.13 | 4753.95 | both | TRUE
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8 | 14642 | 37594.3225 | 2.5676 | 12500 | 22515.3668 | 12242 | 32198.665 | 22050.6496 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2000 | 3602.46 | 2011 | 923.01 | 3622.2722 | january | 2852.72 | 2605.04 | -4731.51 | 1534.7 | both | TRUE
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8 | 14642 | 37594.3225 | 2.5676 | 14641 | 26371.7988 | 14641 | 37594.3225 | 26371.7988 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2141 | 3856.43 | 2399 | 5395.66 | 4321.1492 | february | 2852.72 | 3983.13 | -2364.98 | 2561.52 | both | TRUE
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8 | 14642 | 37594.3225 | 2.5676 | 14641 | 26371.7988 | 14641 | 37594.3225 | 26373.6 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 1.8012 | march | 0 | 0 | 0 | 0 | left_only | FALSE
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.06 | 12.52 | 24591 | 187160.795 | 7.6109 | 1100 | 13776.4614 | 1067 | 8111.045 | 13363.1676 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.06 | 12.52 | 24591 | 187160.795 | 7.6109 | 8000 | 100192.4468 | 7837 | 59559.59 | 98151.0257 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 6900 | 86415.99 | 6770 | 51448.55 | 84787.8581 | october | 50751.9 | 59925.17 | 60368.85 | 53786.76 | both | TRUE
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.06 | 12.52 | 24591 | 187160.795 | 7.6109 | 18500 | 231695.0332 | 18645 | 141701.38 | 233511.0213 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 10500 | 131502.59 | 10808 | 82141.79 | 135359.9956 | november | 50751.9 | 78623.83 | 83028.86 | 66276.45 | both | TRUE
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.06 | 12.52 | 24591 | 187160.795 | 7.6109 | 22500 | 281791.2566 | 20626 | 156761.355 | 258321.176 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 4000 | 50096.22 | 1981 | 15059.98 | 24810.1546 | december | 50751.9 | 57902.14 | 62182.38 | 51822.23 | both | TRUE
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.06 | 12.52 | 24591 | 187160.795 | 7.6109 | 22804 | 285598.5696 | 22804 | 173309.795 | 285598.5696 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 304 | 3807.31 | 2178 | 16548.44 | 27277.3936 | january | 9318.44 | 14390.72 | 8937.66 | 10325.15 | both | TRUE
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.06 | 12.52 | 24591 | 187160.795 | 7.6109 | 24591 | 307979.0574 | 24591 | 187160.795 | 307979.0574 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 1787 | 22380.49 | 1787 | 13851 | 22380.4878 | february | 26663.16 | 20095.29 | 11653.73 | 19768.44 | both | TRUE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 2 | 6857.1429 | 6 | 21821.88 | 9000 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 6 | 20571.4286 | 10 | 37971.88 | 15000 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 13714.29 | 4 | 16150 | 6000 | october | 19644.48 | 17001.6 | 18743.06 | 17151.22 | both | TRUE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 8 | 27428.5714 | 16 | 63096.88 | 24000 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2 | 6857.14 | 6 | 25125 | 9000 | november | 19644.48 | 21186.18 | 25414.07 | 19677.9 | both | TRUE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 10 | 34285.7143 | 20 | 79246.88 | 30000 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2 | 6857.14 | 4 | 16150 | 6000 | december | 11719.06 | 15150.41 | 18448.16 | 13039 | both | TRUE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 12 | 41142.8571 | 24 | 91359.38 | 36000 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2 | 6857.14 | 4 | 12112.5 | 6000 | january | 11719.06 | 13388.13 | 15380.75 | 11947.72 | both | TRUE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 14 | 48000 | 28 | 107509.38 | 42000 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2 | 6857.14 | 4 | 16150 | 6000 | february | 11719.06 | 15143.57 | 18414.12 | 13231.35 | both | TRUE
901 | Project Management | 14 | weeks | 48000 | 3428.57 | 32 | 123128.13 | 3847.7541 | 14 | 48000 | 32 | 123128.13 | 48000 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 4 | 15618.75 | 6000 | march | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 2 | 4521.8182 | 1.5 | 3366 | 2664.6429 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 6 | 13565.4545 | 8 | 18013.5 | 14211.4286 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 9043.64 | 6.5 | 14647.5 | 11546.7857 | october | 19644.48 | 16080.99 | 17832.9 | 16973.25 | both | TRUE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 10 | 22609.0909 | 15 | 34605 | 26646.4286 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 9043.64 | 7 | 16591.5 | 12435 | november | 19644.48 | 15556.82 | 16251.63 | 16591.6 | both | TRUE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 13 | 29391.8182 | 18 | 40995 | 31975.7143 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 3 | 6782.73 | 3 | 6390 | 5329.2857 | december | 11719.06 | 8138.87 | 7356.97 | 9014.08 | both | TRUE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 16 | 36174.5455 | 23 | 53320.5 | 40857.8571 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 3 | 6782.73 | 5 | 12325.5 | 8882.1429 | january | 11719.06 | 10965.59 | 11560.32 | 10890.03 | both | TRUE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 20 | 45218.1818 | 27 | 63130.5 | 47963.5714 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 9043.64 | 4 | 9810 | 7105.7143 | february | 11719.06 | 9598.87 | 9385.81 | 10199.79 | both | TRUE
902 | Project Supervision | 22 | weeks | 49740 | 2260.91 | 28 | 64840.5 | 2315.7321 | 22 | 49740 | 28 | 64840.5 | 49740 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2 | 4521.82 | 1 | 1710 | 1776.4286 | march | 3058.72 | 2407.08 | 889.66 | 2523.72 | both | TRUE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 0 | 0 | 1 | 9804.26 | 681.0417 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 4 | 3269 | 5 | 11488.22 | 3405.2083 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 3269 | 4 | 1683.96 | 2724.1667 | october | 3058.72 | 2143.71 | 2188.28 | 2315.07 | both | TRUE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 8 | 6538 | 9 | 13821.77 | 6129.375 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 3269 | 4 | 2333.55 | 2724.1667 | november | 3058.72 | 2667.55 | 2267.46 | 2611.06 | both | TRUE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 11 | 8989.75 | 12 | 18600.36 | 8172.5 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 3 | 2451.75 | 3 | 4778.59 | 2043.125 | december | 3058.72 | 4315.41 | 5735.86 | 3402.69 | both | TRUE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 14 | 11441.5 | 16 | 21448.227 | 10896.6667 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 3 | 2451.75 | 4 | 2847.87 | 2724.1667 | january | 3058.72 | 3382.94 | 3983.2 | 2847.97 | both | TRUE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 18 | 14710.5 | 20 | 27285.857 | 13620.8333 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 4 | 3269 | 4 | 5837.63 | 2724.1667 | february | 3058.72 | 4974.65 | 6662.56 | 4041.87 | both | TRUE
903 | Project Facilities | 20 | weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 20 | 16345 | 24 | 30417.647 | 16345 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 2 | 1634.5 | 4 | 3131.79 | 2724.1667 | march | 1856.64 | 2694.48 | 3889.14 | 1931.53 | both | TRUE
904 | Project Insurance, Fees & Levies | 1 | item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 0.5 | 9375 | 0.6 | 7581.75 | 11250 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 0.5 | 9375 | 0.75 | 9309.02 | 14062.5 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0.15 | 1727.27 | 2812.5 | october | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 0.5 | 9375 | 0.9 | 10840.22 | 16875 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0.15 | 1531.2 | 2812.5 | november | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 0.5 | 9375 | 0.9 | 11089.41 | 16875 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0 | 249.19 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 0.5 | 9375 | 0.95 | 11707.29 | 17812.5 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0 | 0 | 0.05 | 617.88 | 937.5 | january | 0 | 0 | 0 | 0 | left_only | FALSE
904 | Project Insurance, Fees & Levies | 1 | item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 1 | 18750 | 1 | 12162.09 | 18750 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-02-01 | 0.5 | 9375 | 0.05 | 454.8 | 937.5 | february | 2795.89 | 4720.75 | 5948.53 | 3788.87 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.1 | 500 | 0.1 | 881.26 | 500 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.3 | 1500 | 0.3 | 1574.18 | 1500 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.2 | 1000 | 0.2 | 692.92 | 1000 | october | 609.44 | 597.22 | 746.82 | 541.71 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.5 | 2500 | 0.5 | 1739.62 | 2500 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.2 | 1000 | 0.2 | 165.44 | 1000 | november | 609.44 | 487.59 | -177.67 | 428.1 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.6 | 3000 | 0.6 | 2403.98 | 3000 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.1 | 500 | 0.1 | 664.36 | 500 | december | 303.01 | 539.35 | 795.95 | 98.08 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.7 | 3500 | 0.7 | 2904.89 | 3500 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.1 | 500 | 0.1 | 500.91 | 500 | january | 1158.64 | 569.29 | 370.09 | 433.21 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.9 | 4500 | 0.9 | 3413.1 | 4500 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.2 | 1000 | 0.2 | 508.21 | 1000 | february | 303.01 | 513.31 | 673.76 | 287.96 | both | TRUE
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 1 | 5000 | 1 | 3413.1 | 5000 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.1 | 500 | 0.1 | 0 | 500 | march | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 0.5 | 8577 | 0.5 | 28767.095 | 8577 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 0.5 | 8577 | 0.5 | 29388.905 | 8577 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 621.81 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 0.5 | 8577 | 0.6 | 33807.425 | 10292.4 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0.1 | 4418.52 | 1715.4 | november | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 0.75 | 12865.5 | 0.75 | 38294.425 | 12865.5 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.25 | 4288.5 | 0.15 | 4487 | 2573.1 | december | 5051.4 | 3903.58 | 4432.12 | 3865.15 | both | TRUE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 1 | 17154 | 0.9 | 39093.1242 | 15438.6 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0.25 | 4288.5 | 0.15 | 798.7 | 2573.1 | january | 5051.4 | 1947.83 | 1058.18 | 2648.78 | both | TRUE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 1 | 17154 | 0.9 | 41265.1542 | 15438.6 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 2172.03 | 0 | february | 0 | 0 | 0 | 0 | left_only | FALSE
907 | Site Establishment | 1 | item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 1 | 17154 | 1 | 43545.1542 | 17154 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0.1 | 2280 | 1715.4 | march | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0 | 0 | 0 | 0 | 0 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0 | 0 | 0 | 739.25 | 0 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 739.25 | 0 | november | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0.25 | 4500 | 0.25 | 5441.92 | 4500 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0.25 | 4500 | 0.25 | 4702.67 | 4500 | december | 5051.4 | 4402.44 | 5423.08 | 4095.8 | both | TRUE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0.25 | 4500 | 0.25 | 5626.92 | 4500 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0 | 0 | 0 | 185 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0.5 | 9000 | 0.5 | 10359.815 | 9000 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0.25 | 4500 | 0.25 | 4732.9 | 4500 | february | 5051.4 | 4205.02 | 5087.09 | 4164.93 | both | TRUE
910 | De-Establishment & Cleanup | 1 | item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 1 | 18000 | 1 | 21497.045 | 18000 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-11-01 | 2015-03-01 | 0.5 | 9000 | 0.5 | 11137.23 | 9000 | march | 2795.89 | 4291.11 | 5598.06 | 3377.08 | both | TRUE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 30 | 5605 | 66 | 12235.97 | 18496.5 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 90 | 16815 | 100 | 18465.17 | 28025 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 60 | 11210 | 34 | 6229.2 | 9528.5 | october | 14917.02 | 8966.36 | 6208.85 | 9754.35 | both | TRUE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 150 | 28025 | 182 | 33585.04 | 51005.5 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 60 | 11210 | 82 | 15119.87 | 22980.5 | november | 6137.31 | 12672.79 | 13362.32 | 9362.57 | both | TRUE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 210 | 39235 | 221 | 40939.25 | 61935.25 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 60 | 11210 | 39 | 7354.21 | 10929.75 | december | 6137.31 | 2488.92 | -2009.92 | 2519.99 | both | TRUE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 270 | 50445 | 237 | 43793.14 | 66419.25 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 60 | 11210 | 16 | 2853.89 | 4484 | january | 6137.31 | 2962.57 | -1534.74 | 2874.46 | both | TRUE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 330 | 61655 | 238 | 44122.03 | 66699.5 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 60 | 11210 | 1 | 328.89 | 280.25 | february | 6137.31 | 1861.9 | -3026.56 | 2311.34 | both | TRUE
911 | Accommodation | 360 | nights | 67260 | 186.83 | 240 | 44449.3 | 185.2054 | 360 | 67260 | 240 | 44449.3 | 67260 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 30 | 5605 | 2 | 327.27 | 560.5 | march | 3058.72 | 2865.06 | 302.39 | 1661.62 | both | TRUE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 60 | 2880 | 105 | 5061.125 | 2477.5281 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 180 | 8640 | 441 | 21148.614 | 10405.618 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 120 | 5760 | 336 | 16087.49 | 7928.0899 | october | 19644.48 | 16242.99 | 18650.32 | 16809.12 | both | TRUE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 300 | 14400 | 818 | 39284.409 | 19301.1236 | 2014-11-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 120 | 5760 | 377 | 18135.79 | 8895.5056 | november | 19644.48 | 16788.25 | 18763.43 | 17118.95 | both | TRUE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 420 | 20160 | 983 | 47196.964 | 23194.382 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 120 | 5760 | 165 | 7912.55 | 3893.2584 | december | 11719.06 | 9130.48 | 9227.64 | 9431.27 | both | TRUE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 540 | 25920 | 1310 | 62881.144 | 30910.1124 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 120 | 5760 | 327 | 15684.18 | 7715.7303 | january | 11719.06 | 13199.12 | 15398.68 | 12110.25 | both | TRUE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 660 | 31680 | 1420 | 68170.729 | 33505.618 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 120 | 5760 | 110 | 5289.58 | 2595.5056 | february | 11719.06 | 9539.73 | 9852.85 | 9892.67 | both | TRUE
916 | Site Administration | 700 | hrs | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 700 | 33600 | 1424 | 68350.729 | 33600 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 40 | 1920 | 4 | 180 | 94.382 | march | 2954.94 | 2206.32 | 1099.6 | 2116.03 | both | TRUE
qmr | Supply Rock | 320 | tonne | 9595.75 | 29.99 | 0 | 0 | 0 | 100 | 2998.6719 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Supply Rock | 320 | tonne | 9595.75 | 29.99 | 0 | 0 | 0 | 320 | 9595.75 | 0 | 0 | 0 | 2014-12-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 220 | 6597.08 | 0 | 0 | 0 | december | 0 | 0 | 0 | 0 | left_only | FALSE
qmr | Supply Rock | 320 | tonne | 9595.75 | 29.99 | 0 | 0 | 0 | 320 | 9595.75 | 0 | 0 | 9595.75 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-09-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 9595.75 | march | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 6.3 | tonne | 151.2 | 24 | 36 | 862.1 | 23.9472 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 6.3 | tonne | 151.2 | 24 | 36 | 862.1 | 23.9472 | 6.3 | 151.2 | 0 | 0 | 0 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 6.3 | 151.2 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 6.3 | tonne | 151.2 | 24 | 36 | 862.1 | 23.9472 | 6.3 | 151.2 | 0 | 862.1 | 0 | 2015-01-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 0 | 0 | 862.1 | 0 | january | 0 | 0 | 0 | 0 | left_only | FALSE
qms | Sand | 6.3 | tonne | 151.2 | 24 | 36 | 862.1 | 23.9472 | 6.3 | 151.2 | 36 | 862.1 | 151.2 | 2015-02-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-02-01 | 0 | 0 | 36 | 0 | 151.2 | february | 0 | 0 | 0 | 0 | left_only | FALSE
swp | Supply Stormwater Pipe | 25.2 | m | 4027.85 | 159.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014-09-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 0 | september | 0 | 0 | 0 | 0 | left_only | FALSE
swp | Supply Stormwater Pipe | 25.2 | m | 4027.85 | 159.84 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 0 | 2014-10-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 25.2 | 4027.85 | 0 | 0 | 0 | october | 0 | 0 | 0 | 0 | left_only | FALSE
swp | Supply Stormwater Pipe | 25.2 | m | 4027.85 | 159.84 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 4027.848 | 2015-03-01 | P039 - P18 Rural Road Repairs | 2014-10-01 | 2015-03-01 | 0 | 0 | 0 | 0 | 4027.848 | march | 0 | 0 | 0 | 0 | left_only | FALSE