## Estimate
| Line No. | Comment | Unit | Type | No | Production | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
[9 empty] | 1433245.2003 |  |  | 346083.0344 | -51859.9702 | 340142.26 | 798879.8761 | 1433245.2003
| Line No 1 Item No | Schedule A - Roadworks Dysart Bypass Road Widening
| Line No 2 Item No 1 | Preliminaries
5 | Line No 3 Item No (a) | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | Item |  |  |  | 1 |  | 34725 |  | 2 | 14385 | 0 | 16840 | 3500 | 34725
| 1 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 1 | 3350 | 0 | 0 | 0 | 3350 | 902 |  | QMS | 147.8127
| 2 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
| 3 | Float | LS | P | 1 | 1 | 2400 | 1 | 2400 | 2400 | 2400 | 0 | 0 | 2400 | 0 | 2400 | 907
| 4 | Float | LS | P | 1 | 1 | 2000 | 1 | 2000 | 2000 | 2000 | 0 | 0 | 2000 | 0 | 2000 | 907
| 5 | Float | LS | P | 1 | 1 | 2000 | 1 | 2000 | 2000 | 2000 | 0 | 0 | 2000 | 0 | 2000 | 907
| 6 | Float | LS | P | 1 | 1 | 1800 | 1 | 1800 | 1800 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 907
| 7 | Float | LS | P | 1 | 1 | 1800 | 1 | 1800 | 1800 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 907
| 8 | Float | LS | P | 1 | 1 | 1800 | 1 | 1800 | 1800 | 1800 | 0 | 0 | 1800 | 0 | 1800 | 907
| 9 | Accommodation | day | S | 1 | 1 | 28 | 125 | 3500 | 28 | 28 | 0 | 0 | 0 | 3500 | 3500 | 911
| 10 | Labour | hr | L | 1 | 1 | 150 | 51.9 | 7785 | 150 | 150 | 7785 | 0 | 0 | 0 | 7785 | 907
| 11 | Clean Up
| 12 | Bobcat | hr | P | 1 | 1 | 18 | 95 | 1710 | 18 | 18 | 0 | 0 | 1710 | 0 | 1710 | 910
| 13 | Tipper | hr | P | 1 | 1 | 18 | 90 | 1620 | 18 | 18 | 0 | 0 | 1620 | 0 | 1620 | 910
| 14 | Water Cart - Hire | hr | P | 1 | 1 | 18 | 95 | 1710 | 18 | 18 | 0 | 0 | 1710 | 0 | 1710 | 910
6 | Line No 4 Item No (b) | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | Item |  |  |  | 1 |  | 76266.8311 |  | 71 | 69266.8311 | 4000 | 3000 | 0 | 76266.8311
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 901
| 2 | T-Top Bollards | each | P | 1 | 1 | 50 | 60 | 3000 | 50 | 50 | 0 | 0 | 3000 | 0 | 3000 | 141
| 3 | Nightline | m | M | 1 | 1 | 2000 | 2 | 4000 |  |  | 0 | 4000 | 0 | 0 | 4000 | 141
| 4 | Labour | hr | L | 2 | 1 | 636.0003 | 51.9 | 66016.8311 | 1272.0006 | 636.0003 | 66016.8311 | 0 | 0 | 0 | 66016.8311 | 141
7 | Line No 5 Item No (c ) | Construction Setout by Contractor | Item |  |  |  | 1 |  | 23680 |  | 9 | 23680 | 0 | 0 | 0 | 23680
| 1 | Surveyor | hr | L | 1 | 1 | 24 | 185 | 4440 | 24 | 24 | 4440 | 0 | 0 | 0 | 4440 | 11
| 2 | Surveyor | hr | L | 1 | 1 | 24 | 185 | 4440 | 24 | 24 | 4440 | 0 | 0 | 0 | 4440 | 11
| 3 | Surveyor | hr | L | 1 | 1 | 80 | 185 | 14800 | 80 | 80 | 14800 | 0 | 0 | 0 | 14800 | 11
| Line No 6 Item No | [Note: Council to provide an initial control line, TBM's, prior to commencement of works; Contractor shall be responsible for all other setout to construct the works
8 | Line No 7 Item No (d ) | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | Item |  |  |  | 1 |  | 10400 |  | 1 | 0 | 0 | 0 | 10400 | 10400
| 1 | CAR | Item | S | 1 | 1 | 10400 | 1 | 10400 | 10400 | 10400 | 0 | 0 | 0 | 10400 | 10400 | 904
9 | Line No 8 Item No (e) | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | Item |  |  |  | 1 |  | 6800 |  | 2 | 3200 | 0 | 0 | 3600 | 6800
| 1 | WHSO | week | L | 1 | 1 | 1 | 3200 | 3200 | 1 | 1 | 3200 | 0 | 0 | 0 | 3200 | 901
| 2 | Service Locator | hr | S | 1 | 1 | 18 | 200 | 3600 | 18 | 18 | 0 | 0 | 0 | 3600 | 3600 | 15
10 | Line No 9 Item No (f) | As Constructed Survey Data to Council Requirements. | Item |  |  |  | 1 |  | 8880 |  | 6 | 8880 | 0 | 0 | 0 | 8880
| 1 | Surveyor | hr | L | 0 | 1 | 1 | 185 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11
| 2 | Surveyor | hr | L | 48 | 1 | 1 | 185 | 8880 | 48 | 1 | 8880 | 0 | 0 | 0 | 8880 | 11
| Line No 10 Item No (g) | Geotechnical Testing by NATA Registered laboratory
11 | Line No 11 Item No (i) | Geotechnical Testing by NATA Registered laboratory - Subgrade CBR tests ("soaked" 4 day, 4 point) (allow 3 confirmation tests on final subgrade for pavement design) | No |  |  |  | 3 |  | 2700 |  | 0 | 0 | 0 | 0 | 2700 | 2700
| 1 | Geotech Travel | km | S | 250 | 1 | 3 | 2 | 1500 | 750 | 3 | 0 | 0 | 0 | 1500 | 1500 | 13
| 2 | CBR Test | each | S | 1 | 1 | 3 | 400 | 1200 | 3 | 3 | 0 | 0 | 0 | 1200 | 1200 | 13
12 | Line No 12 Item No (ii) | Subgrade Compaction testing as specified | No |  |  |  | 28 |  | 5926.6667 |  | 0 | 0 | 0 | 0 | 5926.6667 | 5926.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 9.3333 | 2 | 4666.6667 | 2333.3333 | 9.3333 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 28 | 45 | 1260 | 28 | 28 | 0 | 0 | 0 | 1260 | 1260 | 13
13 | Line No 13 Item No (iii) | Sub-Base Compaction testing as specified - assume 1 layer | No |  |  |  | 28 |  | 5926.6667 |  | 0 | 0 | 0 | 0 | 5926.6667 | 5926.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 9.3333 | 2 | 4666.6667 | 2333.3333 | 9.3333 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 28 | 45 | 1260 | 28 | 28 | 0 | 0 | 0 | 1260 | 1260 | 13
14 | Line No 14 Item No (iv) | Base Compaction testing as specified | No |  |  |  | 28 |  | 5926.6667 |  | 0 | 0 | 0 | 0 | 5926.6667 | 5926.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 9.3333 | 2 | 4666.6667 | 2333.3333 | 9.3333 | 0 | 0 | 0 | 4666.6667 | 4666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 28 | 45 | 1260 | 28 | 28 | 0 | 0 | 0 | 1260 | 1260 | 13
15 | Line No 15 Item No (v) | Sub-Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results - assume 1 layer | No |  |  |  | 2 |  | 2580 |  | 0 | 0 | 0 | 0 | 2580 | 2580
| 1 | Geotech Travel | km | S | 250 | 1 | 2 | 2 | 1000 | 500 | 2 | 0 | 0 | 0 | 1000 | 1000 | 13
| 2 | Gravel Properties Testing | each | S | 1 | 1 | 2 | 390 | 780 | 2 | 2 | 0 | 0 | 0 | 780 | 780 | 13
| 3 | CBR Test | each | S | 1 | 1 | 2 | 400 | 800 | 2 | 2 | 0 | 0 | 0 | 800 | 800 | 13
16 | Line No 16 Item No (vi) | Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results. | No |  |  |  | 2 |  | 2580 |  | 0 | 0 | 0 | 0 | 2580 | 2580
| 1 | Geotech Travel | km | S | 250 | 1 | 2 | 2 | 1000 | 500 | 2 | 0 | 0 | 0 | 1000 | 1000 | 13
| 2 | Gravel Properties Testing | each | S | 1 | 1 | 2 | 390 | 780 | 2 | 2 | 0 | 0 | 0 | 780 | 780 | 13
| 3 | CBR Test | each | S | 1 | 1 | 2 | 400 | 800 | 2 | 2 | 0 | 0 | 0 | 800 | 800 | 13
17 | Line No 17 Item No (vii) | Culvert Trench Backfilling - Compaction Tests as ordered | No |  |  |  | 11 |  | 2328.3333 |  | 0 | 0 | 0 | 0 | 2328.3333 | 2328.3333
| 1 | Geotech Travel | km | S | 250 | 1 | 3.6667 | 2 | 1833.3333 | 916.6667 | 3.6667 | 0 | 0 | 0 | 1833.3333 | 1833.3333 | 13
| 2 | Field Density | each | S | 1 | 1 | 11 | 45 | 495 | 11 | 11 | 0 | 0 | 0 | 495 | 495 | 13
18 | Line No 19 Item No 2 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | Item |  |  |  | 1 |  | 12317.3333 |  | 3 | 1384 | 0 | 10933.3333 | 0 | 12317.3333
18.1 | 1 | Area to be stripped |  |  |  |  | 16000
18.2 | 2 | Excavator - 25T | hr | P | 1 | 60 | 1600 | 135 | 3600 | 26.6667 | 26.6667 | 0 | 0 | 3600 | 0 | 3600 | 21
| 3 | Tipper | hr | P | 2 | 60 | 1600 | 90 | 4800 | 53.3333 | 26.6667 | 0 | 0 | 4800 | 0 | 4800 | 21
| 4 | Labour | hr | L | 1 | 60 | 1600 | 51.9 | 1384 | 26.6667 | 26.6667 | 1384 | 0 | 0 | 0 | 1384 | 21
| 5 | Water Cart - Hire | hr | P | 1 | 60 | 1600 | 95 | 2533.3333 | 26.6667 | 26.6667 | 0 | 0 | 2533.3333 | 0 | 2533.3333 | 21
| Line No 21 Item No 3 | Earthworks - excavate and place as embankment as directed
19 | Line No 22 Item No (a) | Earthworks - excavate and place as embankment as directed - Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will be spoiled at IRC Tip | m3 |  |  |  | 2804 |  | 33689.752 |  | 7 | 3844.752 | 0 | 29845 | 0 | 33689.752
| 1 | Cut Embankment
19.1 | 2 | Excavator - 25T | hr | P | 1 | 50 | 2804 | 135 | 7570.8 | 56.08 | 56.08 | 0 | 0 | 7570.8 | 0 | 7570.8 | 53
| 3 | Tipper | hr | P | 3 | 50 | 2804 | 90 | 15141.6 | 168.24 | 56.08 | 0 | 0 | 15141.6 | 0 | 15141.6 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 50 | 2804 | 95 | 5327.6 | 56.08 | 56.08 | 0 | 0 | 5327.6 | 0 | 5327.6 | 53
| 5 | Labour | hr | L | 1 | 50 | 2804 | 51.9 | 2910.552 | 56.08 | 56.08 | 2910.552 | 0 | 0 | 0 | 2910.552 | 53
| 6 | Fill Where Required
| 7 | PF Roller | day | P | 1 | 225 | 225 | 365 | 365 | 1 | 1 | 0 | 0 | 365 | 0 | 365 | 53
| 8 | Grader | hr | P | 1 | 25 | 225 | 160 | 1440 | 9 | 9 | 0 | 0 | 1440 | 0 | 1440 | 53
| 9 | Labour | hr | L | 2 | 25 | 225 | 51.9 | 934.2 | 18 | 9 | 934.2 | 0 | 0 | 0 | 934.2 | 53
20 | Line No 23 Item No (c) | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 |  |  |  | 40 |  | 2514.8 |  | 1 | 622.8 | 0 | 1892 | 0 | 2514.8
20.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | 40 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 57
| 2 | Tipper | hr | P | 1 | 10 | 40 | 90 | 360 | 4 | 4 | 0 | 0 | 360 | 0 | 360 | 57
| 3 | PF Roller Wet - No OP | hr | P | 1 | 10 | 40 | 58 | 232 | 4 | 4 | 0 | 0 | 232 | 0 | 232 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 10 | 40 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 57
| 5 | Labour | hr | L | 3 | 10 | 40 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 57
| 6 | Bobcat | hr | P | 1 | 10 | 40 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 57
21 | Line No 24 Item No (d) | Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | m3 |  |  |  | 423 |  | 9338.148 |  | 2 | 878.148 | 0 | 8460 | 0 | 9338.148
| 1 | Cut Embankment
21.1 | 2 | Excavator - 25T | hr | P | 1 | 25 | 423 | 135 | 2284.2 | 16.92 | 16.92 | 0 | 0 | 2284.2 | 0 | 2284.2 | 53
| 3 | Tipper | hr | P | 3 | 25 | 423 | 90 | 4568.4 | 50.76 | 16.92 | 0 | 0 | 4568.4 | 0 | 4568.4 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 25 | 423 | 95 | 1607.4 | 16.92 | 16.92 | 0 | 0 | 1607.4 | 0 | 1607.4 | 53
| 5 | Labour | hr | L | 1 | 25 | 423 | 51.9 | 878.148 | 16.92 | 16.92 | 878.148 | 0 | 0 | 0 | 878.148 | 53
| Line No 26 Item No 4 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
22 | Line No 27 Item No (a) | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | m2 |  |  |  | 11271 |  | 32988.3385 |  | 7 | 8774.4735 | 0 | 24213.865 | 0 | 32988.3385
22.1 | 1 | Grader | hr | P | 1 | 200 | 11271 | 160 | 9016.8 | 56.355 | 56.355 | 0 | 0 | 9016.8 | 0 | 9016.8 | 61
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 11271 | 55 | 3099.525 | 56.355 | 56.355 | 0 | 0 | 3099.525 | 0 | 3099.525 | 61
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | 11271 | 58 | 3268.59 | 56.355 | 56.355 | 0 | 0 | 3268.59 | 0 | 3268.59 | 61
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 11271 | 95 | 5353.725 | 56.355 | 56.355 | 0 | 0 | 5353.725 | 0 | 5353.725 | 61
| 5 | Labour | hr | L | 3 | 200 | 11271 | 51.9 | 8774.4735 | 169.065 | 56.355 | 8774.4735 | 0 | 0 | 0 | 8774.4735 | 61
| 6 | Bobcat | hr | P | 1 | 600 | 11271 | 95 | 1784.575 | 18.785 | 18.785 | 0 | 0 | 1784.575 | 0 | 1784.575 | 61
| 7 | Tipper | hr | P | 1 | 600 | 11271 | 90 | 1690.65 | 18.785 | 18.785 | 0 | 0 | 1690.65 | 0 | 1690.65 | 61
| Line No 29 Item No 5 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results
23 | Line No 30 Item No (a) | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | m2 |  |  |  | 7375 |  | 15618.0152 |  | 3 | 4175.5909 | 0 | 11442.4242 | 0 | 15618.0152
23.1 | 1 | Grader | hr | P | 1 | 275 | 7375 | 160 | 4290.9091 | 26.8182 | 26.8182 | 0 | 0 | 4290.9091 | 0 | 4290.9091 | 63
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 275 | 7375 | 55 | 1475 | 26.8182 | 26.8182 | 0 | 0 | 1475 | 0 | 1475 | 63
| 3 | MW Roller | hr | P | 1 | 275 | 7375 | 55 | 1475 | 26.8182 | 26.8182 | 0 | 0 | 1475 | 0 | 1475 | 63
| 4 | Water Cart - Hire | hr | P | 1 | 275 | 7375 | 95 | 2547.7273 | 26.8182 | 26.8182 | 0 | 0 | 2547.7273 | 0 | 2547.7273 | 63
| 5 | Labour | hr | L | 3 | 275 | 7375 | 51.9 | 4175.5909 | 80.4545 | 26.8182 | 4175.5909 | 0 | 0 | 0 | 4175.5909 | 63
| 6 | Bobcat | hr | P | 1 | 825 | 7375 | 95 | 849.2424 | 8.9394 | 8.9394 | 0 | 0 | 849.2424 | 0 | 849.2424 | 63
| 7 | Tipper | hr | P | 1 | 825 | 7375 | 90 | 804.5455 | 8.9394 | 8.9394 | 0 | 0 | 804.5455 | 0 | 804.5455 | 63
| Line No 31 Item No 6 | Gravel Pavement
| Line No 32 Item No | In Place complete, including supply, spreading, watering, rolling and trimming:-
| Line No 33 Item No | (a) Bypass Road Widening Ch 18 to Ch 2801
24 | Line No 34 Item No (i) | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - QT Type 2.1 @ 150mm deep x widening area | m3 |  |  |  | 1231 |  | 131510.4074 |  | 5 | 6756.2512 | 97633.6875 | 27120.4687 | 0 | 131510.4074
| 1 | CBR80 | tonne | M | 1 | 1 | 2892.85 | 33.75 | 97633.6875 |  |  | 0 | 97633.6875 | 0 | 0 | 97633.6875 | QM2.3
24.1 | 2 | Grader | hr | P | 1 | 66.6667 | 2892.85 | 160 | 6942.84 | 43.3927 | 43.3927 | 0 | 0 | 6942.84 | 0 | 6942.84 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.6667 | 2892.85 | 55 | 2386.6012 | 43.3927 | 43.3927 | 0 | 0 | 2386.6012 | 0 | 2386.6012 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.6667 | 2892.85 | 95 | 4122.3112 | 43.3927 | 43.3927 | 0 | 0 | 4122.3112 | 0 | 4122.3112 | 62
| 5 | Labour | hr | L | 3 | 66.6667 | 2892.85 | 51.9 | 6756.2512 | 130.1782 | 43.3927 | 6756.2512 | 0 | 0 | 0 | 6756.2512 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.6667 | 2892.85 | 135 | 5858.0212 | 43.3927 | 43.3927 | 0 | 0 | 5858.0212 | 0 | 5858.0212 | 62
| 8 | Tipper | hr | P | 2 | 66.6667 | 2892.85 | 90 | 7810.695 | 86.7855 | 43.3927 | 0 | 0 | 7810.695 | 0 | 7810.695 | 62
25 | Line No 35 Item No (ii) | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 -Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | m3 |  |  |  | 2032 |  | 211113.9796 |  | 8 | 11152.4796 | 155194 | 44767.5 | 0 | 211113.9796
| 1 | CBR45 | tonne | M | 1 | 1 | 4775.2 | 32.5 | 155194 |  |  | 0 | 155194 | 0 | 0 | 155194 | QM2.3
25.1 | 2 | Grader | hr | P | 1 | 66.6667 | 4775.2 | 160 | 11460.48 | 71.628 | 71.628 | 0 | 0 | 11460.48 | 0 | 11460.48 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.6667 | 4775.2 | 55 | 3939.54 | 71.628 | 71.628 | 0 | 0 | 3939.54 | 0 | 3939.54 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.6667 | 4775.2 | 95 | 6804.66 | 71.628 | 71.628 | 0 | 0 | 6804.66 | 0 | 6804.66 | 62
| 5 | Labour | hr | L | 3 | 66.6667 | 4775.2 | 51.9 | 11152.4796 | 214.884 | 71.628 | 11152.4796 | 0 | 0 | 0 | 11152.4796 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.6667 | 4775.2 | 135 | 9669.78 | 71.628 | 71.628 | 0 | 0 | 9669.78 | 0 | 9669.78 | 62
| 8 | Tipper | hr | P | 2 | 66.6667 | 4775.2 | 90 | 12893.04 | 143.256 | 71.628 | 0 | 0 | 12893.04 | 0 | 12893.04 | 62
26 | Line No 36 Item No (iii) | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of length - Only if ordered by the Superintendent | m3 |  |  |  | 423 |  | 48873.2138 |  | 3 | 3482.4057 | 31411.98 | 13978.8281 | 0 | 48873.2138
| 1 | CBR15 | tonne | M | 1 | 1 | 994.05 | 31.6 | 31411.98 |  |  | 0 | 31411.98 | 0 | 0 | 31411.98 | QM2.3
26.1 | 2 | Grader | hr | P | 1 | 44.4444 | 994.05 | 160 | 3578.58 | 22.3661 | 22.3661 | 0 | 0 | 3578.58 | 0 | 3578.58 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 44.4444 | 994.05 | 55 | 1230.1369 | 22.3661 | 22.3661 | 0 | 0 | 1230.1369 | 0 | 1230.1369 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 44.4444 | 994.05 | 95 | 2124.7819 | 22.3661 | 22.3661 | 0 | 0 | 2124.7819 | 0 | 2124.7819 | 62
| 5 | Labour | hr | L | 3 | 44.4444 | 994.05 | 51.9 | 3482.4057 | 67.0984 | 22.3661 | 3482.4057 | 0 | 0 | 0 | 3482.4057 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 44.4444 | 994.05 | 135 | 3019.4269 | 22.3661 | 22.3661 | 0 | 0 | 3019.4269 | 0 | 3019.4269 | 62
| 8 | Tipper | hr | P | 2 | 44.4444 | 994.05 | 90 | 4025.9025 | 44.7323 | 22.3661 | 0 | 0 | 4025.9025 | 0 | 4025.9025 | 62
| Line No 38 Item No 7 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED
27 | Line No 39 Item No (a) | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | m2 |  |  |  | 140 |  | 754.6 |  | 1 | 0 | 0 | 0 | 754.6 | 754.6
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 154 | 4.9 | 754.6 | 154 | 154 | 0 | 0 | 0 | 754.6 | 754.6 | 64
28 | Line No 40 Item No (b) | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | m2 |  |  |  | 371 |  | 1999.69 |  | 1 | 0 | 0 | 0 | 1999.69 | 1999.69
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 408.1 | 4.9 | 1999.69 | 408.1 | 408.1 | 0 | 0 | 0 | 1999.69 | 1999.69 | 64
29 | Line No 41 Item No (c) | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | m2 |  |  |  | 37 |  | 199.43 |  | 1 | 0 | 0 | 0 | 199.43 | 199.43
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 40.7 | 4.9 | 199.43 | 40.7 | 40.7 | 0 | 0 | 0 | 199.43 | 199.43 | 64
| Line No 43 Item No 8 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED
30 | Line No 44 Item No (a) | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | m2 |  |  |  | 812 |  | 5198.424 |  | 1 | 0 | 0 | 0 | 5198.424 | 5198.424
| 1 | Primer Seal - 16mm | m² | S | 1 | 1 | 893.2 | 5.82 | 5198.424 | 893.2 | 893.2 | 0 | 0 | 0 | 5198.424 | 5198.424 | 64
31 | Line No 45 Item No (b) | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | m2 |  |  |  | 3549 |  | 22720.698 |  | 1 | 0 | 0 | 0 | 22720.698 | 22720.698
| 1 | Primer Seal - 16mm | m² | S | 1 | 1 | 3903.9 | 5.82 | 22720.698 | 3903.9 | 3903.9 | 0 | 0 | 0 | 22720.698 | 22720.698 | 64
| Line No 47 Item No 9 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED
32 | Line No 48 Item No (a) | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | m2 |  |  |  | 3444 |  | 13676.124 |  | 1 | 0 | 0 | 0 | 13676.124 | 13676.124
| 1 | Seal Visit One | m² | S | 1 | 1 | 3788.4 | 3.61 | 13676.124 | 3788.4 | 3788.4 | 0 | 0 | 0 | 13676.124 | 13676.124 | 64
33 | Line No 49 Item No (b) | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 650 to Ch 2801 | m2 |  |  |  | 15057 |  | 59791.347 |  | 2 | 0 | 0 | 0 | 59791.347 | 59791.347
| 1 | Seal Visit One | m² | S | 1 | 1 | 16562.7 | 3.61 | 59791.347 | 16562.7 | 16562.7 | 0 | 0 | 0 | 59791.347 | 59791.347 | 64
| Line No 51 Item No 10 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins
34 | Line No 52 Item No (a) | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | m2 |  |  |  | 1260 |  | 34546.8375 |  | 1 | 0 | 0 | 0 | 34546.8375 | 34546.8375
| 1 | 35mm AC | tonne | S | 1 | 1 | 110.25 | 313.35 | 34546.8375 | 110.25 | 110.25 | 0 | 0 | 0 | 34546.8375 | 34546.8375 | 65
Line No 53 Item No
| Line No 54 Item No 11 | Access Ch 826 RHS (Dysart Horse Performance Association)
35 | Line No 55 Item No (a) | Access Ch 826 RHS (Dysart Horse Performance Association) - Provide smooth transition between existing access and new shoulder (no pipe required; reinstate to similar) | Item |  |  |  | 1 |  | 723.8 |  | 1 | 103.8 | 0 | 620 | 0 | 723.8
35.1 | 1 | Grader | hr | P | 1 | 0.5 | 1 | 160 | 320 | 2 | 2 | 0 | 0 | 320 | 0 | 320 | 62
| 2 | Water Cart - Hire | hr | P | 1 | 0.5 | 1 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 0.5 | 1 | 55 | 110 | 2 | 2 | 0 | 0 | 110 | 0 | 110 | 62
| 4 | Labour | hr | L | 1 | 0.5 | 1 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 62
| Line No 57 Item No 12 | Access Ch 1642 RHS (Cemetery Carpark Access)
36 | Line No 58 Item No (a) | Access Ch 1642 RHS (Cemetery Carpark Access) - Reinstate sealed driveway between New shoulder and Carpark Access (no works on culvert required); neat smooth join. | Item |  |  |  | 1 |  | 1014.8 |  | 1 | 103.8 | 0 | 620 | 291 | 1014.8
36.1 | 1 | Grader | hr | P | 1 | 0.5 | 1 | 160 | 320 | 2 | 2 | 0 | 0 | 320 | 0 | 320 | 62
| 2 | Water Cart - Hire | hr | P | 1 | 0.5 | 1 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 0.5 | 1 | 55 | 110 | 2 | 2 | 0 | 0 | 110 | 0 | 110 | 62
| 4 | Labour | hr | L | 1 | 0.5 | 1 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 62
| 5 | Primer Seal - 16mm | m² | S | 1 | 1 | 50 | 5.82 | 291 | 50 | 50 | 0 | 0 | 0 | 291 | 291 | 64
| Line No 60 Item No 13 | Access Ch 1660 RHS (Cemetery Access)
37 | Line No 61 Item No (a) | Access Ch 1660 RHS (Cemetery Access) - Reinstate sealed driveway between New shoulder and Cemetery Access (no works on culvert required); neat smooth join. | Item |  |  |  | 1 |  | 1014.8 |  | 1 | 103.8 | 0 | 620 | 291 | 1014.8
37.1 | 1 | Grader | hr | P | 1 | 0.5 | 1 | 160 | 320 | 2 | 2 | 0 | 0 | 320 | 0 | 320 | 62
| 2 | Water Cart - Hire | hr | P | 1 | 0.5 | 1 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 0.5 | 1 | 55 | 110 | 2 | 2 | 0 | 0 | 110 | 0 | 110 | 62
| 4 | Labour | hr | L | 1 | 0.5 | 1 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 62
| 5 | Primer Seal - 16mm | m² | S | 1 | 1 | 50 | 5.82 | 291 | 50 | 50 | 0 | 0 | 0 | 291 | 291 | 64
| Line No 63 Item No 14 | Soil Management Measures inclusive of:
38 | Line No 64 Item No (a) | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | m2 |  |  |  | 27830 |  | 21352.5675 |  | 8 | 3610.9425 | 0 | 17741.625 | 0 | 21352.5675
38.1 | 1 | Grader | hr | P | 1 | 400 | 27830 | 160 | 11132 | 69.575 | 69.575 | 0 | 0 | 11132 | 0 | 11132 | 59
| 2 | Water Cart - Hire | hr | P | 1 | 400 | 27830 | 95 | 6609.625 | 69.575 | 69.575 | 0 | 0 | 6609.625 | 0 | 6609.625 | 59
| 3 | Labour | hr | L | 1 | 400 | 27830 | 51.9 | 3610.9425 | 69.575 | 69.575 | 3610.9425 | 0 | 0 | 0 | 3610.9425 | 59
39 | Line No 65 Item No (b) | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters & drains) | m2 |  |  |  | 27830 |  | 27731.05 |  | 4 | 0 | 0 | 1710 | 26021.05 | 27731.05
| 1 | Hydromulch Subbie | m² | S | 1 | 1 | 30613 | 0.85 | 26021.05 | 30613 | 30613 | 0 | 0 | 0 | 26021.05 | 26021.05 | 121
39.1 | 2 | Water Cart - Hire | hr | P | 1 | 1700.7222 | 30613 | 95 | 1710 | 18 | 18 | 0 | 0 | 1710 | 0 | 1710 | 121
40 | Line No 66 Item No (c) | Soil Management Measures inclusive of: Rock check dams as directed | No |  |  |  | 40 |  | 10842.6667 |  | 2 | 2076 | 6300 | 2466.6667 | 0 | 10842.6667
| 1 | Gabion Rock | tonne | M | 1 | 1 | 180 | 35 | 6300 |  |  | 0 | 6300 | 0 | 0 | 6300 | QMR
40.1 | 2 | Bobcat | hr | P | 1 | 3 | 40 | 95 | 1266.6667 | 13.3333 | 13.3333 | 0 | 0 | 1266.6667 | 0 | 1266.6667 | 151
| 3 | Labour | hr | L | 3 | 3 | 40 | 51.9 | 2076 | 40 | 13.3333 | 2076 | 0 | 0 | 0 | 2076 | 151
| 4 | Tipper | hr | P | 1 | 3 | 40 | 90 | 1200 | 13.3333 | 13.3333 | 0 | 0 | 1200 | 0 | 1200 | 151
| Line No 67 Item No 15 | Road Furniture
41 | Line No 68 Item No (a) | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | No |  |  |  | 40 |  | 2000 |  | 0 | 0 | 2000 | 0 | 0 | 2000
| 1 | Guide Post | each | M | 1 | 1 | 40 | 50 | 2000 |  |  | 0 | 2000 | 0 | 0 | 2000 | 67
42 | Line No 69 Item No (b) | Supply and Install Floodway Depth markers (G9-22-1A) | No |  |  |  | 2 |  | 957.6 |  | 1 | 207.6 | 560 | 190 | 0 | 957.6
| 1 | Signs Complete | each | M | 1 | 1 | 4 | 140 | 560 |  |  | 0 | 560 | 0 | 0 | 560 | 67
42.1 | 2 | Bobcat | hr | P | 1 | 1 | 2 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 67
| 3 | Labour | hr | L | 2 | 1 | 2 | 51.9 | 207.6 | 4 | 2 | 207.6 | 0 | 0 | 0 | 207.6 | 67
43 | Line No 70 Item No (c) | Remove Signs for widening and reinstate | Item |  |  |  | 1 |  | 338.8 |  | 1 | 103.8 | 140 | 95 | 0 | 338.8
| 1 | Signs Complete | each | M | 1 | 1 | 1 | 140 | 140 |  |  | 0 | 140 | 0 | 0 | 140 | 67
43.1 | 2 | Bobcat | hr | P | 1 | 1 | 1 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 67
| 3 | Labour | hr | L | 2 | 1 | 1 | 51.9 | 103.8 | 2 | 1 | 103.8 | 0 | 0 | 0 | 103.8 | 67
44 | Line No 71 Item No (d) | Provisional Item Guardrail as per Note 5 on plan 842-R02 allow (3 lengths of Armoc ® 'W' Beam type XR & standard posts rammed into the ground with bull nose terminal ends) Only if ordered by Superintendent | No |  |  |  | 4 |  | 28000 |  | 4 | 0 | 0 | 0 | 28000 | 28000
| 1 | Guard Rail | m | S | 1 | 1 | 4 | 7000 | 28000 | 4 | 4 | 0 | 0 | 0 | 28000 | 28000 | 67
| Line No 77 Item No | Schedule B - Drainage Dysart Bypass Rd
| Line No 78 Item No 1 | Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
45 | Line No 79 Item No (a) | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfill. | m |  |  |  | 1.22 |  | 1297.351 |  | 1 | 363.3 | 219.051 | 715 | 0 | 1297.351
| 1 | Purchase Materials
| 2 | 375 RCP | m | M | 1 | 1 | 2.44 | 83.4 | 203.496 |  |  | 0 | 203.496 | 0 | 0 | 203.496 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 0.61 | 25.5 | 15.555 |  |  | 0 | 15.555 | 0 | 0 | 15.555 | QMS | y
| 4 | Remove Existing Headwall
45.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 1.22 | 1.22 | 51.9 | 51.9 | 1 | 1 | 51.9 | 0 | 0 | 0 | 51.9 | 81
| 8 | Place Bedding Sand
45.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 1.22 | 95 | 47.5 | 0.5 | 0.5 | 0 | 0 | 47.5 | 0 | 47.5 | 81
| 11 | Install Pipe
45.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 13 | Labour | hr | L | 1 | 0.61 | 1.22 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 81
| 14 | Backfill & Compact
45.4 | 15 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 1.22 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 1.22 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
46 | Line No 80 Item No (b) | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | No |  |  |  | 1 |  | 1257.8 |  | 1 | 622.8 | 365 | 270 | 0 | 1257.8
| 1 | HW - 375 | each | M | 1 | 1 | 1 | 365 | 365 |  |  | 0 | 365 | 0 | 0 | 365 | SWC
46.1 | 2 | Excavator - 25T | hr | P | 1 | 0.5 | 1 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 3 | Labour | hr | L | 3 | 0.25 | 1 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 81
| Line No 82 Item No 2 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
47 | Line No 83 Item No (a) | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 1344.931 |  | 1 | 363.3 | 266.631 | 715 | 0 | 1344.931
| 1 | Purchase Materials
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 2.44 | 102.9 | 251.076 |  |  | 0 | 251.076 | 0 | 0 | 251.076 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 0.61 | 25.5 | 15.555 |  |  | 0 | 15.555 | 0 | 0 | 15.555 | QMS | y
| 4 | Remove Existing Headwall
47.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 1.22 | 1.22 | 51.9 | 51.9 | 1 | 1 | 51.9 | 0 | 0 | 0 | 51.9 | 81
| 8 | Place Bedding Sand
47.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 1.22 | 95 | 47.5 | 0.5 | 0.5 | 0 | 0 | 47.5 | 0 | 47.5 | 81
| 11 | Install Pipe
47.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 13 | Labour | hr | L | 1 | 0.61 | 1.22 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 81
| 14 | Backfill & Compact
47.4 | 15 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 1.22 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 1.22 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
48 | Line No 84 Item No (b) | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 1 |  | 2338.85 |  | 1 | 1245.6 | 553.25 | 540 | 0 | 2338.85
| 1 | N40 | m³ | M | 1 | 1 | 1.21 | 325 | 393.25 |  |  | 0 | 393.25 | 0 | 0 | 393.25 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 6 | 10 | 60 |  |  | 0 | 60 | 0 | 0 | 60 | 72
| 3 | Form Boards | m | M | 1 | 1 | 20 | 5 | 100 |  |  | 0 | 100 | 0 | 0 | 100 | 72
48.1 | 4 | Labour | hr | L | 3 | 0.125 | 1 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 5 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
| Line No 86 Item No 3 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359
49 | Line No 87 Item No (a) | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 2.44 |  | 20898.8887 |  | 4 | 2135.685 | 14141.4538 | 2626.75 | 1994.9999 | 20898.8887
| 1 | Culvert to be installed in halves. Traffic control with loghts outside working hours.
| 2 | Excavate Culvert
49.1 | 3 | Excavator - 25T | hr | P | 1 | 0.61 | 2.44 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 81
| 4 | Tipper | hr | P | 1 | 0.61 | 2.44 | 90 | 360 | 4 | 4 | 0 | 0 | 360 | 0 | 360 | 81
| 5 | Labour | hr | L | 2 | 0.61 | 2.44 | 51.9 | 415.2 | 8 | 4 | 415.2 | 0 | 0 | 0 | 415.2 | 81
| 6 | Bedding
| 7 | Sand | tonne | M | 1 | 1 | 4.4335 | 28 | 124.1374 |  |  | 0 | 124.1374 | 0 | 0 | 124.1374 | QMS | y
49.2 | 8 | Excavator - 25T | hr | P | 1 | 1.22 | 2.44 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 9 | Labour | hr | L | 3 | 0.488 | 2.44 | 51.9 | 778.5 | 15 | 5 | 778.5 | 0 | 0 | 0 | 778.5 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 0.488 | 2.44 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 81
| 11 | Pour Base
| 12 | Steel | tonne | M | 1 | 1 | 0.6 | 2200 | 1320 |  |  | 0 | 1320 | 0 | 0 | 1320 | RSM
| 13 | Steel Fixing | tonne | S | 1 | 1 | 0.6 | 2200 | 1320 | 0.6 | 0.6 | 0 | 0 | 0 | 1320 | 1320 | 72
| 14 | Concrete Subbie | m² | S | 1 | 1 | 15 | 45 | 674.9999 | 15 | 15 | 0 | 0 | 0 | 674.9999 | 674.9999 | 72
| 15 | N40 | m³ | M | 1 | 1 | 21 | 325 | 6824.9989 |  |  | 0 | 6824.9989 | 0 | 0 | 6824.9989 | C40
| 16 | Place Culverts
| 17 | RCBC - 1800 x 600 | m | M | 1 | 1 | 6.1 | 935 | 5703.5 |  |  | 0 | 5703.5 | 0 | 0 | 5703.5 | SWC
| 18 | Excavator - 25T | hr | P | 1 | 2 | 6.1 | 135 | 411.75 | 3.05 | 3.05 | 0 | 0 | 411.75 | 0 | 411.75 | 81
| 19 | Labour | hr | L | 3 | 2 | 6.1 | 51.9 | 474.885 | 9.15 | 3.05 | 474.885 | 0 | 0 | 0 | 474.885 | 81
| 20 | Backfill
| 21 | CBR80 | tonne | M | 1 | 1 | 5.002 | 33.75 | 168.8175 |  |  | 0 | 168.8175 | 0 | 0 | 168.8175 | QM2.3
| 22 | Bobcat | hr | P | 1 | 1.6673 | 5.002 | 95 | 285 | 3 | 3 | 0 | 0 | 285 | 0 | 285 | 72
| 23 | Labour | hr | L | 3 | 1.6673 | 5.002 | 51.9 | 467.1 | 9 | 3 | 467.1 | 0 | 0 | 0 | 467.1 | 72
| 24 | Water Cart - Hire | hr | P | 1 | 1.6673 | 5.002 | 95 | 285 | 3 | 3 | 0 | 0 | 285 | 0 | 285 | 72
50 | Line No 88 Item No (b) | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | m |  |  |  | 12.2 |  | 64286.6382 |  | 2 | 5892.0212 | 42394.8625 | 6808.6923 | 9191.0622 | 64286.6382
| 1 | Culvert to be installed in halves. Traffic control with loghts outside working hours.
| 2 | Excavate Culvert
50.1 | 3 | Excavator - 25T | hr | P | 1 | 1.525 | 12.2 | 135 | 1080 | 8 | 8 | 0 | 0 | 1080 | 0 | 1080 | 81
| 4 | Tipper | hr | P | 1 | 1.525 | 12.2 | 90 | 720 | 8 | 8 | 0 | 0 | 720 | 0 | 720 | 81
| 5 | Labour | hr | L | 2 | 1.525 | 12.2 | 51.9 | 830.4 | 16 | 8 | 830.4 | 0 | 0 | 0 | 830.4 | 81
| 6 | Bedding
| 7 | Sand | tonne | M | 1 | 1 | 32.9058 | 28 | 921.3635 |  |  | 0 | 921.3635 | 0 | 0 | 921.3635 | QMS | y
50.2 | 8 | Excavator - 25T | hr | P | 1 | 3.0499 | 12.2 | 135 | 540.01 | 4.0001 | 4.0001 | 0 | 0 | 540.01 | 0 | 540.01 | 81
| 9 | Labour | hr | L | 3 | 1.3555 | 12.2 | 51.9 | 1401.326 | 27.0005 | 9.0002 | 1401.326 | 0 | 0 | 0 | 1401.326 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 1.3555 | 12.2 | 95 | 855.0158 | 9.0002 | 9.0002 | 0 | 0 | 855.0158 | 0 | 855.0158 | 81
| 11 | Pour Base
| 12 | Steel | tonne | M | 1 | 1 | 2.03 | 2200 | 4466.0388 |  |  | 0 | 4466.0388 | 0 | 0 | 4466.0388 | RSM
| 13 | Steel Fixing | tonne | S | 1 | 1 | 2.03 | 2200 | 4466.0388 | 2.03 | 2.03 | 0 | 0 | 0 | 4466.0388 | 4466.0388 | 72
| 14 | Concrete Subbie | m² | S | 1 | 1 | 105.0005 | 45 | 4725.0234 | 10.5001 | 10.5001 | 0 | 0 | 0 | 4725.0234 | 4725.0234 | 72
| 15 | N40 | m³ | M | 1 | 1 | 21.0001 | 325 | 6825.0338 |  |  | 0 | 6825.0338 | 0 | 0 | 6825.0338 | C40
| 16 | Place Culverts
| 17 | RCBC - 1800 x 600 | m | M | 1 | 1 | 31.0173 | 935 | 29001.1568 |  |  | 0 | 29001.1568 | 0 | 0 | 29001.1568 | SWC
| 18 | Excavator - 25T | hr | P | 1 | 2 | 31.0173 | 135 | 2093.6664 | 15.5086 | 15.5086 | 0 | 0 | 2093.6664 | 0 | 2093.6664 | 81
| 19 | Labour | hr | L | 3 | 2 | 31.0173 | 51.9 | 2414.6952 | 46.5259 | 15.5086 | 2414.6952 | 0 | 0 | 0 | 2414.6952 | 81
| 20 | Backfill
| 21 | CBR80 | tonne | M | 1 | 1 | 35.0006 | 33.75 | 1181.2696 |  |  | 0 | 1181.2696 | 0 | 0 | 1181.2696 | QM2.3
| 22 | Bobcat | hr | P | 1 | 4.3751 | 35.0006 | 95 | 760 | 8 | 8 | 0 | 0 | 760 | 0 | 760 | 72
| 23 | Labour | hr | L | 3 | 4.3751 | 35.0006 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 24 | Water Cart - Hire | hr | P | 1 | 4.3751 | 35.0006 | 95 | 760 | 8 | 8 | 0 | 0 | 760 | 0 | 760 | 72
51 | Line No 89 Item No (c) | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | No |  |  |  | 2 |  | 2161.4 |  | 1 | 311.4 | 1675 | 175 | 0 | 2161.4
| 1 | N40 | m³ | M | 1 | 1 | 3 | 325 | 975 |  |  | 0 | 975 | 0 | 0 | 975 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 20 | 10 | 200 |  |  | 0 | 200 | 0 | 0 | 200 | 72
| 3 | Form Boards | m | M | 1 | 1 | 100 | 5 | 500 |  |  | 0 | 500 | 0 | 0 | 500 | 72
51.1 | 4 | Labour | hr | L | 3 | 1 | 2 | 51.9 | 311.4 | 6 | 2 | 311.4 | 0 | 0 | 0 | 311.4 | 72
| 5 | Concrete Pump | hr | P | 1 | 4 | 4 | 175 | 175 | 1 | 1 | 0 | 0 | 175 | 0 | 175 | 72
52 | Line No 90 Item No (d) | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | Item |  |  |  | 1 |  | 1661.4 |  | 1 | 311.4 | 0 | 1350 | 0 | 1661.4
52.1 | 1 | Excavator - 25T | hr | P | 1 | 0.16667 | 1 | 135 | 810 | 6 | 6 | 0 | 0 | 810 | 0 | 810 | 53
| 2 | Tipper | hr | P | 1 | 0.16667 | 1 | 90 | 540 | 6 | 6 | 0 | 0 | 540 | 0 | 540 | 53
| 3 | Labour | hr | L | 1 | 0.16667 | 1 | 51.9 | 311.4 | 6 | 6 | 311.4 | 0 | 0 | 0 | 311.4 | 53
53 | Line No 91 Item No (e) | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | Item |  |  |  | 1 |  | 3372.6 |  | 1 | 207.6 | 2625 | 540 | 0 | 3372.6
| 1 | Gabion Rock | tonne | M | 1 | 1 | 75 | 35 | 2625 |  |  | 0 | 2625 | 0 | 0 | 2625 | QMR
53.1 | 2 | Excavator - 25T | hr | P | 1 | 18.75 | 75 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 81
| 3 | Labour | hr | L | 1 | 18.75 | 75 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| Line No 93 Item No 4 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
54 | Line No 94 Item No (a) | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 2118.874 |  | 1 | 337.35 | 1066.524 | 715 | 0 | 2118.874
| 1 | Purchase Materials
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 9.76 | 102.9 | 1004.304 |  |  | 0 | 1004.304 | 0 | 0 | 1004.304 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 2.44 | 25.5 | 62.22 |  |  | 0 | 62.22 | 0 | 0 | 62.22 | QMS | y
| 4 | Remove Existing Headwall
54.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 2.44 | 1.22 | 51.9 | 25.95 | 0.5 | 0.5 | 25.95 | 0 | 0 | 0 | 25.95 | 81
| 8 | Place Bedding Sand
54.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 1.22 | 95 | 47.5 | 0.5 | 0.5 | 0 | 0 | 47.5 | 0 | 47.5 | 81
| 11 | Install Pipe
54.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 13 | Labour | hr | L | 1 | 0.61 | 1.22 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 81
| 14 | Backfill & Compact
54.4 | 15 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 1.22 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 1.22 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
55 | Line No 95 Item No (b) | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 1 |  | 2338.85 |  | 1 | 1245.6 | 553.25 | 540 | 0 | 2338.85
| 1 | N40 | m³ | M | 1 | 1 | 1.21 | 325 | 393.25 |  |  | 0 | 393.25 | 0 | 0 | 393.25 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 6 | 10 | 60 |  |  | 0 | 60 | 0 | 0 | 60 | 72
| 3 | Form Boards | m | M | 1 | 1 | 20 | 5 | 100 |  |  | 0 | 100 | 0 | 0 | 100 | 72
55.1 | 4 | Labour | hr | L | 3 | 0.125 | 1 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 5 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
| Line No 97 Item No 5 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359
56 | Line No 98 Item No (a) | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 2078.392 |  | 1 | 296.868 | 1066.524 | 715 | 0 | 2078.392
| 1 | Purchase Materials
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 9.76 | 102.9 | 1004.304 |  |  | 0 | 1004.304 | 0 | 0 | 1004.304 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 2.44 | 25.5 | 62.22 |  |  | 0 | 62.22 | 0 | 0 | 62.22 | QMS | y
| 4 | Remove Existing Headwall
56.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 2.44 | 1.22 | 51.9 | 25.95 | 0.5 | 0.5 | 25.95 | 0 | 0 | 0 | 25.95 | 81
| 8 | Place Bedding Sand
56.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 1.22 | 95 | 47.5 | 0.5 | 0.5 | 0 | 0 | 47.5 | 0 | 47.5 | 81
| 11 | Install Pipe
56.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 13 | Labour | hr | L | 1 | 1 | 1.22 | 51.9 | 63.318 | 1.22 | 1.22 | 63.318 | 0 | 0 | 0 | 63.318 | 81
| 14 | Backfill & Compact
56.4 | 15 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 1.22 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 1.22 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
57 | Line No 99 Item No (b) | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 1 |  | 2338.85 |  | 1 | 1245.6 | 553.25 | 540 | 0 | 2338.85
| 1 | N40 | m³ | M | 1 | 1 | 1.21 | 325 | 393.25 |  |  | 0 | 393.25 | 0 | 0 | 393.25 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 6 | 10 | 60 |  |  | 0 | 60 | 0 | 0 | 60 | 72
| 3 | Form Boards | m | M | 1 | 1 | 20 | 5 | 100 |  |  | 0 | 100 | 0 | 0 | 100 | 72
57.1 | 4 | Labour | hr | L | 3 | 0.125 | 1 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 5 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
| Line No 101 Item No 6 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
58 | Line No 102 Item No (a) | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 1306.8446 |  | 1 | 337.35 | 254.4946 | 715 | 0 | 1306.8446
| 1 | Purchase Materials
| 2 | 375 RCP | m | M | 1 | 1 | 2.44 | 83.4 | 203.496 |  |  | 0 | 203.496 | 0 | 0 | 203.496 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 1.9999 | 25.5 | 50.9986 |  |  | 0 | 50.9986 | 0 | 0 | 50.9986 | QMS | y
| 4 | Remove Existing Headwall
58.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 2.44 | 1.22 | 51.9 | 25.95 | 0.5 | 0.5 | 25.95 | 0 | 0 | 0 | 25.95 | 81
| 8 | Place Bedding Sand
58.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 1.22 | 95 | 47.5 | 0.5 | 0.5 | 0 | 0 | 47.5 | 0 | 47.5 | 81
| 11 | Install Pipe
58.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 13 | Labour | hr | L | 1 | 0.61 | 1.22 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 81
| 14 | Backfill & Compact
58.4 | 15 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 1.22 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 1.22 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
59 | Line No 103 Item No (b) | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | No |  |  |  | 1 |  | 1257.8 |  | 1 | 622.8 | 365 | 270 | 0 | 1257.8
| 1 | HW - 375 | each | M | 1 | 1 | 1 | 365 | 365 |  |  | 0 | 365 | 0 | 0 | 365 | SWC
59.1 | 2 | Excavator - 25T | hr | P | 1 | 0.5 | 1 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 3 | Labour | hr | L | 3 | 0.25 | 1 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 81
| Line No 105 Item No 7 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
60 | Line No 106 Item No (a) | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 2147.6137 |  | 2 | 571.4113 | 562.9759 | 1013.2265 | 0 | 2147.6137
| 1 | Purchase Materials
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 4.4798 | 102.9 | 460.9755 |  |  | 0 | 460.9755 | 0 | 0 | 460.9755 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 4 | 25.5 | 102.0004 |  |  | 0 | 102.0004 | 0 | 0 | 102.0004 | QMS | y
| 4 | Remove Existing Headwall
60.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 1.22 | 1.22 | 51.9 | 51.9 | 1 | 1 | 51.9 | 0 | 0 | 0 | 51.9 | 81
| 8 | Place Bedding Sand
60.2 | 9 | Excavator - 25T | hr | P | 1 | 0.813 | 1.22 | 135 | 202.583 | 1.5006 | 1.5006 | 0 | 0 | 202.583 | 0 | 202.583 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.439 | 1.22 | 95 | 47.5195 | 0.50021 | 0.50021 | 0 | 0 | 47.5195 | 0 | 47.5195 | 81
| 11 | Install Pipe
60.3 | 12 | Excavator - 25T | hr | P | 1 | 0.61 | 1.22 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 13 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 14 | Backfill & Compact
60.4 | 15 | Labour | hr | L | 1 | 0.203 | 1.22 | 51.9 | 311.9113 | 6.0099 | 6.0099 | 311.9113 | 0 | 0 | 0 | 311.9113 | 81
| 16 | Bobcat | hr | P | 1 | 0.406 | 1.22 | 95 | 285.468 | 3.0049 | 3.0049 | 0 | 0 | 285.468 | 0 | 285.468 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.218 | 1.22 | 95 | 95.156 | 1.0016 | 1.0016 | 0 | 0 | 95.156 | 0 | 95.156 | 81
61 | Line No 107 Item No (b) | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 1 |  | 2147.975 |  | 1 | 1245.6 | 362.375 | 540 | 0 | 2147.975
| 1 | N40 | m³ | M | 1 | 1 | 0.715 | 325 | 232.375 |  |  | 0 | 232.375 | 0 | 0 | 232.375 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 3 | 10 | 30 |  |  | 0 | 30 | 0 | 0 | 30 | 72
| 3 | Form Boards | m | M | 1 | 1 | 20 | 5 | 100 |  |  | 0 | 100 | 0 | 0 | 100 | 72
61.1 | 4 | Labour | hr | L | 3 | 0.125 | 1 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 5 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
| Line No 109 Item No 8 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
62 | Line No 110 Item No (a) | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 3165.3298 |  | 2 | 726.8563 | 1548.6863 | 1260.3948 | 692.5353 | 3398.3134
| 1 | Purchase Materials
| 2 | 750 RCP | m | M | 1 | 1 | 4.4798 | 215.2 | 964.0616 |  |  | 0 | 964.0616 | 0 | 0 | 964.0616 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 8 | 25.5 | 204.0007 |  |  | 0 | 204.0007 | 0 | 0 | 204.0007 | QMS | y
| 4 | Remove Existing Headwall
62.1 | 5 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 6 | Tipper | hr | P | 1 | 1.22 | 1.22 | 90 | 90 | 1 | 1 | 0 | 0 | 90 | 0 | 90 | 81
| 7 | Labour | hr | L | 1 | 0.61 | 1.22 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 81
| 8 | Place Bedding Sand
62.2 | 9 | Excavator - 25T | hr | P | 1 | 0.813 | 1.22 | 135 | 202.583 | 1.5006 | 1.5006 | 0 | 0 | 202.583 | 0 | 202.583 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.439 | 1.22 | 95 | 47.5195 | 0.50021 | 0.50021 | 0 | 0 | 47.5195 | 0 | 47.5195 | 81
| 11 | Install Pipe
62.3 | 12 | Excavator - 25T | hr | P | 1 | 0.407 | 1.22 | 135 | 404.6683 | 2.9975 | 2.9975 | 0 | 0 | 404.6683 | 0 | 404.6683 | 81
| 13 | Labour | hr | L | 1 | 0.2035 | 1.22 | 51.9 | 311.145 | 5.9951 | 5.9951 | 311.145 | 0 | 0 | 0 | 311.145 | 81
| 14 | Backfill & Compact
62.4 | 15 | Labour | hr | L | 1 | 0.203 | 1.22 | 51.9 | 311.9113 | 6.0099 | 6.0099 | 311.9113 | 0 | 0 | 0 | 311.9113 | 81
| 16 | Bobcat | hr | P | 1 | 0.406 | 1.22 | 95 | 285.468 | 3.0049 | 3.0049 | 0 | 0 | 285.468 | 0 | 285.468 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.218 | 1.22 | 95 | 95.156 | 1.0016 | 1.0016 | 0 | 0 | 95.156 | 0 | 95.156 | 81
63 | Line No 111 Item No (b) | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 1 |  | 4019.9 |  | 1 | 1401.3 | 1204.8 | 1240 | 173.8 | 4019.9
63.1 | 1 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
| 2 | Sand | tonne | M | 1 | 1 | 2 | 28 | 56 |  |  | 0 | 56 | 0 | 0 | 56 | QMS | y
| 3 | N40 | m³ | M | 1 | 1 | 3 | 325 | 975 |  |  | 0 | 975 | 0 | 0 | 975 | C40
| 4 | Steel Fixing | tonne | S | 1 | 1 | 0.079 | 2200 | 173.8 | 0.079 | 0.079 | 0 | 0 | 0 | 173.8 | 173.8 | 72
| 5 | Steel | tonne | M | 1 | 1 | 0.079 | 2200 | 173.8 |  |  | 0 | 173.8 | 0 | 0 | 173.8 | RSM
63.2 | 6 | Labour | hr | L | 3 | 0.11111 | 1 | 51.9 | 1401.3 | 27 | 9 | 1401.3 | 0 | 0 | 0 | 1401.3 | 72
| 7 | Concrete Pump | hr | P | 1 | 0.25 | 1 | 175 | 700 | 4 | 4 | 0 | 0 | 700 | 0 | 700 | 72
| Line No 113 Item No 9 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
64 | Line No 114 Item No (a) | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 1332.7946 |  | 1 | 363.3 | 254.4946 | 715 | 0 | 1332.7946
| 1 | Purchase Materials
| 2 | 375 RCP | m | M | 1 | 1 | 2.44 | 83.4 | 203.496 |  |  | 0 | 203.496 | 0 | 0 | 203.496 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 1.9999 | 25.5 | 50.9986 |  |  | 0 | 50.9986 | 0 | 0 | 50.9986 | QMS | y
| 4 | Remove Existing Headwall
64.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 1.22 | 90 | 45 | 0.5 | 0.5 | 0 | 0 | 45 | 0 | 45 | 81
| 7 | Labour | hr | L | 1 | 1.22 | 1.22 | 51.9 | 51.9 | 1 | 1 | 51.9 | 0 | 0 | 0 | 51.9 | 81
| 8 | Place Bedding Sand
64.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 1.22 | 95 | 47.5 | 0.5 | 0.5 | 0 | 0 | 47.5 | 0 | 47.5 | 81
| 11 | Install Pipe
64.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 1.22 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 13 | Labour | hr | L | 1 | 0.61 | 1.22 | 51.9 | 103.8 | 2 | 2 | 103.8 | 0 | 0 | 0 | 103.8 | 81
| 14 | Backfill & Compact
64.4 | 15 | Labour | hr | L | 1 | 0.305 | 1.22 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 1.22 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 1.22 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
65 | Line No 115 Item No (b) | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | No |  |  |  | 1 |  | 892.8 |  | 1 | 622.8 | 0 | 270 | 0 | 892.8
| 1 | HW - 375 | each | M | 1 | 1 | 1 | 365 | 365 |  |  | 0 | 365 | 0 | 0 | 365 | SWC
65.1 | 2 | Excavator - 25T | hr | P | 1 | 0.5 | 1 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 72
| 3 | Labour | hr | L | 3 | 0.25 | 1 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 72
| Line No 117 Item No 10 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
66 | Line No 118 Item No (a) | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 1.22 |  | 1980.785 |  | 2 | 427.1293 | 475.6292 | 1078.0265 | 0 | 1980.785
| 1 | Purchase Materials
| 2 | 375 RCP | m | M | 1 | 1 | 4.48 | 83.4 | 373.6288 |  |  | 0 | 373.6288 | 0 | 0 | 373.6288 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 4 | 25.5 | 102.0004 |  |  | 0 | 102.0004 | 0 | 0 | 102.0004 | QMS | y
| 4 | Remove Existing Headwall
66.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 1.22 | 135 | 67.5 | 0.5 | 0.5 | 0 | 0 | 67.5 | 0 | 67.5 | 81
| 6 | Tipper | hr | P | 1 | 1 | 1.22 | 90 | 109.8 | 1.22 | 1.22 | 0 | 0 | 109.8 | 0 | 109.8 | 81
| 7 | Labour | hr | L | 1 | 1 | 1.22 | 51.9 | 63.318 | 1.22 | 1.22 | 63.318 | 0 | 0 | 0 | 63.318 | 81
| 8 | Place Bedding Sand
66.2 | 9 | Excavator - 25T | hr | P | 1 | 0.813 | 1.22 | 135 | 202.583 | 1.5006 | 1.5006 | 0 | 0 | 202.583 | 0 | 202.583 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.439 | 1.22 | 95 | 47.5195 | 0.50021 | 0.50021 | 0 | 0 | 47.5195 | 0 | 47.5195 | 81
| 11 | Install Pipe
66.3 | 12 | Excavator - 25T | hr | P | 1 | 0.61 | 1.22 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 13 | Labour | hr | L | 1 | 1.22 | 1.22 | 51.9 | 51.9 | 1 | 1 | 51.9 | 0 | 0 | 0 | 51.9 | 81
| 14 | Backfill & Compact
66.4 | 15 | Labour | hr | L | 1 | 0.203 | 1.22 | 51.9 | 311.9113 | 6.0099 | 6.0099 | 311.9113 | 0 | 0 | 0 | 311.9113 | 81
| 16 | Bobcat | hr | P | 1 | 0.406 | 1.22 | 95 | 285.468 | 3.0049 | 3.0049 | 0 | 0 | 285.468 | 0 | 285.468 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.218 | 1.22 | 95 | 95.156 | 1.0016 | 1.0016 | 0 | 0 | 95.156 | 0 | 95.156 | 81
265 | Line No 119 Item No (b) | 2 x 375 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 1 |  | 2147.975 |  | 1 | 1245.6 | 362.375 | 540 | 0 | 2147.975
| 1 | N40 | m³ | M | 1 | 1 | 0.715 | 325 | 232.375 |  |  | 0 | 232.375 | 0 | 0 | 232.375 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 3 | 10 | 30 |  |  | 0 | 30 | 0 | 0 | 30 | 72
| 3 | Form Boards | m | M | 1 | 1 | 20 | 5 | 100 |  |  | 0 | 100 | 0 | 0 | 100 | 72
265.1 | 4 | Labour | hr | L | 3 | 0.125 | 1 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 5 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
| Line No 121 Item No 11 | Ch 2780 New 1/600 x 300 RCBC,Installation to Main Roads Std Dwg 1359
266 | Line No 122 Item No (a) | Ch 2780 New 1/600 x 300 RCBC,Installation to Main Roads Std Dwg 1359 - Ch 2780 New 1/600 x 300 RCBC,Installation to Main Roads Std Dwg 1359 - 1/600 x 300 RCBC Complete in place, including excavate, sand, supply, lay and backfill. | m |  |  |  | 14.4 |  | 9926.3853 |  | 3 | 2491.2 | 4095.1853 | 3340 | 0 | 9926.3853
| 1 | Buy Materials
| 2 | RCBC - 600 x 300 | each | M | 1 | 1 | 12 | 247.5 | 2970 |  |  | 0 | 2970 | 0 | 0 | 2970 | SWC
| 3 | Sand | tonne | M | 1 | 1 | 4.435 | 28 | 124.18 |  |  | 0 | 124.18 | 0 | 0 | 124.18 | QMS | y
| 4 | N40 | m³ | M | 1 | 1 | 3.08 | 325 | 1001.0053 |  |  | 0 | 1001.0053 | 0 | 0 | 1001.0053 | C40
| 5 | Excavate
266.1 | 6 | Excavator - 25T | hr | P | 1 | 3.6 | 14.4 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 181
| 7 | Tipper | hr | P | 1 | 3.6 | 14.4 | 90 | 360 | 4 | 4 | 0 | 0 | 360 | 0 | 360 | 181
| 8 | Water Cart - Hire | hr | P | 1 | 3.6 | 14.4 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 181
| 9 | Labour | hr | L | 3 | 3.6 | 14.4 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 181
| 10 | Base
266.2 | 11 | Bobcat | hr | P | 1 | 1.8 | 14.4 | 95 | 760 | 8 | 8 | 0 | 0 | 760 | 0 | 760 | 181
| 12 | Labour | hr | L | 3 | 1.8 | 14.4 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 181
| 13 | Stand
266.3 | 14 | Excavator - 25T | hr | P | 1 | 3 | 12 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 181
| 15 | Labour | hr | L | 3 | 3 | 12 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 181
| 16 | Backfill
266.4 | 17 | Bobcat | hr | P | 1 | 3.6 | 14.4 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 181
| 18 | Water Cart - Hire | hr | P | 1 | 3.6 | 14.4 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 181
67 | Line No 123 Item No (b) | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 2 |  | 947.8 |  | 1 | 622.8 | 325 | 0 | 0 | 947.8
| 1 | N40 | m³ | M | 1 | 1 | 1 | 325 | 325 |  |  | 0 | 325 | 0 | 0 | 325 | C40
67.1 | 2 | Labour | hr | L | 3 | 0.5 | 2 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 72
68 | Line No 124 Item No (c) | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | Item |  |  |  | 1 |  | 1658.0838 |  | 1 | 310.7784 | 0 | 1347.3054 | 0 | 1658.0838
68.1 | 1 | Excavator - 25T | hr | P | 1 | 0.167 | 1 | 135 | 808.3832 | 5.988 | 5.988 | 0 | 0 | 808.3832 | 0 | 808.3832 | 53
| 2 | Tipper | hr | P | 1 | 0.167 | 1 | 90 | 538.9222 | 5.988 | 5.988 | 0 | 0 | 538.9222 | 0 | 538.9222 | 53
| 3 | Labour | hr | L | 1 | 0.167 | 1 | 51.9 | 310.7784 | 5.988 | 5.988 | 310.7784 | 0 | 0 | 0 | 310.7784 | 53
69 | Line No 125 Item No (d) | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock | Item |  |  |  | 1 |  | 2322.6 |  | 1 | 207.6 | 1575 | 540 | 0 | 2322.6
| 1 | Gabion Rock | tonne | M | 1 | 1 | 45 | 35 | 1575 |  |  | 0 | 1575 | 0 | 0 | 1575 | QMR
69.1 | 2 | Excavator - 25T | hr | P | 1 | 11.25 | 45 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 81
| 3 | Labour | hr | L | 1 | 11.25 | 45 | 51.9 | 207.6 | 4 | 4 | 207.6 | 0 | 0 | 0 | 207.6 | 81
70 | Line No 127 Item No 12 | Ch 2800 Take up and stack existing 1/600 x 300 RCBC and backfill to reinstate roadway. | Item |  |  |  | 1 |  | 4666.85 |  | 1 | 1245.6 | 1181.25 | 2240 | 0 | 4666.85
| 1 | Excavate & Stack
70.1 | 2 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 21
| 3 | Tipper | hr | P | 2 | 0.25 | 1 | 90 | 720 | 8 | 4 | 0 | 0 | 720 | 0 | 720 | 21
| 4 | Labour | hr | L | 3 | 0.25 | 1 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 21
| 5 | Backfill
| 6 | CBR80 | tonne | M | 1 | 1 | 35 | 33.75 | 1181.25 |  |  | 0 | 1181.25 | 0 | 0 | 1181.25 | QM2.3
70.2 | 7 | Bobcat | hr | P | 1 | 0.25 | 1 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 62
| 8 | Water Cart - Hire | hr | P | 1 | 0.25 | 1 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 62
| 9 | SD Roller - Wet (No Op) | hr | P | 1 | 0.25 | 1 | 55 | 220 | 4 | 4 | 0 | 0 | 220 | 0 | 220 | 62
| 10 | Labour | hr | L | 3 | 0.25 | 1 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 62
| Line No 131 Item No | Schedule C - Dysart Middlemount / Dysart Bypass Intersection
| Line No 132 Item No 1 | Preliminaries
| Line No 133 Item No (a) | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | Item |  |  |  | 1
| 1 | There is no cost estimate for this item
71 | Line No 134 Item No (b) | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | Item |  |  |  | 1 |  | 28325.0469 |  | 13 | 8774.987 | 0 | 0 | 19550.0599 | 28325.0469
| 1 | Project Engineer | week | L | 1 | 1 | 0.5 | 3250 | 1625 | 0.5 | 0.5 | 1625 | 0 | 0 | 0 | 1625 | 901
| 2 | Traffic Controller | hr | L | 1 | 1 | 109.9998 | 65 | 7149.987 | 109.9998 | 109.9998 | 7149.987 | 0 | 0 | 0 | 7149.987 | 141
| 3 | Traffic Control Crew | hr | S | 1 | 1 | 109.9998 | 130 | 14299.974 | 109.9998 | 109.9998 | 0 | 0 | 0 | 14299.974 | 14299.974 | 141
| 4 | Accommodation | day | S | 3 | 1 | 14.0002 | 125 | 5250.0859 | 42.0007 | 14.0002 | 0 | 0 | 0 | 5250.0859 | 5250.0859 | 911
72 | Line No 135 Item No (c ) | Construction Setout by Contractor | Item |  |  |  | 1 |  | 5180 |  | 4 | 5180 | 0 | 0 | 0 | 5180
| 1 | Surveyor | hr | L | 1 | 1 | 8 | 185 | 1480 | 8 | 8 | 1480 | 0 | 0 | 0 | 1480 | 11
| 2 | Surveyor | hr | L | 1 | 1 | 12 | 185 | 2220 | 12 | 12 | 2220 | 0 | 0 | 0 | 2220 | 11
| 3 | Surveyor | hr | L | 1 | 1 | 8 | 185 | 1480 | 8 | 8 | 1480 | 0 | 0 | 0 | 1480 | 11
| Line No 136 Item No | [Note: Council to provide an initial control line, TBM's, prior to commencement of works; Contractor shall be responsible for all other setout to construct the works
73 | Line No 137 Item No (d ) | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | Item |  |  |  | 1 |  | 2800 |  | 1 | 0 | 0 | 0 | 2800 | 2800
| 1 | CAR | Item | S | 1 | 1 | 2800 | 1 | 2800 | 2800 | 2800 | 0 | 0 | 0 | 2800 | 2800 | 904
74 | Line No 138 Item No (e) | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | Item |  |  |  | 1 |  | 3200 |  | 1 | 1600 | 0 | 0 | 1600 | 3200
| 1 | WHSO | week | L | 1 | 1 | 0.5 | 3200 | 1600 | 0.5 | 0.5 | 1600 | 0 | 0 | 0 | 1600 | 901
| 2 | Service Locator | hr | S | 1 | 1 | 8 | 200 | 1600 | 8 | 8 | 0 | 0 | 0 | 1600 | 1600 | 15
75 | Line No 139 Item No (f) | As Constructed Survey Data to Council Requirements. | Item |  |  |  | 1 |  | 5920 |  | 2 | 5920 | 0 | 0 | 0 | 5920
| 1 | Surveyor | hr | L | 1 | 1 | 18 | 185 | 3330 | 18 | 18 | 3330 | 0 | 0 | 0 | 3330 | 11
| 2 | Surveyor | hr | L | 1 | 1 | 6 | 185 | 1110 | 6 | 6 | 1110 | 0 | 0 | 0 | 1110 | 11
| 3 | Surveyor | hr | L | 1 | 1 | 8 | 185 | 1480 | 8 | 8 | 1480 | 0 | 0 | 0 | 1480 | 11
| Line No 140 Item No (g) | Geotechnical Testing by NATA Registered laboratory
76 | Line No 141 Item No (i) | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | No |  |  |  | 4 |  | 846.6667 |  | 0 | 0 | 0 | 0 | 846.6667 | 846.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 1.3333 | 2 | 666.6667 | 333.3333 | 1.3333 | 0 | 0 | 0 | 666.6667 | 666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 4 | 45 | 180 | 4 | 4 | 0 | 0 | 0 | 180 | 180 | 13
77 | Line No 142 Item No (ii) | Sub-Base Compaction testing as specified - assume 2 layers | No |  |  |  | 4 |  | 846.6667 |  | 0 | 0 | 0 | 0 | 846.6667 | 846.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 1.3333 | 2 | 666.6667 | 333.3333 | 1.3333 | 0 | 0 | 0 | 666.6667 | 666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 4 | 45 | 180 | 4 | 4 | 0 | 0 | 0 | 180 | 180 | 13
78 | Line No 143 Item No (iii) | Base Compaction testing as specified | No |  |  |  | 2 |  | 423.3333 |  | 0 | 0 | 0 | 0 | 423.3333 | 423.3333
| 1 | Geotech Travel | km | S | 250 | 1 | 0.66667 | 2 | 333.3333 | 166.6667 | 0.66667 | 0 | 0 | 0 | 333.3333 | 333.3333 | 13
| 2 | Field Density | each | S | 1 | 1 | 2 | 45 | 90 | 2 | 2 | 0 | 0 | 0 | 90 | 90 | 13
79 | Line No 144 Item No (iv) | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | No |  |  |  | 1 |  | 1290 |  | 0 | 0 | 0 | 0 | 1290 | 1290
| 1 | Geotech Travel | km | S | 250 | 1 | 1 | 2 | 500 | 250 | 1 | 0 | 0 | 0 | 500 | 500 | 13
| 2 | Gravel Properties Testing | each | S | 1 | 1 | 1 | 390 | 390 | 1 | 1 | 0 | 0 | 0 | 390 | 390 | 13
| 3 | CBR Test | each | S | 1 | 1 | 1 | 400 | 400 | 1 | 1 | 0 | 0 | 0 | 400 | 400 | 13
80 | Line No 145 Item No (v) | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | No |  |  |  | 1 |  | 1290 |  | 0 | 0 | 0 | 0 | 1290 | 1290
| 1 | Geotech Travel | km | S | 250 | 1 | 1 | 2 | 500 | 250 | 1 | 0 | 0 | 0 | 500 | 500 | 13
| 2 | Gravel Properties Testing | each | S | 1 | 1 | 1 | 390 | 390 | 1 | 1 | 0 | 0 | 0 | 390 | 390 | 13
| 3 | CBR Test | each | S | 1 | 1 | 1 | 400 | 400 | 1 | 1 | 0 | 0 | 0 | 400 | 400 | 13
81 | Line No 147 Item No 2 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | Item |  |  |  | 1 |  | 5321.3964 |  | 2 | 1402.7027 | 0 | 3693.6937 | 225 | 5321.3964
| 1 | Excavator - 25T | hr | P | 1 | 0.111 | 1 | 135 | 1216.2162 | 9.009 | 9.009 | 0 | 0 | 1216.2162 | 0 | 1216.2162 | 21
| 2 | Tipper | hr | P | 2 | 0.111 | 1 | 90 | 1621.6216 | 18.018 | 9.009 | 0 | 0 | 1621.6216 | 0 | 1621.6216 | 21
| 3 | Water Cart - Hire | hr | P | 1 | 0.111 | 1 | 95 | 855.8559 | 9.009 | 9.009 | 0 | 0 | 855.8559 | 0 | 855.8559 | 21
| 4 | Tip Fees | tonne | S | 1 | 1 | 15 | 15 | 225 | 15 | 15 | 0 | 0 | 0 | 225 | 225 | 21
| 5 | Labour | hr | L | 3 | 0.111 | 1 | 51.9 | 1402.7027 | 27.027 | 9.009 | 1402.7027 | 0 | 0 | 0 | 1402.7027 | 21
| Line No 149 Item No 3 | Earthworks - excavate and place as embankment as directed
82 | Line No 150 Item No (a) | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | m3 |  |  |  | 379 |  | 4967.1131 |  | 2 | 467.1012 | 0 | 4500.0119 | 0 | 4967.1131
| 1 | Cut Embankment
82.1 | 2 | Excavator - 25T | hr | P | 1 | 42.111 | 379 | 135 | 1215.0032 | 9 | 9 | 0 | 0 | 1215.0032 | 0 | 1215.0032 | 53
| 3 | Tipper | hr | P | 3 | 42.111 | 379 | 90 | 2430.0064 | 27.0001 | 9 | 0 | 0 | 2430.0064 | 0 | 2430.0064 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 42.111 | 379 | 95 | 855.0023 | 9 | 9 | 0 | 0 | 855.0023 | 0 | 855.0023 | 53
| 5 | Labour | hr | L | 1 | 42.111 | 379 | 51.9 | 467.1012 | 9 | 9 | 467.1012 | 0 | 0 | 0 | 467.1012 | 53
83 | Line No 151 Item No (b) | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 |  |  |  | 50 |  | 3143.5 |  | 1 | 778.5 | 0 | 2365 | 0 | 3143.5
83.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | 50 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 57
| 2 | Tipper | hr | P | 1 | 10 | 50 | 90 | 450 | 5 | 5 | 0 | 0 | 450 | 0 | 450 | 57
| 3 | PF Roller Wet - No OP | hr | P | 1 | 10 | 50 | 58 | 290 | 5 | 5 | 0 | 0 | 290 | 0 | 290 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 10 | 50 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 57
| 5 | Labour | hr | L | 3 | 10 | 50 | 51.9 | 778.5 | 15 | 5 | 778.5 | 0 | 0 | 0 | 778.5 | 57
| 6 | Bobcat | hr | P | 1 | 10 | 50 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 57
| Line No 153 Item No 4 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
84 | Line No 154 Item No (a) | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | m2 |  |  |  | 630 |  | 1843.905 |  | 1 | 490.455 | 0 | 1353.45 | 0 | 1843.905
84.1 | 1 | Grader | hr | P | 1 | 200 | 630 | 160 | 504 | 3.15 | 3.15 | 0 | 0 | 504 | 0 | 504 | 62
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 630 | 55 | 173.25 | 3.15 | 3.15 | 0 | 0 | 173.25 | 0 | 173.25 | 62
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | 630 | 58 | 182.7 | 3.15 | 3.15 | 0 | 0 | 182.7 | 0 | 182.7 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 630 | 95 | 299.25 | 3.15 | 3.15 | 0 | 0 | 299.25 | 0 | 299.25 | 62
| 5 | Labour | hr | L | 3 | 200 | 630 | 51.9 | 490.455 | 9.45 | 3.15 | 490.455 | 0 | 0 | 0 | 490.455 | 62
| 6 | Bobcat | hr | P | 1 | 600 | 630 | 95 | 99.75 | 1.05 | 1.05 | 0 | 0 | 99.75 | 0 | 99.75 | 62
| 7 | Tipper | hr | P | 1 | 600 | 630 | 90 | 94.5 | 1.05 | 1.05 | 0 | 0 | 94.5 | 0 | 94.5 | 62
85 | Line No 155 Item No (b) | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | m2 |  |  |  | 574 |  | 1680.0023 |  | 1 | 446.859 | 0 | 1233.1433 | 0 | 1680.0023
85.1 | 1 | Grader | hr | P | 1 | 200 | 574 | 160 | 459.2 | 2.87 | 2.87 | 0 | 0 | 459.2 | 0 | 459.2 | 62
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 574 | 55 | 157.85 | 2.87 | 2.87 | 0 | 0 | 157.85 | 0 | 157.85 | 62
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | 574 | 58 | 166.46 | 2.87 | 2.87 | 0 | 0 | 166.46 | 0 | 166.46 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 574 | 95 | 272.65 | 2.87 | 2.87 | 0 | 0 | 272.65 | 0 | 272.65 | 62
| 5 | Labour | hr | L | 3 | 200 | 574 | 51.9 | 446.859 | 8.61 | 2.87 | 446.859 | 0 | 0 | 0 | 446.859 | 62
| 6 | Bobcat | hr | P | 1 | 600 | 574 | 95 | 90.8833 | 0.95667 | 0.95667 | 0 | 0 | 90.8833 | 0 | 90.8833 | 62
| 7 | Tipper | hr | P | 1 | 600 | 574 | 90 | 86.1 | 0.95667 | 0.95667 | 0 | 0 | 86.1 | 0 | 86.1 | 62
| Line No 157 Item No 5 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results
86 | Line No 158 Item No (a) | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | m2 |  |  |  | 437 |  | 925.4336 |  | 1 | 247.4215 | 0 | 678.0121 | 0 | 925.4336
86.1 | 1 | Grader | hr | P | 1 | 275 | 437 | 160 | 254.2545 | 1.5891 | 1.5891 | 0 | 0 | 254.2545 | 0 | 254.2545 | 63
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 275 | 437 | 55 | 87.4 | 1.5891 | 1.5891 | 0 | 0 | 87.4 | 0 | 87.4 | 63
| 3 | MW Roller | hr | P | 1 | 275 | 437 | 55 | 87.4 | 1.5891 | 1.5891 | 0 | 0 | 87.4 | 0 | 87.4 | 63
| 4 | Water Cart - Hire | hr | P | 1 | 275 | 437 | 95 | 150.9636 | 1.5891 | 1.5891 | 0 | 0 | 150.9636 | 0 | 150.9636 | 63
| 5 | Labour | hr | L | 3 | 275 | 437 | 51.9 | 247.4215 | 4.7673 | 1.5891 | 247.4215 | 0 | 0 | 0 | 247.4215 | 63
| 6 | Bobcat | hr | P | 1 | 825 | 437 | 95 | 50.3212 | 0.5297 | 0.5297 | 0 | 0 | 50.3212 | 0 | 50.3212 | 63
| 7 | Tipper | hr | P | 1 | 825 | 437 | 90 | 47.6727 | 0.5297 | 0.5297 | 0 | 0 | 47.6727 | 0 | 47.6727 | 63
87 | Line No 159 Item No (b) | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | m2 |  |  |  | 415 |  | 878.8442 |  | 1 | 234.9655 | 0 | 643.8788 | 0 | 878.8442
87.1 | 1 | Grader | hr | P | 1 | 275 | 415 | 160 | 241.4545 | 1.5091 | 1.5091 | 0 | 0 | 241.4545 | 0 | 241.4545 | 63
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 275 | 415 | 55 | 83 | 1.5091 | 1.5091 | 0 | 0 | 83 | 0 | 83 | 63
| 3 | MW Roller | hr | P | 1 | 275 | 415 | 55 | 83 | 1.5091 | 1.5091 | 0 | 0 | 83 | 0 | 83 | 63
| 4 | Water Cart - Hire | hr | P | 1 | 275 | 415 | 95 | 143.3636 | 1.5091 | 1.5091 | 0 | 0 | 143.3636 | 0 | 143.3636 | 63
| 5 | Labour | hr | L | 3 | 275 | 415 | 51.9 | 234.9655 | 4.5273 | 1.5091 | 234.9655 | 0 | 0 | 0 | 234.9655 | 63
| 6 | Bobcat | hr | P | 1 | 825 | 415 | 95 | 47.7879 | 0.50303 | 0.50303 | 0 | 0 | 47.7879 | 0 | 47.7879 | 63
| 7 | Tipper | hr | P | 1 | 825 | 415 | 90 | 45.2727 | 0.50303 | 0.50303 | 0 | 0 | 45.2727 | 0 | 45.2727 | 63
| Line No 161 Item No 6 | Gravel Pavement
| Line No 162 Item No | In Place complete, including supply, spreading, watering, rolling and trimming:-
| Line No 163 Item No | (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS
88 | Line No 164 Item No (i) | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | m3 |  |  |  | 70 |  | 7478.2426 |  | 1 | 384.1878 | 5551.875 | 1542.1798 | 0 | 7478.2426
88.1 | 1 | CBR80 | tonne | M | 1 | 1 | 164.5 | 33.75 | 5551.875 |  |  | 0 | 5551.875 | 0 | 0 | 5551.875 | QM2.3
| 2 | Grader | hr | P | 1 | 66.667 | 164.5 | 160 | 394.798 | 2.4675 | 2.4675 | 0 | 0 | 394.798 | 0 | 394.798 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 164.5 | 55 | 135.7118 | 2.4675 | 2.4675 | 0 | 0 | 135.7118 | 0 | 135.7118 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 164.5 | 95 | 234.4113 | 2.4675 | 2.4675 | 0 | 0 | 234.4113 | 0 | 234.4113 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 164.5 | 51.9 | 384.1878 | 7.4025 | 2.4675 | 384.1878 | 0 | 0 | 0 | 384.1878 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 164.5 | 135 | 333.1108 | 2.4675 | 2.4675 | 0 | 0 | 333.1108 | 0 | 333.1108 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 164.5 | 90 | 444.1478 | 4.935 | 2.4675 | 0 | 0 | 444.1478 | 0 | 444.1478 | 62
89 | Line No 165 Item No (ii) | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 |  |  |  | 107 |  | 11116.7155 |  | 1 | 587.2585 | 8172.125 | 2357.332 | 0 | 11116.7155
| 1 | CBR45 | tonne | M | 1 | 1 | 251.45 | 32.5 | 8172.125 |  |  | 0 | 8172.125 | 0 | 0 | 8172.125 | QM2.3
89.1 | 2 | Grader | hr | P | 1 | 66.667 | 251.45 | 160 | 603.477 | 3.7717 | 3.7717 | 0 | 0 | 603.477 | 0 | 603.477 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 251.45 | 55 | 207.4452 | 3.7717 | 3.7717 | 0 | 0 | 207.4452 | 0 | 207.4452 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 251.45 | 95 | 358.3145 | 3.7717 | 3.7717 | 0 | 0 | 358.3145 | 0 | 358.3145 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 251.45 | 51.9 | 587.2585 | 11.3152 | 3.7717 | 587.2585 | 0 | 0 | 0 | 587.2585 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 251.45 | 135 | 509.1837 | 3.7717 | 3.7717 | 0 | 0 | 509.1837 | 0 | 509.1837 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 251.45 | 90 | 678.9116 | 7.5435 | 3.7717 | 0 | 0 | 678.9116 | 0 | 678.9116 | 62
90 | Line No 166 Item No (iii) | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 |  |  |  | 90 |  | 9160.1584 |  | 1 | 493.9558 | 6683.4 | 1982.8026 | 0 | 9160.1584
| 1 | CBR15 | tonne | M | 1 | 1 | 211.5 | 31.6 | 6683.4 |  |  | 0 | 6683.4 | 0 | 0 | 6683.4 | QM2.3
90.1 | 2 | Grader | hr | P | 1 | 66.667 | 211.5 | 160 | 507.5975 | 3.1725 | 3.1725 | 0 | 0 | 507.5975 | 0 | 507.5975 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 211.5 | 55 | 174.4866 | 3.1725 | 3.1725 | 0 | 0 | 174.4866 | 0 | 174.4866 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 211.5 | 95 | 301.386 | 3.1725 | 3.1725 | 0 | 0 | 301.386 | 0 | 301.386 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 211.5 | 51.9 | 493.9558 | 9.5175 | 3.1725 | 493.9558 | 0 | 0 | 0 | 493.9558 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 211.5 | 135 | 428.2854 | 3.1725 | 3.1725 | 0 | 0 | 428.2854 | 0 | 428.2854 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 211.5 | 90 | 571.0471 | 6.345 | 3.1725 | 0 | 0 | 571.0471 | 0 | 571.0471 | 62
| Line No 167 Item No | (b) Dysart Bypass Rd - Middlemount Rd Intersection RHS
91 | Line No 168 Item No (i) | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | m3 |  |  |  | 66 |  | 7050.9145 |  | 1 | 362.2342 | 5234.625 | 1454.0552 | 0 | 7050.9145
| 1 | CBR80 | tonne | M | 1 | 1 | 155.1 | 33.75 | 5234.625 |  |  | 0 | 5234.625 | 0 | 0 | 5234.625 | QM2.3
91.1 | 2 | Grader | hr | P | 1 | 66.667 | 155.1 | 160 | 372.2381 | 2.3265 | 2.3265 | 0 | 0 | 372.2381 | 0 | 372.2381 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 155.1 | 55 | 127.9569 | 2.3265 | 2.3265 | 0 | 0 | 127.9569 | 0 | 127.9569 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 155.1 | 95 | 221.0164 | 2.3265 | 2.3265 | 0 | 0 | 221.0164 | 0 | 221.0164 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 155.1 | 51.9 | 362.2342 | 6.9795 | 2.3265 | 362.2342 | 0 | 0 | 0 | 362.2342 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 155.1 | 135 | 314.0759 | 2.3265 | 2.3265 | 0 | 0 | 314.0759 | 0 | 314.0759 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 155.1 | 90 | 418.7679 | 4.653 | 2.3265 | 0 | 0 | 418.7679 | 0 | 418.7679 | 62
92 | Line No 169 Item No (ii) | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 |  |  |  | 99 |  | 10285.5592 |  | 1 | 543.3514 | 7561.125 | 2181.0828 | 0 | 10285.5592
| 1 | CBR45 | tonne | M | 1 | 1 | 232.65 | 32.5 | 7561.125 |  |  | 0 | 7561.125 | 0 | 0 | 7561.125 | QM2.3
92.1 | 2 | Grader | hr | P | 1 | 66.667 | 232.65 | 160 | 558.3572 | 3.4897 | 3.4897 | 0 | 0 | 558.3572 | 0 | 558.3572 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 232.65 | 55 | 191.9353 | 3.4897 | 3.4897 | 0 | 0 | 191.9353 | 0 | 191.9353 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 232.65 | 95 | 331.5246 | 3.4897 | 3.4897 | 0 | 0 | 331.5246 | 0 | 331.5246 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 232.65 | 51.9 | 543.3514 | 10.4692 | 3.4897 | 543.3514 | 0 | 0 | 0 | 543.3514 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 232.65 | 135 | 471.1139 | 3.4897 | 3.4897 | 0 | 0 | 471.1139 | 0 | 471.1139 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 232.65 | 90 | 628.1519 | 6.9795 | 3.4897 | 0 | 0 | 628.1519 | 0 | 628.1519 | 62
93 | Line No 170 Item No (iii) | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 |  |  |  | 83 |  | 8447.7016 |  | 1 | 455.537 | 6163.58 | 1828.5846 | 0 | 8447.7016
| 1 | CBR15 | tonne | M | 1 | 1 | 195.05 | 31.6 | 6163.58 |  |  | 0 | 6163.58 | 0 | 0 | 6163.58 | QM2.3
93.1 | 2 | Grader | hr | P | 1 | 66.667 | 195.05 | 160 | 468.1177 | 2.9257 | 2.9257 | 0 | 0 | 468.1177 | 0 | 468.1177 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 195.05 | 55 | 160.9154 | 2.9257 | 2.9257 | 0 | 0 | 160.9154 | 0 | 160.9154 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 195.05 | 95 | 277.9449 | 2.9257 | 2.9257 | 0 | 0 | 277.9449 | 0 | 277.9449 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 195.05 | 51.9 | 455.537 | 8.7772 | 2.9257 | 455.537 | 0 | 0 | 0 | 455.537 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 195.05 | 135 | 394.9743 | 2.9257 | 2.9257 | 0 | 0 | 394.9743 | 0 | 394.9743 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 195.05 | 90 | 526.6324 | 5.8515 | 2.9257 | 0 | 0 | 526.6324 | 0 | 526.6324 | 62
| Line No 173 Item No 7 | Provisional Item Pavement Repairs
94 | Line No 174 Item No (a) | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | m2 |  |  |  | 30 |  | 5610.0655 |  | 2 | 0 | 162.0006 | 5448.0648 | 0 | 5610.0655
94.1 | 1 | Stabilising |  | P | 1 | 3.333 | 30 | 605.28 | 5448.0648 | 9.0009 | 9.0009 | 0 | 0 | 5448.0648 | 0 | 5448.0648 | 68
| 2 | Cement | tonne | M | 1 | 1 | 0.36 | 450 | 162.0006 |  |  | 0 | 162.0006 | 0 | 0 | 162.0006 | CSA
| Line No 176 Item No 8 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED
95 | Line No 177 Item No (a) | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | m2 |  |  |  | 437 |  | 2355.43 |  | 1 | 0 | 0 | 0 | 2355.43 | 2355.43
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 480.7 | 4.9 | 2355.43 | 480.7 | 480.7 | 0 | 0 | 0 | 2355.43 | 2355.43 | 64
96 | Line No 178 Item No (b) | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | m2 |  |  |  | 415 |  | 2236.85 |  | 1 | 0 | 0 | 0 | 2236.85 | 2236.85
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 456.5 | 4.9 | 2236.85 | 456.5 | 456.5 | 0 | 0 | 0 | 2236.85 | 2236.85 | 64
| Line No 180 Item No 9 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place.
97 | Line No 181 Item No (a) | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | m2 |  |  |  | 2776 |  | 115460.5466 |  | 2 | 0 | 0 | 0 | 115460.5466 | 115460.5466
| 1 | 60mm AC | tonne | S | 1 | 1 | 416.4042 | 277.28 | 115460.5466 | 416.4042 | 416.4042 | 0 | 0 | 0 | 115460.5466 | 115460.5466 | 65
| Line No 183 Item No 10 | Medians Kerb at Intersections
98 | Line No 184 Item No (a) | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | m |  |  |  | 67 |  | 5701.1957 |  | 1 | 0 | 2686.1957 | 0 | 3015 | 5701.1957
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 7.2043 | 309 | 2226.129 |  |  | 0 | 2226.129 | 0 | 0 | 2226.129 | CKM
| 2 | Sand | tonne | M | 1 | 1 | 4.4667 | 28 | 125.0667 |  |  | 0 | 125.0667 | 0 | 0 | 125.0667 | QMS | y
| 3 | Cement - 20 kg Bags | each | M | 1 | 1 | 22.3333 | 15 | 335 |  |  | 0 | 335 | 0 | 0 | 335 | 71
| 4 | Kerb Subbie | m | S | 1 | 1 | 67 | 45 | 3015 | 67 | 67 | 0 | 0 | 0 | 3015 | 3015 | 71
Line No 185 Item No
| Line No 186 Item No 11 | Street Lighting - Conduits and Bases
99 | Line No 187 Item No (a) | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | m |  |  |  | 79 |  | 2078.1625 |  | 1 | 155.7 | 1740.9625 | 181.5 | 0 | 2078.1625
| 1 | 125 LD uPVC Electrical | m | M | 1 | 1 | 79 | 8 | 632 |  |  | 0 | 632 | 0 | 0 | 632 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 98.75 | 0.11 | 10.8625 |  |  | 0 | 10.8625 | 0 | 0 | 10.8625 | ETC
| 3 | Hard Cover - Electrical | m | M | 1 | 1 | 79 | 2.7 | 213.3 |  |  | 0 | 213.3 | 0 | 0 | 213.3 | ETC
| 4 | Sand | tonne | M | 1 | 1 | 31.6 | 28 | 884.8 |  |  | 0 | 884.8 | 0 | 0 | 884.8 | QMS | y
99.1 | 5 | Excavator - 25T | hr | P | 1 | 79 | 79 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 111
| 6 | CAT297 | hr | P | 1 | 79 | 79 | 46.5 | 46.5 | 1 | 1 | 0 | 0 | 46.5 | 0 | 46.5 | 111
| 7 | Labour | hr | L | 3 | 79 | 79 | 51.9 | 155.7 | 3 | 1 | 155.7 | 0 | 0 | 0 | 155.7 | 111
100 | Line No 188 Item No (b) | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | m |  |  |  | 20 |  | 3600 |  | 3 | 0 | 0 | 0 | 3600 | 3600
| 1 | Underbore | m | S | 1 | 1 | 20 | 130 | 2600 | 20 | 20 | 0 | 0 | 0 | 2600 | 2600 | 111
| 2 | Underbore Estab | Item | S | 1 | 1 | 1 | 1000 | 1000 | 1 | 1 | 0 | 0 | 0 | 1000 | 1000 | 111
101 | Line No 189 Item No (c) | Electrical Mains Cable Pit (Provisional Item) | No |  |  |  | 2 |  | 2452.8 |  | 1 | 622.8 | 1560 | 270 | 0 | 2452.8
| 1 | Type 7 Elec Pit | each | M | 1 | 1 | 2 | 780 | 1560 |  |  | 0 | 1560 | 0 | 0 | 1560 | ETP
101.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 2 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 111
| 3 | Labour | hr | L | 3 | 0.5 | 2 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 111
102 | Line No 190 Item No (d) | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | No |  |  |  | 2 |  | 2690.8 |  | 1 | 622.8 | 1528 | 540 | 0 | 2690.8
| 1 | Supply of Materials
| 2 | Rag Bolt | each | M | 1 | 1 | 2 | 425 | 850 |  |  | 0 | 850 | 0 | 0 | 850 | ETC
| 3 | N32 | m³ | M | 1 | 1 | 2 | 309 | 618 |  |  | 0 | 618 | 0 | 0 | 618 | C32
| 4 | 50 HD uPVC Electrical | m | M | 10 | 1 | 2 | 3 | 60 |  |  | 0 | 60 | 0 | 0 | 60 | ETC
| 5 | Installation
| 6 | Allow 2 hours per footing to set up and pour.
102.1 | 7 | Excavator - 25T | hr | P | 1 | 0.5 | 2 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 111
| 8 | Labour | hr | L | 3 | 0.5 | 2 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 111
| Line No 192 Item No 12 | Soil Management Measures inclusive of:
103 | Line No 193 Item No (a) | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | m2 |  |  |  | 1000 |  | 767.25 |  | 1 | 129.75 | 0 | 637.5 | 0 | 767.25
103.1 | 1 | Grader | hr | P | 1 | 400 | 1000 | 160 | 400 | 2.5 | 2.5 | 0 | 0 | 400 | 0 | 400 | 59
| 2 | Water Cart - Hire | hr | P | 1 | 400 | 1000 | 95 | 237.5 | 2.5 | 2.5 | 0 | 0 | 237.5 | 0 | 237.5 | 59
| 3 | Labour | hr | L | 1 | 400 | 1000 | 51.9 | 129.75 | 2.5 | 2.5 | 129.75 | 0 | 0 | 0 | 129.75 | 59
104 | Line No 194 Item No (b) | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | m2 |  |  |  | 1000 |  | 1125 |  | 1 | 0 | 0 | 190 | 935 | 1125
| 1 | Hydromulch Subbie | m² | S | 1 | 1 | 1100 | 0.85 | 935 | 1100 | 1100 | 0 | 0 | 0 | 935 | 935 | 121
104.1 | 2 | Water Cart - Hire | hr | P | 1 | 550 | 1100 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 121
105 | Line No 195 Item No (c) | Soil Management Measures inclusive of: Rock check dams as directed | No |  |  |  | 6 |  | 1626.4 |  | 1 | 311.4 | 945 | 370 | 0 | 1626.4
| 1 | Gabion Rock | tonne | M | 1 | 1 | 27 | 35 | 945 |  |  | 0 | 945 | 0 | 0 | 945 | QMR
105.1 | 2 | Bobcat | hr | P | 1 | 3 | 6 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 3 | Labour | hr | L | 3 | 3 | 6 | 51.9 | 311.4 | 6 | 2 | 311.4 | 0 | 0 | 0 | 311.4 | 81
| 4 | Tipper | hr | P | 1 | 3 | 6 | 90 | 180 | 2 | 2 | 0 | 0 | 180 | 0 | 180 | 81
| Line No 197 Item No 13 | Road Furniture
106 | Line No 198 Item No (a) | Supply and Install New Guide Posts | No |  |  |  | 11 |  | 550 |  | 1 | 0 | 550 | 0 | 0 | 550
| 1 | Guide Post | each | M | 1 | 1 | 11 | 50 | 550 |  |  | 0 | 550 | 0 | 0 | 550 | 67
107 | Line No 199 Item No (b) | Supply and Install New Give Way Sign R1-2 | No |  |  |  | 1 |  | 338.8 |  | 1 | 103.8 | 140 | 95 | 0 | 338.8
| 1 | Signs Complete | each | M | 1 | 1 | 1 | 140 | 140 |  |  | 0 | 140 | 0 | 0 | 140 | 67
| 2 | Bobcat | hr | P | 1 | 1 | 1 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 67
107.1 | 3 | Labour | hr | L | 2 | 1 | 1 | 51.9 | 103.8 | 2 | 1 | 103.8 | 0 | 0 | 0 | 103.8 | 67
108 | Line No 200 Item No (c) | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | Item |  |  |  | 1 |  | 7500 |  | 1 | 0 | 0 | 0 | 7500 | 7500
| 1 | Line Marking | m² | S | 1 | 1 | 7500 | 1 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 7500 | 7500 | 66
| Line No 202 Item No 14 | Drainage - Ch 140 Middlemount Road
109 | Line No 203 Item No (a) | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | m |  |  |  | 3.6 |  | 4014.9044 |  | 1 | 1401.3 | 1078.6044 | 1535 | 0 | 4014.9044
| 1 | Buy Materials
| 2 | RCBC - 600 x 300 | each | M | 1 | 1 | 3 | 247.5 | 742.5 |  |  | 0 | 742.5 | 0 | 0 | 742.5 | SWC
| 3 | Sand | tonne | M | 1 | 1 | 1.325 | 28 | 37.1011 |  |  | 0 | 37.1011 | 0 | 0 | 37.1011 | QMS | y
| 4 | N40 | m³ | M | 1 | 1 | 0.92001 | 325 | 299.0033 |  |  | 0 | 299.0033 | 0 | 0 | 299.0033 | C40
| 5 | Excavate
109.1 | 6 | Excavator - 25T | hr | P | 1 | 1.8 | 3.6 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 181
| 7 | Tipper | hr | P | 1 | 1.8 | 3.6 | 90 | 180 | 2 | 2 | 0 | 0 | 180 | 0 | 180 | 181
| 8 | Water Cart - Hire | hr | P | 1 | 1.8 | 3.6 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 181
| 9 | Labour | hr | L | 3 | 1.8 | 3.6 | 51.9 | 311.4 | 6 | 2 | 311.4 | 0 | 0 | 0 | 311.4 | 181
| 10 | Base
109.2 | 11 | Bobcat | hr | P | 1 | 0.9 | 3.6 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 181
| 12 | Labour | hr | L | 3 | 0.9 | 3.6 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 181
| 13 | Stand
109.3 | 14 | Excavator - 25T | hr | P | 1 | 3 | 3 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 181
| 15 | Labour | hr | L | 3 | 3 | 3 | 51.9 | 155.7 | 3 | 1 | 155.7 | 0 | 0 | 0 | 155.7 | 181
| 16 | Backfill
109.4 | 17 | Bobcat | hr | P | 1 | 1.8 | 3.6 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 181
| 18 | Water Cart - Hire | hr | P | 1 | 1.8 | 3.6 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 181
| 19 | Labour | hr | L | 3 | 1.8 | 3.6 | 51.9 | 311.4 | 6 | 2 | 311.4 | 0 | 0 | 0 | 311.4 | 181
110 | Line No 204 Item No (b) | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | No |  |  |  | 1 |  | 947.8 |  | 1 | 622.8 | 325 | 0 | 0 | 947.8
| 1 | N40 | m³ | M | 1 | 1 | 1 | 325 | 325 |  |  | 0 | 325 | 0 | 0 | 325 | C40
110.1 | 2 | Labour | hr | L | 3 | 0.25 | 1 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 72
| Line No 210 Item No | Schedule D - Golden Mile Road & Dysart Bypass Road Intersection Upgrade Works
| Line No 211 Item No 1 | Preliminaries
| Line No 212 Item No (a) | Schedule D - Golden Mile Road & Dysart Bypass Road Intersection Upgrade Works - Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | Item |  |  |  | 1
| 1 | There is no cost estimate for this item
111 | Line No 213 Item No (b) | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | Item |  |  |  | 1 |  | 28325.0469 |  | 13 | 8774.987 | 0 | 0 | 19550.0599 | 28325.0469
| 1 | Project Engineer | week | L | 1 | 1 | 0.5 | 3250 | 1625 | 0.5 | 0.5 | 1625 | 0 | 0 | 0 | 1625 | 901
| 2 | Traffic Controller | hr | L | 1 | 1 | 109.9998 | 65 | 7149.987 | 109.9998 | 109.9998 | 7149.987 | 0 | 0 | 0 | 7149.987 | 141
| 3 | Traffic Control Crew | hr | S | 1 | 1 | 109.9998 | 130 | 14299.974 | 109.9998 | 109.9998 | 0 | 0 | 0 | 14299.974 | 14299.974 | 141
| 4 | Accommodation | day | S | 3 | 1 | 14.0002 | 125 | 5250.0859 | 42.0007 | 14.0002 | 0 | 0 | 0 | 5250.0859 | 5250.0859 | 911
112 | Line No 214 Item No (c ) | Construction Setout by Contractor | Item |  |  |  | 1 |  | 5180 |  | 2 | 5180 | 0 | 0 | 0 | 5180
| 1 | Surveyor | hr | L | 1 | 1 | 8 | 185 | 1480 | 8 | 8 | 1480 | 0 | 0 | 0 | 1480 | 11
| 2 | Surveyor | hr | L | 1 | 1 | 12 | 185 | 2220 | 12 | 12 | 2220 | 0 | 0 | 0 | 2220 | 11
| 3 | Surveyor | hr | L | 1 | 1 | 8 | 185 | 1480 | 8 | 8 | 1480 | 0 | 0 | 0 | 1480 | 11
| Line No 215 Item No | [Note: Council to provide an initial control line, TBM's, prior to commencement of works; Contractor shall be responsible for all other setout to construct the works
113 | Line No 216 Item No (d ) | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | Item |  |  |  | 1 |  | 2800 |  | 1 | 0 | 0 | 0 | 2800 | 2800
| 1 | CAR | Item | S | 1 | 1 | 2800 | 1 | 2800 | 2800 | 2800 | 0 | 0 | 0 | 2800 | 2800 | 904
114 | Line No 217 Item No (e) | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | Item |  |  |  | 1 |  | 3200 |  | 1 | 1600 | 0 | 0 | 1600 | 3200
| 1 | WHSO | week | L | 1 | 1 | 0.5 | 3200 | 1600 | 0.5 | 0.5 | 1600 | 0 | 0 | 0 | 1600 | 901
| 2 | Service Locator | hr | S | 1 | 1 | 8 | 200 | 1600 | 8 | 8 | 0 | 0 | 0 | 1600 | 1600 | 15
115 | Line No 218 Item No (f) | As Constructed Survey Data to Council Requirements. | Item |  |  |  | 1 |  | 5920 |  | 4 | 5920 | 0 | 0 | 0 | 5920
| 1 | Surveyor | hr | L | 1 | 1 | 18 | 185 | 3330 | 18 | 18 | 3330 | 0 | 0 | 0 | 3330 | 11
| 2 | Surveyor | hr | L | 1 | 1 | 6 | 185 | 1110 | 6 | 6 | 1110 | 0 | 0 | 0 | 1110 | 11
| 3 | Surveyor | hr | L | 1 | 1 | 8 | 185 | 1480 | 8 | 8 | 1480 | 0 | 0 | 0 | 1480 | 11
| Line No 219 Item No (g) | Geotechnical Testing by NATA Registered laboratory
116 | Line No 220 Item No (i) | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | No |  |  |  | 4 |  | 846.6667 |  | 0 | 0 | 0 | 0 | 846.6667 | 846.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 1.3333 | 2 | 666.6667 | 333.3333 | 1.3333 | 0 | 0 | 0 | 666.6667 | 666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 4 | 45 | 180 | 4 | 4 | 0 | 0 | 0 | 180 | 180 | 13
117 | Line No 221 Item No (ii) | Sub-Base Compaction testing as specified - assume 2 layers | No |  |  |  | 4 |  | 846.6667 |  | 0 | 0 | 0 | 0 | 846.6667 | 846.6667
| 1 | Geotech Travel | km | S | 250 | 1 | 1.3333 | 2 | 666.6667 | 333.3333 | 1.3333 | 0 | 0 | 0 | 666.6667 | 666.6667 | 13
| 2 | Field Density | each | S | 1 | 1 | 4 | 45 | 180 | 4 | 4 | 0 | 0 | 0 | 180 | 180 | 13
118 | Line No 222 Item No (iii) | Base Compaction testing as specified | No |  |  |  | 2 |  | 423.3333 |  | 0 | 0 | 0 | 0 | 423.3333 | 423.3333
| 1 | Geotech Travel | km | S | 250 | 1 | 0.66667 | 2 | 333.3333 | 166.6667 | 0.66667 | 0 | 0 | 0 | 333.3333 | 333.3333 | 13
| 2 | Field Density | each | S | 1 | 1 | 2 | 45 | 90 | 2 | 2 | 0 | 0 | 0 | 90 | 90 | 13
119 | Line No 223 Item No (iv) | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | No |  |  |  | 1 |  | 1290 |  | 0 | 0 | 0 | 0 | 1290 | 1290
| 1 | Geotech Travel | km | S | 250 | 1 | 1 | 2 | 500 | 250 | 1 | 0 | 0 | 0 | 500 | 500 | 13
| 2 | Gravel Properties Testing | each | S | 1 | 1 | 1 | 390 | 390 | 1 | 1 | 0 | 0 | 0 | 390 | 390 | 13
| 3 | CBR Test | each | S | 1 | 1 | 1 | 400 | 400 | 1 | 1 | 0 | 0 | 0 | 400 | 400 | 13
120 | Line No 224 Item No (v) | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | No |  |  |  | 1 |  | 1290 |  | 0 | 0 | 0 | 0 | 1290 | 1290
| 1 | Geotech Travel | km | S | 250 | 1 | 1 | 2 | 500 | 250 | 1 | 0 | 0 | 0 | 500 | 500 | 13
| 2 | Gravel Properties Testing | each | S | 1 | 1 | 1 | 390 | 390 | 1 | 1 | 0 | 0 | 0 | 390 | 390 | 13
| 3 | CBR Test | each | S | 1 | 1 | 1 | 400 | 400 | 1 | 1 | 0 | 0 | 0 | 400 | 400 | 13
Line No 225 Item No
121 | Line No 226 Item No 2 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | Item |  |  |  | 1 |  | 5321.3964 |  | 2 | 1402.7027 | 0 | 3693.6937 | 225 | 5321.3964
121.1 | 1 | Excavator - 25T | hr | P | 1 | 0.111 | 1 | 135 | 1216.2162 | 9.009 | 9.009 | 0 | 0 | 1216.2162 | 0 | 1216.2162 | 21
| 2 | Tipper | hr | P | 2 | 0.111 | 1 | 90 | 1621.6216 | 18.018 | 9.009 | 0 | 0 | 1621.6216 | 0 | 1621.6216 | 21
| 3 | Water Cart - Hire | hr | P | 1 | 0.111 | 1 | 95 | 855.8559 | 9.009 | 9.009 | 0 | 0 | 855.8559 | 0 | 855.8559 | 21
| 4 | Tip Fees | tonne | S | 1 | 1 | 15 | 15 | 225 | 15 | 15 | 0 | 0 | 0 | 225 | 225 | 21
| 5 | Labour | hr | L | 3 | 0.111 | 1 | 51.9 | 1402.7027 | 27.027 | 9.009 | 1402.7027 | 0 | 0 | 0 | 1402.7027 | 21
Line No 227 Item No
| Line No 228 Item No 3 | Earthworks - excavate and place as embankment as directed
122 | Line No 229 Item No (a) | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | m3 |  |  |  | 396 |  | 4967.1 |  | 1 | 467.1 | 0 | 4500 | 0 | 4967.1
| 1 | Cut Embankment
122.1 | 2 | Excavator - 25T | hr | P | 1 | 44 | 396 | 135 | 1215 | 9 | 9 | 0 | 0 | 1215 | 0 | 1215 | 53
| 3 | Tipper | hr | P | 3 | 44 | 396 | 90 | 2430 | 27 | 9 | 0 | 0 | 2430 | 0 | 2430 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 44 | 396 | 95 | 855 | 9 | 9 | 0 | 0 | 855 | 0 | 855 | 53
| 5 | Labour | hr | L | 1 | 44 | 396 | 51.9 | 467.1 | 9 | 9 | 467.1 | 0 | 0 | 0 | 467.1 | 53
123 | Line No 230 Item No (b) | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 |  |  |  | 50 |  | 3143.5 |  | 1 | 778.5 | 0 | 2365 | 0 | 3143.5
123.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | 50 | 135 | 675 | 5 | 5 | 0 | 0 | 675 | 0 | 675 | 57
| 2 | Tipper | hr | P | 1 | 10 | 50 | 90 | 450 | 5 | 5 | 0 | 0 | 450 | 0 | 450 | 57
| 3 | PF Roller Wet - No OP | hr | P | 1 | 10 | 50 | 58 | 290 | 5 | 5 | 0 | 0 | 290 | 0 | 290 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 10 | 50 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 57
| 5 | Labour | hr | L | 3 | 10 | 50 | 51.9 | 778.5 | 15 | 5 | 778.5 | 0 | 0 | 0 | 778.5 | 57
| 6 | Bobcat | hr | P | 1 | 10 | 50 | 95 | 475 | 5 | 5 | 0 | 0 | 475 | 0 | 475 | 57
Line No 231 Item No
| Line No 232 Item No 4 | Prepare Dysart Bypass Rd - Golden Mile Rd Intersection Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
124 | Line No 233 Item No (a) | Prepare Dysart Bypass Rd - Golden Mile Rd Intersection Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | m2 |  |  |  | 434 |  | 1270.2457 |  | 1 | 337.869 | 0 | 932.3767 | 0 | 1270.2457
124.1 | 1 | Grader | hr | P | 1 | 200 | 434 | 160 | 347.2 | 2.17 | 2.17 | 0 | 0 | 347.2 | 0 | 347.2 | 61
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 434 | 55 | 119.35 | 2.17 | 2.17 | 0 | 0 | 119.35 | 0 | 119.35 | 61
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | 434 | 58 | 125.86 | 2.17 | 2.17 | 0 | 0 | 125.86 | 0 | 125.86 | 61
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 434 | 95 | 206.15 | 2.17 | 2.17 | 0 | 0 | 206.15 | 0 | 206.15 | 61
| 5 | Labour | hr | L | 3 | 200 | 434 | 51.9 | 337.869 | 6.51 | 2.17 | 337.869 | 0 | 0 | 0 | 337.869 | 61
| 6 | Bobcat | hr | P | 1 | 600 | 434 | 95 | 68.7167 | 0.72333 | 0.72333 | 0 | 0 | 68.7167 | 0 | 68.7167 | 61
| 7 | Tipper | hr | P | 1 | 600 | 434 | 90 | 65.1 | 0.72333 | 0.72333 | 0 | 0 | 65.1 | 0 | 65.1 | 61
125 | Line No 234 Item No (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | m2 |  |  |  | 830 |  | 2429.2717 |  | 1 | 646.155 | 0 | 1783.1167 | 0 | 2429.2717
125.1 | 1 | Grader | hr | P | 1 | 200 | 830 | 160 | 664 | 4.15 | 4.15 | 0 | 0 | 664 | 0 | 664 | 61
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 830 | 55 | 228.25 | 4.15 | 4.15 | 0 | 0 | 228.25 | 0 | 228.25 | 61
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | 830 | 58 | 240.7 | 4.15 | 4.15 | 0 | 0 | 240.7 | 0 | 240.7 | 61
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 830 | 95 | 394.25 | 4.15 | 4.15 | 0 | 0 | 394.25 | 0 | 394.25 | 61
| 5 | Labour | hr | L | 3 | 200 | 830 | 51.9 | 646.155 | 12.45 | 4.15 | 646.155 | 0 | 0 | 0 | 646.155 | 61
| 6 | Bobcat | hr | P | 1 | 600 | 830 | 95 | 131.4167 | 1.3833 | 1.3833 | 0 | 0 | 131.4167 | 0 | 131.4167 | 61
| 7 | Tipper | hr | P | 1 | 600 | 830 | 90 | 124.5 | 1.3833 | 1.3833 | 0 | 0 | 124.5 | 0 | 124.5 | 61
Line No 235 Item No
| Line No 236 Item No 5 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results
126 | Line No 237 Item No (a) | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | m2 |  |  |  | 283 |  | 599.3082 |  | 1 | 160.2295 | 0 | 439.0788 | 0 | 599.3082
126.1 | 1 | Grader | hr | P | 1 | 275 | 283 | 160 | 164.6545 | 1.0291 | 1.0291 | 0 | 0 | 164.6545 | 0 | 164.6545 | 63
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 275 | 283 | 55 | 56.6 | 1.0291 | 1.0291 | 0 | 0 | 56.6 | 0 | 56.6 | 63
| 3 | MW Roller | hr | P | 1 | 275 | 283 | 55 | 56.6 | 1.0291 | 1.0291 | 0 | 0 | 56.6 | 0 | 56.6 | 63
| 4 | Water Cart - Hire | hr | P | 1 | 275 | 283 | 95 | 97.7636 | 1.0291 | 1.0291 | 0 | 0 | 97.7636 | 0 | 97.7636 | 63
| 5 | Labour | hr | L | 3 | 275 | 283 | 51.9 | 160.2295 | 3.0873 | 1.0291 | 160.2295 | 0 | 0 | 0 | 160.2295 | 63
| 6 | Bobcat | hr | P | 1 | 825 | 283 | 95 | 32.5879 | 0.34303 | 0.34303 | 0 | 0 | 32.5879 | 0 | 32.5879 | 63
| 7 | Tipper | hr | P | 1 | 825 | 283 | 90 | 30.8727 | 0.34303 | 0.34303 | 0 | 0 | 30.8727 | 0 | 30.8727 | 63
127 | Line No 238 Item No (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | m2 |  |  |  | 597 |  | 1264.2651 |  | 1 | 338.0105 | 0 | 926.2545 | 0 | 1264.2651
127.1 | 1 | Grader | hr | P | 1 | 275 | 597 | 160 | 347.3455 | 2.1709 | 2.1709 | 0 | 0 | 347.3455 | 0 | 347.3455 | 63
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 275 | 597 | 55 | 119.4 | 2.1709 | 2.1709 | 0 | 0 | 119.4 | 0 | 119.4 | 63
| 3 | MW Roller | hr | P | 1 | 275 | 597 | 55 | 119.4 | 2.1709 | 2.1709 | 0 | 0 | 119.4 | 0 | 119.4 | 63
| 4 | Water Cart - Hire | hr | P | 1 | 275 | 597 | 95 | 206.2364 | 2.1709 | 2.1709 | 0 | 0 | 206.2364 | 0 | 206.2364 | 63
| 5 | Labour | hr | L | 3 | 275 | 597 | 51.9 | 338.0105 | 6.5127 | 2.1709 | 338.0105 | 0 | 0 | 0 | 338.0105 | 63
| 6 | Bobcat | hr | P | 1 | 825 | 597 | 95 | 68.7455 | 0.72364 | 0.72364 | 0 | 0 | 68.7455 | 0 | 68.7455 | 63
| 7 | Tipper | hr | P | 1 | 825 | 597 | 90 | 65.1273 | 0.72364 | 0.72364 | 0 | 0 | 65.1273 | 0 | 65.1273 | 63
Line No 239 Item No
| Line No 240 Item No 6 | Gravel Pavement
| Line No 241 Item No | In Place complete, including supply, spreading, watering, rolling and trimming:-
| Line No 242 Item No (a) | Dysart Bypass Rd - Golden Mile Rd Intersection LHS
128 | Line No 243 Item No (i) | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | m3 |  |  |  | 46 |  | 4914.2737 |  | 1 | 252.4663 | 3648.375 | 1013.4324 | 0 | 4914.2737
| 1 | CBR80 | tonne | M | 1 | 1 | 108.1 | 33.75 | 3648.375 |  |  | 0 | 3648.375 | 0 | 0 | 3648.375 | QM2.3
128.1 | 2 | Grader | hr | P | 1 | 66.667 | 108.1 | 160 | 259.4387 | 1.6215 | 1.6215 | 0 | 0 | 259.4387 | 0 | 259.4387 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 108.1 | 55 | 89.1821 | 1.6215 | 1.6215 | 0 | 0 | 89.1821 | 0 | 89.1821 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 108.1 | 95 | 154.0417 | 1.6215 | 1.6215 | 0 | 0 | 154.0417 | 0 | 154.0417 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 108.1 | 51.9 | 252.4663 | 4.8645 | 1.6215 | 252.4663 | 0 | 0 | 0 | 252.4663 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 108.1 | 135 | 218.9014 | 1.6215 | 1.6215 | 0 | 0 | 218.9014 | 0 | 218.9014 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 108.1 | 90 | 291.8685 | 3.243 | 1.6215 | 0 | 0 | 291.8685 | 0 | 291.8685 | 62
129 | Line No 244 Item No (ii) | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 |  |  |  | 72 |  | 7480.4067 |  | 1 | 395.1646 | 5499 | 1586.2421 | 0 | 7480.4067
| 1 | CBR45 | tonne | M | 1 | 1 | 169.2 | 32.5 | 5499 |  |  | 0 | 5499 | 0 | 0 | 5499 | QM2.3
129.1 | 2 | Grader | hr | P | 1 | 66.667 | 169.2 | 160 | 406.078 | 2.538 | 2.538 | 0 | 0 | 406.078 | 0 | 406.078 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 169.2 | 55 | 139.5893 | 2.538 | 2.538 | 0 | 0 | 139.5893 | 0 | 139.5893 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 169.2 | 95 | 241.1088 | 2.538 | 2.538 | 0 | 0 | 241.1088 | 0 | 241.1088 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 169.2 | 51.9 | 395.1646 | 7.614 | 2.538 | 395.1646 | 0 | 0 | 0 | 395.1646 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 169.2 | 135 | 342.6283 | 2.538 | 2.538 | 0 | 0 | 342.6283 | 0 | 342.6283 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 169.2 | 90 | 456.8377 | 5.076 | 2.538 | 0 | 0 | 456.8377 | 0 | 456.8377 | 62
130 | Line No 245 Item No (iii) | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 |  |  |  | 62 |  | 6310.3313 |  | 1 | 340.2806 | 4604.12 | 1365.9307 | 0 | 6310.3313
| 1 | CBR15 | tonne | M | 1 | 1 | 145.7 | 31.6 | 4604.12 |  |  | 0 | 4604.12 | 0 | 0 | 4604.12 | QM2.3
130.1 | 2 | Grader | hr | P | 1 | 66.667 | 145.7 | 160 | 349.6783 | 2.1855 | 2.1855 | 0 | 0 | 349.6783 | 0 | 349.6783 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 145.7 | 55 | 120.2019 | 2.1855 | 2.1855 | 0 | 0 | 120.2019 | 0 | 120.2019 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 145.7 | 95 | 207.6215 | 2.1855 | 2.1855 | 0 | 0 | 207.6215 | 0 | 207.6215 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 145.7 | 51.9 | 340.2806 | 6.5565 | 2.1855 | 340.2806 | 0 | 0 | 0 | 340.2806 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 145.7 | 135 | 295.041 | 2.1855 | 2.1855 | 0 | 0 | 295.041 | 0 | 295.041 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 145.7 | 90 | 393.388 | 4.371 | 2.1855 | 0 | 0 | 393.388 | 0 | 393.388 | 62
| Line No 246 Item No (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS
131 | Line No 247 Item No (i) | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | m3 |  |  |  | 95 |  | 10149.0436 |  | 1 | 521.3978 | 7534.6875 | 2092.9583 | 0 | 10149.0436
| 1 | CBR80 | tonne | M | 1 | 1 | 223.25 | 33.75 | 7534.6875 |  |  | 0 | 7534.6875 | 0 | 0 | 7534.6875 | QM2.3
131.1 | 2 | Grader | hr | P | 1 | 66.667 | 223.25 | 160 | 535.7973 | 3.3487 | 3.3487 | 0 | 0 | 535.7973 | 0 | 535.7973 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 223.25 | 55 | 184.1803 | 3.3487 | 3.3487 | 0 | 0 | 184.1803 | 0 | 184.1803 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 223.25 | 95 | 318.1297 | 3.3487 | 3.3487 | 0 | 0 | 318.1297 | 0 | 318.1297 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 223.25 | 51.9 | 521.3978 | 10.0462 | 3.3487 | 521.3978 | 0 | 0 | 0 | 521.3978 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 223.25 | 135 | 452.079 | 3.3487 | 3.3487 | 0 | 0 | 452.079 | 0 | 452.079 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 223.25 | 90 | 602.772 | 6.6975 | 3.3487 | 0 | 0 | 602.772 | 0 | 602.772 | 62
132 | Line No 248 Item No (ii) | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 |  |  |  | 143 |  | 14856.9188 |  | 1 | 784.8409 | 10921.625 | 3150.453 | 0 | 14856.9188
| 1 | CBR45 | tonne | M | 1 | 1 | 336.05 | 32.5 | 10921.625 |  |  | 0 | 10921.625 | 0 | 0 | 10921.625 | QM2.3
132.1 | 2 | Grader | hr | P | 1 | 66.667 | 336.05 | 160 | 806.516 | 5.0407 | 5.0407 | 0 | 0 | 806.516 | 0 | 806.516 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 336.05 | 55 | 277.2399 | 5.0407 | 5.0407 | 0 | 0 | 277.2399 | 0 | 277.2399 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 336.05 | 95 | 478.8689 | 5.0407 | 5.0407 | 0 | 0 | 478.8689 | 0 | 478.8689 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 336.05 | 51.9 | 784.8409 | 15.1222 | 5.0407 | 784.8409 | 0 | 0 | 0 | 784.8409 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 336.05 | 135 | 680.4978 | 5.0407 | 5.0407 | 0 | 0 | 680.4978 | 0 | 680.4978 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 336.05 | 90 | 907.3305 | 10.0814 | 5.0407 | 0 | 0 | 907.3305 | 0 | 907.3305 | 62
133 | Line No 249 Item No (iii) | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 |  |  |  | 119 |  | 12111.765 |  | 1 | 653.1193 | 8836.94 | 2621.7056 | 0 | 12111.765
| 1 | CBR15 | tonne | M | 1 | 1 | 279.65 | 31.6 | 8836.94 |  |  | 0 | 8836.94 | 0 | 0 | 8836.94 | QM2.3
133.1 | 2 | Grader | hr | P | 1 | 66.667 | 279.65 | 160 | 671.1566 | 4.1947 | 4.1947 | 0 | 0 | 671.1566 | 0 | 671.1566 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.667 | 279.65 | 55 | 230.7101 | 4.1947 | 4.1947 | 0 | 0 | 230.7101 | 0 | 230.7101 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.667 | 279.65 | 95 | 398.4993 | 4.1947 | 4.1947 | 0 | 0 | 398.4993 | 0 | 398.4993 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 279.65 | 51.9 | 653.1193 | 12.5842 | 4.1947 | 653.1193 | 0 | 0 | 0 | 653.1193 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.667 | 279.65 | 135 | 566.2884 | 4.1947 | 4.1947 | 0 | 0 | 566.2884 | 0 | 566.2884 | 62
| 8 | Tipper | hr | P | 2 | 66.667 | 279.65 | 90 | 755.0512 | 8.3895 | 4.1947 | 0 | 0 | 755.0512 | 0 | 755.0512 | 62
Line No 250 Item No
| Line No 251 Item No 7 | Provisional Item Pavement Repairs
134 | Line No 252 Item No (a) | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | m2 |  |  |  | 30 |  | 5610.0655 |  | 2 | 0 | 162.0006 | 5448.0648 | 0 | 5610.0655
134.1 | 1 | Stabilising |  | P | 1 | 3.333 | 30 | 605.28 | 5448.0648 | 9.0009 | 9.0009 | 0 | 0 | 5448.0648 | 0 | 5448.0648 | 68
| 2 | Cement | tonne | M | 1 | 1 | 0.36 | 450 | 162.0006 |  |  | 0 | 162.0006 | 0 | 0 | 162.0006 | CSA
Line No 253 Item No
| Line No 254 Item No 8 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED
135 | Line No 255 Item No (a) | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | m2 |  |  |  | 283 |  | 1525.37 |  | 1 | 0 | 0 | 0 | 1525.37 | 1525.37
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 311.3 | 4.9 | 1525.37 | 311.3 | 311.3 | 0 | 0 | 0 | 1525.37 | 1525.37 | 64
136 | Line No 256 Item No (b) | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection RHS | m2 |  |  |  | 597 |  | 3217.83 |  | 1 | 0 | 0 | 0 | 3217.83 | 3217.83
| 1 | Primer Seal - 10mm | m² | S | 1 | 1 | 656.7 | 4.9 | 3217.83 | 656.7 | 656.7 | 0 | 0 | 0 | 3217.83 | 3217.83 | 64
Line No 257 Item No
| Line No 258 Item No 9 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place.
137 | Line No 259 Item No (a) | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Golden Mile Rd Intersection Complete (overlaying existing seal area) | m2 |  |  |  | 2912 |  | 121115.2984 |  | 2 | 0 | 0 | 0 | 121115.2984 | 121115.2984
| 1 | 60mm AC | tonne | S | 1 | 1 | 436.7978 | 277.28 | 121115.2984 | 436.7978 | 436.7978 | 0 | 0 | 0 | 121115.2984 | 121115.2984 | 65
Line No 260 Item No
| Line No 261 Item No 10 | Medians Kerb at Intersections
138 | Line No 262 Item No (a) | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | m |  |  |  | 67 |  | 5701.1988 |  | 1 | 0 | 2686.1988 | 0 | 3015 | 5701.1988
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 7.2043 | 309 | 2226.1287 |  |  | 0 | 2226.1287 | 0 | 0 | 2226.1287 | CKM
| 2 | Sand | tonne | M | 1 | 1 | 4.4667 | 28 | 125.0676 |  |  | 0 | 125.0676 | 0 | 0 | 125.0676 | QMS | y
| 3 | Cement - 20 kg Bags | each | M | 1 | 1 | 22.3335 | 15 | 335.0025 |  |  | 0 | 335.0025 | 0 | 0 | 335.0025 | 71
| 4 | Kerb Subbie | m | S | 1 | 1 | 67 | 45 | 3015 | 67 | 67 | 0 | 0 | 0 | 3015 | 3015 | 71
Line No 263 Item No
| Line No 264 Item No 11 | Street Lighting - Conduits and Bases
139 | Line No 265 Item No (a) | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | m |  |  |  | 78 |  | 2770.989 |  | 1 | 485.784 | 1718.925 | 566.28 | 0 | 2770.989
| 1 | 125 LD uPVC Electrical | m | M | 1 | 1 | 78 | 8 | 624 |  |  | 0 | 624 | 0 | 0 | 624 | ETC
| 2 | Draw Rope - Conduits | m | M | 1 | 1 | 97.5 | 0.11 | 10.725 |  |  | 0 | 10.725 | 0 | 0 | 10.725 | ETC
| 3 | Hard Cover - Electrical | m | M | 1 | 1 | 78 | 2.7 | 210.6 |  |  | 0 | 210.6 | 0 | 0 | 210.6 | ETC
| 4 | Sand | tonne | M | 1 | 1 | 31.2 | 28 | 873.6 |  |  | 0 | 873.6 | 0 | 0 | 873.6 | QMS | y
139.1 | 5 | Excavator - 25T | hr | P | 1 | 25 | 78 | 135 | 421.2 | 3.12 | 3.12 | 0 | 0 | 421.2 | 0 | 421.2 | 111
| 6 | CAT297 | hr | P | 1 | 25 | 78 | 46.5 | 145.08 | 3.12 | 3.12 | 0 | 0 | 145.08 | 0 | 145.08 | 111
| 7 | Labour | hr | L | 3 | 25 | 78 | 51.9 | 485.784 | 9.36 | 3.12 | 485.784 | 0 | 0 | 0 | 485.784 | 111
140 | Line No 266 Item No (b) | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | m |  |  |  | 22 |  | 3860 |  | 3 | 0 | 0 | 0 | 3860 | 3860
| 1 | Underbore | m | S | 1 | 1 | 22 | 130 | 2860 | 22 | 22 | 0 | 0 | 0 | 2860 | 2860 | 111
| 2 | Underbore Estab | Item | S | 1 | 1 | 1 | 1000 | 1000 | 1 | 1 | 0 | 0 | 0 | 1000 | 1000 | 111
141 | Line No 267 Item No (c) | Electrical Mains Cable Pit (Provisional Item) | No |  |  |  | 2 |  | 2452.8 |  | 1 | 622.8 | 1560 | 270 | 0 | 2452.8
| 1 | Type 7 Elec Pit | each | M | 1 | 1 | 2 | 780 | 1560 |  |  | 0 | 1560 | 0 | 0 | 1560 | ETP
| 2 | Excavator - 25T | hr | P | 1 | 1 | 2 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 111
141.1 | 3 | Labour | hr | L | 3 | 0.5 | 2 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 111
142 | Line No 268 Item No (d) | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | No |  |  |  | 2 |  | 2690.8 |  | 1 | 622.8 | 1528 | 540 | 0 | 2690.8
| 1 | Supply of Materials
| 2 | Rag Bolt | each | M | 1 | 1 | 2 | 425 | 850 |  |  | 0 | 850 | 0 | 0 | 850 | ETC
| 3 | N32 | m³ | M | 1 | 1 | 2 | 309 | 618 |  |  | 0 | 618 | 0 | 0 | 618 | C32
| 4 | 50 HD uPVC Electrical | m | M | 10 | 1 | 2 | 3 | 60 |  |  | 0 | 60 | 0 | 0 | 60 | ETC
| 5 | Installation
| 6 | Allow 2 hours per footing to set up and pour.
142.1 | 7 | Excavator - 25T | hr | P | 1 | 0.5 | 2 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 111
| 8 | Labour | hr | L | 3 | 0.5 | 2 | 51.9 | 622.8 | 12 | 4 | 622.8 | 0 | 0 | 0 | 622.8 | 111
Line No 269 Item No
| Line No 270 Item No 12 | Soil Management Measures inclusive of:
143 | Line No 271 Item No (a) | Soil Management Measures inclusive of: - Prepare batters and drains for hydromulch placement | m2 |  |  |  | 1000 |  | 767.25 |  | 1 | 129.75 | 0 | 637.5 | 0 | 767.25
143.1 | 1 | Grader | hr | P | 1 | 400 | 1000 | 160 | 400 | 2.5 | 2.5 | 0 | 0 | 400 | 0 | 400 | 59
| 2 | Water Cart - Hire | hr | P | 1 | 400 | 1000 | 95 | 237.5 | 2.5 | 2.5 | 0 | 0 | 237.5 | 0 | 237.5 | 59
| 3 | Labour | hr | L | 1 | 400 | 1000 | 51.9 | 129.75 | 2.5 | 2.5 | 129.75 | 0 | 0 | 0 | 129.75 | 59
144 | Line No 272 Item No (b) | Hydromulch to all disturbed areas as directed (batters & drains) | m2 |  |  |  | 1000 |  | 1125 |  | 1 | 0 | 0 | 190 | 935 | 1125
| 1 | Hydromulch Subbie | m² | S | 1 | 1 | 1100 | 0.85 | 935 | 1100 | 1100 | 0 | 0 | 0 | 935 | 935 | 121
144.1 | 2 | Water Cart - Hire | hr | P | 1 | 550 | 1100 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 121
145 | Line No 273 Item No (c) | Rock check dams as directed | No |  |  |  | 6 |  | 1626.4 |  | 1 | 311.4 | 945 | 370 | 0 | 1626.4
| 1 | Gabion Rock | tonne | M | 1 | 1 | 27 | 35 | 945 |  |  | 0 | 945 | 0 | 0 | 945 | QMR
145.1 | 2 | Bobcat | hr | P | 1 | 3 | 6 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
| 3 | Labour | hr | L | 3 | 3 | 6 | 51.9 | 311.4 | 6 | 2 | 311.4 | 0 | 0 | 0 | 311.4 | 81
| 4 | Tipper | hr | P | 1 | 3 | 6 | 90 | 180 | 2 | 2 | 0 | 0 | 180 | 0 | 180 | 81
| Line No 275 Item No 13 | Road Furniture
146 | Line No 276 Item No (a) | Supply and Install New Guide Posts | No |  |  |  | 10 |  | 500 |  | 1 | 0 | 500 | 0 | 0 | 500
| 1 | Guide Post | each | M | 1 | 1 | 10 | 50 | 500 |  |  | 0 | 500 | 0 | 0 | 500 | 67
147 | Line No 277 Item No (b) | Supply and Install New Give Way Sign R1-2 | No |  |  |  | 1 |  | 338.8 |  | 1 | 103.8 | 140 | 95 | 0 | 338.8
| 1 | Signs Complete | each | M | 1 | 1 | 1 | 140 | 140 |  |  | 0 | 140 | 0 | 0 | 140 | 67
147.1 | 2 | Bobcat | hr | P | 1 | 1 | 1 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 67
| 3 | Labour | hr | L | 2 | 1 | 1 | 51.9 | 103.8 | 2 | 1 | 103.8 | 0 | 0 | 0 | 103.8 | 67
148 | Line No 278 Item No (c) | Linemarking Complete,Dysart Bypass Rd - Golden Mile Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | Item |  |  |  | 1 |  | 7500 |  | 1 | 0 | 0 | 0 | 7500 | 7500
| 1 | Line Marking | m² | S | 1 | 1 | 7500 | 1 | 7500 | 7500 | 7500 | 0 | 0 | 0 | 7500 | 7500 | 66
| Line No. | Comment | Unit | Type | No | Production | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
149 | PV01 | PV01 - Revised Tender Rates - Seal & Asphalt | item |  |  |  | 1 |  | 35549.91 |  | 0 | 0 | 0 | 0 | 35549.91 | 35549.91
149.1 | 1 | E/0 Primer Seal - 10mm | m² | S | 1 | 1 | 2280 | 0.52 | 1185.6 |  | 0 | 0 | 0 | 0 | 1185.6 | 1185.6 | 64
149.2 | 2 | E/O First Seal | m² | S | 1 | 1 | 4361 | 0.66 | 2878.26 |  | 0 | 0 | 0 | 0 | 2878.26 | 2878.26 | 64
149.3 | 3 | E/O Second Seal | m² | S | 1 | 1 | 18501 | 0.45 | 8325.45 |  | 0 | 0 | 0 | 0 | 8325.45 | 8325.45 | 64
149.4 | 4 | E/O DG10 AC | m² | S | 1 | 1 | 1260 | 2.13 | 2683.8 |  | 0 | 0 | 0 | 0 | 2683.8 | 2683.8 | 65
149.5 | 5 | E/O DG14 AC | m² | S | 1 | 1 | 5688 | 3.6 | 20476.8 |  | 0 | 0 | 0 | 0 | 20476.8 | 20476.8 | 66
150 | PV02 | PV02 - Revised pavement design | Item |  |  |  | 1 |  | -416088.2822 |  | 0 | 19944.1255 | -550329.2675 | -14963.4202 | 129260.28 | -416088.2822
This Variation is to Revise the pavement design to a 200mm full width overlay, mixed to a depth of 300mm incorporating the top 100mm of existing poavement using Principal supplied material. Contractor to load and cart material from Principal's quarry.
|  | REMOVE GRAVEL SUPPLY: | [6 empty] | -266089.6 |  |  | 0 | -266089.6 | 0 | 0 | -266089.6
Items to be removed from Schedule A: - Principal will supply all gravel - these rates are supply component of gravel only:
150.1 |  | CBR80 | t | M | 1 | 1 | -2708 | 33.75 | -91395 |  | 0 | 0 | -91395 | 0 | 0 | -91395 | QM2.3
150.2 |  | CBR45 | t | M | 1 | 1 | -4470 | 32.5 | -145275 |  | 0 | 0 | -145275 | 0 | 0 | -145275 | QM2.3
150.3 |  | CBR15 | t | M | 1 | 1 | -931 | 31.6 | -29419.6 |  | 0 | 0 | -29419.6 | 0 | 0 | -29419.6 | QM2.3
Items to be removed from Schedule:
REMOVE THIS ITEM: - Earthworks - excavate and place as embankment as directed
151 | PV02.1 | Earthworks - excavate and place as embankment as directed - Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will be spoiled at IRC Tip | m3 |  |  |  | -2804 |  | -28211.352 |  |  | -1976.352 | 0 | -26235 | 0 | -28211.352
| 1 | Cut Embankment
151.1 | 2 | Excavator - 25T | hr | P | 1 | 50 | -2804 | 135 | -7570.8 |  | 0 | 0 | 0 | -7570.8 | 0 | -7570.8 | 53
| 3 | Tipper | hr | P | 3 | 50 | -2804 | 90 | -15141.6 |  | 0 | 0 | 0 | -15141.6 | 0 | -15141.6 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 50 | -2804 | 95 | -5327.6 |  | 0 | 0 | 0 | -5327.6 | 0 | -5327.6 | 53
| 5 | Labour | hr | L | 1 | 50 | -2804 | 51.9 | -2910.552 |  | 0 | -2910.552 | 0 | 0 | 0 | -2910.552 | 53
| 6 | Fill Where Required | [8 empty] | 0
| 7 | PF Roller | day | P | 1 | 225 | 225 | 365 | 365 |  | 0 | 0 | 0 | 365 | 0 | 365 | 53
| 8 | Grader | hr | P | 1 | 25 | 225 | 160 | 1440 |  | 0 | 0 | 0 | 1440 | 0 | 1440 | 53
| 9 | Labour | hr | L | 2 | 25 | 225 | 51.9 | 934.2 |  | 0 | 934.2 | 0 | 0 | 0 | 934.2 | 53
152 | PV02.2 | REMOVE THIS ITEM: - Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 |  |  |  | -40 |  | -2514.8 |  |  | -622.8 | 0 | -1892 | 0 | -2514.8
152.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | -40 | 135 | -540 |  | 0 | 0 | 0 | -540 | 0 | -540 | 57
| 2 | Tipper | hr | P | 1 | 10 | -40 | 90 | -360 |  | 0 | 0 | 0 | -360 | 0 | -360 | 57
| 3 | PF Roller Wet - No OP | hr | P | 1 | 10 | -40 | 58 | -232 |  | 0 | 0 | 0 | -232 | 0 | -232 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 10 | -40 | 95 | -380 |  | 0 | 0 | 0 | -380 | 0 | -380 | 57
| 5 | Labour | hr | L | 3 | 10 | -40 | 51.9 | -622.8 |  | 0 | -622.8 | 0 | 0 | 0 | -622.8 | 57
| 6 | Bobcat | hr | P | 1 | 10 | -40 | 95 | -380 |  | 0 | 0 | 0 | -380 | 0 | -380 | 57
153 | PV02.3 | REMOVE THIS ITEM: - Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | m3 |  |  |  | -423 |  | -9338.148 |  |  | -878.148 | 0 | -8460 | 0 | -9338.148
| 1 | Cut Embankment
153.1 | 2 | Excavator - 25T | hr | P | 1 | 25 | -423 | 135 | -2284.2 |  | 0 | 0 | 0 | -2284.2 | 0 | -2284.2 | 53
| 3 | Tipper | hr | P | 3 | 25 | -423 | 90 | -4568.4 |  | 0 | 0 | 0 | -4568.4 | 0 | -4568.4 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 25 | -423 | 95 | -1607.4 |  | 0 | 0 | 0 | -1607.4 | 0 | -1607.4 | 53
| 5 | Labour | hr | L | 1 | 25 | -423 | 51.9 | -878.148 |  | 0 | -878.148 | 0 | 0 | 0 | -878.148 | 53
REMOVE THIS ITEM: - Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
154 | PV02.4 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | m2 |  |  |  | -11270 |  | -32985.4117 |  |  | -8773.695 | 0 | -24211.7167 | 0 | -32985.4117
154.1 | 1 | Grader | hr | P | 1 | 200 | -11270 | 160 | -9016 |  | 0 | 0 | 0 | -9016 | 0 | -9016 | 61
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | -11270 | 55 | -3099.25 |  | 0 | 0 | 0 | -3099.25 | 0 | -3099.25 | 61
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | -11270 | 58 | -3268.3 |  | 0 | 0 | 0 | -3268.3 | 0 | -3268.3 | 61
| 4 | Water Cart - Hire | hr | P | 1 | 200 | -11270 | 95 | -5353.25 |  | 0 | 0 | 0 | -5353.25 | 0 | -5353.25 | 61
| 5 | Labour | hr | L | 3 | 200 | -11270 | 51.9 | -8773.695 |  | 0 | -8773.695 | 0 | 0 | 0 | -8773.695 | 61
| 6 | Bobcat | hr | P | 1 | 600 | -11270 | 95 | -1784.4167 |  | 0 | 0 | 0 | -1784.4167 | 0 | -1784.4167 | 61
| 7 | Tipper | hr | P | 1 | 600 | -11270 | 90 | -1690.5 |  | 0 | 0 | 0 | -1690.5 | 0 | -1690.5 | 61
REMOVE THIS ITEM: - Gravel Pavement
In Place complete, including supply, spreading, watering, rolling and trimming:-
(a) Bypass Road Widening Ch 18 to Ch 2801
155 | PV02.5 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - QT Type 2.1 @ 150mm deep x widening area | m3 |  |  |  | -1231 |  | -131510.4074 |  |  | -6756.2512 | -97633.6875 | -27120.4687 | 0 | -131510.4074
| 1 | CBR80 | tonne | M | 1 | 1 | -2892.85 | 33.75 | -97633.6875 |  |  | 0 | -97633.6875 | 0 | 0 | -97633.6875 | QM2.3
155.1 | 2 | Grader | hr | P | 1 | 66.6667 | -2892.85 | 160 | -6942.84 |  | 0 | 0 | 0 | -6942.84 | 0 | -6942.84 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.6667 | -2892.85 | 55 | -2386.6012 |  | 0 | 0 | 0 | -2386.6012 | 0 | -2386.6012 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.6667 | -2892.85 | 95 | -4122.3112 |  | 0 | 0 | 0 | -4122.3112 | 0 | -4122.3112 | 62
| 5 | Labour | hr | L | 3 | 66.6667 | -2892.85 | 51.9 | -6756.2512 |  | 0 | -6756.2512 | 0 | 0 | 0 | -6756.2512 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.6667 | -2892.85 | 135 | -5858.0212 |  | 0 | 0 | 0 | -5858.0212 | 0 | -5858.0212 | 62
| 8 | Tipper | hr | P | 2 | 66.6667 | -2892.85 | 90 | -7810.695 |  | 0 | 0 | 0 | -7810.695 | 0 | -7810.695 | 62
156 | PV02.6 | REMOVE THIS ITEM: - Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 -Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | m3 |  |  |  | -2032 |  | -211113.9796 |  |  | -11152.4796 | -155194 | -44767.5 | 0 | -211113.9796
| 1 | CBR45 | tonne | M | 1 | 1 | -4775.2 | 32.5 | -155194 |  |  | 0 | -155194 | 0 | 0 | -155194 | QM2.3
156.1 | 2 | Grader | hr | P | 1 | 66.6667 | -4775.2 | 160 | -11460.48 |  | 0 | 0 | 0 | -11460.48 | 0 | -11460.48 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 66.6667 | -4775.2 | 55 | -3939.54 |  | 0 | 0 | 0 | -3939.54 | 0 | -3939.54 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 66.6667 | -4775.2 | 95 | -6804.66 |  | 0 | 0 | 0 | -6804.66 | 0 | -6804.66 | 62
| 5 | Labour | hr | L | 3 | 66.6667 | -4775.2 | 51.9 | -11152.4796 |  | 0 | -11152.4796 | 0 | 0 | 0 | -11152.4796 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 66.6667 | -4775.2 | 135 | -9669.78 |  | 0 | 0 | 0 | -9669.78 | 0 | -9669.78 | 62
| 8 | Tipper | hr | P | 2 | 66.6667 | -4775.2 | 90 | -12893.04 |  | 0 | 0 | 0 | -12893.04 | 0 | -12893.04 | 62
157 | PV02.7 | REMOVE THIS ITEM: - Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of length - Only if ordered by the Superintendent | m3 |  |  |  | -423 |  | -48873.2138 |  |  | -3482.4057 | -31411.98 | -13978.8281 | 0 | -48873.2138
| 1 | CBR15 | tonne | M | 1 | 1 | -994.05 | 31.6 | -31411.98 |  |  | 0 | -31411.98 | 0 | 0 | -31411.98 | QM2.3
157.1 | 2 | Grader | hr | P | 1 | 44.4444 | -994.05 | 160 | -3578.58 |  | 0 | 0 | 0 | -3578.58 | 0 | -3578.58 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 44.4444 | -994.05 | 55 | -1230.1369 |  | 0 | 0 | 0 | -1230.1369 | 0 | -1230.1369 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 44.4444 | -994.05 | 95 | -2124.7819 |  | 0 | 0 | 0 | -2124.7819 | 0 | -2124.7819 | 62
| 5 | Labour | hr | L | 3 | 44.4444 | -994.05 | 51.9 | -3482.4057 |  | 0 | -3482.4057 | 0 | 0 | 0 | -3482.4057 | 62
| 6 | Gravel will be transported to stockpile. Allow for double handling
| 7 | Excavator - 25T | hr | P | 1 | 44.4444 | -994.05 | 135 | -3019.4269 |  | 0 | 0 | 0 | -3019.4269 | 0 | -3019.4269 | 62
| 8 | Tipper | hr | P | 2 | 44.4444 | -994.05 | 90 | -4025.9025 |  | 0 | 0 | 0 | -4025.9025 | 0 | -4025.9025 | 62
ADD THIS ITEM: - Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
158 | PV02.4 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | m2 |  |  |  | 11455 | 2.9268 | 33526.8758 |  |  | 8917.7175 | 0 | 24609.1583 | 0 | 33526.8758
158.1 | 1 | Grader | hr | P | 1 | 200 | 11455 | 160 | 9164 |  | 0 | 0 | 0 | 9164 | 0 | 9164 | 61
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 11455 | 55 | 3150.125 |  | 0 | 0 | 0 | 3150.125 | 0 | 3150.125 | 61
| 3 | PF Roller Wet - No OP | hr | P | 1 | 200 | 11455 | 58 | 3321.95 |  | 0 | 0 | 0 | 3321.95 | 0 | 3321.95 | 61
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 11455 | 95 | 5441.125 |  | 0 | 0 | 0 | 5441.125 | 0 | 5441.125 | 61
| 5 | Labour | hr | L | 3 | 200 | 11455 | 51.9 | 8917.7175 |  | 0 | 8917.7175 | 0 | 0 | 0 | 8917.7175 | 61
| 6 | Bobcat | hr | P | 1 | 600 | 11455 | 95 | 1813.7083 |  | 0 | 0 | 0 | 1813.7083 | 0 | 1813.7083 | 61
| 7 | Tipper | hr | P | 1 | 600 | 11455 | 90 | 1718.25 |  | 0 | 0 | 0 | 1718.25 | 0 | 1718.25 | 61
159 | PV02.7 | ADD THIS ITEM: - Gravel Pavement Base In Place complete, 200 mm OVERLAY - PRINCIPAL SUPPLIED GRAVEL, spreading, MIXING TO 300 mm DEPTH, watering, rolling and trimming: | m3 |  |  |  | 4842 | 39.3427 | 190497.4744 |  |  | 44668.5394 | 0 | 107092.935 | 38736 | 190497.4744
| 1 | Gravel Cartage | m3 | S | 1 | 1 | 4842 | 8 | 38736 |  | 0 | 0 | 0 | 0 | 38736 | 38736 | QM2.3
159.1 | 2 | Grader | hr | P | 1 | 200 | 11378.7 | 160 | 9102.96 |  | 0 | 0 | 0 | 9102.96 | 0 | 9102.96 | 62
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 11378.7 | 55 | 3129.1425 |  | 0 | 0 | 0 | 3129.1425 | 0 | 3129.1425 | 62
| 4 | Water Cart - Hire | hr | P | 1 | 200 | 11378.7 | 95 | 5404.8825 |  | 0 | 0 | 0 | 5404.8825 | 0 | 5404.8825 | 62
| 5 | Labour | hr | L | 3 | 200 | 11378.7 | 51.9 | 8858.318 |  | 0 | 8858.318 | 0 | 0 | 0 | 8858.318 | 62
| 6 | Gravel will be mixed to a depth of 300mm, incorporating top 100mm of existing pavement.
159.2 | 7 | WS220 | day | P | 1 | 2000 | 24210 | 1500 | 18157.5 |  | 0 | 0 | 0 | 18157.5 | 0 | 18157.5 | 62
| 8 | Water Cart - Hire | hr | P | 1 | 222.2222 | 24210 | 95 | 10349.775 |  | 0 | 0 | 0 | 10349.775 | 0 | 10349.775 | 62
| 9 | Grader | hr | P | 1 | 222.2222 | 24210 | 160 | 17431.2 |  | 0 | 0 | 0 | 17431.2 | 0 | 17431.2 | 62
| 10 | SD Roller - Wet (No Op) | hr | P | 1 | 222.2222 | 24210 | 55 | 5991.975 |  | 0 | 0 | 0 | 5991.975 | 0 | 5991.975 | 62
| 11 | Labour | hr | L | 3 | 222.2222 | 24210 | 51.9 | 16962.7365 |  | 0 | 16962.7365 | 0 | 0 | 0 | 16962.7365 | 62
Trim & Prepare for seal:
159.3 | 12 | Grader | hr | P | 1 | 200 | 24210 | 160 | 19368 |  | 0 | 0 | 0 | 19368 | 0 | 19368 | 63
| 13 | Water Cart - Hire | hr | P | 1 | 200 | 24210 | 95 | 11499.75 |  | 0 | 0 | 0 | 11499.75 | 0 | 11499.75 | 63
| 14 | SD Roller - Wet (No Op) | hr | P | 1 | 200 | 24210 | 55 | 6657.75 |  | 0 | 0 | 0 | 6657.75 | 0 | 6657.75 | 63
| 15 | Labour | hr | L | 3 | 200 | 24210 | 51.9 | 18847.485 |  | 0 | 18847.485 | 0 | 0 | 0 | 18847.485 | 63
160 | PV02.8 | Bitumen Seal - complete in place (16mm primerseal ) Road Widening: | m2 |  |  |  | 14140 |  | 90524.28 |  |  | 0 | 0 | 0 | 90524.28 | 90524.28
| 1 | Primer Seal - 16mm | m² | S | 1 | 1 | 15554 | 5.82 | 90524.28 |  | 0 | 0 | 0 | 0 | 90524.28 | 90524.28 | 64
161 | PV03 | Remove & replace unsuitable | m3 |  |  |  | 63 |  | 3300.675 |  | 1 | 817.425 | 0 | 2483.25 | 0 | 3300.675
161.1 | 1 | Excavator - 25T | hr | P | 1 | 12 | 63 | 135 | 708.75 | 5.25 | 5.25 | 0 | 0 | 708.75 | 0 | 708.75 | 57
| 2 | Tipper | hr | P | 1 | 12 | 63 | 90 | 472.5 | 5.25 | 5.25 | 0 | 0 | 472.5 | 0 | 472.5 | 57
| 3 | PF Roller Wet - No OP | hr | P | 1 | 12 | 63 | 58 | 304.5 | 5.25 | 5.25 | 0 | 0 | 304.5 | 0 | 304.5 | 57
| 4 | Water Cart - Hire | hr | P | 1 | 12 | 63 | 95 | 498.75 | 5.25 | 5.25 | 0 | 0 | 498.75 | 0 | 498.75 | 57
| 5 | Labour | hr | L | 3 | 12 | 63 | 51.9 | 817.425 | 15.75 | 5.25 | 817.425 | 0 | 0 | 0 | 817.425 | 57
| 6 | Bobcat | hr | P | 1 | 12 | 63 | 95 | 498.75 | 5.25 | 5.25 | 0 | 0 | 498.75 | 0 | 498.75 | 57
162 | PV04 | Additional Drainage Items |  |  |  |  | 1 |  | 7048.884 |  |  | 1839.336 | 3239.548 | 1970 | 0 | 7048.884
163 | PV04.1 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | m |  |  |  | 2.44 |  | 4156.784 |  | 2 | 593.736 | 2133.048 | 1430 | 0 | 4156.784
| 1 | Purchase Materials
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 19.52 | 102.9 | 2008.608 |  |  | 0 | 2008.608 | 0 | 0 | 2008.608 | SWP
| 3 | Crusher Dust - Delivered | tonne | M | 1 | 1 | 4.88 | 25.5 | 124.44 |  |  | 0 | 124.44 | 0 | 0 | 124.44 | QMS | y
| 4 | Remove Existing Headwall
163.1 | 5 | Excavator - 25T | hr | P | 1 | 2.44 | 2.44 | 135 | 135 | 1 | 1 | 0 | 0 | 135 | 0 | 135 | 81
| 6 | Tipper | hr | P | 1 | 2.44 | 2.44 | 90 | 90 | 1 | 1 | 0 | 0 | 90 | 0 | 90 | 81
| 7 | Labour | hr | L | 1 | 2.44 | 2.44 | 51.9 | 51.9 | 1 | 1 | 51.9 | 0 | 0 | 0 | 51.9 | 81
| 8 | Place Bedding Sand
163.2 | 9 | Excavator - 25T | hr | P | 1 | 1.22 | 2.44 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 10 | Water Cart - Hire | hr | P | 1 | 2.44 | 2.44 | 95 | 95 | 1 | 1 | 0 | 0 | 95 | 0 | 95 | 81
| 11 | Install Pipe
163.3 | 12 | Excavator - 25T | hr | P | 1 | 1.22 | 2.44 | 135 | 270 | 2 | 2 | 0 | 0 | 270 | 0 | 270 | 81
| 13 | Labour | hr | L | 1 | 1 | 2.44 | 51.9 | 126.636 | 2.44 | 2.44 | 126.636 | 0 | 0 | 0 | 126.636 | 81
| 14 | Backfill & Compact
163.4 | 15 | Labour | hr | L | 1 | 0.305 | 2.44 | 51.9 | 415.2 | 8 | 8 | 415.2 | 0 | 0 | 0 | 415.2 | 81
| 16 | Bobcat | hr | P | 1 | 0.61 | 2.44 | 95 | 380 | 4 | 4 | 0 | 0 | 380 | 0 | 380 | 81
| 17 | Water Cart - Hire | hr | P | 1 | 1.22 | 2.44 | 95 | 190 | 2 | 2 | 0 | 0 | 190 | 0 | 190 | 81
164 | PV04.2 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No |  |  |  | 2 |  | 2892.1 |  | 1 | 1245.6 | 1106.5 | 540 | 0 | 2892.1
| 1 | N40 | m³ | M | 1 | 1 | 2.42 | 325 | 786.5 |  |  | 0 | 786.5 | 0 | 0 | 786.5 | C40
| 2 | Form Ply | m² | M | 1 | 1 | 12 | 10 | 120 |  |  | 0 | 120 | 0 | 0 | 120 | 72
| 3 | Form Boards | m | M | 1 | 1 | 40 | 5 | 200 |  |  | 0 | 200 | 0 | 0 | 200 | 72
164.1 | 4 | Labour | hr | L | 3 | 0.125 | 1 | 51.9 | 1245.6 | 24 | 8 | 1245.6 | 0 | 0 | 0 | 1245.6 | 72
| 5 | Excavator - 25T | hr | P | 1 | 0.25 | 1 | 135 | 540 | 4 | 4 | 0 | 0 | 540 | 0 | 540 | 72
165 | PV05 | Asphalt redesign at floodway ch510-651 |  |  |  |  | 32 |  | 8872.96 |  |  | 0 | 0 | 0 | 8872.96 | 8872.96
| 1 | 60mm AC | tonne | S | 1 | 1 | 32 | 277.28 | 8872.96 |  | 0 | 0 | 0 | 0 | 8872.96 | 8872.96 | 65
166 | PV06 | Corrector course asphalt dysart-middlemount intersection |  |  |  |  | 15.9 |  | 4408.752 |  |  | 0 | 0 | 0 | 4408.752 | 4408.752
| 1 | 60mm AC | tonne | S | 1 | 1 | 15.9 | 277.28 | 4408.752 |  | 0 | 0 | 0 | 0 | 4408.752 | 4408.752 | 65
167 | PV07 | Corrector course asphalt dysart-middlemount road (DMR section) |  |  |  |  | 35 |  | 9704.8 |  |  | 0 | 0 | 0 | 9704.8 | 9704.8
| 1 | 60mm AC | tonne | S | 1 | 1 | 35 | 277.28 | 9704.8 |  | 0 | 0 | 0 | 0 | 9704.8 | 9704.8 | 65
168 | PV08 | Cement Stabilise 4% by weight 200mm deep Bypass Road Edges | m2 |  |  |  | 3628 |  | 22336.2232 |  | 5 | 0 | 19591.2784 | 2744.9448 | 0 | 22336.2232
168.1 | 1 | Stabilising |  | P | 1 | 800 | 3628 | 605.28 | 2744.9448 | 4.535 | 4.535 | 0 | 0 | 2744.9448 | 0 | 2744.9448 | 68
| 2 | Cement | tonne | M | 1 | 1 | 43.5362 | 450 | 19591.2784 |  |  | 0 | 19591.2784 | 0 | 0 | 19591.2784 | CSA
PROJECT OVERHEADS
| Line No. | Comment | Unit | Type | No | Production | Quantity | Rate |  |  |  | Labour | Material | Plant | Subcontract | Total
9000 | Line No OH 1 Item No | Project Supervision |  |  |  |  | 15 |  | 50250 |  | 15 | 50250 | 0 | 0 | 0 | 50250
|  | Project Supervisor | week | L | 1 | 1 | 15 | 3350 | 50250 | 15 | 15 | 50250 | 0 | 0 | 0 | 50250 | 902
9005 | Line No OH 2 Item No | Project Engineering |  |  |  |  | 5 |  | 16250 |  | 5 | 16250 | 0 | 0 | 0 | 16250
|  | Project Engineer | week | L | 1 | 1 | 5 | 3250 | 16250 | 5 | 5 | 16250 | 0 | 0 | 0 | 16250 | 901
9010 | Line No OH 3 Item No | Site Facilities |  |  |  |  | 14 |  | 24500 |  | 14 | 0 | 0 | 24500 | 0 | 24500
| 1 | Crib Facilities | week | P | 1 | 1 | 14 | 1750 | 24500 | 14 | 14 | 0 | 0 | 24500 | 0 | 24500 | 903
9015 | Line No OH 5 Item No | Retention Costs |  |  |  |  | 1 |  | 9000 |  | 1 | 0 | 0 | 0 | 9000 | 9000
| 1 | Retention Costs | Item | S | 9000 | 1 | 1 | 1 | 9000 | 9000 | 1 | 0 | 0 | 0 | 9000 | 9000 | 904
9020 | Line No OH 6 Item No | Dual Grade Laser |  |  |  |  | 12 |  | 3324 |  | 12 | 0 | 0 | 3324 | 0 | 3324
|  | Dual Grade Laser | week | P | 1 | 1 | 12 | 277 | 3324 | 12 | 12 | 0 | 0 | 3324 | 0 | 3324 | 905
9025 | Line No OH 7 Item No | Small Tools Allowance |  |  |  |  | 2500 |  | 2500 |  | 2500 | 0 | 0 | 2500 | 0 | 2500
|  | Small Tools | Item | P | 1 | 1 | 2500 | 1 | 2500 | 2500 | 2500 | 0 | 0 | 2500 | 0 | 2500 | 905
9030 | Line No OH 8 Item No | Accommodation (Engineers & Directors) |  |  |  |  | 30 |  | 3750 |  | 30 | 0 | 0 | 0 | 3750 | 3750
|  | Accommodation | day | S | 1 | 1 | 30 | 125 | 3750 | 30 | 30 | 0 | 0 | 0 | 3750 | 3750 | 911
9040 | Line No OH 9 Item No | Accommodation Supervisors |  |  |  |  | 112 |  | 14000 |  | 112 | 0 | 0 | 0 | 14000 | 14000
|  | Accommodation | day | S | 1 | 1 | 112 | 125 | 14000 | 112 | 112 | 0 | 0 | 0 | 14000 | 14000 | 911

## Resources
| Resource Name | Description | Type | Unit | Currency | Base Rate
GROUP RESOURCES | Stabilising | Stabilising In House | G |  |  | 605.28
LABOUR RESOURCES | Labour | Labour | L | hr | AUD | 51.9
| Project Engineer | Project Engineer - Weekly Rate | L | week | AUD | 3250
| Project Supervisor | Project Supervisor | L | week | AUD | 3350
| Surveyor | Survey Team | L | hr | AUD | 185
| Traffic Controller | Traffic Controller with Vehicle | L | hr | AUD | 65
| WHSO | Work Place Health & Safety Officer | L | week | AUD | 3200
MATERIAL RESOURCES | 125 LD uPVC Electrical |  | M | m | AUD | 8
| 375 RCP |  | M | m | AUD | 83.4
| 450 RCP FJ CL2 |  | M | m | AUD | 102.9
| 50 HD uPVC Electrical |  | M | m | AUD | 3
| 750 RCP |  | M | m | AUD | 215.2
| CBR15 | CBR15 Road Base | M | tonne | AUD | 31.6
| CBR45 | CBR45 Road Base | M | tonne | AUD | 32.5
| CBR80 | CBR80 Road Base - Delivered | M | tonne | AUD | 33.75
| Cement | Bulk GP / GB Cement | M | tonne | AUD | 450
| Cement - 20 kg Bags | 20 KG cement bags | M | each | AUD | 15
| Crusher Dust - Delivered |  | M | tonne | AUD | 25.5
| Draw Rope - Conduits |  | M | m | AUD | 0.11
| Form Boards |  | M | m | AUD | 5
| Form Ply |  | M | m² | AUD | 10
| Gabion Rock | Gabion Rock (150 - 300) | M | tonne | AUD | 35
| Guide Post |  | M | each | AUD | 50
| HW - 375 | Head Wall 375 RCP | M | each | AUD | 365
| Hard Cover - Electrical |  | M | m | AUD | 2.7
| N32 | N32 Concrete | M | m³ | AUD | 309
| N40 |  | M | m³ | AUD | 325
| Nightline |  | M | m | AUD | 2
| RCBC - 1800 x 600 |  | M | m | AUD | 935
| RCBC - 600 x 300 |  | M | each | AUD | 247.5
| Rag Bolt |  | M | each | AUD | 425
| S32 - Kerb Mix | S32 - Kerb Mix | M | m³ | AUD | 309
| Sand | Bedding Sand | M | tonne | AUD | 28
| Signs Complete |  | M | each | AUD | 140
| Small Tools |  | M | Item | AUD | 1
| Steel |  | M | tonne | AUD | 2200
| Type 7 Elec Pit |  | M | each | AUD | 780
PLANT RESOURCES | Bobcat | Bobcat - Wet Hire | P | hr | AUD | 95
| CAT297 | CAT297C MTL - No Operator | P | hr | AUD | 46.5
| CAT297 Stabiliser | CAT297 Stabiliser - No operator | P | hr | AUD | 66.07
| Concrete Pump |  | P | hr | AUD | 175
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 1750
| Dual Grade Laser |  | P | week | AUD | 277
| Excavator - 25T | 25T Excavator - Wet Hire | P | hr | AUD | 135
| Float |  | P | LS | AUD | 1
| Grader | Grader - Wet Hire | P | hr | AUD | 160
| WS220 | Wirtgen Stabiliser | P | day | AUD | 1500
| MW Roller | MW Roller Hourly Rate (No Op) | P | hr | AUD | 55
| PF Roller | Pad Foot Roller - Dry | P | day | AUD | 365
| PF Roller Wet - No OP |  | P | hr | AUD | 58
| SD Roller - Wet (No Op) | SD Roller Wet Hire - No Operator | P | hr | AUD | 55
| T-Top Bollards | T - Top Bollards with 6kg base & reflective collar | P | each | AUD | 60
| Tipper | Tipper (Wet Hire) | P | hr | AUD | 90
| UD Spreader | UD Spreader Truck - No Driver | P | hr | AUD | 21.61
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 95
SUBCONTRACT RESOURCES | 35mm AC |  | S | tonne | AUD | 313.35
| 60mm AC |  | S | tonne | AUD | 277.28
| Accommodation | Accommodation & 3 meals Rate | S | day | AUD | 125
| CAR | CAR Insurance | S | Item | AUD | 1
| CBR Test |  | S | each | AUD | 400
| Concrete Subbie | Slab on Ground | S | m² | AUD | 45
| Field Density |  | S | each | AUD | 45
| Geotech Travel | Travel rate per km. | S | km | AUD | 2
| Gravel Properties Testing |  | S | each | AUD | 390
| Gravel Cartage | Rate per cubic metre | S | m³ | AUD | 8
| Guard Rail | Guard Rail Subbie, including bull nose | S | m | AUD | 7000
| Hydromulch Subbie |  | S | m² | AUD | 0.85
| Kerb Subbie |  | S | m | AUD | 45
| Line Marking |  | S | m² | AUD | 1
| Primer Seal - 10mm |  | S | m² | AUD | 4.9
| Primer Seal - 16mm |  | S | m² | AUD | 5.82
| Retention Costs |  | S | Item | AUD | 1
| Seal Visit One |  | S | m² | AUD | 3.61
| Service Locator |  | S | hr | AUD | 200
| Steel Fixing |  | S | tonne | AUD | 2200
| Tip Fees | Tip fees per ton of waste | S | tonne | AUD | 15
| Traffic Control Crew | 2 x TC's + Ute, Signs & Comms | S | hr | AUD | 130
| Underbore | Includes 1 x 100 HD Orange | S | m | AUD | 130
| Underbore Estab |  | S | Item | AUD | 1000

## Model Inputs
WBS | DESCRIPTION | MODEL INPUT | TYPE | UOM
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 1 | Q | Item
6 | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 1 | Q | Item
7 | Construction Setout by Contractor | 1 | Q | Item
8 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | Q | Item
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | Q | Item
10 | As Constructed Survey Data to Council Requirements. | 1 | Q | Item
11 | Geotechnical Testing by NATA Registered laboratory - Subgrade CBR tests ("soaked" 4 day, 4 point) (allow 3 confirmation tests on final subgrade for pavement design) | 3 | Q | No
12 | Subgrade Compaction testing as specified | 28 | Q | No
13 | Sub-Base Compaction testing as specified - assume 1 layer | 28 | Q | No
14 | Base Compaction testing as specified | 28 | Q | No
15 | Sub-Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results - assume 1 layer | 2 | Q | No
16 | Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results. | 2 | Q | No
17 | Culvert Trench Backfilling - Compaction Tests as ordered | 11 | Q | No
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 1 | Q | Item
18.1 | Area to be stripped | 16000 | P | 0
18.2 | Excavator - 25T | 60 | P | hr
19 | Earthworks - excavate and place as embankment as directed - Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will be spoiled at IRC Tip | 2804 | Q | m3
19.1 | Excavator - 25T | 50 | P | hr
20 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 40 | Q | m3
20.1 | Excavator - 25T | 10 | P | hr
21 | Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | 423 | Q | m3
21.1 | Excavator - 25T | 25 | P | hr
22 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | 11271 | Q | m2
22.1 | Grader | 200 | P | hr
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 7375 | Q | m2
23.1 | Grader | 275 | P | hr
24 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - QT Type 2.1 @ 150mm deep x widening area | 1231 | Q | m3
24.1 | Grader | 66.6667 | P | hr
25 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 -Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | 2032 | Q | m3
25.1 | Grader | 66.6667 | P | hr
26 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of length - Only if ordered by the Superintendent | 423 | Q | m3
26.1 | Grader | 44.4444 | P | hr
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 140 | Q | m2
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 371 | Q | m2
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 37 | Q | m2
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 812 | Q | m2
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 3549 | Q | m2
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 3444 | Q | m2
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 650 to Ch 2801 | 15057 | Q | m2
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 1260 | Q | m2
35 | Access Ch 826 RHS (Dysart Horse Performance Association) - Provide smooth transition between existing access and new shoulder (no pipe required; reinstate to similar) | 1 | Q | Item
35.1 | Grader | 0.5 | P | hr
36 | Access Ch 1642 RHS (Cemetery Carpark Access) - Reinstate sealed driveway between New shoulder and Carpark Access (no works on culvert required); neat smooth join. | 1 | Q | Item
36.1 | Grader | 0.5 | P | hr
37 | Access Ch 1660 RHS (Cemetery Access) - Reinstate sealed driveway between New shoulder and Cemetery Access (no works on culvert required); neat smooth join. | 1 | Q | Item
37.1 | Grader | 0.5 | P | hr
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 27830 | Q | m2
38.1 | Grader | 400 | P | hr
39 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters & drains) | 27830 | Q | m2
39.1 | Water Cart - Hire | 1700.7222 | P | hr
40 | Soil Management Measures inclusive of: Rock check dams as directed | 40 | Q | No
40.1 | Bobcat | 3 | P | hr
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 40 | Q | No
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 2 | Q | No
42.1 | Bobcat | 1 | P | hr
43 | Remove Signs for widening and reinstate | 1 | Q | Item
43.1 | Bobcat | 1 | P | hr
44 | Provisional Item Guardrail as per Note 5 on plan 842-R02 allow (3 lengths of Armoc ® 'W' Beam type XR & standard posts rammed into the ground with bull nose terminal ends) Only if ordered by Superintendent | 4 | Q | No
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfill. | 1.22 | Q | m
45.1 | Excavator - 25T | 2.44 | P | hr
45.2 | Excavator - 25T | 1.22 | P | hr
45.3 | Excavator - 25T | 1.22 | P | hr
45.4 | Labour | 0.305 | P | hr
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | Q | No
46.1 | Excavator - 25T | 0.5 | P | hr
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
47.1 | Excavator - 25T | 2.44 | P | hr
47.2 | Excavator - 25T | 1.22 | P | hr
47.3 | Excavator - 25T | 1.22 | P | hr
47.4 | Labour | 0.305 | P | hr
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | Q | No
48.1 | Labour | 0.125 | P | hr
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 2.44 | Q | m
49.1 | Excavator - 25T | 0.61 | P | hr
49.2 | Excavator - 25T | 1.22 | P | hr
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 12.2 | Q | m
50.1 | Excavator - 25T | 1.525 | P | hr
50.2 | Excavator - 25T | 3.0499 | P | hr
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 2 | Q | No
51.1 | Labour | 1 | P | hr
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | Q | Item
52.1 | Excavator - 25T | 0.16667 | P | hr
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 1 | Q | Item
53.1 | Excavator - 25T | 18.75 | P | hr
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
54.1 | Excavator - 25T | 2.44 | P | hr
54.2 | Excavator - 25T | 1.22 | P | hr
54.3 | Excavator - 25T | 1.22 | P | hr
54.4 | Labour | 0.305 | P | hr
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | Q | No
55.1 | Labour | 0.125 | P | hr
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
56.1 | Excavator - 25T | 2.44 | P | hr
56.2 | Excavator - 25T | 1.22 | P | hr
56.3 | Excavator - 25T | 1.22 | P | hr
56.4 | Labour | 0.305 | P | hr
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | Q | No
57.1 | Labour | 0.125 | P | hr
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
58.1 | Excavator - 25T | 2.44 | P | hr
58.2 | Excavator - 25T | 1.22 | P | hr
58.3 | Excavator - 25T | 1.22 | P | hr
58.4 | Labour | 0.305 | P | hr
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | Q | No
59.1 | Excavator - 25T | 0.5 | P | hr
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
60.1 | Excavator - 25T | 2.44 | P | hr
60.2 | Excavator - 25T | 0.813 | P | hr
60.3 | Excavator - 25T | 0.61 | P | hr
60.4 | Labour | 0.203 | P | hr
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | Q | No
61.1 | Labour | 0.125 | P | hr
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
62.1 | Excavator - 25T | 1.22 | P | hr
62.2 | Excavator - 25T | 0.813 | P | hr
62.3 | Excavator - 25T | 0.407 | P | hr
62.4 | Labour | 0.203 | P | hr
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 1 | Q | No
63.1 | Excavator - 25T | 0.25 | P | hr
63.2 | Labour | 0.11111 | P | hr
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
64.1 | Excavator - 25T | 2.44 | P | hr
64.2 | Excavator - 25T | 1.22 | P | hr
64.3 | Excavator - 25T | 1.22 | P | hr
64.4 | Labour | 0.305 | P | hr
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | Q | No
65.1 | Excavator - 25T | 0.5 | P | hr
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1.22 | Q | m
66.1 | Excavator - 25T | 2.44 | P | hr
66.2 | Excavator - 25T | 0.813 | P | hr
66.3 | Excavator - 25T | 0.61 | P | hr
66.4 | Labour | 0.203 | P | hr
265 | 2 x 375 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | Q | No
265.1 | Labour | 0.125 | P | hr
266 | Ch 2780 New 1/600 x 300 RCBC,Installation to Main Roads Std Dwg 1359 - Ch 2780 New 1/600 x 300 RCBC,Installation to Main Roads Std Dwg 1359 - 1/600 x 300 RCBC Complete in place, including excavate, sand, supply, lay and backfill. | 14.4 | Q | m
266.1 | Excavator - 25T | 3.6 | P | hr
266.2 | Bobcat | 1.8 | P | hr
266.3 | Excavator - 25T | 3 | P | hr
266.4 | Bobcat | 3.6 | P | hr
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 2 | Q | No
67.1 | Labour | 0.5 | P | hr
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | Q | Item
68.1 | Excavator - 25T | 0.167 | P | hr
69 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock | 1 | Q | Item
69.1 | Excavator - 25T | 11.25 | P | hr
70 | Ch 2800 Take up and stack existing 1/600 x 300 RCBC and backfill to reinstate roadway. | 1 | Q | Item
70.1 | Excavator - 25T | 0.25 | P | hr
70.2 | Bobcat | 0.25 | P | hr
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 1 | Q | Item
72 | Construction Setout by Contractor | 1 | Q | Item
73 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | Q | Item
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | Q | Item
75 | As Constructed Survey Data to Council Requirements. | 1 | Q | Item
76 | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | 4 | Q | No
77 | Sub-Base Compaction testing as specified - assume 2 layers | 4 | Q | No
78 | Base Compaction testing as specified | 2 | Q | No
79 | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | 1 | Q | No
80 | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | 1 | Q | No
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 1 | Q | Item
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 379 | Q | m3
82.1 | Excavator - 25T | 42.111 | P | hr
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 50 | Q | m3
83.1 | Excavator - 25T | 10 | P | hr
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 630 | Q | m2
84.1 | Grader | 200 | P | hr
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 574 | Q | m2
85.1 | Grader | 200 | P | hr
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 437 | Q | m2
86.1 | Grader | 275 | P | hr
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 415 | Q | m2
87.1 | Grader | 275 | P | hr
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 70 | Q | m3
0 | #N/A | 66.667 | P | #N/A
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 107 | Q | m3
89.1 | Grader | 66.667 | P | hr
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 90 | Q | m3
90.1 | Grader | 66.667 | P | hr
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 66 | Q | m3
91.1 | Grader | 66.667 | P | hr
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 99 | Q | m3
92.1 | Grader | 66.667 | P | hr
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 83 | Q | m3
93.1 | Grader | 66.667 | P | hr
94 | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | 30 | Q | m2
94.1 | Stabilising | 3.333 | P | 0
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 437 | Q | m2
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 415 | Q | m2
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2776 | Q | m2
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 67 | Q | m
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 79 | Q | m
99.1 | Excavator - 25T | 79 | Q | hr
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 20 | Q | m
101 | Electrical Mains Cable Pit (Provisional Item) | 2 | Q | No
101.1 | Excavator - 25T | 1 | P | hr
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 2 | Q | No
102.1 | Excavator - 25T | 0.5 | P | hr
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 1000 | Q | m2
103.1 | Grader | 400 | P | hr
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1000 | Q | m2
104.1 | Water Cart - Hire | 550 | P | hr
105 | Soil Management Measures inclusive of: Rock check dams as directed | 6 | Q | No
105.1 | Bobcat | 3 | P | hr
106 | Supply and Install New Guide Posts | 11 | Q | No
107 | Supply and Install New Give Way Sign R1-2 | 1 | Q | No
107.1 | Labour | 1 | P | hr
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 1 | Q | Item
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 3.6 | Q | m
109.1 | Excavator - 25T | 1.8 | P | hr
109.2 | Bobcat | 0.9 | P | hr
109.3 | Excavator - 25T | 3 | P | hr
109.4 | Bobcat | 1.8 | P | hr
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 1 | Q | No
110.1 | Labour | 0.25 | P | hr
111 | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 1 | Q | Item
112 | Construction Setout by Contractor | 1 | Q | Item
113 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | Q | Item
114 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | Q | Item
115 | As Constructed Survey Data to Council Requirements. | 1 | Q | Item
116 | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | 4 | Q | No
117 | Sub-Base Compaction testing as specified - assume 2 layers | 4 | Q | No
118 | Base Compaction testing as specified | 2 | Q | No
119 | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | 1 | Q | No
120 | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | 1 | Q | No
121 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 1 | Q | Item
121.1 | Excavator - 25T | 0.111 | P | hr
122 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 396 | Q | m3
122.1 | Excavator - 25T | 44 | P | hr
123 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 50 | Q | m3
123.1 | Excavator - 25T | 10 | P | hr
124 | Prepare Dysart Bypass Rd - Golden Mile Rd Intersection Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 434 | Q | m2
124.1 | Grader | 200 | P | hr
125 | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 830 | Q | m2
125.1 | Grader | 200 | P | hr
126 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 283 | Q | m2
126.1 | Grader | 275 | P | hr
127 | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 597 | Q | m2
127.1 | Grader | 275 | P | hr
128 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 46 | Q | m3
128.1 | Grader | 66.667 | P | hr
129 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | 72 | Q | m3
129.1 | Grader | 66.667 | P | hr
130 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 62 | Q | m3
130.1 | Grader | 66.667 | P | hr
131 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 95 | Q | m3
131.1 | Grader | 66.667 | P | hr
132 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | 143 | Q | m3
132.1 | Grader | 66.667 | P | hr
133 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 119 | Q | m3
133.1 | Grader | 66.667 | P | hr
134 | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | 30 | Q | m2
134.1 | Stabilising | 3.333 | P | 0
135 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 283 | Q | m2
136 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 597 | Q | m2
137 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Golden Mile Rd Intersection Complete (overlaying existing seal area) | 2912 | Q | m2
138 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 67 | Q | m
139 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 78 | Q | m
139.1 | Excavator - 25T | 25 | P | hr
140 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 22 | Q | m
141 | Electrical Mains Cable Pit (Provisional Item) | 2 | Q | No
141.1 | Labour | 0.5 | P | hr
142 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 2 | Q | No
142.1 | Excavator - 25T | 0.5 | P | hr
143 | Soil Management Measures inclusive of: - Prepare batters and drains for hydromulch placement | 1000 | Q | m2
143.1 | Grader | 400 | P | hr
144 | Hydromulch to all disturbed areas as directed (batters & drains) | 1000 | Q | m2
144.1 | Water Cart - Hire | 550 | P | hr
145 | Rock check dams as directed | 6 | Q | No
145.1 | Bobcat | 3 | P | hr
146 | Supply and Install New Guide Posts | 10 | Q | No
147 | Supply and Install New Give Way Sign R1-2 | 1 | Q | No
147.1 | Bobcat | 1 | P | hr
148 | Linemarking Complete,Dysart Bypass Rd - Golden Mile Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 1 | Q | Item
149 | PV01 - Revised Tender Rates - Seal & Asphalt | 1 | Q | item
149.1 | E/0 Primer Seal - 10mm | 2280 | Q | m²
149.2 | E/O First Seal | 4361 | Q | m²
149.3 | E/O Second Seal | 18501 | Q | m²
149.4 | E/O DG10 AC | 1260 | Q | m²
149.5 | E/O DG14 AC | 5688 | Q | m²
150 | PV02 - Revised pavement design | 1 | Q | Item
150.1 | CBR80 | -2708 | Q | t
150.2 | CBR45 | -4470 | Q | t
150.3 | CBR15 | -931 | Q | t
151 | Earthworks - excavate and place as embankment as directed - Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will be spoiled at IRC Tip | -2804 | Q | m3
151.1 | Excavator - 25T | 50 | P | hr
152 | REMOVE THIS ITEM: - Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | -40 | Q | m3
152.1 | Excavator - 25T | 10 | P | hr
153 | REMOVE THIS ITEM: - Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | -423 | Q | m3
153.1 | Excavator - 25T | 25 | P | hr
154 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | -11270 | Q | m2
154.1 | Grader | 200 | P | hr
155 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - QT Type 2.1 @ 150mm deep x widening area | -1231 | Q | m3
155.1 | Grader | 66.6667 | P | hr
156 | REMOVE THIS ITEM: - Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 -Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | -2032 | Q | m3
156.1 | Grader | 66.6667 | P | hr
157 | REMOVE THIS ITEM: - Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of length - Only if ordered by the Superintendent | -423 | Q | m3
157.1 | Grader | 44.4444 | P | hr
158 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | 11455 | Q | m2
158.1 | Grader | 200 | P | hr
159 | ADD THIS ITEM: - Gravel Pavement Base In Place complete, 200 mm OVERLAY - PRINCIPAL SUPPLIED GRAVEL, spreading, MIXING TO 300 mm DEPTH, watering, rolling and trimming: | 4842 | Q | m3
159.1 | Grader | 200 | P | hr
159.2 | WS220 | 2000 | P | day
159.3 | Grader | 200 | P | hr
160 | Bitumen Seal - complete in place (16mm primerseal ) Road Widening: | 14140 | Q | m2
161 | Remove & replace unsuitable | 63 | Q | m3
161.1 | Excavator - 25T | 12 | P | hr
162 | Additional Drainage Items |  |  | 0
163 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 2.44 | Q | m
163.1 | Excavator - 25T | 2.44 | P | hr
163.2 | Excavator - 25T | 1.22 | P | hr
163.3 | Excavator - 25T | 1.22 | P | hr
163.4 | Labour | 0.305 | P | hr
164 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 2 | Q | No
164.1 | Labour | 0.125 | P | hr
165 | Asphalt redesign at floodway ch510-651 | 32 | Q | 0
166 | Corrector course asphalt dysart-middlemount intersection | 15.9 | Q | 0
167 | Corrector course asphalt dysart-middlemount road (DMR section) | 35 | Q | 0
168 | Cement Stabilise 4% by weight 200mm deep Bypass Road Edges | 3628 | Q | m2
168.1 | Stabilising | 800 | P | 0
9000 | Project Supervision | 15 | Q | 0
9005 | Project Engineering | 5 | Q | 0
9010 | Site Facilities | 14 | Q | 0
9015 | Retention Costs | 1 | Q | 0
9020 | Dual Grade Laser | 12 | Q | 0
9025 | Small Tools Allowance | 2500 | Q | 0
9030 | Accommodation (Engineers & Directors) | 30 | Q | 0
9040 | Accommodation Supervisors | 112 | Q | 0

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | 2013-01-26 | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Workhrs | 9
Start Date | 2011-10-25

## Program Links
WBS | Task | Duration | Predecessors | Successors | Budget | %C Claim 01 | %C Claim 02 | %C Claim 03 | %C Claim 04 | %C Claim 05 | %C Claim 06
1 | CONTRACT AWARD |  |  | 5,8,73,75,113
2 | PRACTICAL COMPLETION |  | 10,108,115,145,6,70,105,75
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 2 | 3,8 | 6,7,9,45,74,73,76,11,15,16,71,79,80,119,120 | 34725 | 80% | 80% | 80% | 80% | 85% | 85%
6 | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 71 | 5 | 4 | 76266.8311 | 10% | 60% | 70% | 80% | 85% | 85%
7 | Construction Setout by Contractor | 9 | 5 | 9 | 23680 | 100% | 100% | 100% | 100% | 100% | 100%
8 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | 3 | 5 | 10400 | 100% | 100% | 100% | 100% | 100% | 100%
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 2 | 5,7 | 18 | 6800 | 100% | 100% | 100% | 100% | 100% | 100%
10 | As Constructed Survey Data to Council Requirements. | 6 | 44 | 4 | 8880 | 0% | 0% | 0% | 0% | 0% | 0%
11 | Geotechnical Testing by NATA Registered laboratory - Subgrade CBR tests (soaked 4 day, 4 point) (allow 3 confirmation tests on final subgrade for pavement design) | 0 | 5 | 12 | 2700 | 0% | 100% | 100% | 100% | 100% | 100%
12 | Subgrade Compaction testing as specified | 0 | 11 |  | 5926.6667 | 0% | 28.57% | 57.14% | 89.29% | 89.29% | 89.29%
13 | Sub-Base Compaction testing as specified - assume 1 layer | 0 | 25 | 24 | 5926.6667 | 0% | 28.57% | 57.14% | 89.29% | 89.29% | 89.29%
14 | Base Compaction testing as specified | 0 | 23 | 27 | 5926.6667 | 0% | 28.57% | 57.14% | 89.29% | 89.29% | 89.29%
15 | Sub-Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results - assume 1 layer | 0 | 5 | 26 | 2580 | 0% | 100% | 100% | 100% | 100% | 100%
16 | Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results. | 0 | 5 | 24 | 2580 | 0% | 100% | 100% | 100% | 100% | 100%
17 | Culvert Trench Backfilling - Compaction Tests as ordered | 0 |  |  | 2328.3333 | 0% | 100% | 100% | 100% | 100% | 100%
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 3 | 145,9 | 19,45,152 | 12317.3333 | 0% | 100% | 100% | 100% | 100% | 100%
19 | Earthworks - excavate and place as embankment as directed - Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will b | 7 | 18152 | 20151 | 33689.752
20 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 19151 | 21 | 2514.8
21 | Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | 2 | 20 | 22 | 9338.148
22 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | 7 | 21 | 45 | 32988.3385
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 3 | 24153 | 14 | 15618.0152 | 0% | 0% | 100% | 100% | 100% | 100%
24 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - QT Type 2.1 @ 150mm deep x widening area | 5 | 25,16,13 | 23153 | 131510.4074
25 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 -Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | 8 | 26 | 24,13 | 211113.9796
26 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of l | 3 | 67,15 | 25 | 48873.2138
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 1 | 14 | 28 | 754.6 | 0% | 0% | 100% | 100% | 100% | 100%
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 1 | 27 | 29 | 1999.69 | 0% | 0% | 100% | 100% | 100% | 100%
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 1 | 28 | 30 | 199.43 | 0% | 0% | 100% | 100% | 100% | 100%
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 1 | 29 | 31 | 5198.424 | 0% | 0% | 100% | 100% | 100% | 100%
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 30 | 32 | 22720.698 | 0% | 0% | 100% | 100% | 100% | 100%
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 1 | 31 | 33 | 13676.124 | 0% | 0% | 100% | 100% | 100% | 100%
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 2 | 32 | 34,35FF | 59791.347 | 0% | 0% | 49.84% | 49.84% | 86.19% | 86.19%
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 1 | 33,37 | 38,41 | 34546.8375 | 0% | 0% | 0% | 0% | 100% | 100%
35 | Access Ch 826 RHS (Dysart Horse Performance Association) - Provide smooth transition between existing access and new shoulder (no pipe required; reinstate to similar) | 1 | 33FF | 36FF | 723.8 | 0% | 0% | 0% | 100% | 100% | 100%
36 | Access Ch 1642 RHS (Cemetery Carpark Access) - Reinstate sealed driveway between New shoulder and Carpark Access (no works on culvert required); neat smooth join. | 1 | 35FF | 37FF | 1014.8 | 0% | 0% | 0% | 0% | 0% | 0%
37 | Access Ch 1660 RHS (Cemetery Access) - Reinstate sealed driveway between New shoulder and Cemetery Access (no works on culvert required); neat smooth join. | 1 | 36FF | 34 | 1014.8 | 0% | 0% | 0% | 0% | 0% | 0%
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 8 | 34 | 39 | 21352.5675 | 0% | 0% | 0% | 0% | 100% | 100%
39 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters & drains) | 4 | 38 | 40 | 27731.05 | 0% | 0% | 0% | 0% | 0% | 0%
40 | Soil Management Measures inclusive of: Rock check dams as directed | 2 | 39 |  | 10842.6667 | 0% | 0% | 0% | 0% | 0% | 0%
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 0 | 34 | 42 | 2000 | 0% | 0% | 0% | 100% | 100% | 100%
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 41 | 43 | 957.6 | 0% | 0% | 0% | 100% | 100% | 100%
43 | Remove Signs for widening and reinstate | 1 | 42 | 44 | 338.8 | 0% | 0% | 0% | 100% | 100% | 100%
44 | Provisional Item Guardrail as per Note 5 on plan 842-R02 allow (3 lengths of Armoc ® 'W' Beam type XR & standard posts rammed into the ground with bull nose terminal ends) Only if ordered by Superintendent | 4 | 43 | 10 | 28000 | 0% | 0% | 0% | 0% | 0% | 0%
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 1 | 5,18,22 | 46 | 1297.351 | 100% | 100% | 100% | 100% | 100% | 100%
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 45 | 47 | 1257.8 | 0% | 100% | 100% | 100% | 100% | 100%
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 46 | 48 | 1344.931 | 100% | 100% | 100% | 100% | 100% | 100%
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 47 | 49 | 2338.85 | 0% | 100% | 100% | 100% | 100% | 100%
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 4 | 48 | 50 | 20898.8887 | 0% | 100% | 100% | 100% | 100% | 100%
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 2 | 49 | 51 | 64286.6382 | 0% | 100% | 100% | 100% | 100% | 100%
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 1 | 50 | 52,54 | 2161.4 | 0% | 100% | 100% | 100% | 100% | 100%
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | 51 | 53 | 1661.4 | 0% | 100% | 100% | 100% | 100% | 100%
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 1 | 52 | 68 | 3372.6 | 0% | 0% | 100% | 100% | 100% | 100%
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 51 | 55 | 2118.874 | 100% | 100% | 100% | 100% | 100% | 100%
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 54 | 56 | 2338.85 | 0% | 100% | 100% | 100% | 100% | 100%
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1 | 55 | 57 | 2078.392 | 100% | 100% | 100% | 100% | 100% | 100%
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 56 | 58 | 2338.85 | 0% | 0% | 100% | 100% | 100% | 100%
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 57 | 59 | 1306.8446 | 100% | 100% | 100% | 100% | 100% | 100%
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | 58 | 60 | 1257.8 | 0% | 100% | 100% | 100% | 100% | 100%
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 59 | 61 | 2147.6137 | 100% | 100% | 100% | 100% | 100% | 100%
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 60 | 62 | 2147.975 | 0% | 100% | 100% | 100% | 100% | 100%
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 61 | 63 | 3398.3134 | 100% | 100% | 100% | 100% | 100% | 100%
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 1 | 62 | 64 | 4019.9 | 0% | 0% | 100% | 100% | 100% | 100%
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 63 | 65 | 1332.7946 | 100% | 100% | 100% | 100% | 100% | 100%
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 64 | 66 | 892.8 | 0% | 100% | 100% | 100% | 100% | 100%
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 65 | 67 | 1980.785 | 100% | 100% | 100% | 100% | 100% | 100%
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 1 | 66 | 68,26 | 947.8 | 0% | 100% | 100% | 100% | 100% | 100%
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | 67,53 | 69 | 1658.0838 | 0% | 100% | 100% | 100% | 100% | 100%
69 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock | 1 | 68 | 70 | 2322.6 | 0% | 0% | 0% | 0% | 0% | 0%
70 | Ch 2800 Take up and stack existing 1/600 x 300 RCBC and backfill to reinstate roadway. | 1 | 69 | 4 | 4666.85 | 0% | 0% | 0% | 0% | 0% | 0%
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 13 | 5 | 72 | 28325.0469 | 0% | 80% | 80% | 80% | 100% | 100%
72 | Construction Setout by Contractor | 4 | 71,73 | 74 | 5180 | 0% | 100% | 100% | 100% | 100% | 100%
73 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | 3,5 | 72 | 2800 | 0% | 100% | 100% | 100% | 100% | 100%
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 5,72 | 81 | 3200 | 0% | 100% | 100% | 100% | 100% | 100%
75 | As Constructed Survey Data to Council Requirements. | 2 | 3108 | 4 | 5920 | 0% | 0% | 0% | 0% | 0% | 0%
76 | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | 0 | 5,85 | 90 | 846.6667 | 0% | 100% | 100% | 100% | 100% | 100%
77 | Sub-Base Compaction testing as specified - assume 2 layers | 0 | 92 | 88 | 846.6667 | 0% | 100% | 100% | 100% | 100% | 100%
78 | Base Compaction testing as specified | 0 | 87,85 | 95 | 423.3333 | 0% | 0% | 0% | 100% | 100% | 100%
79 | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | 0 | 5 | 90 | 1290 | 0% | 100% | 100% | 100% | 100% | 100%
80 | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | 0 | 5 | 88 | 1290 | 0% | 100% | 100% | 100% | 100% | 100%
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 74 | 82 | 5321.3964 | 0% | 100% | 100% | 100% | 100% | 100%
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 2 | 81 | 83 | 4967.1131 | 0% | 100% | 100% | 100% | 100% | 100%
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 82 | 84,99 | 3143.5 | 0% | 100% | 0% | 0% | 0% | 0%
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 83,99,110,109 | 85 | 1843.905 | 0% | 100% | 100% | 100% | 100% | 100%
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 84 | 111,76,90,78 | 1680.0023 | 0% | 100% | 100% | 100% | 100% | 100%
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 91 | 87 | 925.4336 | 0% | 0% | 100% | 100% | 100% | 100%
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 86 | 78 | 878.8442 | 0% | 0% | 100% | 100% | 100% | 100%
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 98,77,80 | 91 | 7478.2426 | 0% | 100% | 100% | 100% | 100% | 100%
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 93 | 92 | 11116.7155 | 0% | 100% | 100% | 100% | 100% | 100%
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 85,76,79 | 93 | 9160.1584 | 0% | 100% | 100% | 100% | 100% | 100%
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 1 | 88 | 86,94 | 7050.9145 | 0% | 100% | 100% | 100% | 100% | 100%
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 89 | 98,77 | 10285.5592 | 0% | 100% | 100% | 100% | 100% | 100%
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 90 | 89 | 8447.7016 | 0% | 100% | 100% | 100% | 100% | 100%
94 | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | 2 | 91 | 100,95 | 5610.0655 | 0% | 0% | 0% | 0% | 0% | 0%
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 78,94 | 96FF | 2355.43 | 0% | 0% | 100% | 100% | 100% | 100%
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 95FF | 97 | 2236.85 | 0% | 0% | 100% | 100% | 100% | 100%
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 96 | 106 | 115460.5466 | 0% | 0% | 0% | 0% | 100% | 100%
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 1 | 92 | 88102 | 5701.1957 | 0% | 0% | 0% | 0% | 100% | 100%
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 83 | 100,84,109 | 2078.1625 | 0% | 0% | 0% | 0% | 100% | 100%
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 3 | 94,99 | 101 | 3600 | 0% | 0% | 100% | 100% | 100% | 100%
101 | Electrical Mains Cable Pit (Provisional Item) | 1 | 111100102 | 103 | 2452.8 | 0% | 0% | 0% | 0% | 100% | 100%
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 1 | 98 | 103101 | 2690.8 | 0% | 0% | 0% | 0% | 100% | 100%
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 1 | 102101 | 104 | 767.25 | 0% | 0% | 0% | 0% | 100% | 100%
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1 | 103 | 105 | 1125 | 0% | 0% | 0% | 0% | 0% | 0%
105 | Soil Management Measures inclusive of: Rock check dams as directed | 1 | 104 | 4 | 1626.4 | 0% | 0% | 0% | 0% | 0% | 0%
106 | Supply and Install New Guide Posts | 1 | 97 | 107 | 550 | 0% | 0% | 0% | 100% | 100% | 100%
107 | Supply and Install New Give Way Sign R1-2 | 1 | 106 | 108 | 338.8 | 0% | 0% | 0% | 100% | 100% | 100%
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 1 | 107 | 4,75 | 7500 | 0% | 0% | 0% | 0% | 0% | 100%
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 1 | 99 | 110,84 | 4014.9044 | 0% | 100% | 100% | 100% | 100% | 100%
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 1 | 109 | 84 | 947.8 | 0% | 100% | 100% | 100% | 100% | 100%
111 | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 13 | 85 | 112101 | 28325.0469 | 0% | 0% | 0% | 0% | 0% | 0%
112 | Construction Setout by Contractor | 2 | 111113 | 114 | 5180 | 0% | 0% | 0% | 0% | 0% | 0%
113 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | 3 | 112 | 2800 | 0% | 0% | 0% | 0% | 0% | 0%
114 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 112 | 121 | 3200 | 0% | 0% | 0% | 0% | 0% | 0%
115 | As Constructed Survey Data to Council Requirements. | 4 | 148 | 4 | 5920 | 0% | 0% | 0% | 0% | 0% | 0%
116 | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | 0 | 125 | 130 | 846.6667 | 0% | 0% | 0% | 0% | 0% | 0%
117 | Sub-Base Compaction testing as specified - assume 2 layers | 0 | 132 | 128 | 846.6667 | 0% | 0% | 0% | 0% | 0% | 0%
118 | Base Compaction testing as specified | 0 | 131 | 135 | 423.3333 | 0% | 0% | 0% | 0% | 0% | 0%
119 | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | 0 | 5 | 130 | 1290 | 0% | 0% | 0% | 0% | 0% | 0%
120 | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | 0 | 5 | 128 | 1290 | 0% | 0% | 0% | 0% | 0% | 0%
121 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 114 | 122 | 5321.3964 | 0% | 0% | 0% | 0% | 0% | 0%
122 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 1 | 121 | 123 | 4967.1 | 0% | 0% | 0% | 0% | 0% | 0%
123 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 122 | 139 | 3143.5 | 0% | 0% | 0% | 0% | 0% | 0%
124 | Prepare Dysart Bypass Rd - Golden Mile Rd Intersection Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 1 | 139 | 125 | 1270.2457 | 0% | 0% | 0% | 0% | 0% | 0%
125 | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 1 | 124 | 116 | 2429.2717 | 0% | 0% | 0% | 0% | 0% | 0%
126 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 1 | 131 | 127 | 599.3082 | 0% | 0% | 0% | 0% | 0% | 0%
127 | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 1 | 126 | 134 | 1264.2651 | 0% | 0% | 0% | 0% | 0% | 0%
128 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 138117120 | 131 | 4914.2737 | 0% | 0% | 0% | 0% | 0% | 0%
129 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 133 | 132 | 7480.4067 | 0% | 0% | 0% | 0% | 0% | 0%
130 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 116119 | 133 | 6310.3313 | 0% | 0% | 0% | 0% | 0% | 0%
131 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 1 | 128 | 118126 | 10149.0436 | 0% | 0% | 0% | 0% | 0% | 0%
132 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 129 | 138117 | 14856.9188 | 0% | 0% | 0% | 0% | 0% | 0%
133 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 130 | 129 | 12111.765 | 0% | 0% | 0% | 0% | 0% | 0%
134 | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | 2 | 127 | 135 | 5610.0655 | 0% | 0% | 0% | 0% | 0% | 0%
135 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 1 | 118134 | 136FF | 1525.37 | 0% | 0% | 0% | 0% | 0% | 0%
136 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 1 | 135FF | 137 | 3217.83 | 0% | 0% | 0% | 0% | 0% | 0%
137 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Golden Mile Rd Intersection Complete (overlaying existing seal area) | 2 | 136 | 146 | 121115.2984 | 0% | 0% | 0% | 0% | 0% | 0%
138 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 1 | 132 | 128142 | 5701.1988 | 0% | 0% | 0% | 0% | 0% | 0%
139 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 123 | 140124 | 2770.989 | 0% | 0% | 0% | 0% | 0% | 0%
140 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 3 | 139 | 142 | 3860 | 0% | 0% | 0% | 0% | 0% | 0%
141 | Electrical Mains Cable Pit (Provisional Item) | 1 | 142 | 143 | 2452.8 | 0% | 0% | 0% | 0% | 0% | 0%
142 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 1 | 138140 | 141 | 2690.8 | 0% | 0% | 0% | 0% | 0% | 0%
143 | Soil Management Measures inclusive of: - Prepare batters and drains for hydromulch placement | 1 | 141 | 144 | 767.25 | 0% | 0% | 0% | 0% | 0% | 0%
144 | Hydromulch to all disturbed areas as directed (batters & drains) | 1 | 143 | 145 | 1125 | 0% | 0% | 0% | 0% | 0% | 0%
145 | Rock check dams as directed | 1 | 144 | 4,18 | 1626.4 | 0% | 0% | 0% | 0% | 0% | 0%
146 | Supply and Install New Guide Posts | 1 | 137 | 147 | 500 | 0% | 0% | 0% | 0% | 0% | 0%
147 | Supply and Install New Give Way Sign R1-2 | 1 | 146 | 148 | 338.8 | 0% | 0% | 0% | 0% | 0% | 0%
148 | Linemarking Complete,Dysart Bypass Rd - Golden Mile Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 1 | 147 | 115 | 7500 | 0% | 0% | 0% | 0% | 0% | 0%
161 | Remove & replace unsuitable - ch0 | 1 | 19 | 20 | 3300.675 | 0% | 100% | 100% | 100% | 100% | 100%
162 | Addiitonal drainage items | 0 | 18 | 19 | 7048.884 | 0% | 100% | 100% | 100% | 100% | 100%
168 | Stabilisation of Edges - Bypass Road | 5 | 24 | 23 | 22336.2232 | 0% | 0% | 0% | 0% | 0% | 100%

## Budget & Revenue
WBS | Item No | Description | Unit | Budget | Tender Quantity | Contract Quantity | Tender Rate | Tender Total | Contract Total | Oct -11 QTY | %C Oct-11 | Nov-11 QTY | %C Nov-11 | Dec-11 QTY | %C Dec-11 | Jan-12 QTY | %C Jan-12 | Feb-12 QTY | %C Feb-12 | Jun-12 QTY | %C Jun-12 | Revenue Oct-11 | Revenue Nov-11 | Revenue Dec-11 | Revenue Jan-12 | Revenue Feb-12 | Revenue Jun-12
Contract Items
Schedule A - Roadworks Dysart Bypass Road Widening
| 1 | Preliminaries
5 | (a) | Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | Item | 34725 | 1 | 1 | 44020.23 | 44020.23 | 44020.23 | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.85 | 85% | 0.85 | 85% | 35216.184 | 35216.184 | 35216.184 | 35216.184 | 37417.1955 | 37417.1955
6 | (b) | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | Item | 76266.8311 | 1 | 1 | 96682 | 96682 | 96682 | 0.1 | 10% | 0.6 | 60% | 0.7 | 70% | 0.8 | 80% | 0.85 | 85% | 0.85 | 85% | 9668.2 | 58009.2 | 67677.4 | 77345.6 | 82179.7 | 82179.7
7 | (c ) | Construction Setout by Contractor | Item | 23680 | 1 | 1 | 30018.69 | 30018.69 | 30018.69 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 30018.69 | 30018.69 | 30018.69 | 30018.69 | 30018.69 | 30018.69
[Note: Council to provide an initial control line, TBM's, prior to commencement of works; Contractor shall be responsible for all other setout to construct the works
8 | (d ) | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | Item | 10400 | 1 | 1 | 13183.89 | 13183.89 | 13183.89 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 13183.89 | 13183.89 | 13183.89 | 13183.89 | 13183.89 | 13183.89
9 | (e) | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | Item | 6800 | 1 | 1 | 8620.23 | 8620.23 | 8620.23 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 8620.23 | 8620.23 | 8620.23 | 8620.23 | 8620.23 | 8620.23
10 | (f) | As Constructed Survey Data to Council Requirements. | Item | 8880 | 1 | 1 | 13602.22 | 13602.22 | 13602.22 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| (g) | Geotechnical Testing by NATA Registered laboratory
11 | (i) | Subgrade CBR tests ("soaked" 4 day, 4 point) (allow 3 confirmation tests on final subgrade for pavement design) | No | 2700 | 3 | 3 | 1140.91 | 3422.73 | 3422.73 |  | 0% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 3422.73 | 3422.73 | 3422.73 | 3422.73 | 3422.73
12 | (ii) | Subgrade Compaction testing as specified | No | 5926.6667 | 28 | 28 | 268.33 | 7513.24 | 7513.24 |  | 0% | 8 | 28.57% | 16 | 57.14% | 25 | 89.29% | 25 | 89.29% | 25 | 89.29% | 0 | 2146.64 | 4293.28 | 6708.25 | 6708.25 | 6708.25
13 | (iii) | Sub-Base Compaction testing as specified - assume 1 layer | No | 5926.6667 | 28 | 28 | 268.33 | 7513.24 | 7513.24 |  | 0% | 8 | 28.57% | 16 | 57.14% | 25 | 89.29% | 25 | 89.29% | 25 | 89.29% | 0 | 2146.64 | 4293.28 | 6708.25 | 6708.25 | 6708.25
14 | (iv) | Base Compaction testing as specified | No | 5926.6667 | 28 | 28 | 268.32 | 7512.96 | 7512.96 |  | 0% | 8 | 28.57% | 16 | 57.14% | 25 | 89.29% | 25 | 89.29% | 25 | 89.29% | 0 | 2146.56 | 4293.12 | 6708 | 6708 | 6708
15 | (v) | Sub-Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results - assume 1 layer | No | 2580 | 2 | 2 | 1635.31 | 3270.62 | 3270.62 |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 3270.62 | 3270.62 | 3270.62 | 3270.62 | 3270.62
16 | (vi) | Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results. | No | 2580 | 2 | 2 | 1635.31 | 3270.62 | 3270.62 |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 3270.62 | 3270.62 | 3270.62 | 3270.62 | 3270.62
17 | (vii) | Culvert Trench Backfilling - Compaction Tests as ordered | No | 2328.3333 | 11 | 11 | 268.33 | 2951.63 | 2951.63 |  | 0% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 0 | 2951.63 | 2951.63 | 2951.63 | 2951.63 | 2951.63
18 | 2 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | Item | 12317.3333 | 1 | 1 | 15614.45 | 15614.45 | 15614.45 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 15614.45 | 15614.45 | 15614.45 | 15614.45 | 15614.45
| 3 | Earthworks - excavate and place as embankment as directed
19 | (a) | Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will be spoiled at IRC Tip | m3 | 33689.752 | 2804 |  | 15.23 | 42704.92 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | (c) | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 | 2514.8 | 40 |  | 62.87 | 2514.8 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
21 | (d) | Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | m3 | 9338.148 | 423 |  | 22.08 | 9339.84 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
22 | (a) | Bypass Road Widening from Ch 18 to Ch 2801 | m2 | 32988.3385 | 11271 |  | 3.71 | 41815.41 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results
23 | (a) | Bypass Road Widening Ch 18 to 2801 | m2 | 15618.0152 | 7375 | 7375 | 2.68 | 19765 | 19765 |  | 0% |  | 0% | 7375 | 100% | 7375 | 100% | 7375 | 100% | 7375 | 100% | 0 | 0 | 19765 | 19765 | 19765 | 19765
| 6 | Gravel Pavement
In Place complete, including supply, spreading, watering, rolling and trimming:-
(a) Bypass Road Widening Ch 18 to Ch 2801
24 | (i) | Base QT Type 2.1 @ 150mm deep x widening area | m3 | 131510.4074 | 1231 |  | 135.43 | 166714.33 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
25 | (ii) | Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | m3 | 211113.9796 | 2032 |  | 131.7 | 267614.4 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
26 | (iii) | Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of length - Only if ordered by the Superintendent | m3 | 48873.2138 | 423 |  | 115.54 | 48873.42 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED
27 | (a) | Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | m2 | 754.6 | 140 | 140 | 5.52 | 772.8 | 772.8 |  | 0% |  | 0% | 140 | 100% | 140 | 100% | 140 | 100% | 140 | 100% | 0 | 0 | 772.8 | 772.8 | 772.8 | 772.8
28 | (b) | Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | m2 | 1999.69 | 371 | 371 | 5.52 | 2047.92 | 2047.92 |  | 0% |  | 0% | 371 | 100% | 371 | 100% | 371 | 100% | 371 | 100% | 0 | 0 | 2047.92 | 2047.92 | 2047.92 | 2047.92
29 | (c) | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | m2 | 199.43 | 37 | 37 | 5.52 | 204.24 | 204.24 |  | 0% |  | 0% | 37 | 100% | 37 | 100% | 37 | 100% | 37 | 100% | 0 | 0 | 204.24 | 204.24 | 204.24 | 204.24
| 8 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED
30 | (a) | Bypass Road Widening Ch 18 to Ch 510 | m2 | 5198.424 | 812 | 812 | 6.56 | 5326.72 | 5326.72 |  | 0% |  | 0% | 812 | 100% | 812 | 100% | 812 | 100% | 812 | 100% | 0 | 0 | 5326.72 | 5326.72 | 5326.72 | 5326.72
31 | (b) | Bypass Road Widening Ch 650 to Ch 2801 | m2 | 22720.698 | 3549 | 3549 | 6.56 | 23281.44 | 23281.44 |  | 0% |  | 0% | 3549 | 100% | 3549 | 100% | 3549 | 100% | 3549 | 100% | 0 | 0 | 23281.44 | 23281.44 | 23281.44 | 23281.44
| 9 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED
32 | (a) | Bypass Road Widening Ch 18 to Ch 510 | m2 | 13676.124 | 3444 | 3444 | 4.07 | 14017.08 | 14017.08 |  | 0% |  | 0% | 3444 | 100% | 3444 | 100% | 3444 | 100% | 3444 | 100% | 0 | 0 | 14017.08 | 14017.08 | 14017.08 | 14017.08
33 | (b) | Bypass Road Widening Ch 650 to Ch 2801 | m2 | 59791.347 | 15057 | 15057 | 4.07 | 61281.99 | 61281.99 |  | 0% |  | 0% | 7504 | 49.84% | 7504 | 49.84% | 12977 | 86.19% | 12977 | 86.19% | 0 | 0 | 30541.28 | 30541.28 | 52816.39 | 52816.39
| 10 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins
34 | (a) | Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | m2 | 34546.8375 | 1260 | 1260 | 28.1 | 35406 | 35406 |  | 0% |  | 0% |  | 0% |  | 0% | 1260 | 100% | 1260 | 100% | 0 | 0 | 0 | 0 | 35406 | 35406
| 11 | Access Ch 826 RHS (Dysart Horse Performance Association)
35 | (a) | Provide smooth transition between existing access and new shoulder (no pipe required; reinstate to similar) | Item | 723.8 | 1 | 1 | 917.55 | 917.55 | 917.55 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 917.55 | 917.55 | 917.55
| 12 | Access Ch 1642 RHS (Cemetery Carpark Access)
36 | (a) | Reinstate sealed driveway between New shoulder and Carpark Access (no works on culvert required); neat smooth join. | Item | 1014.8 | 1 | 1 | 1286.44 | 1286.44 | 1286.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 13 | Access Ch 1660 RHS (Cemetery Access)
37 | (a) | Reinstate sealed driveway between New shoulder and Cemetery Access (no works on culvert required); neat smooth join. | Item | 1014.8 | 1 | 1 | 1286.44 | 1286.44 | 1286.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 14 | Soil Management Measures inclusive of:
38 | (a) | Prepare batters and drains for hydromulch placement | m2 | 21352.5675 | 27830 | 27830 | 0.97 | 26995.1 | 26995.1 |  | 0% |  | 0% |  | 0% |  | 0% | 27830 | 100% | 27830 | 100% | 0 | 0 | 0 | 0 | 26995.1 | 26995.1
39 | (b) | Hydromulch to all disturbed areas as directed (batters & drains) | m2 | 27731.05 | 27830 | 27830 | 1.26 | 35065.8 | 35065.8 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
40 | (c) | Rock check dams as directed | No | 10842.6667 | 40 | 40 | 343.63 | 13745.2 | 13745.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 15 | Road Furniture
41 | (a) | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | No | 2000 | 40 | 40 | 63.38 | 2535.2 | 2535.2 |  | 0% |  | 0% |  | 0% | 40 | 100% | 40 | 100% | 40 | 100% | 0 | 0 | 0 | 2535.2 | 2535.2 | 2535.2
42 | (b) | Supply and Install Floodway Depth markers (G9-22-1A) | No | 957.6 | 2 | 2 | 606.97 | 1213.94 | 1213.94 |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 1213.94 | 1213.94 | 1213.94
43 | (c) | Remove Signs for widening and reinstate | Item | 338.8 | 1 | 1 | 429.49 | 429.49 | 429.49 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 429.49 | 429.49 | 429.49
44 | (d) | Provisional Item Guardrail as per Note 5 on plan 842-R02 allow (3 lengths of Armoc ® 'W' Beam type XR & standard posts rammed into the ground with bull nose terminal ends) Only if ordered by Superintendent | No | 28000 | 4 | 4 | 7000 | 28000 | 28000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 16 | Contingency | PS |  | 1 | 1 | 20000 | 20000 | 20000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
Schedule B - Drainage Dysart Bypass Rd
| 1 | Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
45 | (a) | 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfill. | m | 1297.351 | 1.22 | 1.22 | 1644.63 | 2006.45 | 2006.4486 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 2006.4486 | 2006.4486 | 2006.4486 | 2006.4486 | 2006.4486 | 2006.4486
46 | (b) | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | No | 1257.8 | 1 | 1 | 1594.49 | 1594.49 | 1594.49 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1594.49 | 1594.49 | 1594.49 | 1594.49 | 1594.49
| 2 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
47 | (a) | 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 1344.931 | 1.22 | 1.22 | 2718.95 | 3317.12 | 3317.119 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 3317.119 | 3317.119 | 3317.119 | 3317.119 | 3317.119 | 3317.119
48 | (b) | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No | 2338.85 | 1 | 1 | 2964.92 | 2964.92 | 2964.92 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2964.92 | 2964.92 | 2964.92 | 2964.92 | 2964.92
| 3 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359
49 | (a) | Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | m | 20898.8887 | 2.44 | 2.44 | 10857.8 | 26493.03 | 26493.032 |  | 0% | 2.44 | 100% | 2.44 | 100% | 2.44 | 100% | 2.44 | 100% | 2.44 | 100% | 0 | 26493.032 | 26493.032 | 26493.032 | 26493.032 | 26493.032
50 | (b) | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | m | 64286.6382 | 12.2 | 12.2 | 6679.84 | 81494.05 | 81494.048 |  | 0% | 12.2 | 100% | 12.2 | 100% | 12.2 | 100% | 12.2 | 100% | 12.2 | 100% | 0 | 81494.048 | 81494.048 | 81494.048 | 81494.048 | 81494.048
51 | (c) | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | No | 2161.4 | 2 | 2 | 2294.88 | 4589.76 | 4589.76 |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 4589.76 | 4589.76 | 4589.76 | 4589.76 | 4589.76
52 | (d) | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | Item | 1661.4 | 1 | 1 | 2105.7 | 2105.7 | 2105.7 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2105.7 | 2105.7 | 2105.7 | 2105.7 | 2105.7
53 | (e) | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | Item | 3372.6 | 1 | 1 | 4275.38 | 4275.38 | 4275.38 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 4275.38 | 4275.38 | 4275.38 | 4275.38
| 4 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
54 | (a) | 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 2118.874 | 1.22 | 1.22 | 2718.95 | 3317.12 | 3317.119 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 3317.119 | 3317.119 | 3317.119 | 3317.119 | 3317.119 | 3317.119
55 | (b) | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No | 2338.85 | 1 | 1 | 2964.92 | 2964.92 | 2964.92 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2964.92 | 2964.92 | 2964.92 | 2964.92 | 2964.92
| 5 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359
56 | (a) | 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | m | 2078.392 | 1.22 | 1.22 | 2718.95 | 3317.12 | 3317.119 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 3317.119 | 3317.119 | 3317.119 | 3317.119 | 3317.119 | 3317.119
57 | (b) | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No | 2338.85 | 1 | 1 | 2964.92 | 2964.92 | 2964.92 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 2964.92 | 2964.92 | 2964.92 | 2964.92
| 6 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
58 | (a) | 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 1306.8446 | 1.22 | 1.22 | 1689.56 | 2061.26 | 2061.2632 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 2061.2632 | 2061.2632 | 2061.2632 | 2061.2632 | 2061.2632 | 2061.2632
59 | (b) | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | No | 1257.8 | 1 | 1 | 1594.49 | 1594.49 | 1594.49 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1594.49 | 1594.49 | 1594.49 | 1594.49 | 1594.49
| 7 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
60 | (a) | 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 2147.6137 | 1.22 | 1.22 | 2720.94 | 3319.55 | 3319.5468 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 3319.5468 | 3319.5468 | 3319.5468 | 3319.5468 | 3319.5468 | 3319.5468
61 | (b) | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No | 2147.975 | 1 | 1 | 2722.95 | 2722.95 | 2722.95 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2722.95 | 2722.95 | 2722.95 | 2722.95 | 2722.95
| 8 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
62 | (a) | 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 3398.3134 | 1.22 | 1.22 | 3999.15 | 4878.96 | 4878.963 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 4878.963 | 4878.963 | 4878.963 | 4878.963 | 4878.963 | 4878.963
63 | (b) | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | No | 4019.9 | 1 | 1 | 5093.34 | 5093.34 | 5093.34 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 5093.34 | 5093.34 | 5093.34 | 5093.34
| 9 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
64 | (a) | 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 1332.7946 | 1.22 | 1.22 | 1689.56 | 2061.26 | 2061.2632 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 2061.2632 | 2061.2632 | 2061.2632 | 2061.2632 | 2061.2632 | 2061.2632
65 | (b) | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | No | 892.8 | 1 | 1 | 1594.49 | 1594.49 | 1594.49 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1594.49 | 1594.49 | 1594.49 | 1594.49 | 1594.49
| 10 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359
66 | (a) | 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | m | 1980.785 | 1.22 | 1.22 | 2610.2 | 3184.44 | 3184.444 | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 1.22 | 100% | 3184.444 | 3184.444 | 3184.444 | 3184.444 | 3184.444 | 3184.444
265 | (b) | 2 x 375 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | No | 2147.975 | 1 | 1 | 2722.95 | 2722.95 | 2722.95 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2722.95 | 2722.95 | 2722.95 | 2722.95 | 2722.95
| 11 | Ch 2780 New 1/600 x 300 RCBC,Installation to Main Roads Std Dwg 1359
266 | (a) | 1/600 x 300 RCBC Complete in place, including excavate, sand, supply, lay and backfill. | m | 9926.3853 | 14.4 | 14.4 | 928.68 | 13372.99 | 13372.992 |  | 0% | 14.4 | 100% | 14.4 | 100% | 14.4 | 100% | 14.4 | 100% | 14.4 | 100% | 0 | 13372.992 | 13372.992 | 13372.992 | 13372.992 | 13372.992
67 | (b) | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | No | 947.8 | 2 | 2 | 600.75 | 1201.5 | 1201.5 |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 1201.5 | 1201.5 | 1201.5 | 1201.5 | 1201.5
68 | (c) | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | Item | 1658.0838 | 1 | 1 | 2105.7 | 2105.7 | 2105.7 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2105.7 | 2105.7 | 2105.7 | 2105.7 | 2105.7
69 | (d) | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock | Item | 2322.6 | 1 | 1 | 2944.32 | 2944.32 | 2944.32 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
70 | 12 | Ch 2800 Take up and stack existing 1/600 x 300 RCBC and backfill to reinstate roadway. | Item | 4666.85 | 1 | 1 | 5916.08 | 5916.08 | 5916.08 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
1326531.48
Schedule C - Dysart Middlemount / Dysart Bypass Intersection
| 1 | Preliminaries
| (a) | Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | Item |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
71 | (b) | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | Item | 28325.0469 | 1 | 1 | 35907.08 | 35907.08 | 35907.08 |  | 0% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 0 | 28725.664 | 28725.664 | 28725.664 | 35907.08 | 35907.08
72 | (c ) | Construction Setout by Contractor | Item | 5180 | 1 | 1 | 6566.59 | 6566.59 | 6566.59 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 6566.59 | 6566.59 | 6566.59 | 6566.59 | 6566.59
[Note: Council to provide an initial control line, TBM's, prior to commencement of works; Contractor shall be responsible for all other setout to construct the works
73 | (d ) | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | Item | 2800 | 1 | 1 | 3549.51 | 3549.51 | 3549.51 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 3549.51 | 3549.51 | 3549.51 | 3549.51 | 3549.51
74 | (e) | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | Item | 3200 | 1 | 1 | 4056.58 | 4056.58 | 4056.58 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 4056.58 | 4056.58 | 4056.58 | 4056.58 | 4056.58
75 | (f) | As Constructed Survey Data to Council Requirements. | Item | 5920 | 1 | 1 | 7504.67 | 7504.67 | 7504.67 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| (g) | Geotechnical Testing by NATA Registered laboratory
76 | (i) | Subgrade Compaction testing as specified | No | 846.6667 | 4 | 4 | 268.32 | 1073.28 | 1073.28 |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 1073.28 | 1073.28 | 1073.28 | 1073.28 | 1073.28
77 | (ii) | Sub-Base Compaction testing as specified - assume 2 layers | No | 846.6667 | 4 | 4 | 268.32 | 1073.28 | 1073.28 |  | 0% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 1073.28 | 1073.28 | 1073.28 | 1073.28 | 1073.28
78 | (iii) | Base Compaction testing as specified | No | 423.3333 | 2 | 2 | 268.34 | 536.68 | 536.68 |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 536.68 | 536.68 | 536.68
79 | (iv) | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | No | 1290 | 1 | 1 | 1635.31 | 1635.31 | 1635.31 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1635.31 | 1635.31 | 1635.31 | 1635.31 | 1635.31
80 | (v) | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | No | 1290 | 1 | 1 | 1635.31 | 1635.31 | 1635.31 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1635.31 | 1635.31 | 1635.31 | 1635.31 | 1635.31
81 | 2 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | Item | 5321.3964 | 1 | 1 | 6740.02 | 6740.02 | 6740.02 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 6740.02 | 6740.02 | 6740.02 | 6740.02 | 6740.02
| 3 | Earthworks - excavate and place as embankment as directed
82 | (a) | Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | m3 | 4967.1131 | 379 | 379 | 16.61 | 6295.19 | 6295.19 |  | 0% | 379 | 100% | 379 | 100% | 379 | 100% | 379 | 100% | 379 | 100% | 0 | 6295.19 | 6295.19 | 6295.19 | 6295.19 | 6295.19
83 | (b) | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 | 3143.5 | 50 | 63.5 | 62.87 | 3143.5 | 3992.245 |  | 0% | 63.5 | 100% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 3992.245 | 0 | 0 | 0 | 0
| 4 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
84 | (a) | Dysart Bypass Rd - Middlemount Rd Intersection LHS | m2 | 1843.905 | 630 | 630 | 3.71 | 2337.3 | 2337.3 |  | 0% | 630 | 100% | 630 | 100% | 630 | 100% | 630 | 100% | 630 | 100% | 0 | 2337.3 | 2337.3 | 2337.3 | 2337.3 | 2337.3
85 | (b) | Dysart Bypass Rd - Middlemount Rd Intersection RHS | m2 | 1680.0023 | 574 | 574 | 3.71 | 2129.54 | 2129.54 |  | 0% | 574 | 100% | 574 | 100% | 574 | 100% | 574 | 100% | 574 | 100% | 0 | 2129.54 | 2129.54 | 2129.54 | 2129.54 | 2129.54
| 5 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results
86 | (a) | Dysart Bypass Rd - Middlemount Rd Intersection LHS | m2 | 925.4336 | 437 | 437 | 2.68 | 1171.16 | 1171.16 |  | 0% |  | 0% | 437 | 100% | 437 | 100% | 437 | 100% | 437 | 100% | 0 | 0 | 1171.16 | 1171.16 | 1171.16 | 1171.16
87 | (b) | Dysart Bypass Rd - Middlemount Rd Intersection RHS | m2 | 878.8442 | 415 | 415 | 2.68 | 1112.2 | 1112.2 |  | 0% |  | 0% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 0 | 0 | 1112.2 | 1112.2 | 1112.2 | 1112.2
| 6 | Gravel Pavement
In Place complete, including supply, spreading, watering, rolling and trimming:-
(a) Dysart Bypass Rd - Middlemount Rd Intersection LHS
88 | (i) | Base QT Type 2.1 @ 150mm deep | m3 | 7478.2426 | 70 | 70 | 135.43 | 9480.1 | 9480.1 |  | 0% | 70 | 100% | 70 | 100% | 70 | 100% | 70 | 100% | 70 | 100% | 0 | 9480.1 | 9480.1 | 9480.1 | 9480.1 | 9480.1
89 | (ii) | Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 | 11116.7155 | 107 | 107 | 131.71 | 14092.97 | 14092.97 |  | 0% | 107 | 100% | 107 | 100% | 107 | 100% | 107 | 100% | 107 | 100% | 0 | 14092.97 | 14092.97 | 14092.97 | 14092.97 | 14092.97
90 | (iii) | Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 | 9160.1584 | 90 | 90 | 129.02 | 11611.8 | 11611.8 |  | 0% | 90 | 100% | 90 | 100% | 90 | 100% | 90 | 100% | 90 | 100% | 0 | 11611.8 | 11611.8 | 11611.8 | 11611.8 | 11611.8
(b) Dysart Bypass Rd - Middlemount Rd Intersection RHS
91 | (i) | Base QT Type 2.1 @ 150mm deep | m3 | 7050.9145 | 66 | 66 | 135.43 | 8938.38 | 8938.38 |  | 0% | 66 | 100% | 66 | 100% | 66 | 100% | 66 | 100% | 66 | 100% | 0 | 8938.38 | 8938.38 | 8938.38 | 8938.38 | 8938.38
92 | (ii) | Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 | 10285.5592 | 99 | 99 | 131.71 | 13039.29 | 13039.29 |  | 0% | 99 | 100% | 99 | 100% | 99 | 100% | 99 | 100% | 99 | 100% | 0 | 13039.29 | 13039.29 | 13039.29 | 13039.29 | 13039.29
93 | (iii) | Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 | 8447.7016 | 83 | 83 | 129.02 | 10708.66 | 10708.66 |  | 0% | 83 | 100% | 83 | 100% | 83 | 100% | 83 | 100% | 83 | 100% | 0 | 10708.66 | 10708.66 | 10708.66 | 10708.66 | 10708.66
| 7 | Provisional Item Pavement Repairs
94 | (a) | Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | m2 | 5610.0655 | 30 | 30 | 186.99 | 5609.7 | 5609.7 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED
95 | (a) | Dysart Bypass Rd - Middlemount Rd Intersection LHS | m2 | 2355.43 | 437 | 437 | 5.52 | 2412.24 | 2412.24 |  | 0% |  | 0% | 437 | 100% | 437 | 100% | 437 | 100% | 437 | 100% | 0 | 0 | 2412.24 | 2412.24 | 2412.24 | 2412.24
96 | (b) | Dysart Bypass Rd - Middlemount Rd Intersection RHS | m2 | 2236.85 | 415 | 415 | 5.52 | 2290.8 | 2290.8 |  | 0% |  | 0% | 415 | 100% | 415 | 100% | 415 | 100% | 415 | 100% | 0 | 0 | 2290.8 | 2290.8 | 2290.8 | 2290.8
| 9 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place.
97 | (a) | Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | m2 | 115460.5466 | 2776 | 2776 | 42.63 | 118340.88 | 118340.88 |  | 0% |  | 0% |  | 0% |  | 0% | 2776 | 100% | 2776 | 100% | 0 | 0 | 0 | 0 | 118340.88 | 118340.88
| 10 | Medians Kerb at Intersections
98 | (a) | Type 5 Concrete Kerb in minimum 25 MPa concrete | m | 5701.1957 | 67 | 67 | 107.87 | 7227.29 | 7227.29 |  | 0% |  | 0% |  | 0% |  | 0% | 67 | 100% | 67 | 100% | 0 | 0 | 0 | 0 | 7227.29 | 7227.29
| 11 | Street Lighting - Conduits and Bases
99 | (a) | Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | m | 2078.1625 | 79 | 79 | 45.04 | 3558.16 | 3558.16 |  | 0% |  | 0% |  | 0% |  | 0% | 79 | 100% | 79 | 100% | 0 | 0 | 0 | 0 | 3558.16 | 3558.16
100 | (b) | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | m | 3600 | 20 | 20 | 228.18 | 4563.6 | 4563.6 |  | 0% |  | 0% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 0 | 4563.6 | 4563.6 | 4563.6 | 4563.6
101 | (c) | Electrical Mains Cable Pit (Provisional Item) | No | 2452.8 | 2 | 2 | 1554.68 | 3109.36 | 3109.36 |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 3109.36 | 3109.36
102 | (d) | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | No | 2690.8 | 2 | 2 | 1705.54 | 3411.08 | 3411.08 |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 3411.08 | 3411.08
| 12 | Soil Management Measures inclusive of:
103 | (a) | Prepare batters and drains for hydromulch placement | m2 | 767.25 | 1000 | 1000 | 0.97 | 970 | 970 |  | 0% |  | 0% |  | 0% |  | 0% | 1000 | 100% | 1000 | 100% | 0 | 0 | 0 | 0 | 970 | 970
104 | (b) | Hydromulch to all disturbed areas as directed (batters and drains) | m2 | 1125 | 1000 | 1000 | 1.43 | 1430 | 1430 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
105 | (c) | Rock check dams as directed | No | 1626.4 | 6 | 6 | 343.63 | 2061.78 | 2061.78 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 13 | Road Furniture
106 | (a) | Supply and Install New Guide Posts | No | 550 | 11 | 11 | 63.38 | 697.18 | 697.18 |  | 0% |  | 0% |  | 0% | 11 | 100% | 11 | 100% | 11 | 100% | 0 | 0 | 0 | 697.18 | 697.18 | 697.18
107 | (b) | Supply and Install New Give Way Sign R1-2 | No | 338.8 | 1 | 1 | 429.49 | 429.49 | 429.49 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 429.49 | 429.49 | 429.49
108 | (c) | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | Item | 7500 | 1 | 1 | 9507.61 | 9507.61 | 9507.61 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 9507.61
| 14 | Drainage - Ch 140 Middlemount Road
109 | (a) | Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | m | 4014.9044 | 3.6 | 3.6 | 1413.78 | 5089.61 | 5089.608 |  | 0% | 3.6 | 100% | 3.6 | 100% | 3.6 | 100% | 3.6 | 100% | 3.6 | 100% | 0 | 5089.608 | 5089.608 | 5089.608 | 5089.608 | 5089.608
110 | (b) | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | No | 947.8 | 1 | 1 | 1201.51 | 1201.51 | 1201.51 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1201.51 | 1201.51 | 1201.51 | 1201.51 | 1201.51
| 15 | Contingency | PS |  | 1 | 1 | 10000 | 10000 | 10000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
336248.69
Schedule D - Golden Mile Road & Dysart Bypass Road Intersection Upgrade Works
| 1 | Preliminaries
| (a) | Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | Item |  | 1 | 1 |  |  |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
111 | (b) | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | Item | 28325.0469 | 1 | 1 | 35907.08 | 35907.08 | 35907.08 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
112 | (c ) | Construction Setout by Contractor | Item | 5180 | 1 | 1 | 6566.59 | 6566.59 | 6566.59 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
[Note: Council to provide an initial control line, TBM's, prior to commencement of works; Contractor shall be responsible for all other setout to construct the works
113 | (d ) | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | Item | 2800 | 1 | 1 | 3549.51 | 3549.51 | 3549.51 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
114 | (e) | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | Item | 3200 | 1 | 1 | 4056.58 | 4056.58 | 4056.58 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
115 | (f) | As Constructed Survey Data to Council Requirements. | Item | 5920 | 1 | 1 | 7504.67 | 7504.67 | 7504.67 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| (g) | Geotechnical Testing by NATA Registered laboratory
116 | (i) | Subgrade Compaction testing as specified | No | 846.6667 | 4 | 4 | 268.32 | 1073.28 | 1073.28 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
117 | (ii) | Sub-Base Compaction testing as specified - assume 2 layers | No | 846.6667 | 4 | 4 | 268.32 | 1073.28 | 1073.28 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
118 | (iii) | Base Compaction testing as specified | No | 423.3333 | 2 | 2 | 268.34 | 536.68 | 536.68 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
119 | (iv) | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | No | 1290 | 1 | 1 | 1635.31 | 1635.31 | 1635.31 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
120 | (v) | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | No | 1290 | 1 | 1 | 1635.31 | 1635.31 | 1635.31 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
121 | 2 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | Item | 5321.3964 | 1 | 1 | 6740.02 | 6740.02 | 6740.02 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 3 | Earthworks - excavate and place as embankment as directed
122 | (a) | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | m3 | 4967.1 | 396 | 396 | 15.9 | 6296.4 | 6296.4 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
123 | (b) | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | m3 | 3143.5 | 50 | 50 | 62.87 | 3143.5 | 3143.5 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 4 | Prepare Dysart Bypass Rd - Golden Mile Rd Intersection Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor)
124 | (a) | Dysart Bypass Rd - Golden Mile Rd Intersection LHS | m2 | 1270.2457 | 434 | 434 | 3.71 | 1610.14 | 1610.14 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
125 | (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | m2 | 2429.2717 | 830 | 830 | 3.71 | 3079.3 | 3079.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 5 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results
126 | (a) | Dysart Bypass Rd - Golden Mile Rd Intersection LHS | m2 | 599.3082 | 283 | 283 | 2.68 | 758.44 | 758.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
127 | (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | m2 | 1264.2651 | 597 | 597 | 2.68 | 1599.96 | 1599.96 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 6 | Gravel Pavement
In Place complete, including supply, spreading, watering, rolling and trimming:-
| (a) | Dysart Bypass Rd - Golden Mile Rd Intersection LHS
128 | (i) | Base QT Type 2.1 @ 150mm deep | m3 | 4914.2737 | 46 | 46 | 135.43 | 6229.78 | 6229.78 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
129 | (ii) | Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 | 7480.4067 | 72 | 72 | 131.71 | 9483.12 | 9483.12 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
130 | (iii) | Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 | 6310.3313 | 62 | 62 | 129.02 | 7999.24 | 7999.24 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS
131 | (i) | Base QT Type 2.1 @ 150mm deep | m3 | 10149.0436 | 95 | 95 | 135.43 | 12865.85 | 12865.85 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
132 | (ii) | Upper Sub-Base QT Type 2.3 @ 200mm deep | m3 | 14856.9188 | 143 | 143 | 131.71 | 18834.53 | 18834.53 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
133 | (iii) | Lower Sub-Base QT Type 2.5 @ 150mm deep | m3 | 12111.765 | 119 | 119 | 129.02 | 15353.38 | 15353.38 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 7 | Provisional Item Pavement Repairs
134 | (a) | Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | m2 | 5610.0655 | 30 | 30 | 186.99 | 5609.7 | 5609.7 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED
135 | (a) | Dysart Bypass Rd - Golden Mile Rd Intersection LHS | m2 | 1525.37 | 283 | 283 | 5.52 | 1562.16 | 1562.16 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
136 | (b) | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | m2 | 3217.83 | 597 | 597 | 5.52 | 3295.44 | 3295.44 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 9 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place.
137 | (a) | Dysart Bypass Rd - Golden Mile Rd Intersection Complete (overlaying existing seal area) | m2 | 121115.2984 | 2912 | 2912 | 42.63 | 124138.56 | 124138.56 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 10 | Medians Kerb at Intersections
138 | (a) | Type 5 Concrete Kerb in minimum 25 MPa concrete | m | 5701.1988 | 67 | 67 | 107.87 | 7227.29 | 7227.29 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 11 | Street Lighting - Conduits and Bases
139 | (a) | Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | m | 2770.989 | 78 | 78 | 45.04 | 3513.12 | 3513.12 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
140 | (b) | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | m | 3860 | 22 | 22 | 222.42 | 4893.24 | 4893.24 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
141 | (c) | Electrical Mains Cable Pit (Provisional Item) | No | 2452.8 | 2 | 2 | 1554.68 | 3109.36 | 3109.36 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
142 | (d) | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | No | 2690.8 | 2 | 2 | 1705.54 | 3411.08 | 3411.08 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 12 | Soil Management Measures inclusive of:
143 | (a) | Prepare batters and drains for hydromulch placement | m2 | 767.25 | 1000 | 1000 | 0.97 | 970 | 970 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
144 | (b) | Hydromulch to all disturbed areas as directed (batters & drains) | m2 | 1125 | 1000 | 1000 | 1.43 | 1430 | 1430 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
145 | (c) | Rock check dams as directed | No | 1626.4 | 6 | 6 | 343.63 | 2061.78 | 2061.78 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 13 | Road Furniture
146 | (a) | Supply and Install New Guide Posts | No | 500 | 10 | 10 | 63.38 | 633.8 | 633.8 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
147 | (b) | Supply and Install New Give Way Sign R1-2 | No | 338.8 | 1 | 1 | 429.49 | 429.49 | 429.49 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
148 | (c) | Linemarking Complete,Dysart Bypass Rd - Golden Mile Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | Item | 7500 | 1 | 1 | 9507.61 | 9507.61 | 9507.61 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
| 14 | Contingency | PS |  | 1 | 1 | 10000 | 10000 | 10000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0
339324.58
Variations
149 | PV01 | Revised Tender Rates - Seal & Asphalt | each | 35549.91 | 1 | 1 | 47264.15 | 47264.15 | 47264.15 |  | 0% |  | 0% | 0.2383 | 23.83% | 0.2383 | 23.83% | 0.8 | 80% | 0.8 | 80% | 0 | 0 | 11263.0469 | 11263.0469 | 37811.32 | 37811.32
150 | PV02 | Revised pavement design | each | -416088.2822 | 1 | 1 | 579577.12 | 579577.12 | 579577.12 |  | 0% | 0.33 | 33% | 0.5918 | 59.18% | 0.8918 | 89.18% | 1 | 100% | 1 | 100% | 0 | 191260.4496 | 342993.7396 | 516866.8756 | 579577.12 | 579577.12
161 | PV03 | Remove & replace unsuitable - ch0 | each | 3300.675 | 1 | 1 | 3992.25 | 3992.25 | 3992.25 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 3992.25 | 3992.25 | 3992.25 | 3992.25 | 3992.25
162 | PV04 | Addiitonal drainage items | each | 7048.884 | 1 | 1 | 10555.47 | 10555.47 | 10555.47 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 10555.47 | 10555.47 | 10555.47 | 10555.47 | 10555.47
165 | PV05 | Asphalt redesign at floodway ch510-650 | tonne | 8872.96 | 32 | 32 | 406.42 | 13005.44 | 13005.44 |  | 0% |  | 0% |  | 0% |  | 0% | 32 | 100% | 32 | 100% | 0 | 0 | 0 | 0 | 13005.44 | 13005.44
166 | PV06 | Corrector course asphalt dysart-middlemount intersection | tonne | 4408.752 | 15.9 | 15.9 | 313.15 | 4979.09 | 4979.085 |  | 0% |  | 0% |  | 0% |  | 0% | 15.9 | 100% | 15.9 | 100% | 0 | 0 | 0 | 0 | 4979.085 | 4979.085
167 | PV07 | Corrector course asphalt dysart-middlemount road (DMR section) | tonne | 9704.8 | 35 | 35 | 313.15 | 10960.25 | 10960.25 |  | 0% |  | 0% |  | 0% |  | 0% | 35 | 100% | 35 | 100% | 0 | 0 | 0 | 0 | 10960.25 | 10960.25
168 | PV08 | Stabilisation of Edges - Bypass Road | m² | 22336.2232 | 3628 | 3628 | 25.4 | 92151.2 | 92151.2 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 3628 | 100% | 0 | 0 | 0 | 0 | 0 | 92151.2
|  | Total, all contract items and variations |  | 1309549.2003 |  |  |  | 2672285.655 | [13 empty] | 124170.4798 | 704783.6184 | 999735.8704 | 1197281.5564 | 1550994.3563 | 1652653.1663

## Portfolio WBS
Portfolio WBS | Description | Quantity | UOM | BAC | BAC Rate | Final Qty (AQ) | Final Cost (AC) | Final Rate | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 377 | hrs | 54760 | 145.252 | 477 | 71680.95 | 150.2745 | 24 | 3486.0477 | 0 | 0 | 0 | 74 | 10748.6472 | 121 | 27510.7 | 13890.9015 | 150 | 21787.7984 | 330 | 49553.2 | 37884.2767 | 250 | 36312.9973 | 423 | 63518.2 | 48560.7547 | 325 | 47206.8966 | 423 | 63518.2 | 48560.7547 | 377 | 54760 | 423 | 63518.2 | 48560.7547 | 377 | 54760 | 423 | 63518.2 | 48560.7547 | 377 | 54760 | 423 | 63518.2 | 48560.7547 | 377 | 54760 | 477 | 71680.95 | 54760
13 | QA Testing | 1 | item | 37361.6667 | 37361.6667 | 1 | 12680 | 12680 | 0 | 0 | 0 | 200 | 0 | 0.2 | 7472.3333 | 0 | 350 | 0 | 0.5 | 18680.8333 | 0 | 350 | 0 | 0.7 | 26153.1667 | 0 | 350 | 0 | 1 | 37361.6667 | 1 | 12680 | 37361.6667 | 1 | 37361.6667 | 1 | 12680 | 37361.6667 | 1 | 37361.6667 | 1 | 12680 | 37361.6667 | 1 | 37361.6667 | 1 | 12680 | 37361.6667 | 1 | 37361.6667 | 1 | 12680 | 37361.6667
15 | Service Locations | 20 | hrs | 6800 | 340 | 12 | 4080 | 340 | 20 | 6800 | 3.6 | 1260 | 2040 | 20 | 6800 | 3.6 | 1260 | 2040 | 20 | 6800 | 8.8 | 3010 | 4986.6667 | 20 | 6800 | 12 | 4080 | 6800 | 20 | 6800 | 12 | 4080 | 6800 | 20 | 6800 | 12 | 4080 | 6800 | 20 | 6800 | 12 | 4080 | 6800 | 20 | 6800 | 12 | 4080 | 6800 | 20 | 6800 | 12 | 4080 | 6800
21 | Clearing to Stockpile | 16000 | m2 | 24842.9261 | 1.5527 | 16000 | 1562.955 | 0.097685 | 2000 | 3105.3658 | 0 | 0 | 0 | 16000 | 24842.9261 | 16000 | 1520.005 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1520.005 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261 | 16000 | 24842.9261 | 16000 | 1562.955 | 24842.9261
53 | Cut to Spoil | 802 | m3 | 18732.0969 | 23.3567 | 802 | 3969.35 | 4.9493 | 0 | 0 | 0 | 0 | 0 | 600 | 14014.0376 | 500 | 2656.775 | 11678.3647 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969 | 802 | 18732.0969 | 802 | 3969.35 | 18732.0969
57 | Remove & Replace unsuitable | 153.5 | m3 | 9587.675 | 62.4604 | 153 | 4381.225 | 28.6355 | 0 | 0 | 0 | 0 | 0 | 50 | 3123.0212 | 0 | 0 | 0 | 153.5 | 9587.675 | 0 | 0 | 0 | 153.5 | 9587.675 | 135 | 3616.465 | 8459.7132 | 153.5 | 9587.675 | 135 | 3616.465 | 8459.7132 | 153.5 | 9587.675 | 153 | 4381.225 | 9587.675 | 153.5 | 9587.675 | 153 | 4381.225 | 9587.675 | 153.5 | 9587.675 | 153 | 4381.225 | 9587.675 | 153.5 | 9587.675 | 153 | 4381.225 | 9587.675
59 | Trim unpaved areas - footpaths, batters, drains etc | 29830 | m2 | 22887.0675 | 0.76725 | 29830 | 13518.27 | 0.45318 | 0 | 0 | 0 | 0 | 0 | 5000 | 3836.25 | 13600 | 4299.595 | 10434.6 | 20000 | 15345 | 25500 | 8091.27 | 19564.875 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675 | 29830 | 22887.0675 | 29830 | 13518.27 | 22887.0675
61 | Subgrade Preparation | 12535 | m2 | 37229.32 | 2.97 | 12535 | 213777.52 | 17.0544 | 0 | 0 | 0 | 0 | 0 | 6500 | 19305.1919 | 6000 | 103959.82 | 17820.1771 | 12535 | 37229.32 | 11500 | 198512.82 | 34155.3394 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32 | 12535 | 37229.32 | 12535 | 213777.52 | 37229.32
62 | Place & Compact Gravel | 4019 | m3 | 131637.1501 | 32.7537 | 4610 | 102754.37 | 22.2895 | 0 | 0 | 0 | 0 | 0 | 1000 | 32753.7074 | 800 | 18755.945 | 22843.7571 | 3000 | 98261.1223 | 1950 | 44983.34 | 55681.6579 | 4019 | 131637.1501 | 4500 | 100730.83 | 128496.1335 | 4019 | 131637.1501 | 4610 | 102754.37 | 131637.1501 | 4019 | 131637.1501 | 4610 | 102754.37 | 131637.1501 | 4019 | 131637.1501 | 4610 | 102754.37 | 131637.1501 | 4019 | 131637.1501 | 4610 | 102754.37 | 131637.1501 | 4019 | 131637.1501 | 4610 | 102754.37 | 131637.1501
63 | Trim All Layers | 9107 | m2 | 75658.8513 | 8.3078 | 9107 | 21913.25 | 2.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 20769.4222 | 0 | 0 | 0 | 9107 | 75658.8513 | 5750 | 14389.575 | 47769.6711 | 9107 | 75658.8513 | 9107 | 21913.25 | 75658.8513 | 9107 | 75658.8513 | 9107 | 21913.25 | 75658.8513 | 9107 | 75658.8513 | 9107 | 21913.25 | 75658.8513 | 9107 | 75658.8513 | 9107 | 21913.25 | 75658.8513 | 9107 | 75658.8513 | 9107 | 21913.25 | 75658.8513
64 | Sweep & Prime / Primer seal or Seal | 25142 | m2 | 217171.383 | 8.6378 | 21275 | 277417.806 | 13.0396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12500 | 107972.4082 | 12535 | 112816.375 | 127955.0311 | 12500 | 107972.4082 | 12535 | 112816.375 | 127955.0311 | 25142 | 217171.383 | 19500 | 175198.256 | 199052.5015 | 25142 | 217171.383 | 19500 | 176683.256 | 199052.5015 | 25142 | 217171.383 | 19500 | 176683.256 | 199052.5015 | 25142 | 217171.383 | 19500 | 176683.256 | 199052.5015 | 25142 | 217171.383 | 21275 | 277417.806 | 217171.383
65 | Asphalt | 605 | tonne | 296792.9945 | 490.5669 | 605 | 202459.38 | 334.6436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 605 | 296792.9945 | 605 | 202459.38 | 296792.9945 | 605 | 296792.9945 | 605 | 202459.38 | 296792.9945 | 605 | 296792.9945 | 605 | 202459.38 | 296792.9945 | 605 | 296792.9945 | 605 | 202459.38 | 296792.9945 | 605 | 296792.9945 | 605 | 202459.38 | 296792.9945
66 | Linemarking | 1 | item | 35476.8 | 35476.8 | 1 | 5622 | 5622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 35476.8 | 0 | 0 | 0 | 1 | 35476.8 | 0 | 0 | 0 | 1 | 35476.8 | 0 | 0 | 0 | 1 | 35476.8 | 0 | 0 | 0 | 1 | 35476.8 | 1 | 5622 | 35476.8
67 | Install Road Furniture | 1 | item | 33024 | 33024 | 1 | 2209.45 | 2209.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33024 | 1 | 2209.45 | 33024 | 1 | 33024 | 1 | 2209.45 | 33024 | 1 | 33024 | 1 | 2209.45 | 33024 | 1 | 33024 | 1 | 2209.45 | 33024 | 1 | 33024 | 1 | 2209.45 | 33024
68 | Insitu Stabilisation of Subgrade (cement/lime) | 600 | m2 | 13641.0744 | 22.7351 | 12535 | 51538.065 | 4.1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 13641.0744 | 12535 | 51538.065 | 13641.0744
71 | Place Kerb & Channel / Inverts | 134 | m | 6700.0025 | 50 | 134 | 4537.241 | 33.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 6700.0025 | 0 | 0 | 0 | 134 | 6700.0025 | 0 | 0 | 0 | 134 | 6700.0025 | 46 | 1562.241 | 2300.0009 | 134 | 6700.0025 | 134 | 4537.241 | 6700.0025 | 134 | 6700.0025 | 134 | 4537.241 | 6700.0025 | 134 | 6700.0025 | 134 | 4537.241 | 6700.0025 | 134 | 6700.0025 | 134 | 4537.241 | 6700.0025
72 | Form & Pour Headwalls | 11 | each | 32902.2621 | 2991.1147 | 11 | 18303.345 | 1663.9405 | 0 | 0 | 0 | 0 | 0 | 11 | 32902.2621 | 8 | 12371.185 | 23928.9179 | 11 | 32902.2621 | 9.5 | 14502.865 | 28415.59 | 11 | 32902.2621 | 10.5 | 17386.22 | 31406.7047 | 11 | 32902.2621 | 11 | 18303.345 | 32902.2621 | 11 | 32902.2621 | 11 | 18303.345 | 32902.2621 | 11 | 32902.2621 | 11 | 18303.345 | 32902.2621 | 11 | 32902.2621 | 11 | 18303.345 | 32902.2621 | 11 | 32902.2621 | 11 | 18303.345 | 32902.2621
81 | > 450 | 12.2 | m | 31756.2972 | 2602.9752 | 12.2 | 29127.06 | 2387.4639 | 6.1 | 15878.1486 | 6 | 11906.41 | 15617.8511 | 12.2 | 31756.2972 | 9.76 | 27821.715 | 25405.0377 | 12.2 | 31756.2972 | 9.76 | 27821.715 | 25405.0377 | 12.2 | 31756.2972 | 12.2 | 28091.715 | 31756.2972 | 12.2 | 31756.2972 | 12.2 | 29127.06 | 31756.2972 | 12.2 | 31756.2972 | 12.2 | 29127.06 | 31756.2972 | 12.2 | 31756.2972 | 12.2 | 29127.06 | 31756.2972 | 12.2 | 31756.2972 | 12.2 | 29127.06 | 31756.2972 | 12.2 | 31756.2972 | 12.2 | 29127.06 | 31756.2972
111 | Install Conduits / pits / rag bolts | 157 | m | 12960.464 | 82.5507 | 157 | 8890.215 | 56.6256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 12960.464 | 35 | 2010.27 | 2889.2754 | 157 | 12960.464 | 35 | 2010.27 | 2889.2754 | 157 | 12960.464 | 130 | 7286.295 | 10731.5944 | 157 | 12960.464 | 157 | 8890.215 | 12960.464 | 157 | 12960.464 | 157 | 8890.215 | 12960.464 | 157 | 12960.464 | 157 | 8890.215 | 12960.464 | 157 | 12960.464 | 157 | 8890.215 | 12960.464
121 | Lanscaping Sub-contractors | 29830 |  | 29981.05 | 1.0051 | 0 | 57433.5525 | 0 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 29830 | 29981.05 | 0 | 0 | 29981.05 | 29830 | 29981.05 | 0 | 0 | 29981.05 | 29830 | 29981.05 | 0 | 0 | 29981.05 | 29830 | 29981.05 | 0 | 0 | 29981.05 | 29830 | 29981.05 | 0 | 0 | 29981.05
141 | Traffic Controllers | 1104 | hrs | 115916.7531 | 104.9971 | 545 | 2466.425 | 4.5256 | 50 | 5249.853 | 0 | 0 | 0 | 250 | 26249.2648 | 122 | 12821.645 | 25948.3374 | 450 | 47248.6766 | 219 | 23008.6915 | 46579.3925 | 750 | 78747.7943 | 330 | 34629.2515 | 70188.1258 | 1104 | 115916.7531 | 480 | 50846.5065 | 102091.8193 | 1104 | 115916.7531 | 481 | 51017.0025 | 102304.5106 | 1104 | 115916.7531 | 481 | 51017.0025 | 102304.5106 | 1104 | 115916.7531 | 481 | 51017.0025 | 102304.5106 | 1104 | 115916.7531 | 545 | 57433.5525 | 115916.7531
151 | Supply & Place Silt fences & protective devices | 40 | each | 4542.6667 | 113.5667 | 40 | 23785.751 | 594.6438 | 0 | 0 | 0 | 0 | 0 | 40 | 4542.6667 | 0 | 0 | 0 | 40 | 4542.6667 | 0 | 0 | 0 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667 | 40 | 4542.6667 | 40 | 2466.425 | 4542.6667
181 | Place Box Culverts | 59.48 | m | 8767.5 | 147.4025 | 59.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 5896.0995 | 44 | 17252.126 | 6485.7095 | 59.48 | 8767.5 | 44 | 17252.126 | 6485.7095 | 59.48 | 8767.5 | 44 | 17252.126 | 6485.7095 | 59.48 | 8767.5 | 59.48 | 23785.751 | 8767.5 | 59.48 | 8767.5 | 59.48 | 23785.751 | 8767.5 | 59.48 | 8767.5 | 59.48 | 23785.751 | 8767.5 | 59.48 | 8767.5 | 59.48 | 23785.751 | 8767.5 | 59.48 | 8767.5 | 59.48 | 23785.751 | 8767.5
901 | Project Management | 10 | weeks | 32400 | 3240 | 1.8 | 5950 | 3305.5556 | 1 | 3240 | 0 | 0 | 0 | 3 | 9720 | 1.8 | 5950 | 32400 | 5 | 16200 | 1.8 | 5950 | 32400 | 7 | 22680 | 1.8 | 5950 | 32400 | 9 | 29160 | 1.8 | 5950 | 32400 | 10 | 32400 | 1.8 | 5950 | 32400 | 10 | 32400 | 1.8 | 5950 | 32400 | 10 | 32400 | 1.8 | 5950 | 32400 | 10 | 32400 | 1.8 | 5950 | 32400
902 | Project Supervision | 16 | weeks | 53600 | 3350 | 19.5 | 65379.85 | 3352.8128 | 2 | 6700 | 1.1 | 3721.65 | 3023.5897 | 9 | 30150 | 7.9 | 26574.775 | 21714.8718 | 12 | 40200 | 10.5 | 35074.775 | 28861.5385 | 15 | 50250 | 15.8 | 53029.9 | 43429.7436 | 16 | 53600 | 18 | 62991.05 | 49476.9231 | 16 | 53600 | 19.5 | 65379.85 | 53600 | 16 | 53600 | 19.5 | 65379.85 | 53600 | 16 | 53600 | 19.5 | 65379.85 | 53600 | 16 | 53600 | 19.5 | 65379.85 | 53600
903 | Project Facilities | 16 | weeks | 24500 | 1531.25 | 6 | 8814.25 | 1469.0417 | 0 | 0 | 0 | 0 | 0 | 2 | 3062.5 | 2.7 | 4260.94 | 11025 | 5 | 7656.25 | 4.7 | 7137.94 | 19191.6667 | 8 | 12250 | 4.7 | 7137.94 | 19191.6667 | 12 | 18375 | 5 | 7347.94 | 20416.6667 | 16 | 24500 | 5 | 7347.94 | 20416.6667 | 16 | 24500 | 6 | 8814.25 | 24500 | 16 | 24500 | 6 | 8814.25 | 24500 | 16 | 24500 | 6 | 8814.25 | 24500
904 | Project Insurance, Fees & Levies | 1 | item | 25000 | 25000 | 1 | 1203.86 | 1203.86 | 1 | 25000 | 0 | 0 | 0 | 1 | 25000 | 0 | 60 | 0 | 1 | 25000 | 0 | 60 | 0 | 1 | 25000 | 0 | 60 | 0 | 1 | 25000 | 0.9 | 1170.86 | 22500 | 1 | 25000 | 0.9 | 1170.86 | 22500 | 1 | 25000 | 0.9 | 1170.86 | 22500 | 1 | 25000 | 0.9 | 1170.86 | 22500 | 1 | 25000 | 1 | 1203.86 | 25000
905 | Small Tools | 1 | item | 5824 | 5824 | 1 | 9544.94 | 9544.94 | 0.25 | 1456 | 0.25 | 3029.05 | 1456 | 0.5 | 2912 | 0.5 | 5050.058 | 2912 | 0.75 | 4368 | 0.5 | 5821.508 | 2912 | 1 | 5824 | 0.75 | 7695.898 | 4368 | 1 | 5824 | 0.8 | 8904.81 | 4659.2 | 1 | 5824 | 0.9 | 9111.85 | 5241.6 | 1 | 5824 | 0.9 | 9111.85 | 5241.6 | 1 | 5824 | 0.9 | 9111.85 | 5241.6 | 1 | 5824 | 1 | 9544.94 | 5824
907 | Site Establishment | 1 | item | 19585 | 19585 | 1 | 45323.639 | 45323.639 | 0.5 | 9792.5 | 0.1 | 5412.915 | 1958.5 | 1 | 19585 | 0.25 | 10632.845 | 4896.25 | 1 | 19585 | 0.35 | 15208.395 | 6854.75 | 1 | 19585 | 0.7 | 31625.37 | 13709.5 | 1 | 19585 | 0.85 | 37969.525 | 16647.25 | 1 | 19585 | 0.9 | 39974.125 | 17626.5 | 1 | 19585 | 0.9 | 40378.175 | 17626.5 | 1 | 19585 | 0.9 | 40378.175 | 17626.5 | 1 | 19585 | 1 | 45323.639 | 19585
910 | De-Establishment & Cleanup | 1 | item | 5040 | 5040 | 1 | 530.25 | 530.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5040 | 0 | 0 | 0 | 1 | 5040 | 1 | 530.25 | 5040 | 1 | 5040 | 1 | 530.25 | 5040 | 1 | 5040 | 1 | 530.25 | 5040 | 1 | 5040 | 1 | 530.25 | 5040
911 | Accommodation | 254 | days | 31750.1718 | 125.0007 | 198 | 24904.43 | 125.7799 | 18 | 2250.0122 | 0 | 0 | 0 | 78 | 9750.0528 | 60 | 7525.35 | 9621.2642 | 138 | 17250.0934 | 67 | 8338.99 | 10743.745 | 198 | 24750.1339 | 128 | 15958.22 | 20525.3636 | 254 | 31750.1718 | 180 | 22436.24 | 28863.7926 | 254 | 31750.1718 | 198 | 24904.43 | 31750.1718 | 254 | 31750.1718 | 198 | 24904.43 | 31750.1718 | 254 | 31750.1718 | 198 | 24904.43 | 31750.1718 | 254 | 31750.1718 | 198 | 24904.43 | 31750.1718
C20 | C20 20MPA | 10 | m3 | 0 | 0 | 8.5 | 2513.5 | 295.7059 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 3.5 | 1035.5 | 0 | 10 | 0 | 3.5 | 1035.5 | 0 | 10 | 0 | 6.2 | 1825.5 | 0 | 10 | 0 | 8.5 | 2513.5 | 0 | 10 | 0 | 8.5 | 2513.5 | 0 | 10 | 0 | 8.5 | 2513.5 | 0 | 10 | 0 | 8.5 | 2513.5 | 0 | 10 | 0 | 8.5 | 2513.5 | 0
C32 | 32 Mpa | 4 | m3 | 1236 | 309 | 22 | 6886.8 | 313.0364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 2438.1 | 438.2182 | 0 | 0 | 8.8 | 2716.5 | 494.4 | 4 | 1236 | 22 | 6886.8 | 1236 | 4 | 1236 | 22 | 6886.8 | 1236 | 4 | 1236 | 22 | 6886.8 | 1236 | 4 | 1236 | 22 | 6886.8 | 1236 | 4 | 1236 | 22 | 6886.8 | 1236 | 4 | 1236 | 22 | 6886.8 | 1236
C40 | 40 MPa Concrete | 50 | m3 | 19981.0413 | 399.6208 | 23.3 | 7571.2 | 324.9442 | 0 | 0 | 0 | 0 | 0 | 50 | 19981.0413 | 21.6 | 7044.6 | 18523.1971 | 50 | 19981.0413 | 21.6 | 7044.6 | 18523.1971 | 50 | 19981.0413 | 21.6 | 7044.6 | 18523.1971 | 50 | 19981.0413 | 23.3 | 7571.2 | 19981.0413 | 50 | 19981.0413 | 23.3 | 7571.2 | 19981.0413 | 50 | 19981.0413 | 23.3 | 7571.2 | 19981.0413 | 50 | 19981.0413 | 23.3 | 7571.2 | 19981.0413 | 50 | 19981.0413 | 23.3 | 7571.2 | 19981.0413
CKM | Kerb Mix | 14.4 | m3 | 4452.2577 | 309.1846 | 7 | 2177.4 | 311.0571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4 | 4452.2577 | 0 | 0 | 0 | 14.4 | 4452.2577 | 0 | 0 | 0 | 14.4 | 4452.2577 | 7 | 2177.4 | 4452.2577 | 14.4 | 4452.2577 | 7 | 2177.4 | 4452.2577 | 14.4 | 4452.2577 | 7 | 2177.4 | 4452.2577 | 14.4 | 4452.2577 | 7 | 2177.4 | 4452.2577 | 14.4 | 4452.2577 | 7 | 2177.4 | 4452.2577
CSA | Cement Powder (Stabilising) | 50 | tonne | 19915.2797 | 398.3056 | 50.1 | 20711.157 | 413.3963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 19915.2797 | 50.1 | 20711.157 | 19915.2797
CSS | Stabilised Sand | 245 | m3 | 0 | 0 | 244 | 6711.32 | 27.5054 | 0 | 0 | 0 | 304 | 0 | 200 | 0 | 48 | 1813.02 | 0 | 245 | 0 | 48 | 1813.02 | 0 | 245 | 0 | 48 | 1813.02 | 0 | 245 | 0 | 244 | 6711.32 | 0 | 245 | 0 | 244 | 6711.32 | 0 | 245 | 0 | 244 | 6711.32 | 0 | 245 | 0 | 244 | 6711.32 | 0 | 245 | 0 | 244 | 6711.32 | 0
ETC | Conduits | 157 | m | 3521.4875 | 22.4299 | 157 | 5070.29 | 32.2948 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 |  | 3350.29 | 0 | 157 | 3521.4875 | 157 | 5070.29 | 3521.4875 | 157 | 3521.4875 | 157 | 5070.29 | 3521.4875 | 157 | 3521.4875 | 157 | 5070.29 | 3521.4875 | 157 | 3521.4875 | 157 | 5070.29 | 3521.4875 | 157 | 3521.4875 | 157 | 5070.29 | 3521.4875
ETP | Pits & Lids | 4 | each | 3120 | 780 | 4 | 3525 | 881.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3120 | 4 | 3525 | 3120 | 4 | 3120 | 4 | 3525 | 3120 | 4 | 3120 | 4 | 3525 | 3120 | 4 | 3120 | 4 | 3525 | 3120 | 4 | 3120 | 4 | 3525 | 3120 | 4 | 3120 | 4 | 3525 | 3120
QM2.3 | CBR45 | 4019 | tonne | -144410.7854 | -35.932 | 4610 | 36883.2 | 8.0007 | 0 | 0 | 0 | 0 | 0 | 1000 | -35932.0193 | 0 | 0 | 0 | 3000 | -107796.0578 | 0 | 0 | 0 | 4019 | -144410.7854 | 4610 | 36883.2 | -144410.7854 | 4019 | -144410.7854 | 4610 | 36883.2 | -144410.7854 | 4019 | -144410.7854 | 4610 | 36883.2 | -144410.7854 | 4019 | -144410.7854 | 4610 | 36883.2 | -144410.7854 | 4019 | -144410.7854 | 4610 | 36883.2 | -144410.7854 | 4019 | -144410.7854 | 4610 | 36883.2 | -144410.7854
QMR | Rock | 354 | tonne | 12390 | 35 | 178 | 6005.268 | 33.7375 | 0 | 0 | 0 | 0 | 0 | 150 | 5250 | 35 | 1222.028 | 2436.236 | 354 | 12390 | 35 | 1222.028 | 2436.236 | 354 | 12390 | 178 | 6005.268 | 12390 | 354 | 12390 | 178 | 6005.268 | 12390 | 354 | 12390 | 178 | 6005.268 | 12390 | 354 | 12390 | 178 | 6005.268 | 12390 | 354 | 12390 | 178 | 6005.268 | 12390 | 354 | 12390 | 178 | 6005.268 | 12390
QMS | Sand | 147.81 | tonne | 4061.305 | 27.4765 | 56 | 1428.3 |  | 100 | 2747.6524 | 0 | 0 | 0 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 147.81 | 4061.305 | 56 | 1428.3 |  | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305 | 147.81 | 4061.305 | 56 | 1428.3 | 4061.305
RSM | Mesh | 2.71 | tonne | 5959.8388 | 2199.2025 | 1.4 | 2909.52 | 2078.2286 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1.4 | 2909.52 | 5959.8388 |  | 0 | 1.4 | 2909.52 | 5959.8388 |  | 0 | 1.4 | 2909.52 | 5959.8388 | 2.71 | 5959.8388 | 1.4 | 2909.52 | 5959.8388 | 2.71 | 5959.8388 | 1.4 | 2909.52 | 5959.8388 | 2.71 | 5959.8388 | 1.4 | 2909.52 | 5959.8388 | 2.71 | 5959.8388 | 1.4 | 2909.52 | 5959.8388 | 2.71 | 5959.8388 | 1.4 | 2909.52 | 5959.8388
SWC | RCBC | 59.48 | m | 39512.1568 | 664.2932 | 59.48 | 20610 | 346.503 | 0 | 0 | 0 | 0 | 0 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568 | 59.48 | 39512.1568 | 59.48 | 20610 | 39512.1568
SWP | RCP | 12.2 | m | 6677.4459 | 547.3316 | 10.98 | 10500.25 | 956.3069 | 12.2 | 6677.4459 | 9.76 | 9270.25 | 5935.5075 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459 | 12.2 | 6677.4459 | 10.98 | 10500.25 | 6677.4459

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | Total | Portfolio WBS
Cost Code 011
2011-11-18 | Inv No - SI3632882 | Field Survey |  | 1 | 27510.7 | 27510.7 | 11
2011-12-12 | Inv No - SI3634032 | Field Survey |  | 1 | 22042.5 | 22042.5 | 11
2012-01-19 | Inv No - SI3636410 | Survey - Construction |  | 1 | 13965 | 13965 | 11
2012-06-30 | Inv No - SI3647090 | Survey - Construction |  | 1 | 901.5 | 901.5 | 11
2012-06-30 | Inv No - SI3650243 | Survey - Construction |  | 1 | 1975 | 1975 | 11
2012-06-30 | Inv No - SI3648966 | Survey - Construction |  | 1 | 3625 | 3625 | 11
2012-06-30 |  | Survey - Construction |  | 1 | 1661.25 | 1661.25 | 11
| Subtotal for 011 |  |  |  |  | 71680.95
Cost Code 013
2011-10-28 | Particle Size Distution(1) & Atterberg Limits (1) Inv No - CBW: 69122091 | Particle Distribution |  | 2 | 100 | 200 | 13
2011-11-25 | Compressive Strength Set (3) Inv No - CBW:69122291 | Compressive Set |  | 1 | 150 | 150 | 13
2012-02-24 | Inv No - CBW69122763 | Field Density |  | 1 | 3640 | 3640 | 13
2012-02-27 | Inv No - CBW 69122542 | Field Density |  | 1 | 8690 | 8690 | 13
| Subtotal for 013 |  |  |  |  | 12680
Cost Code 015
2011-10-25 | Inv - 2898 | Electrical Pit - Precast |  | 1 | 1260 | 1260 | 15
2011-12-11 | Inv No 6065 | Service Locator |  | 1 | 1750 | 1750 | 15
2012-01-31 | Inv No - 2952 | Service Locator |  | 1 | 1070 | 1070 | 15
| Subtotal for 015 |  |  |  |  | 4080
Cost Code 021
2011-11-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 21
2011-11-09 | Excavator Hyundi | Excavator Hyundi | hr | 9.5 | 80 | 760 | 21
2011-11-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 21
2012-01-30 | Disposal for Dysart Landfill. Inv No - 71300 | Waste Disposal |  | 1 | 42.95 | 42.95 | 21
| Subtotal for 021 |  |  |  |  | 1562.955
Cost Code 053
2011-11-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-12 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 53
2011-11-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-12 | Labour HIre | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-12 | Excavator Hyundi | Excavator Hyundi | hr | 2 | 80 | 160 | 53
2011-11-12 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 53
2011-11-14 | Labour HIre | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-11-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 53
2011-11-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 53
2011-11-16 | Excavator Hyundi | Excavator Hyundi | hr | 3.5 | 80 | 280 | 53
2011-11-16 | Labour HIre | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2011-11-16 | Excavator Hyundi | Excavator Hyundi | hr | 2 | 80 | 160 | 53
2011-11-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 53
2011-11-27 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-11-27 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-11-27 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 53
2011-11-27 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-12-08 | Labour HIre | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-12-08 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2011-12-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-12-08 | Excavator Hyundi | Excavator Hyundi | hr | 6 | 80 | 480 | 53
2011-12-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
| Subtotal for 053 |  |  |  |  | 3969.35
Cost Code 057
2012-01-27 | Petrol, Layflat house, Flex Drive Pump & Portable Vibshaft. Inv No - 7778877 | Portable Vibshaft |  | 1 | 139.7 | 139.7 | 57
2012-01-28 | People Resourcing ( Labour Hire ) | Labour | hr | 5.5 | 40.97 | 225.335 | 57
2012-01-28 | Excavator Hyundi | Excavator Hyundi | hr | 5.5 | 80 | 440 | 57
2012-01-28 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5.5 | 66.07 | 363.385 | 57
2012-01-28 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 5.5 | 50 | 275 | 57
2012-01-28 | Truck & Dog Hire | Biles Hire | hr | 8.5 | 130 | 1105 | 57
2012-01-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-01-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-01-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-01-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 57
2012-01-28 | Labour HIre | Labour | hr | 5.5 | 35.35 | 194.425 | 57
2012-01-31 | Tutt & Bryant (Rammer) Inv No - 7779027 | Rammer |  | 1 | 55 | 55 | 57
2012-03-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-03-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-03-07 |  | Plant Float - Allciv | hr | 4 | 7 | 28 | 57
2012-03-07 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 57
2012-03-07 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 57
2012-03-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 57
| Subtotal for 057 |  |  |  |  | 4381.225
Cost Code 059
2011-11-25 | Excavator Hyundi | Excavator Hyundi | hr | 3 | 80 | 240 | 59
2011-11-25 | Labour HIre | Labour | hr | 3 | 35.35 | 106.05 | 59
2011-11-27 | Labour HIre | Labour | hr | 6 | 35.35 | 212.1 | 59
2011-11-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 59
2011-11-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 59
2011-11-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 59
2011-11-27 | Excavator Hyundi | Excavator Hyundi | hr | 6 | 80 | 480 | 59
2011-11-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 59
2011-11-28 | Excavator Hyundi | Excavator Hyundi | hr | 6.5 | 80 | 520 | 59
2011-11-28 | Labour HIre | Labour | hr | 6.5 | 35.35 | 229.775 | 59
2011-11-29 | Excavator Hyundi | Excavator Hyundi | hr | 6.5 | 80 | 520 | 59
2011-11-29 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 59
2011-11-29 | Labour HIre | Labour | hr | 6.5 | 35.35 | 229.775 | 59
2011-11-30 | Excavator Hyundi | Excavator Hyundi | hr | 6.5 | 80 | 520 | 59
2011-11-30 | Labour HIre | Labour | hr | 6.5 | 35.35 | 229.775 | 59
2011-11-30 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 59
2011-12-01 | Labour HIre | Labour | hr | 6 | 35.35 | 212.1 | 59
2011-12-01 | Excavator Hyundi | Excavator Hyundi | hr | 6.5 | 80 | 520 | 59
2011-12-06 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 59
2011-12-06 | Excavator Hyundi | Excavator Hyundi | hr | 6 | 80 | 480 | 59
2011-12-08 | Excavator Hyundi | Excavator Hyundi | hr | 4.5 | 80 | 360 | 59
2011-12-08 | Labour HIre | Labour | hr | 4.5 | 35.35 | 159.075 | 59
2011-12-09 | Labour HIre | Labour | hr | 2 | 35.35 | 70.7 | 59
2011-12-09 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 59
2011-12-09 | Excavator Hyundi | Excavator Hyundi | hr | 2 | 80 | 160 | 59
2011-12-11 | Excavator Hyundi | Excavator Hyundi | hr | 10.5 | 80 | 840 | 59
2011-12-11 | Labour HIre | Labour | hr | 10.5 | 35.35 | 371.175 | 59
2011-12-12 | Labour HIre | Labour | hr | 10.5 | 35.35 | 371.175 | 59
2012-01-26 | Excavator Hyundi | Excavator Hyundi | hr | 10.5 | 80 | 840 | 59
2012-01-29 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 59
2012-01-29 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 59
2012-01-29 | Truck & Dog Hire | Biles Hire | hr | 8.5 | 95 | 807.5 | 59
2012-01-30 | Truck & Dog Hire | Biles Hire | hr | 3 | 95 | 285 | 59
2012-01-30 | Truck & Dog Hire | Biles Hire | hr | 5.5 | 95 | 522.5 | 59
2012-01-30 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 59
2012-01-30 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 59
2012-01-31 | StandBy | Biles Hire | hr | 5 | 45 | 225 | 59
2012-01-31 | Excavator Hyundi | Excavator Hyundi | hr | 5.5 | 80 | 440 | 59
| Subtotal for 059 |  |  |  |  | 13518.27
Cost Code 061
2011-11-13 | Labour HIre | Labour | hr | 2.5 | 35.35 | 88.375 | 61
2011-11-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 61
2011-11-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 61
2011-11-13 | Excavator Hyundi | Excavator Hyundi | hr | 3 | 80 | 240 | 61
2011-11-13 | Trailor | Plant Float - Allciv | hr | 3 | 7 | 21 | 61
2011-11-13 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 61
2011-11-13 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 61
2011-11-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 61
2011-11-14 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 61
2011-11-14 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 61
2011-11-14 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 61
2011-11-14 | Excavator Hyundi | Excavator Hyundi | hr | 6 | 80 | 480 | 61
2011-11-14 | Flexidrive Motor Petrol & Pump and Hoses Inv - 7774106 | Pump |  | 1 | 121 | 121 | 61
2011-11-15 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 61
2011-11-15 | Tutt & Bryant (Rammer) Hire from t Inv - 7774205 | Rammer |  | 1 | 99 | 99 | 61
2011-11-15 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 61
2011-11-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 61
2011-11-16 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 61
2011-11-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 61
2011-11-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 61
2011-11-22 | Excavator Hyundi | Excavator Hyundi | hr | 2 | 80 | 160 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 61
2011-11-22 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 61
2011-11-22 | Foreman | Labour | hr | 2 | 44.2 | 88.4 | 61
2011-11-22 | Labour HIre | Labour | hr | 2 | 35.35 | 70.7 | 61
2011-11-23 | Foreman | Labour | hr | 4 | 44.2 | 176.8 | 61
2011-11-23 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-11-23 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 61
2011-11-23 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 61
2011-11-23 | Padfoot Roller ( Tutt & Bryant ) | PF Roller | day | 1 | 365 | 365 | 61
2011-11-23 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 61
2011-11-23 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 61
2011-11-23 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 61
2011-11-23 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-11-23 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-11-24 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 61
2011-11-24 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 61
2011-11-24 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-11-24 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-11-25 | Grader Hire | Puccini Plant Hire | hr | 6 | 80 | 480 | 61
2011-11-25 | Excavator Hyundi | Excavator Hyundi | hr | 4.5 | 80 | 360 | 61
2011-11-25 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 61
2011-11-25 | Labour HIre | Labour | hr | 4.5 | 35.35 | 159.075 | 61
2011-11-26 | Grader Hire | Puccini Plant Hire | hr | 2 | 80 | 160 | 61
2011-11-27 | Grader Hire | Puccini Plant Hire | hr | 6 | 80 | 480 | 61
2011-11-28 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-11-29 | Grader Hire | Puccini Plant Hire | hr | 8 | 80 | 640 | 61
2011-11-29 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-11-30 | Flexidrive Motor Petrol & Pump and Hoses Inv No - 7775897 | Pump |  | 1 | 283.8 | 283.8 | 61
2011-11-30 | To Load & Delivery of Road Base (7567.31 ) and Loader Hire Inv No 556 | Road Base |  | 1 | 72538.48 | 72538.48 | 61
2011-11-30 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-11-30 | Tutt & Bryant (Portable Vibshaft) Hire from the 25/11/2011 to the 30/11/2011 Inv No 775896 | Portable Vibshaft |  | 1 | 330 | 330 | 61
2011-11-30 | Cat 120H Cat Coates rental Hire from the 31/10/2011 to the 30/11/2011 Inv No - 9070157 | Cat 12H Cat |  | 1 | 12375 | 12375 | 61
2011-11-30 | Tutt & Bryant (Rammer) Hire from the 30/11/2011 to the 30/11/2011 Inv No - 7775898 | Rammer |  | 1 | 77 | 77 | 61
2011-12-01 | Inv - 6000032322 | Cat 12H Cat |  | 1 | 10739.1 | 10739.1 | 61
2011-12-01 | Grader Hire | Puccini Plant Hire | hr | 2 | 80 | 160 | 61
2011-12-01 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-12-02 | Stabilised Sand Inv No - 9405436419 | Stabilised Sand |  | 1 | 751.1 | 751.1 | 61
2011-12-06 | Tipper Hire (Kennards) From th 14/11/2011 to the 28/11/2011 Inv No - 13245682 | Tipper ( Kennards ) |  | 1 | 1940 | 1940 | 61
2011-12-07 | Damage Waiver ( Multi Tyre Roller ) Inv No - 7775891 | Insurance |  | 1 | 910 | 910 | 61
2011-12-09 | Tutt & Bryant (Rammer) Hired from the 8/142/2011 to the 9/12/2011 Inv No 7776370 | Rammer |  | 1 | 60.5 | 60.5 | 61
2011-12-09 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 61
2011-12-10 | Grader Hire | Puccini Plant Hire | hr | 7 | 80 | 560 | 61
2011-12-10 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-12-11 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-12-12 | Tutt & Bryant (Rammer) Hire From the 12/12/2011 tio the 12/12/2011 Inv No 7776455 | Rammer |  | 1 | 60.5 | 60.5 | 61
2011-12-12 | Grader Hire | Puccini Plant Hire | hr | 6 | 80 | 480 | 61
2011-12-12 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 61
2011-12-12 | Tipper Hire (Kennards) Hired from the 28/11/2011 to the 12/12/2011 Inv No - 13284650 | Tipper ( Kennards ) |  | 1 | 1940.01 | 1940.01 | 61
2011-12-12 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 61
2011-12-13 | Excavator Hyundi | Excavator Hyundi | hr | 10.5 | 80 | 840 | 61
2011-12-14 | Flexidrive Motor Petrol & Pump and Hoses Inv - 7774106 | Pump |  | 1 | 204.6 | 204.6 | 61
2011-12-16 | Tipper Hire (Kennards) Hire from the 12/12/2011 to the 16/12/2011 Inv No - 13297542 | Tipper ( Kennards ) |  | 1 | 776 | 776 | 61
2011-12-22 | Hired from the 28/12/2011 to the 27/01/2012 Inv No 6000033304 | Grader |  | 1 | 10739.1 | 10739.1 | 61
2011-12-23 | To Load & Deliver Roadbase (3291.94) & Loader Hire Inv No- 561 | Road Base |  | 1 | 46214.05 | 46214.05 | 61
2011-12-24 | Inv - 3092 | Stemmings |  | 11.9 | 33.6 | 399.84 | 61
2011-12-31 | Multi Tyre Roller Hired from the 16/12/2011 to the 31/12/2011. Inv No 777937 | Multi Tyre Roller |  | 1 | 5005 | 5005 | 61
2011-12-31 | Bedding Sand Inv No 9405436420 | Stabilised Sand |  | 5 | 262.5 | 1312.5 | 61
2012-01-31 | Multi Tyre Roller. Hired from the 19/01/2012 to the 31/01/2012. Inv No - 7779727 | Multi Tyre Roller |  | 1 | 4235 | 4235 | 61
2012-01-31 | SD Roller - Dry. Hired from the 31/12/2011 to the 31/01/2012. Inv No - 7779725 | SD Roller |  | 1 | 3960 | 3960 | 61
2012-01-31 | Multi Tyre Roller.Hired from the 31/12/2011 to the 18/01/2012. Inv No 7779723 | Multi Tyre Roller |  | 1 | 6930 | 6930 | 61
2012-01-31 | Tutt & Bryant (Portable Vibshaft) . Inv N0 - 7778877 | Portable Vibshaft |  | 1 | 139.7 | 139.7 | 61
| Subtotal for 061 |  |  |  |  | 213777.52
Cost Code 062
2011-11-16 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-16 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-11-16 | Labour HIre | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-11-17 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-17 | Excavator Hyundi | Excavator Hyundi | hr | 4.5 | 80 | 360 | 62
2011-11-17 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-17 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-17 | Labour HIre | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-17 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 62
2011-11-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 62
2011-11-25 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-25 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-25 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-11-25 | Labour Hire | Labour | hr | 12 | 35.35 | 424.2 | 62
2011-11-26 | Labour HIre | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-26 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-11-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-11-26 | Excavator Hyundi | Excavator Hyundi | hr | 10.5 | 80 | 840 | 62
2011-11-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-27 | Foreman | Labour | hr | 10 | 44.2 | 442 | 62
2011-11-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-11-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 62
2011-11-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-11-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-27 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2011-11-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-11-28 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-28 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 62
2011-11-28 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-28 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-28 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-29 | Excavator Hyundi | Excavator Hyundi | hr | 2 | 80 | 160 | 62
2011-11-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-29 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2011-11-29 | Labour HIre | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-11-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-11-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-29 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-11-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-30 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-11-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-11-30 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2011-11-30 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 62
2011-11-30 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 62
2011-11-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-11-30 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-01 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-12-01 | Foreman | Labour | hr | 6 | 44.2 | 265.2 | 62
2011-12-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-12-01 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-12-01 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-12-01 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-02 | Tutt & Bryant (Portable Vibshaft) Hired from the 30/11/2011 to the 2/12/2011 Inv No - 7775994 | Portable Vibshaft |  | 1 | 66 | 66 | 62
2011-12-06 | People Resourcing ( Labour Hire ) | Labour | hr | 6 | 40.97 | 245.82 | 62
2011-12-06 | Foreman | Labour | hr | 5 | 44.2 | 221 | 62
2011-12-06 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8.5 | 42.79 | 363.715 | 62
2011-12-06 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-06 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-06 | People Resourcing (Labour Hire) | Labour | hr | 2.5 | 40.97 | 102.425 | 62
2011-12-06 | People Resourcing (Labour Hire) | Labour | hr | 6.5 | 40.97 | 266.305 | 62
2011-12-06 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-06 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-12-06 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2011-12-07 | Flexidrive Motor Petrol & Pump and Hoses Hire from the 30/11/2011 to the 1/11/2011 Inv No - 7775960 | Pump |  | 1 | 94.6 | 94.6 | 62
2011-12-07 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 62
2011-12-07 | People Resourcing ( Labour Hire ) | Labour | hr | 9.5 | 40.97 | 389.215 | 62
2011-12-07 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 62
2011-12-07 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-12-08 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2011-12-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 62
2011-12-08 | People Resourcing ( Labour Hire ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-08 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2011-12-08 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-09 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2011-12-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 62
2011-12-09 | People Resourcing ( Labour Hire ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-09 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 62
2011-12-09 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-09 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-12-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-12-10 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-10 | Excavator Hyundi | Excavator Hyundi | hr | 10.5 | 80 | 840 | 62
2011-12-10 | People Resourcing ( Labour Hire ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-10 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 9.5 | 66.07 | 627.665 | 62
2011-12-10 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-10 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-10 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-10 | Labour HIre | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-10 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-12-10 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-11 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-11 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-12-11 | People Resourcing ( Labour Hire ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-11 | Travell Time | Labour | hr | 2.5 | 40.97 | 102.425 | 62
2011-12-11 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-11 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-11 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-12-11 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-12-12 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2011-12-12 | People Resourcing ( Labour Hire ) | Labour | hr | 10 | 40.97 | 409.7 | 62
2011-12-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-12-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-12-12 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-12-12 | Foreman | Labour | hr | 10 | 44.2 | 442 | 62
2011-12-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-12-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 62
2011-12-13 | People Resourcing ( Labour Hire ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-13 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-12-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-12-14 | People Resourcing ( Labour Hire ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-14 | Excavator Hyundi | Excavator Hyundi | hr | 9 | 80 | 720 | 62
2011-12-14 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-12-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 62
2011-12-15 | Travel Time | Labour | hr | 2.5 | 40.97 | 102.425 | 62
2011-12-15 | People Resourcing ( Labour Hire ) | Labour | hr | 10 | 40.97 | 409.7 | 62
2011-12-15 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2011-12-15 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-12-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 62
2011-12-15 | Travel time | Labour | hr | 2.5 | 40.97 | 102.425 | 62
2011-12-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 62
2011-12-16 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2011-12-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2012-01-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 62
2012-01-09 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-09 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-09 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-01-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-10 | Labour Hire ( People Recourcing ) | Labour | hr | 10 | 40.97 | 409.7 | 62
2012-01-10 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 62
2012-01-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 62
2012-01-11 | Labour Hire ( People Recourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 62
2012-01-11 | Labour Hire ( People Recourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 62
2012-01-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-11 | 7/10mm con Agg Inv No- 3206 | Con Aggregate |  | 23.87 | 33.5 | 799.645 | 62
2012-01-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-12 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 62
2012-01-12 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-12 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-12 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-12 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-12 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-13 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2012-01-13 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-13 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 62
2012-01-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 62
2012-01-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 62
2012-01-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 62
2012-01-14 | Labour Hire ( People Recourcing ) & Travel Time | Labour | hr | 2.5 | 40.97 | 102.425 | 62
2012-01-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-01-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-01-14 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-01-14 | People Resourcing ( Labour Hire ) | Labour | hr | 6.5 | 40.97 | 266.305 | 62
2012-01-14 | People Resourcing (Labour Hire) | Labour | hr | 6.5 | 40.97 | 266.305 | 62
2012-01-15 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2012-01-15 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 62
2012-01-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-01-16 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-01-16 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-01-16 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-01-17 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-19 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2012-01-19 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-19 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-01-19 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 62
2012-01-20 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-23 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-24 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-25 | Truck & Dog Hire | Biles Hire | hr | 6 | 130 | 780 | 62
2012-01-25 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-25 | Truck & Dog Hire | Biles Hire | hr | 3 | 95 | 285 | 62
2012-01-26 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 62
2012-01-26 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 62
2012-01-26 | People Resourcing ( Labour Hire ) & Travel | Labour | hr | 13 | 40.97 | 532.61 | 62
2012-01-26 | Truck & Dog Hire | Biles Hire | hr | 4 | 130 | 520 | 62
2012-01-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-26 | Truck & Dog Hire | Biles Hire | hr | 6 | 95 | 570 | 62
2012-01-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-26 | Labour HIre | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2012-01-27 | Multi Tyre Roller | Tutt Bryant | day | 1 | 365 | 365 | 62
2012-01-27 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 62
2012-01-30 | Cat 120H Cat (Rental) . Hired from the 28/01/2012 to the 27/02/2012 Inv No - 6000034255 | Cat 12H Cat |  | 1 | 10739.1 | 10739.1 | 62
2012-01-30 | To Load & deliver Rosd Base from Waterford Pit to Dysart Bypass Road. Inv No - 556 | Loader Hire |  | 6 | 1000 | 6000 | 62
2012-02-03 | Labour HIre | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-02-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-02-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 62
2012-02-07 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 62
2012-02-07 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-02-07 | Labour Hire ( People Recourcing ) | Labour | hr | 6.5 | 40.97 | 266.305 | 62
2012-02-07 | Excavator Hyundi | Excavator Hyundi | hr | 5 | 80 | 400 | 62
2012-02-07 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-02-07 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
| Subtotal for 062 |  |  |  |  | 102754.37
Cost Code 063
2012-01-17 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 63
2012-01-17 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 63
2012-01-17 | Labour Hire ( People Recourcing) | Labour | hr | 11 | 40.97 | 450.67 | 63
2012-01-17 | People Resourcing ( Labour Hire ) | Labour | hr | 11 | 40.97 | 450.67 | 63
2012-01-17 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 63
2012-01-17 | Grader Hire | Puccini Plant Hire | hr | 9 | 80 | 720 | 63
2012-01-18 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-18 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-18 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-18 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 63
2012-01-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 63
2012-01-28 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3.5 | 66.07 | 231.245 | 63
2012-01-28 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 63
2012-01-28 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 3.5 | 50 | 175 | 63
2012-01-28 | People Resourcing ( Labour Hire ) | Labour | hr | 3.5 | 40.97 | 143.395 | 63
2012-01-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 63
2012-01-28 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-01-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-01-28 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-01-28 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 63
2012-01-29 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-29 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-29 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-29 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 10 | 50 | 500 | 63
2012-01-29 | People Resourcing ( Labour Hire ) | Labour | hr | 10 | 40.97 | 409.7 | 63
2012-01-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 63
2012-01-29 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 63
2012-01-30 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 10 | 66.07 | 660.7 | 63
2012-01-30 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 63
2012-01-30 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 10 | 50 | 500 | 63
2012-01-30 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-30 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 63
2012-01-30 | People Resourcing ( Labour Hire ) | Labour | hr | 10 | 40.97 | 409.7 | 63
2012-02-14 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 63
2012-02-14 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 63
2012-02-14 | Labour HIre | Labour | hr | 10.5 | 35.35 | 371.175 | 63
2012-02-14 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 63
2012-02-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-02-16 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-02-16 | Labour HIre | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-02-16 | Hire for the 16/02/2012 | Twin Drum Roller |  | 1 | 242 | 242 | 63
2012-02-29 | SD Roller - Dry. Hired from the 31/01/2012 to the 29/02/2012. Inv No - 7781612 | SD Roller |  | 1 | 5000 | 5000 | 63
| Subtotal for 063 |  |  |  |  | 21913.25
Cost Code 064
2011-12-17 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 64
2011-12-21 | Inv AQCQA2183-001 | Primer Seal - 16mm |  | 10948 | 9.17 | 100393.16 | 64
2011-12-21 | Inv AQCQA2183-001 | Primer Seal - 10mm |  | 2002 | 6.02 | 12052.04 | 64
2012-02-17 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 64
2012-02-18 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 64
2012-02-18 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 64
2012-02-18 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 64
2012-02-18 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 11.5 | 66.07 | 759.805 | 64
2012-02-20 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 64
2012-02-20 | CAT297C MTL - No Operator | CAT297 | hr | 7.5 | 46.5 | 348.75 | 64
2012-02-20 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-02-20 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 64
2012-02-20 | Toll Personnel ( Labour Hire ) | Labour | hr | 6.5 | 42.624 | 277.056 | 64
2012-02-21 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 64
2012-02-21 | CAT297C MTL - No Operator | CAT297 | hr | 7.5 | 46.5 | 348.75 | 64
2012-02-29 | Inv AQCQA329-002 | Primer Seal - 10mm |  | 1 | 58418.64 | 58418.64 | 64
2012-03-26 | Volvo & Water Cart Hire. Inv No - 3918 | Water Cart - Hire |  | 1 | 1485 | 1485 | 64
2012-06-22 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 64
2012-06-22 | Grader - Wet Hire. Inv No - 7788513 | Grader |  | 1 | 330 | 330 | 64
2012-06-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 64
2012-06-22 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 64
2012-06-22 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 10.5 | 50 | 525 | 64
2012-06-22 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 64
2012-06-22 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 64
2012-06-23 | labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2012-06-23 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 4.5 | 50 | 225 | 64
2012-06-23 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2012-06-23 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2012-06-23 | Truck & Dog Hire | Biles Hire | hr | 2.5 | 130 | 325 | 64
2012-06-23 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 64
2012-06-23 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 64
2012-06-30 | labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-06-30 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 9.5 | 50 | 475 | 64
2012-06-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-06-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-06-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 64
2012-06-30 | Inv No - 00265694 | Primer Seal - 16mm |  | 1 | 94677.7 | 94677.7 | 64
| Subtotal for 064 |  |  |  |  | 277417.806
Cost Code 065
2012-02-20 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 65
2012-02-21 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 65
2012-02-21 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 65
2012-02-21 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 65
2012-02-21 | Labour HIre | Labour | hr | 7 | 35.35 | 247.45 | 65
2012-02-22 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 65
2012-02-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 65
2012-02-22 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 65
2012-02-22 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 65
2012-02-22 | CAT297C MTL - No Operator | CAT297 | hr | 7.5 | 46.5 | 348.75 | 65
2012-02-29 | Inv AQCQA2183-002 | Seal Visit Two |  | 1 | 199063.11 | 199063.11 | 65
| Subtotal for 065 |  |  |  |  | 202459.38
Cost Code 066
2012-06-25 | 2 x TC's + Ute, Signs & Comms. Inv No - 21904 | Traffic Control Crew |  | 1 | 4529 | 4529 | 66
2012-06-25 | Inv No - 21905 | Line Marking |  | 1 | 1093 | 1093 | 66
| Subtotal for 066 |  |  |  |  | 5622
Cost Code 067
2012-02-14 | Labour Hire ( Concrettor ) | Labour | hr | 6.5 | 45 | 292.5 | 67
2012-02-21 | Labour Hire ( Concrettor ) | Labour | hr | 8 | 45 | 360 | 67
2012-02-21 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 67
2012-02-21 | Toll Personnel ( Labour Hire ) | Labour | hr | 6.5 | 42.624 | 277.056 | 67
2012-02-21 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 67
2012-02-27 | Labour Hire & Travel Time. ( People Recourcing ) | Labour | hr | 2.5 | 40.97 | 102.425 | 67
2012-02-27 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 67
2012-02-27 | Toll Personnel ( Labour Hire ) | Labour | hr | 3.5 | 42.624 | 149.184 | 67
2012-02-27 | Labour HIre | Labour | hr | 3 | 35.35 | 106.05 | 67
2012-02-29 | Tutt & Bryant (Rammer) Hired from 28/2/12 -29/2/12. Inv No 7780944 | Rammer |  | 1 | 66 | 66 | 67
| Subtotal for 067 |  |  |  |  | 2209.45
Cost Code 068
2012-06-08 | P & H Gourlay | Ivecko Spreader Truck | day | 1 | 2500 | 2500 | 68
2012-06-08 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 68
2012-06-09 | Labour Hire | Labour | hr | 11.5 | 74.65 | 858.475 | 68
2012-06-09 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-09 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-09 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-09 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-09 | labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-09 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-09 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 68
2012-06-09 | P & H Gourlay | Ivecko Spreader Truck | day | 1 | 2500 | 2500 | 68
2012-06-09 | labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 68
2012-06-10 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | P & H Gourlay | Ivecko Spreader Truck | day | 1 | 2500 | 2500 | 68
2012-06-10 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-10 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 68
2012-06-10 | Labour Hire | Labour | hr | 11 | 74.65 | 821.15 | 68
2012-06-10 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 68
2012-06-11 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 68
2012-06-11 | Labour Hire | Labour | hr | 11 | 74.65 | 821.15 | 68
2012-06-11 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-11 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-11 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-11 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 68
2012-06-11 | P & H Gourlay | Ivecko Spreader Truck | day | 1 | 2500 | 2500 | 68
2012-06-11 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-11 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-11 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-11 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | P & H Gourlay | Ivecko Spreader Truck | day | 1 | 2500 |  | 68
2012-06-12 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-12 | Truck Hire | Biles Hire | hr | 12 | 95 | 1140 | 68
2012-06-12 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 68
2012-06-12 | Labour Hire | Labour | hr | 11 | 74.65 | 821.15 | 68
2012-06-12 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 68
2012-06-12 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-13 | labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-13 | Labour Hire | Labour | hr | 10.5 | 74.65 | 783.825 | 68
2012-06-13 | Sealing Truck ( Allciv ) | Paveline Truck | hr | 11 | 50 | 550 | 68
2012-06-13 | Tractor / Profiller BCLA Pty Ltd | Tractor / Profiller | day | 1 | 2500 | 2500 | 68
2012-06-13 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 68
2012-06-13 | P & H Gourlay | Ivecko Spreader Truck | day | 1 | 2500 | 2500 | 68
2012-06-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-13 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 68
2012-06-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 68
2012-06-13 | labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 68
2012-06-18 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 68
2012-06-18 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 68
2012-06-19 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 68
2012-06-19 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 68
2012-06-19 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
| Subtotal for 068 |  |  |  |  | 51538.065
Cost Code 071
2012-02-15 | Labour Hire ( Concrettor ) | Labour | hr | 5.5 | 45 | 247.5 | 71
2012-02-16 | Labour Hire ( Concrettor ) | Labour | hr | 3 | 45 | 135 | 71
2012-02-22 | Labour Hire ( Concrettor ) | Labour | hr | 10.5 | 45 | 472.5 | 71
2012-02-22 | Toll Personnel ( Labour Hire ) | Labour | hr | 6.5 | 42.624 | 277.056 | 71
2012-02-22 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 71
2012-03-21 | Inv No - 198326 | Kerb Subbie |  | 1 | 2975 | 2975 | 71
| Subtotal for 071 |  |  |  |  | 4537.241
Cost Code 072
2011-11-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 72
2011-11-08 | Pine stud, Conduit, Reo Rod etc | Small Tools |  | 1 | 731.36 | 731.36 | 72
2011-11-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-10 | Steel Posts, Ratchet, Smart Form Beam Inv - 10167800 | Small Tools |  | 1 | 779.8 | 779.8 | 72
2011-11-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-14 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-15 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-22 | Foreman | Labour | hr | 3 | 44.2 | 132.6 | 72
2011-11-22 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 72
2011-11-22 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 72
2011-11-22 | Excavator Hyundi | Excavator Hyundi | hr | 5 | 80 | 400 | 72
2011-11-22 | Labour HIre | Labour | hr | 3 | 35.35 | 106.05 | 72
2011-11-23 | Foreman | Labour | hr | 6 | 57.7 | 346.2 | 72
2011-11-23 | Labour Hire ( People Resourcing ) | Labour | hr | 10 | 40.97 | 409.7 | 72
2011-11-24 | Foreman | Labour | hr | 7.5 | 57.7 | 432.75 | 72
2011-11-24 | Labour Hire ( People Resourcing ) | Labour | hr | 10 | 40.97 | 409.7 | 72
2011-11-25 | Labour Hire ( People Resourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 72
2011-11-25 | Foreman | Labour | hr | 7.5 | 44.2 | 331.5 | 72
2011-11-25 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 72
2011-11-26 | Labour Hire ( People Resourcing ) | Labour | hr | 8.5 | 40.97 | 348.245 | 72
2011-11-26 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 72
2011-11-27 | Labour Hire ( People Resourcing ) | Labour | hr | 9 | 40.97 | 368.73 | 72
2011-11-27 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 72
2011-11-28 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 72
2011-11-28 | Labour Hire ( People Resourcing ) | Labour | hr | 11 | 40.97 | 450.67 | 72
2011-11-28 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 72
2011-11-29 | Labour HIre | Labour | hr | 2 | 35.35 | 70.7 | 72
2011-11-29 | Foreman | Labour | hr | 10 | 57.7 | 577 | 72
2011-11-29 | Excavator Hyundi | Excavator Hyundi | hr | 2 | 80 | 160 | 72
2011-11-29 | Labour Hire ( People Resourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 72
2011-11-30 | Labour Hire ( People Resourcing ) | Labour | hr | 11 | 40.97 | 450.67 | 72
2011-11-30 | Foreman | Labour | hr | 11 | 57.7 | 634.7 | 72
2011-12-01 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 72
2011-12-01 | Labour Hire ( People Resourcing ) | Labour | hr | 9 | 40.97 | 368.73 | 72
2011-12-07 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 72
2011-12-07 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 72
2011-12-07 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 72
2011-12-08 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 72
2011-12-08 | Foreman | Labour | hr | 10.5 | 44.2 | 464.1 | 72
2012-01-26 | Labour Hire ( Concrettor ) | Labour | hr | 10 | 45 | 450 | 72
2012-01-27 | Labour Hire ( People Recourcing) | Labour | hr | 5.5 | 40.97 | 225.335 | 72
2012-01-27 | Labour Hire ( Concrettor ) | Labour | hr | 6.5 | 45 | 292.5 | 72
2012-01-28 | Labour Hire ( Concrettor ) | Labour | hr | 9 | 45 | 405 | 72
2012-01-28 | Labour Hire ( People Recourcing) | Labour | hr | 9 | 40.97 | 368.73 | 72
2012-01-29 | Labour Hire ( Concrettor ) | Labour | hr | 9 | 45 | 405 | 72
2012-01-29 | Labour Hire ( People Recourcing) | Labour | hr | 7 | 40.97 | 286.79 | 72
2012-01-30 | Labour Hire ( Concrettor ) | Labour | hr | 10 | 45 | 450 | 72
2012-02-03 | Labour Hire ( Concrettor ) | Labour | hr | 5 | 45 | 225 | 72
2012-02-07 | Labour Hire ( Concrettor ) | Labour | hr | 4 | 45 | 180 | 72
2012-02-14 | Labour Hire ( People Recourcing ) | Labour | hr | 4 | 40.97 | 163.88 | 72
2012-02-14 | Labour Hire ( People Recourcing ) | Labour | hr | 4 | 40.97 | 163.88 | 72
2012-02-15 | Labour Hire ( People Recourcing ) | Labour | hr | 4.5 | 40.97 | 184.365 | 72
| Subtotal for 072 |  |  |  |  | 18303.345
Cost Code 081
2011-10-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-27 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 81
2011-10-27 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 81
2011-10-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-28 | Plant Float | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 81
2011-10-28 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 81
2011-10-28 | Excavator Hyundi | Excavator Hyundi | hr | 8.5 | 80 | 680 | 81
2011-10-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-29 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 81
2011-10-29 | Excavator Hyundi | Excavator Hyundi | hr | 7.5 | 80 | 600 | 81
2011-10-29 | Plant Float | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 81
2011-10-29 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-10-29 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-10-29 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-10-29 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-10-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-30 | Plant Float | Plant Float - Allciv | hr | 9.5 | 7 | 66.5 | 81
2011-10-30 | Excavator Hyundi | Excavator Hyundi | hr | 9 | 80 | 720 | 81
2011-10-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-30 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 81
2011-10-30 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-31 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-31 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 81
2011-10-31 | Excavator Hyundi | Excavator Hyundi | hr | 9 | 80 | 720 | 81
2011-10-31 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 81
2011-10-31 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-31 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-10-31 | Plate Compactor - Dry Hire Inv- 7773440 | Plate Compactor |  | 1 | 110 | 110 | 81
2011-10-31 | Quick Cut Saw Inv - 7773439 | Quick Cut Saw |  | 1 | 330 | 330 | 81
2011-11-01 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-01 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-01 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-01 | Labour HIre | Labour | hr | 5.5 | 35.35 | 194.425 | 81
2011-11-01 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-01 | Rock Hammer From the 1/11/2011 to the 1/11/2011 Inv - 7773510 | Hammer |  | 1 | 104.5 | 104.5 | 81
2011-11-01 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 81
2011-11-02 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-02 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-02 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-02 | Labour HIre | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-02 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-02 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 81
2011-11-03 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 81
2011-11-03 | Labour HIre | Labour | hr | 4.5 | 35.35 | 159.075 | 81
2011-11-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 81
2011-11-03 | Tutt & Bryant (Rammer) From the 3/11/2011 to the 3/11/2011 Inv 7773604 | Rammer |  | 1 | 77 | 77 | 81
2011-11-03 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 81
2011-11-03 | Quick Cut Saw FRom the 31/10/2011 to the 3/11/2011 Inv - 7773605 | Quick Cut Saw |  | 1 | 165 | 165 | 81
2011-11-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 81
2011-11-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 81
2011-11-03 | Excavator Hyundi | Excavator Hyundi | hr | 5.5 | 80 | 440 | 81
2011-11-03 | Plate Compactor - Dry Hire From the 31/10/2011 to the 3/11/2011 Inv - 7773575 | Plate Compactor |  | 1 | 110 | 110 | 81
2011-11-10 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 81
2011-11-10 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-11-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-11-10 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 81
2011-11-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 81
2011-11-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-11-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-11-14 | Tipper Hire (Kennards) Inv - 13207697 | Tipper ( Kennards ) |  | 1 | 1940 | 1940 | 81
2011-11-14 | Quick Cut Saw Hired from 10/11/2011 to the 14/11/2011 Inv - 7774108 | Quick Cut Saw |  | 1 | 247.5 | 247.5 | 81
2011-11-16 | Rock Hammer Hire from the 10/11/2011 to the 16/11/2011 Inv - 7774288 | Hammer |  | 1 | 275 | 275 | 81
2011-11-23 | Labour HIre | Labour | hr | 6 | 35.35 | 212.1 | 81
2011-11-23 | Excavator Hyundi | Excavator Hyundi | hr | 6 | 80 | 480 | 81
2011-11-23 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2011-11-23 | Foreman | Labour | hr | 6 | 44.2 | 265.2 | 81
2011-11-24 | Foreman | Labour | hr | 10 | 44.2 | 442 | 81
2011-11-24 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-11-24 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-11-24 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 81
2011-11-25 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 81
2011-11-25 | Foreman | Labour | hr | 3 | 44.2 | 132.6 | 81
2011-11-25 | Labour HIre | Labour | hr | 3 | 35.35 | 106.05 | 81
2011-11-25 | Excavator Hyundi | Excavator Hyundi | hr | 3 | 80 | 240 | 81
2011-11-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 81
2012-01-24 | Labour Hire ( Concrettor ) | Labour | hr | 6 | 45 | 270 | 81
2012-02-08 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 81
2012-02-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 81
| Subtotal for 081 |  |  |  |  | 29127.06
Cost Code 111
2011-12-09 | Excavator Hyundi | Excavator Hyundi | hr | 8.5 | 80 | 680 | 111
2011-12-09 | Labour HIre | Labour | hr | 8.5 | 35.35 | 300.475 | 111
2011-12-09 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 111
2011-12-09 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 111
2011-12-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 111
2011-12-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 111
2011-12-09 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 111
2012-02-09 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 111
2012-02-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 111
2012-02-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 111
2012-02-09 | Labour HIre | Labour | hr | 5.5 | 35.35 | 194.425 | 111
2012-02-09 |  | Plant Float - Allciv | hr | 5.5 | 7 | 38.5 | 111
2012-02-09 | Labour Hire ( Concrettor ) | Labour | hr | 4 | 45 | 180 | 111
2012-02-09 | Labour Hire ( People Recourcing ) | Labour | hr | 4 | 40.97 | 163.88 | 111
2012-02-09 | Excavator Hyundi | Excavator Hyundi | hr | 5.5 | 80 | 440 | 111
2012-02-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 111
2012-02-10 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 111
2012-02-10 | Excavator Hyundi | Excavator Hyundi | hr | 5 | 80 | 400 | 111
2012-02-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 111
2012-02-10 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 111
2012-02-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 111
2012-02-10 | Labour Hire ( People Recourcing ) | Labour | hr | 4 | 40.97 | 163.88 | 111
2012-02-10 | Hired from the 10/02/2012 to the 13/02/2012. Inv No - 7780278 | Portable Saw |  | 1 | 132 | 132 | 111
2012-02-11 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 111
2012-02-11 | Labour Hire ( People Recourcing ) | Labour | hr | 6.5 | 40.97 | 266.305 | 111
2012-02-11 | Excavator Hyundi | Excavator Hyundi | hr | 7.5 | 80 | 600 | 111
2012-02-11 |  | Plant Float - Allciv | hr | 8 | 7 | 56 | 111
2012-02-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 111
2012-02-12 | Labour Hire ( People Recourcing ) | Labour | hr | 11 | 40.97 | 450.67 | 111
2012-02-14 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 111
2012-03-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 111
2012-03-09 |  | Plant Float - Allciv | hr | 8 | 7 | 56 | 111
2012-03-09 | Excavator Hyundi | Excavator Hyundi | hr | 8 | 80 | 640 | 111
2012-03-09 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 111
2012-03-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 111
2012-03-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 111
2012-03-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 111
| Subtotal for 111 |  |  |  |  | 8890.215
Cost Code 141
2011-11-08 | General signs & delineation for traffic control. Inv - In- 8201400 | Signs - General |  | 1 | 815.71 | 815.71 | 141
2011-11-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 141
2011-11-16 | General signs & delineation for traffic control. Tratic Cone 700mm Orange Base Inv- IN-8202494 | Signs - General |  | 1 | 1110.5 | 1110.5 | 141
2011-11-22 | Labour Hire ( People Recourcing) | Labour | hr | 5 | 40.97 | 204.85 | 141
2011-11-22 | Labour Hire ( People Recourcing ) | Labour | hr | 5 | 40.97 | 204.85 | 141
2011-11-23 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-23 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-24 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-24 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-25 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-25 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 141
2011-11-25 | Foreman | Labour | hr | 0.5 | 44.2 | 22.1 | 141
2011-11-25 | Labour Hire | Labour | hr | 0.5 | 35.35 | 17.675 | 141
2011-11-26 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-26 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-27 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-27 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-28 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-28 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-29 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-29 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-30 | Hire from the 10/11/2011 to the 30/11/2011 Inv No - 7775894 | traffic lights |  | 1 | 3280.2 | 3280.2 | 141
2011-11-30 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-11-30 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-12-01 | Labour Hire ( People Recourcing ) | Labour | hr | 6.5 | 40.97 | 266.305 | 141
2011-12-01 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-12-07 | People Resourcing (Labour Hire) | Labour | hr | 9.5 | 40.97 | 389.215 | 141
2011-12-07 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 141
2011-12-08 | People Resourcing (Labour Hire) | Labour | hr | 11 | 40.97 | 450.67 | 141
2011-12-08 | Labour Hire ( People Recourcing) | Labour | hr | 11.5 | 40.97 | 471.155 | 141
2011-12-09 | People Resourcing (Labour Hire) | Labour | hr | 11 | 40.97 | 450.67 | 141
2011-12-09 | Labour Hire ( People Recourcing) | Labour | hr | 11.5 | 40.97 | 471.155 | 141
2011-12-09 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 141
2011-12-10 | People Resourcing (Labour Hire) | Labour | hr | 11 | 40.97 | 450.67 | 141
2011-12-10 | Labour Hire ( People Recourcing) | Labour | hr | 11.5 | 40.97 | 471.155 | 141
2011-12-11 | People Resourcing (Labour Hire) | Labour | hr | 10.45 | 40.97 | 428.1365 | 141
2011-12-11 | Labour Hire ( People Recourcing) | Labour | hr | 10 | 40.97 | 409.7 | 141
2011-12-12 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-12-12 | Hire from the 30/11/2011 to the 12/12/2011 Inv No 7776445 | traffic lights |  | 1 | 1718.2 | 1718.2 | 141
2011-12-12 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-12-13 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2011-12-17 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 141
2011-12-19 | 2 x TC's + Ute, Signs & Comms Inv No - 19545 | Traffic Control Crew |  | 1 | 2118.1 | 2118.1 | 141
2012-01-09 | Labour Hire ( People Recourcing ) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-09 | Labour Hire ( People Recourcing) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-10 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-01-10 | Labour Hire ( People Recourcing) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-11 | Labour Hire ( People Recourcing) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-01-11 | Labour Hire ( People Recourcing ) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-01-12 | Labour Hire ( People Recourcing) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-12 | Labour Hire ( People Recourcing ) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-12 | Hire from the 30/11/2011 to the 12/12/2011 Inv No 7776445 | traffic lights |  | 1 | 1718.2 | 1718.2 | 141
2012-01-13 | Labour Hire ( People Recourcing) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-13 | Labour Hire ( People Recourcing ) | Labour | hr | 11 | 40.97 | 450.67 | 141
2012-01-14 | Labour Hire ( People Recourcing) | Labour | hr | 6.5 | 40.97 | 266.305 | 141
2012-01-14 | Labour Hire ( People Recourcing ) & Travel time | Labour | hr | 2.5 | 40.97 | 102.425 | 141
2012-01-17 | People Resourcing (Labour Hire) | Labour | hr | 11.5 | 40.97 | 471.155 | 141
2012-01-18 | People Resourcing (Labour Hire) | Labour | hr | 6 | 40.97 | 245.82 | 141
2012-01-19 | People Resourcing (Labour Hire) | Labour | hr | 7.5 | 40.97 | 307.275 | 141
2012-01-26 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-01-28 | People Resourcing (Labour Hire) | Labour | hr | 9 | 40.97 | 368.73 | 141
2012-01-29 | Labour Hire ( People Recourcing) | Labour | hr | 3 | 40.97 | 122.91 | 141
2012-01-29 | People Resourcing (Labour Hire) | Labour | hr | 10 | 40.97 | 409.7 | 141
2012-01-30 | Travel Time | Labour | hr | 2.5 | 40.97 | 102.425 | 141
2012-01-30 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-01-31 | Hired from the 9/01/2012 to the 31/01/2012. Inv No - 7779726 | traffic lights |  | 1 | 2200 | 2200 | 141
2012-02-09 | General signs & delineation for traffic control. Inv No - 8211664 | Signs - General |  | 1 | 272.96 | 272.96 | 141
2012-02-07 | People Resourcing (Labour Hire) | Labour | hr | 6 | 40.97 | 245.82 | 141
2012-02-08 | People Resourcing (Labour Hire) | Labour | hr | 8.5 | 40.97 | 348.245 | 141
2012-02-08 | Labour Hire ( People Recourcing ) | Labour | hr | 4 | 40.97 | 163.88 | 141
2012-02-09 | Labour Hire ( People Recourcing ) | Labour | hr | 3 | 40.97 | 122.91 | 141
2012-02-09 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-02-10 | People Resourcing (Labour Hire) | Labour | hr | 10 | 40.97 | 409.7 | 141
2012-02-10 | Labour Hire ( People Recourcing ) | Labour | hr | 3 | 40.97 | 122.91 | 141
2012-02-11 | People Resourcing (Labour Hire) | Labour | hr | 8 | 40.97 | 327.76 | 141
2012-02-14 | People Resourcing (Labour Hire) | Labour | hr | 10.5 | 40.97 | 430.185 | 141
2012-02-20 | 2 x TC's + Ute, Signs & Comms. For the 18/2/12. Inv No - 20240 | Traffic Control Crew |  | 1 | 2155.25 | 2155.25 | 141
2012-02-27 | 2 x TC's + Ute, Signs & Comms. Inv No - 20346 | Traffic Control Crew |  | 1 | 8687.45 | 8687.45 | 141
2012-02-29 | Hired from the 31/01/2012 to the 29/02/2012. Inv No - 7781613I | traffic lights |  | 1 | 2500 | 2500 | 141
2012-03-07 | Toll Personnel ( Labour Hire ) | Labour | hr | 4 | 42.624 | 170.496 | 141
2012-06-15 | 2 x TC's + Ute, Signs & Comms. Inv No 21823 | Traffic Control Crew |  | 1 | 1435.65 | 1435.65 | 141
2012-06-25 | 2 x TC's + Ute, Signs & Comms. Inv No - 21906 | Traffic Control Crew |  | 1 | 2734.4 | 2734.4 | 141
2012-06-25 | 2 x TC's + Ute, Signs & Comms. Inv No - 076 | Traffic Control Crew |  | 1 | 2246.5 | 2246.5 | 141
| Subtotal for 141 |  |  |  |  | 57433.5525
Cost Code 151
2012-01-24 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 151
2012-01-24 | Truck & Dog Hire | Biles Hire | hr | 7.5 | 130 | 975 | 151
2012-01-24 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 151
2012-01-24 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5 | 66.07 | 330.35 | 151
2012-01-24 | Labour HIre | Labour | hr | 7.5 | 35.35 | 265.125 | 151
2012-01-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 5 | 66.07 | 330.35 | 151
| Subtotal for 151 |  |  |  |  | 2466.425
Cost Code 181
2011-11-01 | docket No 29966 Inv - 2991 | Crusher Dust - Delivered |  | 12.32 | 16.8 | 206.976 | 181
2011-11-08 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 181
2011-11-08 | Excavator Hyundi | Excavator Hyundi | hr | 4.5 | 80 | 360 | 181
2011-11-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 181
2011-11-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2011-11-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2011-11-09 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-09 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-10 | Steel Posts, Ratchets, Smart Form Beam. Inv- 10167800 | Small Tools |  | 1 | 779.8 | 779.8 | 181
2011-11-11 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-11 | Excavator Hyundi | Excavator Hyundi | hr | 9.5 | 80 | 760 | 181
2011-11-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 181
2011-11-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-11 | Labour Hire | Labour | hr | 13 | 35.35 | 459.55 | 181
2011-11-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-12 | Excavator Hyundi | Excavator Hyundi | hr | 7 | 80 | 560 | 181
2011-11-12 | Labour HIre | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-12 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 181
2011-11-12 | Flexidrive Motor Petrol & Pump and Hoses Inv No - 7069449 | Pump |  | 1 | 121 | 121 | 181
2011-11-12 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 181
2011-11-12 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-12 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-13 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-13 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-13 | Excavator Hyundi | Excavator Hyundi | hr | 6.5 | 80 | 520 | 181
2011-11-13 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 181
2011-11-13 | Labour HIre | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-13 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-11-13 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 181
2011-11-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-11-14 | N20 Concrete Inv 9405357295 | N20 |  | 1 | 485 | 485 | 181
2011-11-14 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-11-14 | Tutt & Bryant (Rammer) | Rammer | day | 1 | 55 | 55 | 181
2011-11-14 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 181
2011-11-14 | Excavator Hyundi | Excavator Hyundi | hr | 3.5 | 80 | 280 | 181
2011-11-14 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 181
2011-11-15 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 181
2011-11-15 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 181
2011-11-15 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 181
2011-11-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 181
2011-11-15 | Reo Rod and Duct tape | Small Tools |  | 1 | 300.64 | 300.64 | 181
2011-11-15 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 181
2011-11-15 | Tutt & Bryant (Rammer) | Rammer | day | 1 | 55 | 55 | 181
2011-11-15 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-11-15 | Excavator Hyundi | Excavator Hyundi | hr | 10 | 80 | 800 | 181
2011-11-16 | Excavator Hyundi | Excavator Hyundi | hr | 4 | 80 | 320 | 181
2011-11-16 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 181
2011-11-16 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 181
2011-11-16 | Labour Hire | Labour | hr | 11 | 35.35 | 388.85 | 181
2011-11-16 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 181
2011-11-16 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 181
2011-11-16 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 181
2011-11-16 | Portable Vibshaft 44mm Hire form the 11/11/2011 to the 16/11/2011 Inv 7774253 | 375 Sloping Headwall |  | 1 | 325.6 | 325.6 | 181
2011-11-17 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 181
2011-11-17 | Excavator Hyundi | Excavator Hyundi | hr | 5 | 80 | 400 | 181
2012-02-08 | Labour Hire ( People Recourcing ) | Labour | hr | 4.5 | 40.97 | 184.365 | 181
2012-02-08 | Labour Hire ( Concrettor ) | Labour | hr | 9.5 | 45 | 427.5 | 181
2012-02-08 | Tutt & Bryant (Portable Vibshaft) . Hire for the 8/02/2012. Inv No - 7780055 | Portable Vibshaft |  | 1 | 99 | 99 | 181
2012-02-08 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2012-02-08 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-08 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2012-02-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-09 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 181
2012-02-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-09 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 181
2012-02-09 | Labour Hire ( People Recourcing ) | Labour | hr | 3.5 | 40.97 | 143.395 | 181
2012-02-09 | Labour Hire ( Concrettor ) | Labour | hr | 6.5 | 45 | 292.5 | 181
2012-02-09 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 181
2012-02-09 | Excavator Hyundi | Excavator Hyundi | hr | 5 | 80 | 400 | 181
2012-02-10 | Excavator Hyundi | Excavator Hyundi | hr | 5 | 80 | 400 | 181
2012-02-10 |  | Plant Float - Allciv | hr | 5 | 7 | 35 | 181
2012-02-10 | Labour Hire ( Concrettor ) | Labour | hr | 10 | 45 | 450 | 181
2012-02-10 | Labour Hire ( People Recourcing ) | Labour | hr | 3.5 | 40.97 | 143.395 | 181
2012-02-10 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-10 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 181
2012-02-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-10 | Tutt & Bryant (Rammer) . Inv No - 7780198 | Rammer |  | 1 | 165 | 165 | 181
2012-02-10 | Portable Saw. Inv No - 7780198 | Portable Saw |  | 1 | 165 | 165 | 181
2012-02-11 | Labour Hire ( Concrettor ) | Labour | hr | 8 | 45 | 360 | 181
2012-02-11 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2012-02-11 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 181
2012-02-11 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 181
2012-02-11 | Labour HIre | Labour | hr | 8 | 35.35 | 282.8 | 181
2012-02-13 | Portable Saw. Hired from the 10/02/2012 to the 13/02/2012.Inv No - 7780278 | Portable Saw |  | 1 | 132 | 132 | 181
| Subtotal for 181 |  |  |  |  | 23785.751
Cost Code 901
2011-11-01 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
2011-11-02 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
2011-11-03 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
2011-11-08 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
2011-11-09 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
2011-11-10 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
2011-11-11 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 901
| Subtotal for 901 |  |  |  |  | 5950
Cost Code 902
2011-10-25 | Project Supervisor | Foreman | hr | 9 | 57.7 | 519.3 | 902
2011-10-26 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-27 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-28 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-29 | Project Supervisor | Foreman | hr | 8 | 57.7 | 461.6 | 902
2011-10-30 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-10-31 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-01 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-02 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-03 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-08 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-08 | Foreman | Labour | hr | 10 | 57.7 | 577 | 902
2011-11-09 | Foreman | Labour | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-09 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-10 | Foreman | Labour | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-10 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-11 | Foreman | Labour | hr | 9.5 | 44.2 | 419.9 | 902
2011-11-11 | Project Supervisor | Foreman | hr | 9.5 | 57.7 | 548.15 | 902
2011-11-12 | Foreman | Labour | hr | 7.5 | 57.7 | 432.75 | 902
2011-11-12 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-13 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-13 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 902
2011-11-14 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-14 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 902
2011-11-15 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-15 | Foreman | Labour | hr | 11 | 57.7 | 634.7 | 902
2011-11-16 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-16 | Foreman | Labour | hr | 11 | 57.7 | 634.7 | 902
2011-11-17 | Foreman | Labour | hr | 9 | 57.7 | 519.3 | 902
2011-11-17 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-22 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 902
2011-11-22 | Foreman | Labour | hr | 10 | 57.7 | 577 | 902
2011-11-22 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-23 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-24 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-25 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-26 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-27 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-28 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-29 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-11-30 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-01 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-06 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-07 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-08 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-09 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-10 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-11 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-12 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-13 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2011-12-17 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-11 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-12 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-13 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-16 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-17 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-17 | Labour Hire | Labour | hr | 11 | 74.65 | 821.15 | 902
2012-01-18 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-18 | Labour Hire | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-01-19 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-19 | Labour Hire | Labour | hr | 11 | 74.65 | 821.15 | 902
2012-01-24 | Supervisor | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-01-24 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-26 | Supervisor | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-01-26 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-27 | Supervisor | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-01-27 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-28 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-28 | Supervisor | Labour | hr | 9.5 | 74.65 | 709.175 | 902
2012-01-29 | Supervisor | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-01-29 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-01-30 | Supervisor | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-01-30 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-02-03 | Labour Hire | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-02-07 | Labour Hire | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-02-08 | Labour Hire | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-02-09 | Labour Hire | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-02-10 | Labour Hire | Labour | hr | 10 | 74.65 | 746.5 | 902
2012-02-11 | Labour Hire | Labour | hr | 8 | 74.65 | 597.2 | 902
2012-02-14 | Labour Hire | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-02-15 | Labour Hire | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-02-15 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 902
2012-02-16 | Labour Hire | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-02-20 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 902
2012-02-21 | Labour Hire | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-02-22 | Labour Hire | Labour | hr | 10.5 | 74.65 | 783.825 | 902
2012-02-27 | Labour Hire | Labour | hr | 8 | 74.65 | 597.2 | 902
2012-03-06 | Labour Hire | Labour | hr | 9 | 74.65 | 671.85 | 902
2012-03-07 | Supervisor | Labour | hr | 9 | 74.65 | 671.85 | 902
2012-03-09 | Supervisor | Labour | hr | 9 | 74.65 | 671.85 | 902
2012-03-10 | Supervisor | Labour | hr | 5 | 74.65 | 373.25 | 902
| Subtotal for 902 |  |  |  |  | 65379.85
Cost Code 903
2011-10-31 | Office Crib Shed Inv - 7773437 | Generator |  |  | 3755.45 |  | 903
2011-11-07 | First Aid Kit Inv - 139 | Small Tools |  | 1 | 154.62 | 154.62 | 903
2011-11-30 | 23 Kva 3 Ph Genset Hire from the 31/10/2011 to the 30/11/2011 Inv No - 7775892 | Generator |  | 1 | 2400 | 2400 | 903
2011-11-30 | Inv No - 7775892 | Insurance |  | 1 | 373.3 | 373.3 | 903
2011-11-30 | hire from the 31/140/2011 to the 30/11/2011 Inv No 7775892. | Crib Facilities |  | 1 | 1333.02 | 1333.02 | 903
2011-12-15 | Repair star picket slide hammer Inv No - 70139 | Hammer |  | 1 | 41.8 | 41.8 | 903
2011-12-31 | Site Office & Tiolet, 1 Pump out during project. Hired from the 30/11/2011 to the 31/12/2011 Inv No - 7777938 | Crib Facilities |  | 1 | 2835.2 | 2835.2 | 903
2012-02-10 | Inv No 909691 | Springwater |  | 1 | 210 | 210 | 903
2012-04-30 | Site Office & Tiolet, 1 Pump out during project.Hired from the 31/83/2012-30/4/2012. Inv No - 7785500 | Crib Facilities |  | 1 | 1466.31 | 1466.31 | 903
| Subtotal for 903 |  |  |  |  | 8814.25
Cost Code 904
2011-11-11 | (Nathan Hood ) Inv - 74571LEN | Labour |  | 1 | 60 | 60 | 904
2012-02-29 | Damage Waiver for Crib Facilitites and Generator. Hired from the 31/1/12 to 29/2/12. Inv No - 7781611. | Insurance |  | 1 | 360.86 | 360.86 | 904
2012-02-29 | Damage Waiver. S/D Roller12 T. Hired from the 31/01/12 to 29/02/12. Inv No - 7781612 | Insurance |  | 1 | 500 | 500 | 904
2012-02-29 | Damage Waiver. Traffic Lights, Hired from the 31/01/2012 to the 29/02 2012. Inv No - 7781613 | Insurance |  | 1 | 250 | 250 | 904
2012-06-22 | Damage Waiver - New Holland Grader. Inv No - 7788513 | Insurance |  | 1 | 33 | 33 | 904
| Subtotal for 904 |  |  |  |  | 1203.86
Cost Code 905
2011-10-27 | Tape Petrolatum Du Inv - 8311782 | Small Tools |  | 10 | 23.1 | 231 | 905
2011-10-27 | Inv 400085510 - Concrete Lifting eyes, latch hook & shackle | Small Tools |  | 1 | 1801.18 | 1801.18 | 905
2011-10-28 | Steel Post HVY Black ( 180cm) Inv 10166856 | Steel |  | 1 | 227.27 | 227.27 | 905
2011-10-28 | Pipe Gal MGPE 50nb - 6.5m | Small Tools |  | 52 | 14.8 | 769.6 | 905
2011-11-07 | Spray & Mark White Trans No 08325735 | Small Tools |  | 1 | 73.54 | 73.54 | 905
2011-11-08 | Shovel Concrete, Batten,Screws, Nail Bright Inv - 10167623 | Small Tools |  | 1 | 72.39 | 72.39 | 905
2011-11-08 | Star Pickets - Inv 10167611 | Small Tools |  | 1 | 220.45 | 220.45 | 905
2011-11-09 | Decking Scfrews, Sealant Windows Dock no A 63492 | Small Tools |  | 1 | 86.77 | 86.77 | 905
2011-11-09 | Pine Stud, Decking screws | Small Tools |  | 1 | 319.59 | 319.59 | 905
2011-11-10 | Screws IHX GP BU. Nail BH Bright Inv - 10167789 | Small Tools |  | 1 | 34.62 | 34.62 | 905
2011-11-11 | Lawnkeeper. Plastic impact, Yellow Sled, Hose Docket No F 75002 | Small Tools |  | 1 | 509.09 | 509.09 | 905
2011-11-11 | SDS Plus Drill Dock no 63572 | Small Tools |  | 1 | 18.18 | 18.18 | 905
2011-11-17 | Wooden Pegs Inv - 10168293 | Small Tools |  | 1 | 114.13 | 114.13 | 905
2011-11-22 | Screw Chipboard Inv No - 8343968 | Small Tools |  | 1 | 381.98 | 381.98 | 905
2011-11-29 | Tape Komelon 8M Green Inv - 10168791 | Small Tools |  | 1 | 43.22 | 43.22 | 905
2011-11-29 | Spray & Mark White . Tran No- 08353591 | Small Tools |  | 24 | 6.127 | 147.048 | 905
2011-12-06 | Bondcrete Can Inv No - F76673 | Small Tools |  | 1 | 32.27 | 32.27 | 905
2011-12-06 | 71 pce Metabo Bit, Milwalkee 2 pce Combo Ham Drill Inv No 10119754 | Small Tools |  | 1 | 568.17 | 568.17 | 905
2011-12-07 | Nutsetter Inv F76693 | Small Tools |  | 1 | 11.8 | 11.8 | 905
2011-12-09 | Mop, Tape Duck, Saw Hand Jack,Bucket Dock No - A64998 | Small Tools |  | 1 | 96.72 | 96.72 | 905
2011-12-13 | Fuel Can Dock No- F77069 | Small Tools |  | 1 | 18.4 | 18.4 | 905
2011-12-19 | Sprayer Pressure Inv No F77399 | Small Tools |  | 1 | 44.09 | 44.09 | 905
2012-01-10 | Broom Bulldozer, Shovel . Inv No - 10171364 | Small Tools |  | 1 | 65.12 | 65.12 | 905
2012-01-10 | Spray & Mark. Inv No - 8467/26743 | Small Signs |  | 1 | 51.27 | 51.27 | 905
2012-01-16 | Form Ply. Inv No 4503-1348 | Small Tools |  | 1 | 510.82 | 510.82 | 905
2012-01-17 | Weed Kill, Spray Pressure. Inv No - F78204 | Small Tools |  | 1 | 27.95 | 27.95 | 905
2012-01-19 | Sprayer Pressure,pruner,Weed Kill. Inv No - 77399 | Small Tools |  | 1 | 44.09 | 44.09 | 905
2012-01-24 | Nutsetter. Inv No - A66714 | Small Tools |  | 1 | 21.23 | 21.23 | 905
2012-01-24 | Hammer Claw Steel, Nipper End Cut In. Inv No - F78668 | Small Tools |  | 1 | 125 | 125 | 905
2012-01-24 | Nutsetter,Bit Hexagon Drive. Inv No - F78677 | Small Tools |  | 1 | 15.5 | 15.5 | 905
2012-01-25 | Knife Retract Blade. Inv No - F78714 | Small Tools |  | 1 | 10.77 | 10.77 | 905
2012-01-27 | Wrench Inpact shinano,OIl,Male Thread, ect. Inv No - 10125474 | Small Tools |  | 1 | 833.38 | 833.38 | 905
2012-01-28 | Goggles. Inv No - A66894 | Small Tools |  | 1 | 12.9 | 12.9 | 905
2012-01-28 | 2 pce Diamond Blade. Inv No- A66879 | Small Tools |  | 1 | 15 | 15 | 905
2012-01-30 | Line Set Chalk,Reo Rod. Inv No =- A66961 | Small Tools |  | 1 | 141.36 | 141.36 | 905
2012-02-07 | Reo Rod. Inv No - A67382 | Small Tools |  | 1 | 196.36 | 196.36 | 905
2012-02-08 | Wheel Co Met Inox. Inv No - A67391 | Small Tools |  | 1 | 15 | 15 | 905
2012-02-09 | Filler Expanda Foam , Tape Duct Silver. Inv No - A67482 | Small Tools |  | 1 | 76.36 | 76.36 | 905
2012-02-10 | Rod Rio,Drill HSS Sinpac. Inv No - A67591 | Small Tools |  | 1 | 509.63 | 509.63 | 905
2012-02-11 | SDS Drill. Inv No - F79702 | Small Tools |  | 1 | 9.09 | 9.09 | 905
2012-02-14 | Batterys. Inv No - A67751 | Small Tools |  | 1 | 14.77 | 14.77 | 905
2012-02-15 | Cement 20 Kg Bags. Inv No - A67789 | Small Tools |  | 6 | 9.272 | 55.632 | 905
2012-02-15 | Spray & Mark. Inv No F79895 | Small Tools |  | 1 | 30.18 | 30.18 | 905
2012-02-15 | Patio W/Har. Inv No - F79898 | Small Tools |  | 1 | 30 | 30 | 905
2012-02-20 | Shovel, Spray & Mark. Inv No - 8467/27808 | Small Tools |  | 1 | 252.89 | 252.89 | 905
2012-02-29 | Ear Muffs. Inv No - 3342 | Small Tools |  | 1 | 19 | 19 | 905
2012-03-07 | Spray Quickdry Flat. Inv No - A68813 | Small Tools |  | 2 | 10.91 | 21.82 | 905
2012-03-09 | Denso Tape. Inv No - 71002 | Denso Tape |  | 3 | 61.74 | 185.22 | 905
2012-03-23 | Rain Coat. Inv No - 10174323 | Small Tools |  | 3 | 14.27 |  | 905
2012-06-21 | Kerosene, Turpentine Minerals. Inv No - F87241 | Small Tools |  | 1 | 90.9 | 90.9 | 905
2012-06-21 | Poly Film, Weed Kill, Hand Clean. Inv No - A73660 | Small Tools |  | 1 | 219.81 | 219.81 | 905
2012-06-21 | Spray & Mark Paint. Inv No - F87235 | Small Tools |  | 1 | 87.38 | 87.38 | 905
2012-06-21 | Mineral Turps. Super Glue. Inv No - A73683 | Small Tools |  | 1 | 35 | 35 | 905
| Subtotal for 905 |  |  |  |  | 9544.94
Cost Code 907
2011-10-25 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 907
2011-10-25 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 907
2011-10-25 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 907
2011-10-25 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 907
2011-10-26 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 907
2011-10-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2011-10-26 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 907
2011-10-26 | Plant Float | Plant Float - Allciv | hr | 10.5 | 7 | 73.5 | 907
2011-10-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2011-10-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2011-10-26 | Constructon Manager | Supervisor | day | 1 | 850 | 850 | 907
2011-10-27 | Plant Float | Plant Float - Allciv | hr | 10.5 | 7 | 73.5 | 907
2011-10-27 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 907
2011-10-27 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 907
2011-10-28 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 907
2011-11-01 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-03 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-03 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-08 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 907
2011-11-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-08 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-12 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 907
2011-11-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-11-22 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 907
2011-11-22 | Labour HIre | Labour | hr | 4.5 | 35.35 | 159.075 | 907
2011-11-22 | Foreman | Labour | hr | 4.5 | 44.2 | 198.9 | 907
2011-11-22 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 907
2011-11-22 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 907
2011-11-22 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 907
2011-11-22 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 907
2011-11-22 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 907
2011-11-30 | Transport Tractor Mixer Inv No 37850 | Float |  | 1 | 1700 | 1700 | 907
2011-12-01 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-01 | Foreman | Labour | hr | 4 | 44.2 | 176.8 | 907
2011-12-01 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-01 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-01 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-06 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-06 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-06 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-06 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-06 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2011-12-06 | Foreman | Labour | hr | 4 | 44.2 | 176.8 | 907
2011-12-07 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 907
2011-12-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2011-12-07 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 907
2011-12-07 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2011-12-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 907
2011-12-22 | Inv - 37724 | Float |  | 1 | 1500 | 1500 | 907
2012-01-09 | Labour Hire & Travel Time ( People Recourcing ) | Labour | hr | 2.5 | 40.97 | 102.425 | 907
2012-01-09 | Labour Hire ( People Recourcing) | Labour | hr | 4 | 40.97 | 163.88 | 907
2012-01-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-16 | People Resourcing (Labour Hire) | Labour | hr | 8 | 40.97 | 327.76 | 907
2012-01-16 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-16 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 907
2012-01-16 | People Resourcing ( Labour Hire ) & Travel time | Labour | hr | 10.5 | 40.97 | 430.185 | 907
2012-01-16 | Labour Hire ( People Recourcing) | Labour | hr | 8.5 | 40.97 | 348.245 | 907
2012-01-18 | Inv No 38625 | Float |  | 1 | 3350 | 3350 | 907
2012-01-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-19 | Labour Hire ( People Recourcing) | Labour | hr | 8.5 | 40.97 | 348.245 | 907
2012-01-22 | Inv No - 38624 | Float |  | 1 | 1300 | 1300 | 907
2012-01-24 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-24 | Labour Hire ( People Recourcing) | Labour | hr | 4 | 40.97 | 163.88 | 907
2012-01-24 | People Resourcing (Labour Hire) | Labour | hr | 10 | 40.97 | 409.7 | 907
2012-01-24 | Truck & Dog Hire | Biles Hire | hr | 4 | 130 | 520 | 907
2012-01-24 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-24 | travel time | Labour | hr | 10.5 | 40.97 | 430.185 | 907
2012-01-24 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-01-25 | People Resourcing ( Labour Hire ) | Labour | hr | 10 | 40.97 | 409.7 | 907
2012-01-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 907
2012-01-27 | Labour HIre | Labour | hr | 8 | 35.35 | 282.8 | 907
2012-01-29 | Trasport 14T Excavator. Inv No - 38721 | Float |  | 1 | 1700 | 1700 | 907
2012-01-31 | Site Office & Tiolet, 1 Pump out during project. Inv No -7779724 | Crib Facilities |  | 1 | 3363.2 | 3363.2 | 907
2012-01-31 | Vechicle Hire . Inv No 160992 | Vechicle Hire |  | 1 | 999.27 | 999.27 | 907
2012-02-03 | Labour Hire | Labour | hr | 11.5 | 35.35 | 406.525 | 907
2012-02-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 907
2012-02-03 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 907
2012-02-07 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 907
2012-02-07 | Labour HIre | Labour | hr | 5.5 | 35.35 | 194.425 | 907
2012-02-07 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 907
2012-02-07 | Labour Hire ( People Recourcing ) | Labour | hr | 3 | 40.97 | 122.91 | 907
2012-02-17 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-02-21 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-02-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 907
2012-02-29 | 23 Kva 3 Ph . Hired from the 31/1/12 to 29/2/12. Inv No 7781611 | Generator |  | 1 | 2320 | 2320 | 907
2012-02-29 | Site Office & Tiolet, 1 Pump out during project.Hired from the 31/1/12 to 29/2/12. Inv No - 7781611 | Crib Facilities |  | 1 | 1288.59 | 1288.59 | 907
2012-02-29 | Vechicle Hire . Inv No 161102 | Vechicle Hire |  | 1 | 756.78 | 756.78 | 907
2012-03-06 | Labour HIre | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-03-06 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-03-06 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 907
2012-03-06 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 907
2012-03-06 |  | Plant Float - Allciv | hr | 10 | 7 | 70 | 907
2012-03-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-03-31 | Vechicle Hire . Inv No - 161620 | Vechicle Hire |  | 1 | 729 | 729 | 907
2012-04-03 | Vechicle Hire . Inv No - 161693 | Vechicle Hire |  | 1 | 404.05 | 404.05 | 907
2012-06-10 | Transport of Tractor/Profiler. Inv No - 41092 | Float |  | 1 | 2950 | 2950 | 907
2012-06-13 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-13 | labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-14 | Labour Hire | Labour | hr | 4 | 74.65 | 298.6 | 907
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-14 | labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.358 | 141.432 | 907
2012-06-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-18 | labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-19 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-25 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 907
2012-06-25 | Labour Hire | Labour | hr | 4 | 35.358 | 141.432 | 907
| Subtotal for 907 |  |  |  |  | 45323.639
Cost Code 910
2012-03-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 910
2012-03-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 910
2012-03-10 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 910
| Subtotal for 910 |  |  |  |  | 530.25
Cost Code 911
2011-11-13 | Accommodation & 3 meals Rate Inv - 56631 | Accommodation |  | 1 | 104.45 | 104.45 | 911
2011-11-15 | Accommodation & 3 meals Rate From the 1/11/2011 to the 15/11/2011 | Accommodation |  | 1 | 2950 | 2950 | 911
2011-11-30 | Middle ENSUITE Inv No -1039301 | Accommodation |  | 1 | 593.1 | 593.1 | 911
2011-11-30 | ENSUITE Inv No 1039137 | Accommodation |  | 1 | 748.8 | 748.8 | 911
2011-11-30 | 3 meals Rate & Crib Inv No 1039511 | Accommodation |  | 1 | 2567.4 | 2567.4 | 911
2011-11-30 | From the 16/11/2011 to the 30/11/2011 Inv - 1039056 | Accommodation |  | 1 | 561.6 | 561.6 | 911
2011-12-31 | Accommodation From the 16/12/2011 to the 17/12/2011 Inv No - 1040721 | Accommodation |  | 1 | 813.64 | 813.64 | 911
2012-01-23 | Accommodation & 3 meals Rate. From the 8/01/2011 to the 11/1/2012 . Inv No - 1041112 | Accommodation |  | 1 | 2113.64 | 2113.64 | 911
2012-01-24 | Billing Period from the 20/10/2011 - 23/01/2012. Acc No 17482038 | Power |  | 1 | 231.27 | 231.27 | 911
2012-01-25 | Billing Period from the 20/10/2011 - 24/01/12 Acc No - 16889789 | Power |  | 1 | 528.86 | 528.86 | 911
2012-01-31 | Accommodation & 3 meals Rate From the 16/01/2012 to the 25/01/2012. Inv No 1041512 | Accommodation |  | 1 | 4745.46 | 4745.46 | 911
2012-02-02 | Billing Period from the27/10/2011 to lthe 02/02/2012. Acc No 16889762 | Power |  | 1 | 595.18 | 595.18 | 911
2012-02-15 | Accommodation & 3 meals Rate. From the 1/02/12 to the 15/02/12. Inv No - 1042504 | Accommodation |  | 1 | 3113.64 | 3113.64 | 911
2012-02-29 | Accommodation & 3 meals Rate. From the 16/02/12 - 28/02/2012. | Accommodation |  | 1 | 2114 | 2114 | 911
2012-02-29 | From the 16/02/2012 to the 29/02/12. Inv No - 1043022 | Accommodation |  | 1 | 655.2 | 655.2 | 911
2012-03-31 | Accommodation & 3 meals Rate. From the 16/03/2012 to 31/3/2012. Inv No - 1045104 | Accommodation |  | 1 | 2468.18 | 2468.19 | 911
| Subtotal for 911 |  |  |  |  | 24904.43
Cost Code C20
2011-11-25 | N20 Concrete Inv No - 9405391085 | N20 |  | 1 | 1035.5 | 1035.5 | C20
2012-01-27 | N20 Concrete. Inv No - 9405524315 | N20 |  | 1 | 295 | 295 | C20
2012-01-31 | N20 Concrete. Inv No - 94055027312 | N20 |  | 1 | 495 | 495 | C20
2012-02-11 | N20 Concrete & N25. Inv No - 9405570082 | N20 |  | 1 | 345.5 | 345.5 | C20
2012-02-14 | N20 Concrete. Inv No - 9405570081 | N20 |  | 1 | 342.5 | 342.5 | C20
| Subtotal for C20 |  |  |  |  | 2513.5
Cost Code C32
2011-11-28 | N32 Concrete Inv No - 9405391084 | N32 |  | 1 | 1417.5 | 1417.5 | C32
2011-11-30 | N32 Concrete Inv No - 9405397632 | N32 |  | 1 | 1020.6 | 1020.6 | C32
2011-12-13 | Inv No - 66990673 | Cement |  | 1 | 278.4 | 278.4 | C32
2012-01-25 | N32 Concrete. Inv No - 9405524314 | N32 |  | 1 | 3816.8 | 3816.8 | C32
2012-01-30 | N32 Concrete. Inv No - 9405524316 | N32 |  | 1 | 353.5 | 353.5 | C32
| Subtotal for C32 |  |  |  |  | 6886.8
Cost Code C40
2011-11-14 | Inv - 540091 | Concrete |  | 1 | 3761.1 | 3761.1 | C40
2011-11-15 | Inv No 9405391086 | N40 |  | 1 | 3283.5 | 3283.5 | C40
2012-02-08 | Inv No- 9405562861 | N40 |  | 1 | 526.6 | 526.6 | C40
| Subtotal for C40 |  |  |  |  | 7571.2
Cost Code CKM
2012-02-15 | Inv No - 9405580233 | Kerb Concrete |  | 1 | 2177.4 | 2177.4 | CKM
| Subtotal for CKM |  |  |  |  | 2177.4
Cost Code CSA
2012-06-07 | Bulk GP / GB Cement. Inv No - 94745152 | Cement Powder |  | 25.35 | 265.57 | 6732.1995 | CSA
2012-06-08 | Bulk GP / GB Cement. Inv No - 94745153 | Cement Powder |  | 24.75 | 265.57 | 6572.8575 | CSA
2012-06-09 | 7/10mm con Agg . Inv No - 4092 | Con Aggregate |  | 6.3 | 48 | 302.4 | CSA
2012-06-10 | 7/10mm con Agg . Inv No - 4094 | Con Aggregate |  | 17.55 | 48 | 842.4 | CSA
2012-06-11 | 7/10mm con Agg. Inv No - 4093 | Con Aggregate |  | 18 | 48 | 864 | CSA
2012-06-13 | 7/10mm con Agg . Inv No - 4147 | Con Aggregate |  | 16.7 | 48 | 801.6 | CSA
2012-06-21 | 7/10mm con Agg . Inv No - 4176 | Con Aggregate |  | 72.9 | 45 | 3280.5 | CSA
2012-06-23 | 7/10mm con Agg. Inv No - 4230 | Con Aggregate |  | 27.4 | 48 | 1315.2 | CSA
| Subtotal for CSA |  |  |  |  | 20711.157
Cost Code CSS
2011-10-25 | Bedding Sand Inv - 532 | Stabilised Sand |  | 12.16 | 25 | 304 | CSS
2011-11-01 | Bedding Sand Docket No 29968 Inv - 2992 | Sand |  | 12 | 24.36 | 292.32 | CSS
2011-11-17 | Stabilised Sand Inv No - 9405391087 | Stabilised Sand |  | 1 | 1216.7 | 1216.7 | CSS
2012-02-09 | Stabilised Sand. Inv No - 9405570080 | Stabilised Sand |  | 1 | 2340 | 2340 | CSS
2012-02-10 | Stabilised Sand. Inv No - 9405570083 | Stabilised Sand |  | 1 | 1901.8 | 1901.8 | CSS
2012-02-29 | Stabilised Sand. Inv No - 591 | Stabilised Sand |  | 26.26 | 25 | 656.5 | CSS
| Subtotal for CSS |  |  |  |  | 6711.32
Cost Code ETC
2012-01-27 | Inv No - 6054523 | Conduits |  | 1 | 3350.29 | 3350.29 | ETC
2012-02-13 | Inv No - SIP33161 | Foundation Cage |  | 1 | 1720 | 1720 | ETC
| Subtotal for ETC |  |  |  |  | 5070.29
Cost Code ETP
2012-01-30 | Inv No- 294291 | Pits & Lids |  | 1 | 3525 | 3525 | ETP
| Subtotal for ETP |  |  |  |  | 3525
Cost Code QM2.3
2012-01-30 | Inv No - 556 | Road Base |  | 4610.4 | 8 | 36883.2 | QM2.3
| Subtotal for QM2.3 |  |  |  |  | 36883.2
Cost Code QMR
2011-11-10 | Docket No 30328,30329 Inv- 3034 | Stemmings |  | 1 | 812.78 | 812.78 | QMR
2011-11-15 | 10-20mm Stemmings docket No 27702 Inv 27702 | Rock Breaker |  | 12.18 | 33.6 | 409.248 | QMR
2012-01-30 | Inv No - 3335 | Rock |  | 1 | 4783.24 | 4783.24 | QMR
| Subtotal for QMR |  |  |  |  | 6005.268
Cost Code QMS
2011-11-14 | Stabilised Sand Inv- 9405357294 | Stabilised Sand |  | 1 | 1428.3 | 1428.3 | QMS
| Subtotal for QMS |  |  |  |  | 1428.3
Cost Code RSM
2011-11-11 | Onemesh Rect 6 * 2.4m, 12mm Dia 500 PLUS Rebar Inv 17145534 S2 00430 | Steel |  | 1 | 2780.72 | 2780.72 | RSM
2011-11-11 | 110-120mm CombDeck Chair Inv - 1715545-S2-00430 | Steel |  | 1 | 128.8 | 128.8 | RSM
| Subtotal for RSM |  |  |  |  | 2909.52
Cost Code SWC
2011-11-07 | Inv 19837 | RCBC - 600 x 300 |  | 15 | 320 | 4800 | SWC
2011-11-07 | Inv 19837 | RCBC - 1200 x 600 |  | 34 | 465 | 15810 | SWC
| Subtotal for SWC |  |  |  |  | 20610
Cost Code SWP
2011-10-15 | 2.44m - 375 mm 2 FJ RC Pipes, Wingwalls Inv - 19669 | Pipes |  | 1 | 9270.25 | 9270.25 | SWP
2011-11-08 | Inv - 19845 | Wing Walls |  | 1 | 417 | 417 | SWP
2011-11-09 | 2.4m -375mm Class 2 FJ RC Pipe Doket No Direct Inv - 19852 | Pipe |  | 1 | 175 | 175 | SWP
2011-11-26 | Quick Cut Saw Hire from the 23/11/2011 to the 25/11/2011 Inv No 7774800 | Quick Cut Saw |  | 1 | 198 | 198 | SWP
2011-11-30 | Makita Jackhammer Inv No - 7775895 | Jackhammer |  | 1 | 440 | 440 | SWP
| Subtotal for SWP |  |  |  |  | 10500.25
| Grand Total |  |  |  |  | 1429262.6045