## Estimate
WBS | Line No. | Resource Name | Unit | Type | No | Prodn | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
[9 empty] | 1122698.2045 |  |  | 248940.0554 | 187943.6643 | 377197.4782 | 308617.0066 | 1122698.2045
5 | Line No 1 Item No | NICOL ST - PROSERPINE
6 | Line No 3 Item No QP1 | Quality System Documents & Records | LS |  |  |  | 1 |  | 3250 |  | 5 | 3250 | 0 | 0 | 0 | 3250
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 5 | 3250 | 0 | 0 | 0 | 3250 | 13
7 | Line No 4 Item No QCP1 | Quality Verification & Control | LS |  |  |  | 1 |  | 11750 |  | 0 | 8060 | 0 | 0 | 3690 | 11750
| 1 | Area of Pavement: qty = 2000 m2 | m² |  |  |  | 2000
| 2 | Field Density | each | S | 3 | 166.6667 | 2000 | 45 | 1620 | 36 | 4 | 0 | 0 | 0 | 1620 | 1620 | 13
| 3 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 | 3 | 3 | 0 | 0 | 0 | 1170 | 1170 | 13
| 4 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 13
| 5 | Surveyor | hr | L | 1 | 1 | 26 | 185 | 4810 | 26 | 26 | 4810 | 0 | 0 | 0 | 4810 | 11
| 6 | Concrete Cylinders | each | S | 1 | 1 | 6 | 150 | 900 | 6 | 6 | 0 | 0 | 0 | 900 | 900 | 13
8 | Line No 5 Item No C101(b) | Site Establishment & Disestablishment | LS |  |  |  | 1 |  | 13900 |  | 5 | 8700 | 0 | 5200 | 0 | 13900
| 1 | Float | LS | P | 800 | 1 | 1 | 1 | 800 | 800 | 1 | 0 | 0 | 800 | 0 | 800 | 907
| 2 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 3 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 4 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 5 | Float | LS | P | 800 | 1 | 1 | 1 | 800 | 800 | 1 | 0 | 0 | 800 | 0 | 800 | 907
| 6 | Float | LS | P | 1200 | 1 | 1 | 1 | 1200 | 1200 | 1 | 0 | 0 | 1200 | 0 | 1200 | 907
| 7 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 8 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 1 | 3350 | 0 | 0 | 0 | 3350 | 902
| 9 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 902
| 10 | Labour | hr | L | 5 | 0.1 | 1 | 42 | 2100 | 50 | 2 | 2100 | 0 | 0 | 0 | 2100 | 907
1
9 | Line No 6 Item No | Preparation of Environmrntal Management Plan | LS |  |  |  | 1 |  | 3250 |  | 5 | 3250 | 0 | 0 | 0 | 3250
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 13
| Line No 8 Item No | ROAD & EARTHWORKS
10 | Line No 9 Item No C201 (a) | Control of Traffic | LS |  |  |  | 1 |  | 15829.5455 |  | 35 | 11454.5455 | 0 | 4375 | 0 | 15829.5455
| 1 | Use a full time traffic controller with a hire ute from Meteor. |  |  | 1 | 1
10.1 | 2 | Traffic Controller | hr | L | 1 | 0.11 | 30 | 42 | 11454.5455 | 272.7273 | 30.303 | 11454.5455 | 0 | 0 | 0 | 11454.5455 | 141
| 3 | Ute - Hire | day | P | 1 | 1 | 35 | 125 | 4375 | 35 | 35 | 0 | 0 | 4375 | 0 | 4375 | 141
11 | Line No 10 Item No C201 (b) | Provision of Temporary Roadways, Sidetracks & Detours | LS |  |  |  | 1 |  | 6600 |  | 0 | 6600 | 0 | 0 | 0 | 6600
| 1 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 1 | 3350 | 0 | 0 | 0 | 3350 | 902
| 2 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 1 | 3250 | 0 | 0 | 0 | 3250 | 902
12 | Line No 11 Item No C211(a) | Temporary Erosion & Sedimentation Control | LS |  |  |  | 1 |  | 5050 |  | 2 | 2100 | 2000 | 950 | 0 | 5050
12.1 | 1 | Silt Fence | m | M | 1 | 1 | 500 | 2 | 1000 | 500 |  | 0 | 1000 | 0 | 0 | 1000 | 151
| 2 | Pickets | each | M | 1 | 1 | 166.6667 | 6 | 1000 | 166.6667 |  | 0 | 1000 | 0 | 0 | 1000 | 151
12.2 | 3 | Labour | hr | L | 5 | 50 | 500 | 42 | 2100 | 50 | 1.1111 | 2100 | 0 | 0 | 0 | 2100 | 151
| 4 | Bobcat | hr | P | 1 | 50 | 500 | 95 | 950 | 10 | 1.1111 | 0 | 0 | 950 | 0 | 950 | 151
13 | Line No 12 Item No C212 (a) | Clearing & Grubbing | LS |  |  |  | 1 |  | 11683.3333 |  | 2 | 2100 | 0 | 7083.3333 | 2500 | 11683.3333
Two days to clear & grub & 100 tonnes to the tip
13.1 | 1 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 1.8519 | 0 | 0 | 2250 | 0 | 2250 | 22
| 2 | Tipper | hr | P | 2 | 0.06 | 1 | 95 | 3166.6667 | 33.3333 | 1.8519 | 0 | 0 | 3166.6667 | 0 | 3166.6667 | 22
| 3 | Labour | hr | L | 3 | 0.06 | 1 | 42 | 2100 | 50 | 1.8519 | 2100 | 0 | 0 | 0 | 2100 | 22
| 4 | Water Cart - Hire | hr | P | 1 | 0.06 | 1 | 100 | 1666.6667 | 16.6667 | 1.8519 | 0 | 0 | 1666.6667 | 0 | 1666.6667 | 22
| 5 | Tip Fees | tonne | S | 1 | 1 | 100 | 25 | 2500 | 100 | 11.1111 | 0 | 0 | 0 | 2500 | 2500 | 22
14 | Line No 13 Item No C213(a) | Removal & Stockpiling of Topsoil for Re-use | cum |  |  |  | 20 |  | 272 |  | 1 | 42 | 0 | 230 | 0 | 272
14.1 | 1 | Excavator - 25T | hr | P | 1 | 20 | 20 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 31
| 2 | Tipper | hr | P | 1 | 20 | 20 | 95 | 95 | 1 | 0.11111 | 0 | 0 | 95 | 0 | 95 | 31
| 3 | Labour | hr | L | 1 | 20 | 20 | 42 | 42 | 1 | 0.11111 | 42 | 0 | 0 | 0 | 42 | 31
15 | Line No 14 Item No C213(b) | General Earthworks (Cut) | cum |  |  |  | 1045 |  | 14496.5549 |  | 3 | 2016.0772 | 0 | 12480.4777 | 0 | 14496.5549
15.1 | 1 | Excavator - 25T | hr | P | 1 | 43.54 | 1045 | 135 | 3240.124 | 24.0009 | 2.6668 | 0 | 0 | 3240.124 | 0 | 3240.124 | 53
| 2 | Tipper | hr | P | 3 | 43.54 | 1045 | 95 | 6840.2618 | 72.0028 | 2.6668 | 0 | 0 | 6840.2618 | 0 | 6840.2618 | 53
| 3 | Labour | hr | L | 2 | 43.54 | 1045 | 42 | 2016.0772 | 48.0018 | 2.6668 | 2016.0772 | 0 | 0 | 0 | 2016.0772 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 43.54 | 1045 | 100 | 2400.0919 | 24.0009 | 2.6668 | 0 | 0 | 2400.0919 | 0 | 2400.0919 | 53
16 | Line No 15 Item No C213(d) | Replace unsuitable material below subgrade with select material complete (Provisional) | cum |  |  |  | 10 |  | 922.3708 |  | 1 | 174.7291 | 0 | 747.6418 | 0 | 922.3708
17.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | 10 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 53
| 2 | Tipper | hr | P | 1 | 10 | 10 | 95 | 95 | 1 | 0.11111 | 0 | 0 | 95 | 0 | 95 | 53
| 3 | Labour | hr | L | 2 | 10 | 10 | 42 | 84 | 2 | 0.11111 | 84 | 0 | 0 | 0 | 84 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 10 | 10 | 100 | 100 | 1 | 0.11111 | 0 | 0 | 100 | 0 | 100 | 53
| 5 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 6 | Gravel to be hauled in tonnes = QTY*Gravel Conversion Factor |  |  |  |  | 24
17.2 | 7 | Grader | hr | P | 1 | 33.33 | 24 | 135 | 97.2097 | 0.72007 | 0.080008 | 0 | 0 | 97.2097 | 0 | 97.2097 | 62
| 8 | Truck & Dog | hr | P | 2 | 33.33 | 24 | 145 | 208.8209 | 1.4401 | 0.080008 | 0 | 0 | 208.8209 | 0 | 208.8209 | 62
| 9 | Water Cart - Hire | hr | P | 1 | 33.33 | 24 | 100 | 72.0072 | 0.72007 | 0.080008 | 0 | 0 | 72.0072 | 0 | 72.0072 | 62
| 10 | SD Roller - Wet (No Op) | hr | P | 1 | 33.33 | 24 | 55 | 39.604 | 0.72007 | 0.080008 | 0 | 0 | 39.604 | 0 | 39.604 | 62
| 11 | Labour | hr | L | 3 | 33.33 | 24 | 42 | 90.7291 | 2.1602 | 0.080008 | 90.7291 | 0 | 0 | 0 | 90.7291 | 62
| Line No 17 Item No | STORMWATER DRAINAGE
18 | Line No 18 Item No | Alteration to Exisiting Stormwater Structures | LS |  |  |  | 1 |  | 1036 |  | 1 | 336 | 0 | 0 | 700 | 1036
| 1 | Core drill two inlets for sub-soil & grout up.
| 2 | Concrete Hole Cutting | each | S | 1 | 1 | 2 | 350 | 700 | 2 | 0.22222 | 0 | 0 | 0 | 700 | 700 | 75
18.1 | 3 | Labour | hr | L | 2 | 0.5 | 2 | 42 | 336 | 8 | 0.44444 | 336 | 0 | 0 | 0 | 336 | 75
19 | Line No 19 Item No C224(h) | Concrete Barrier Kerb (B1) | m |  |  |  | 308 |  | 14424.1456 |  | 2 | 0 | 6764.1456 | 1500 | 6160 | 14424.1456
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry. 8.6 lineal metres per CUM of concrete; 75 m of kerb per tonne of sand; 8:1 mix of sand cement for slurry.
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 35.814 | 181 | 6482.3256 | 35.814 |  | 0 | 6482.3256 | 0 | 0 | 6482.3256 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 4.1067 | 24 | 98.56 | 4.1067 |  | 0 | 98.56 | 0 | 0 | 98.56 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.51333 | 357 | 183.26 | 0.51333 |  | 0 | 183.26 | 0 | 0 | 183.26 | 71
| 5 | Kerb Subbie | m | S | 1 | 1 | 308 | 20 | 6160 | 308 | 1.54 | 0 | 0 | 0 | 6160 | 6160 | 71
| 6 | Float | LS | P | 1 | 1 | 1500 | 1 | 1500 | 1500 | 166.6667 | 0 | 0 | 1500 | 0 | 1500 | 71
20 | Line No 20 Item No C232(b) | 100mm slotted corrugated lastic pipe | m |  |  |  | 260 |  | 10119.7822 |  | 3 | 2948.6949 | 1706.6409 | 5464.4464 | 0 | 10119.7822
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 260 | 2.5 | 650 | 260 |  | 0 | 650 | 0 | 0 | 650 | 87
| 3 | Sub Soil Flush Fittings | each | M | 1 | 1 | 5.2 | 25 | 130 | 5.2 |  | 0 | 130 | 0 | 0 | 130 | 87
| 4 | Sand | tonne | M | 1 | 1 | 38.61 | 24 | 926.6409 | 38.61 |  | 0 | 926.6409 | 0 | 0 | 926.6409 | QMS
20.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 260 | 135 | 3159.3159 | 23.4023 | 2.6003 | 0 | 0 | 3159.3159 | 0 | 3159.3159 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 260 | 42 | 2948.6949 | 70.207 | 2.6003 | 2948.6949 | 0 | 0 | 0 | 2948.6949 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 260 | 95 | 2223.2223 | 23.4023 | 2.6003 | 0 | 0 | 2223.2223 | 0 | 2223.2223 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 260 | 3.5 | 81.9082 | 23.4023 | 2.6003 | 0 | 0 | 81.9082 | 0 | 81.9082 | 87
20.2 | Line No 21 Item No C232(c) | Cleanout Structures | ea |  |  |  | 6 |  | 858 |  | 1 | 0 | 0 | 0 | 858 | 858
| 1 | Sub Soil Clean Out - Inst | each | S | 1 | 1 | 6 | 143 | 858 | 6 | 0.66667 | 0 | 0 | 0 | 858 | 858 | 87
| Line No 23 Item No | PAVEMENTS
21 | Line No 24 Item No C241(a) | Supply stabilising Agent | tonne |  |  |  | 34 |  | 12138 |  | 1 | 0 | 12138 | 0 | 0 | 12138
| 1 | Cement | tonne | M | 1 | 1 | 34 | 357 | 12138 | 34 |  | 0 | 12138 | 0 | 0 | 12138 | CSA
22 | Line No 25 Item No C242(b) | Mixing & Spreading of stabilising agent | sqm |  |  |  | 1893 |  | 12392.6621 |  | 4 | 4770.1215 | 0 | 7622.5406 | 0 | 12392.6621
| 1 | Stabilising | m² |  |  |  | 1893
22.1 | 2 | CAT297 Stabiliser | hr | P | 1 | 66.67 | 1893 | 66.07 | 1875.9639 | 28.3936 | 3.1548 | 0 | 0 | 1875.9639 | 0 | 1875.9639 | 68
| 3 | NH Grader | hr | P | 1 | 66.67 | 1893 | 25.78 | 731.9865 | 28.3936 | 3.1548 | 0 | 0 | 731.9865 | 0 | 731.9865 | 68
| 4 | Water Cart - Hire | hr | P | 1 | 66.67 | 1893 | 100 | 2839.358 | 28.3936 | 3.1548 | 0 | 0 | 2839.358 | 0 | 2839.358 | 68
| 5 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 1893 | 55 | 1561.6469 | 28.3936 | 3.1548 | 0 | 0 | 1561.6469 | 0 | 1561.6469 | 68
| 6 | UD Spreader | hr | P | 1 | 66.67 | 1893 | 21.61 | 613.5853 | 28.3936 | 3.1548 | 0 | 0 | 613.5853 | 0 | 613.5853 | 68
| 7 | Labour | hr | L | 4 | 66.67 | 1893 | 42 | 4770.1215 | 113.5743 | 3.1548 | 4770.1215 | 0 | 0 | 0 | 4770.1215 | 68
23 | Line No 26 Item No C242 | Place only 2.3 | cum |  |  |  | 758 |  | 34836.6157 |  | 5 | 5157.9478 | 0 | 29678.6679 | 0 | 34836.6157
| 1 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 2 | Gravel to be hauled in tonnes = QTY * Gravel Conversion Factor |  |  |  |  | 1819.2
23.1 | 3 | Grader | hr | P | 1 | 44.44 | 1819.2 | 135 | 5526.3726 | 40.9361 | 4.5485 | 0 | 0 | 5526.3726 | 0 | 5526.3726 | 62
| 4 | Truck & Dog | hr | P | 3 | 44.44 | 1819.2 | 145 | 17807.2007 | 122.8083 | 4.5485 | 0 | 0 | 17807.2007 | 0 | 17807.2007 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 1819.2 | 100 | 4093.6094 | 40.9361 | 4.5485 | 0 | 0 | 4093.6094 | 0 | 4093.6094 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 1819.2 | 55 | 2251.4851 | 40.9361 | 4.5485 | 0 | 0 | 2251.4851 | 0 | 2251.4851 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 1819.2 | 42 | 5157.9478 | 122.8083 | 4.5485 | 5157.9478 | 0 | 0 | 0 | 5157.9478 | 62
24 | Line No 27 Item No C242 | Place only 2.1 | cum |  |  |  | 282 |  | 14940.5907 |  | 3 | 2708.5199 | 0 | 12232.0708 | 0 | 14940.5907
| 1 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 2 | Gravel to be hauled in tonnes = QTY * Gravel Conversion Factor |  |  |  |  | 676.8
24.1 | 3 | Grader | hr | P | 1 | 44.44 | 676.8 | 135 | 2055.9856 | 15.2295 | 1.6922 | 0 | 0 | 2055.9856 | 0 | 2055.9856 | 62
| 4 | Truck & Dog | hr | P | 3 | 44.44 | 676.8 | 145 | 6624.8425 | 45.6886 | 1.6922 | 0 | 0 | 6624.8425 | 0 | 6624.8425 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 676.8 | 100 | 1522.9523 | 15.2295 | 1.6922 | 0 | 0 | 1522.9523 | 0 | 1522.9523 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 676.8 | 55 | 837.6238 | 15.2295 | 1.6922 | 0 | 0 | 837.6238 | 0 | 837.6238 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 676.8 | 42 | 1918.9199 | 45.6886 | 1.6922 | 1918.9199 | 0 | 0 | 0 | 1918.9199 | 62
8
| 9 | Final Trim (Layer thickness = 150mm) | m2
24.2 | 10 | Grader | hr | P | 1 | 300 | 1880 | 135 | 846 | 6.2667 | 0.6963 | 0 | 0 | 846 | 0 | 846 | 63
| 11 | MW Roller | hr | P | 1 | 300 | 1880 | 55 | 344.6667 | 6.2667 | 0.6963 | 0 | 0 | 344.6667 | 0 | 344.6667 | 63
| 12 | Labour | hr | L | 3 | 300 | 1880 | 42 | 789.6 | 18.8 | 0.6963 | 789.6 | 0 | 0 | 0 | 789.6 | 63
25 | Line No 28 Item No C242 | Special Item - Take up existing gravel, stabilise & relay as working platform | m3 |  |  |  | 483 |  | 34310.9398 |  | 7 | 5375.5466 | 8276.688 | 20658.7052 | 0 | 34310.9398
| 1 | Take Up the Gravel
| 2 | Excavator - 25T | hr | P | 1 | 40 | 483 | 135 | 1630.125 | 12.075 | 1.3417 | 0 | 0 | 1630.125 | 0 | 1630.125 | 53
| 3 | Tipper | hr | P | 2 | 40 | 483 | 95 | 2294.25 | 24.15 | 1.3417 | 0 | 0 | 2294.25 | 0 | 2294.25 | 53
| 4 | Labour | hr | L | 1 | 40 | 483 | 42 | 507.15 | 12.075 | 1.3417 | 507.15 | 0 | 0 | 0 | 507.15 | 53
| 5 | Relay Gravel
| 6 | Excavator - 25T | hr | P | 1 | 27.778 | 483 | 135 | 2347.3612 | 17.3879 | 1.932 | 0 | 0 | 2347.3612 | 0 | 2347.3612 | 53
| 7 | Tipper | hr | P | 2 | 27.778 | 483 | 95 | 3303.6936 | 34.7757 | 1.932 | 0 | 0 | 3303.6936 | 0 | 3303.6936 | 53
| 8 | Grader | hr | P | 1 | 27.778 | 483 | 135 | 2347.3612 | 17.3879 | 1.932 | 0 | 0 | 2347.3612 | 0 | 2347.3612 | 53
| 9 | SD Roller - Wet (No Op) | hr | P | 1 | 27.778 | 483 | 55 | 956.3323 | 17.3879 | 1.932 | 0 | 0 | 956.3323 | 0 | 956.3323 | 53
| 10 | Stabilise (12kg / m2 spread rate)
| 11 | Cement | tonne | M | 1 | 1 | 23.184 | 357 | 8276.688 | 23.184 |  | 0 | 8276.688 | 0 | 0 | 8276.688 | CSA
| 12 | Stabilising | m² |  |  |  | 1932
25.1 | 13 | CAT297 Stabiliser | hr | P | 1 | 66.67 | 1932 | 66.07 | 1914.6129 | 28.9786 | 3.2198 | 0 | 0 | 1914.6129 | 0 | 1914.6129 | 68
| 14 | NH Grader | hr | P | 1 | 66.67 | 1932 | 25.78 | 747.067 | 28.9786 | 3.2198 | 0 | 0 | 747.067 | 0 | 747.067 | 68
| 15 | Water Cart - Hire | hr | P | 1 | 66.67 | 1932 | 100 | 2897.8551 | 28.9786 | 3.2198 | 0 | 0 | 2897.8551 | 0 | 2897.8551 | 68
| 16 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 1932 | 55 | 1593.8203 | 28.9786 | 3.2198 | 0 | 0 | 1593.8203 | 0 | 1593.8203 | 68
| 17 | UD Spreader | hr | P | 1 | 66.67 | 1932 | 21.61 | 626.2265 | 28.9786 | 3.2198 | 0 | 0 | 626.2265 | 0 | 626.2265 | 68
| 18 | Labour | hr | L | 4 | 66.67 | 1932 | 42 | 4868.3966 | 115.9142 | 3.2198 | 4868.3966 | 0 | 0 | 0 | 4868.3966 | 68
26 | Line No 29 Item No C244(a) | AMC5 | sqm |  |  |  | 1661 |  | 16638.237 |  | 1 | 0 | 0 | 0 | 16638.237 | 16638.237
| 1 | Seal Visit One | m² | S | 1 | 1 | 1744.05 | 9.54 | 16638.237 | 1744.05 | 193.7833 | 0 | 0 | 0 | 16638.237 | 16638.237 | 64
27 | Line No 30 Item No C245(c) | DG14 AC | tonne |  |  |  | 195 |  | 58305 |  | 1 | 0 | 58305 | 0 | 0 | 58305
| 1 | DG14 | tonne | M | 1 | 1 | 195 | 299 | 58305 | 195 |  | 0 | 58305 | 0 | 0 | 58305 | 65
| Line No 32 Item No | MISCELLANEOUS
28 | Line No 33 Item No C271(c) | Industrial Invert Crossing | ea |  |  |  | 15 |  | 40993.6877 |  | 7 | 217.1402 | 25628.4328 | 1189.1012 | 13959.0135 | 40993.6877
| 1 | Purchase Materials
| 2 | sqm of invert = 517 m2 | m² |  |  |  | 517.0005
| 3 | N25 | m³ | M | 1 | 1 | 99.5226 | 165 | 16421.2284 | 99.5226 |  | 0 | 16421.2284 | 0 | 0 | 16421.2284 | C25
| 4 | Sand | tonne | M | 1 | 1 | 77.5501 | 24 | 1861.2018 | 77.5501 |  | 0 | 1861.2018 | 0 | 0 | 1861.2018 | QMS
| 5 | SL72 | m² | M | 1 | 1 | 620.4006 | 9.1 | 5645.6455 | 620.4006 |  | 0 | 5645.6455 | 0 | 0 | 5645.6455 | RSM
| 6 | Abel Flex | m | M | 1 | 1 | 413.6004 | 3 | 1240.8012 | 413.6004 |  | 0 | 1240.8012 | 0 | 0 | 1240.8012 | RSM
| 7 | Detailed Excavation:
28.1 | 8 | Excavator - 25T | hr | P | 1 | 10 | 51.7001 | 135 | 697.9507 | 5.17 | 0.57445 | 0 | 0 | 697.9507 | 0 | 697.9507 | 73
| 9 | Tipper | hr | P | 1 | 10 | 51.7001 | 95 | 491.1505 | 5.17 | 0.57445 | 0 | 0 | 491.1505 | 0 | 491.1505 | 73
| 10 | Labour | hr | L | 1 | 10 | 51.7001 | 42 | 217.1402 | 5.17 | 0.57445 | 217.1402 | 0 | 0 | 0 | 217.1402 | 73
| 11 | Form Pour & Finish
| 12 | Bar Chairs | each | M | 1 | 1 | 574.445 | 0.8 | 459.556 | 574.445 |  | 0 | 459.556 | 0 | 0 | 459.556 | 73
| 13 | Concrete Subbie | m² | S | 1 | 1 | 517.0005 | 27 | 13959.0135 | 517.0005 | 57.4445 | 0 | 0 | 0 | 13959.0135 | 13959.0135 | 73
29 | Line No 34 Item No C273(a) | Grass Seeding | sqm |  |  |  | 1000 |  | 2695 |  | 1 | 0 | 0 | 0 | 2695 | 2695
| 1 | Grass Seeding | m² | S | 1 | 1 | 1100 | 2.45 | 2695 | 1100 | 122.2222 | 0 | 0 | 0 | 2695 | 2695 | 121
30 | Line No 35 Item No C306(a) | Sawcut bitumous pavement |  |  |  |  | 30 |  | 900 |  | 1 | 0 | 0 | 0 | 900 | 900
| 1 | Sawcut | m | S | 1 | 1 | 30 | 30 | 900 | 30 | 0.13333 | 0 | 0 | 0 | 900 | 900 | 75
31 | Line No 36 Item No C306(b) | Remove existing pavement & dispose offsite | m2 |  |  |  | 1661 |  | 3708.45 |  | 1 | 0 | 0 | 2047.45 | 1661 | 3708.45
31.1 | 1 | Grader | hr | P | 1 | 300 | 1661 | 135 | 747.45 | 5.5367 | 0.61519 | 0 | 0 | 747.45 | 0 | 747.45 | 53
31.2 | 2 | Excavator - 25T | hr | P | 1 | 415.25 | 1661 | 135 | 540 | 4 | 0.44444 | 0 | 0 | 540 | 0 | 540 | 53
| 3 | Tipper | hr | P | 2 | 415.25 | 1661 | 95 | 760 | 8 | 0.44444 | 0 | 0 | 760 | 0 | 760 | 53
| 4 | Tip Fees | tonne | S | 1 | 1 | 66.44 | 25 | 1661 | 66.44 | 7.3822 | 0 | 0 | 0 | 1661 | 1661 | 53
32 | Line No 37 Item No | Locate & Protect services | LS |  |  |  | 1 |  | 2025 |  | 2 | 0 | 0 | 0 | 2025 | 2025
| 1 | Service Locator | hr | S | 1 | 1 | 15 | 135 | 2025 | 15 | 1.6667 | 0 | 0 | 0 | 2025 | 2025 | 15
33 | Line No 38 Item No | As Constructed Plans | LS |  |  |  | 1 |  | 4995 |  | 3 | 4995 | 0 | 0 | 0 | 4995
| 1 | Surveyor | hr | L | 1 | 1 | 27 | 185 | 4995 | 27 | 3 | 4995 | 0 | 0 | 0 | 4995 | 11
34 | Line No 42 Item No | WRIGHTS ROAD (STRATHDICKIE)
35 | Line No 44 Item No QP1 | Quality System Documents & Records | LS |  |  |  | 1 |  | 6500 |  | 5 | 6500 | 0 | 0 | 0 | 6500
| 1 | Project Engineer | week | L | 1 | 1 | 2 | 3250 | 6500 | 2 | 5 | 6500 | 0 | 0 | 0 | 6500 | 13
36 | Line No 45 Item No QCP1 | Quality Verification & Control | LS |  |  |  | 1 |  | 15080 |  | 0 | 8060 | 0 | 0 | 7020 | 15080
| 1 | Area Pavement | m² |  |  |  | 10000
| 2 | Field Density | each | S | 1 | 1 | 90 | 45 | 4050 | 90 |  | 0 | 0 | 0 | 4050 | 4050 | 13
| 3 | Gravel Properties Testing | each | S | 1 | 1 | 3 | 390 | 1170 | 3 |  | 0 | 0 | 0 | 1170 | 1170 | 13
| 4 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 |  | 3250 | 0 | 0 | 0 | 3250 | 13
| 5 | Surveyor | hr | L | 1 | 1 | 26 | 185 | 4810 | 26 |  | 4810 | 0 | 0 | 0 | 4810 | 11
| 6 | Concrete Cylinders | each | S | 1 | 1 | 12 | 150 | 1800 | 12 |  | 0 | 0 | 0 | 1800 | 1800 | 13
37 | Line No 46 Item No C101(b) | Site Establishment & Disestablishment | LS |  |  |  | 1 |  | 13100 |  | 5 | 8700 | 0 | 4400 | 0 | 13100
| 1 | Float | LS | P | 800 | 1 | 1 | 1 | 800 | 800 | 1 | 0 | 0 | 800 | 0 | 800 | 907
| 2 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 3 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 4 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 5 | Float | LS | P | 1200 | 1 | 1 | 1 | 1200 | 1200 | 1 | 0 | 0 | 1200 | 0 | 1200 | 907
| 6 | Float | LS | P | 600 | 1 | 1 | 1 | 600 | 600 | 1 | 0 | 0 | 600 | 0 | 600 | 907
| 7 | Project Supervisor | week | L | 1 | 1 | 1 | 3350 | 3350 | 1 | 5 | 3350 | 0 | 0 | 0 | 3350 | 902
| 8 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 5 | 3250 | 0 | 0 | 0 | 3250 | 902
| 9 | Labour | hr | L | 5 | 0.1 | 1 | 42 | 2100 | 50 | 1.1111 | 2100 | 0 | 0 | 0 | 2100 | 907
38 | Line No 47 Item No | Preparation of Environmrntal Management Plan | LS |  |  |  | 1 |  | 3250 |  | 5 | 3250 | 0 | 0 | 0 | 3250
| 1 | Project Engineer | week | L | 1 | 1 | 1 | 3250 | 3250 | 1 | 5 | 3250 | 0 | 0 | 0 | 3250 | 13
| Line No 49 Item No | ROAD & EARTHWORKS
39 | Line No 50 Item No C201 (a) | Control of Traffic | LS |  |  |  | 1 |  | 10024 |  | 28 | 3024 | 0 | 7000 | 0 | 10024
| 1 | Traffic Controller | hr | L | 2 | 1 | 24 | 42 | 2016 | 48 | 24 | 2016 | 0 | 0 | 0 | 2016 | 141
| 2 | Traffic Controller | hr | L | 1 | 1 | 24 | 42 | 1008 | 24 | 24 | 1008 | 0 | 0 | 0 | 1008 | 141
| 3 | Ute - Hire | day | P | 2 | 1 | 28 | 125 | 7000 | 56 | 28 | 0 | 0 | 7000 | 0 | 7000 | 141
40 | Line No 51 Item No C201 (b) | Provision of Temporary Roadways, Sidetracks & Detours | LS |  |  |  | 1 |  | 2100 |  | 0 | 2100 | 0 | 0 | 0 | 2100
| 1 | Labour | hr | L | 1 | 1 | 50 | 42 | 2100 | 50 | 50 | 2100 | 0 | 0 | 0 | 2100 | 141
41 | Line No 52 Item No C211(a) | Temporary Erosion & Sedimentation Control | LS |  |  |  | 1 |  | 10950 |  | 6 | 4200 | 2000 | 4750 | 0 | 10950
| 1 | Silt Fence | m | M | 1 | 1 | 500 | 2 | 1000 | 500 |  | 0 | 1000 | 0 | 0 | 1000 | 151
| 2 | Pickets | each | M | 1 | 1 | 166.6667 | 6 | 1000 | 166.6667 |  | 0 | 1000 | 0 | 0 | 1000 | 151
41.1 | 3 | Bobcat | hr | P | 1 | 10 | 500 | 95 | 4750 | 50 | 5.5556 | 0 | 0 | 4750 | 0 | 4750 | 151
| 4 | Labour | hr | L | 2 | 10 | 500 | 42 | 4200 | 100 | 5.5556 | 4200 | 0 | 0 | 0 | 4200 | 151
42 | Line No 53 Item No C212 (a) | Clearing & Grubbing | LS |  |  |  | 1 |  | 9066.6667 |  | 2 | 1400 | 0 | 7666.6667 | 0 | 9066.6667
42.1 | 1 | Grader | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 1.8519 | 0 | 0 | 2250 | 0 | 2250 | 22
| 2 | Excavator - 25T | hr | P | 1 | 0.06 | 1 | 135 | 2250 | 16.6667 | 1.8519 | 0 | 0 | 2250 | 0 | 2250 | 22
| 3 | Tipper | hr | P | 2 | 0.06 | 1 | 95 | 3166.6667 | 33.3333 | 1.8519 | 0 | 0 | 3166.6667 | 0 | 3166.6667 | 22
| 4 | Labour | hr | L | 2 | 0.06 | 1 | 42 | 1400 | 33.3333 | 1.8519 | 1400 | 0 | 0 | 0 | 1400 | 22
43 | Line No 54 Item No C212(a) | Special Item - Demolition of structures(concrete slabs, culverts pipes) | LS |  |  |  | 1 |  | 13800 |  | 4 | 2800 | 0 | 11000 | 0 | 13800
Allow 4 days for the crew to complete this task
43.1 | 1 | Excavator - 25T | hr | P | 1 | 0.03 | 1 | 135 | 4500 | 33.3333 | 3.7037 | 0 | 0 | 4500 | 0 | 4500 | 41
| 2 | Tipper | hr | P | 1 | 0.03 | 1 | 95 | 3166.6667 | 33.3333 | 3.7037 | 0 | 0 | 3166.6667 | 0 | 3166.6667 | 41
| 3 | Water Cart - Hire | hr | P | 1 | 0.03 | 1 | 100 | 3333.3333 | 33.3333 | 3.7037 | 0 | 0 | 3333.3333 | 0 | 3333.3333 | 41
| 4 | Labour | hr | L | 2 | 0.03 | 1 | 42 | 2800 | 66.6667 | 3.7037 | 2800 | 0 | 0 | 0 | 2800 | 41
44 | Line No 55 Item No C213(a) | Removal & Stockpiling of Topsoil for Re-use | cum |  |  |  | 700 |  | 7707.7708 |  | 3 | 882.0882 | 0 | 6825.6826 | 0 | 7707.7708
44.1 | 1 | Excavator - 25T | hr | P | 1 | 33.33 | 700 | 135 | 2835.2835 | 21.0021 | 2.3336 | 0 | 0 | 2835.2835 | 0 | 2835.2835 | 31
| 2 | Tipper | hr | P | 2 | 33.33 | 700 | 95 | 3990.399 | 42.0042 | 2.3336 | 0 | 0 | 3990.399 | 0 | 3990.399 | 31
| 3 | Labour | hr | L | 1 | 33.33 | 700 | 42 | 882.0882 | 21.0021 | 2.3336 | 882.0882 | 0 | 0 | 0 | 882.0882 | 31
44.2 | Line No 56 Item No C213(b) | General Earthworks (Cut) | cum |  |  |  | 1220 |  | 10075.1575 |  | 4 | 1153.0153 | 0 | 8922.1422 | 0 | 10075.1575
44.3 | 1 | Excavator - 25T | hr | P | 1 | 44.44 | 1220 | 135 | 3706.1206 | 27.4527 | 3.0503 | 0 | 0 | 3706.1206 | 0 | 3706.1206 | 53
| 2 | Tipper | hr | P | 2 | 44.44 | 1220 | 95 | 5216.0216 | 54.9055 | 3.0503 | 0 | 0 | 5216.0216 | 0 | 5216.0216 | 53
| 3 | Labour | hr | L | 1 | 44.44 | 1220 | 42 | 1153.0153 | 27.4527 | 3.0503 | 1153.0153 | 0 | 0 | 0 | 1153.0153 | 53
45 | Line No 57 Item No C213(c) | General Earthworks (Fill) | cum |  |  |  | 410 |  | 6310.5311 |  | 2 | 774.9775 | 0 | 5535.5536 | 0 | 6310.5311
45.1 | 1 | Grader | hr | P | 1 | 44.44 | 410 | 135 | 1245.4995 | 9.2259 | 1.0251 | 0 | 0 | 1245.4995 | 0 | 1245.4995 | 55
| 2 | PF Roller | day | P | 1 | 44.44 | 410 | 365 | 3367.4617 | 9.2259 | 1.0251 | 0 | 0 | 3367.4617 | 0 | 3367.4617 | 55
| 3 | Water Cart - Hire | hr | P | 1 | 44.44 | 410 | 100 | 922.5923 | 9.2259 | 1.0251 | 0 | 0 | 922.5923 | 0 | 922.5923 | 55
| 4 | Labour | hr | L | 2 | 44.44 | 410 | 42 | 774.9775 | 18.4518 | 1.0251 | 774.9775 | 0 | 0 | 0 | 774.9775 | 55
46 | Line No 58 Item No C213(d) | Replace unsuitable material below subgrade with select material complete (Provisional) | cum |  |  |  | 10 |  | 922.3708 |  | 1 | 174.7291 | 0 | 747.6418 | 0 | 922.3708
46.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | 10 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 53
| 2 | Tipper | hr | P | 1 | 10 | 10 | 95 | 95 | 1 | 0.11111 | 0 | 0 | 95 | 0 | 95 | 53
| 3 | Labour | hr | L | 2 | 10 | 10 | 42 | 84 | 2 | 0.11111 | 84 | 0 | 0 | 0 | 84 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 10 | 10 | 100 | 100 | 1 | 0.11111 | 0 | 0 | 100 | 0 | 100 | 53
| 5 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 6 | Gravel to be hauled in tonnes. (QTY*Gravel Conversion Factor) |  |  |  |  | 24
46.2 | 7 | Grader | hr | P | 1 | 33.33 | 24 | 135 | 97.2097 | 0.72007 | 0.080008 | 0 | 0 | 97.2097 | 0 | 97.2097 | 62
| 8 | Truck & Dog | hr | P | 2 | 33.33 | 24 | 145 | 208.8209 | 1.4401 | 0.080008 | 0 | 0 | 208.8209 | 0 | 208.8209 | 62
| 9 | Water Cart - Hire | hr | P | 1 | 33.33 | 24 | 100 | 72.0072 | 0.72007 | 0.080008 | 0 | 0 | 72.0072 | 0 | 72.0072 | 62
| 10 | SD Roller - Wet (No Op) | hr | P | 1 | 33.33 | 24 | 55 | 39.604 | 0.72007 | 0.080008 | 0 | 0 | 39.604 | 0 | 39.604 | 62
| 11 | Labour | hr | L | 3 | 33.33 | 24 | 42 | 90.7291 | 2.1602 | 0.080008 | 90.7291 | 0 | 0 | 0 | 90.7291 | 62
47 | Line No 59 Item No C213(e) | Excavation in Roak (Unrippable) | cum |  |  |  | 5 |  | 425 |  | 0 | 0 | 0 | 425 | 0 | 425
| 1 | Rock Breaker | hr | P | 1 | 1 | 5 | 85 | 425 | 5 | 0.55556 | 0 | 0 | 425 | 0 | 425 | 53
48 | Line No 60 Item No | Minor Rural Accesses | ea |  |  |  | 36 |  | 13464 |  | 4 | 3024 | 0 | 10440 | 0 | 13464
| 1 | Grader | hr | P | 1 | 1 | 36 | 135 | 4860 | 36 | 4 | 0 | 0 | 4860 | 0 | 4860 | 61
| 2 | SD Roller - Wet (No Op) | hr | P | 1 | 1 | 36 | 55 | 1980 | 36 | 4 | 0 | 0 | 1980 | 0 | 1980 | 61
| 3 | Water Cart - Hire | hr | P | 1 | 1 | 36 | 100 | 3600 | 36 | 4 | 0 | 0 | 3600 | 0 | 3600 | 61
| 4 | Labour | hr | L | 2 | 1 | 36 | 42 | 3024 | 72 | 4 | 3024 | 0 | 0 | 0 | 3024 | 61
| Line No 62 Item No | STORMWATER DRAINAGE
49 | Line No 63 Item No C220(a) | Excavation for stromwater structures | cum |  |  |  | 300 |  | 7362 |  | 2 | 1512 | 0 | 5850 | 0 | 7362
49.1 | 1 | Excavator - 25T | hr | P | 1 | 20 | 360 | 135 | 2430 | 18 | 2 | 0 | 0 | 2430 | 0 | 2430 | 53
| 2 | Tipper | hr | P | 2 | 20 | 360 | 95 | 3420 | 36 | 2 | 0 | 0 | 3420 | 0 | 3420 | 53
| 3 | Labour | hr | L | 2 | 20 | 360 | 42 | 1512 | 36 | 2 | 1512 | 0 | 0 | 0 | 1512 | 53
50 | Line No 64 Item No | Removal / Demolition of Drainage Components | LS |  |  |  | 1 |  | 2100 |  | 6 | 2100 | 0 | 0 | 0 | 2100
| 1 | Labour | hr | L | 1 | 1 | 50 | 42 | 2100 | 50 | 5.5556 | 2100 | 0 | 0 | 0 | 2100 | 41
51 | Line No 65 Item No C221(a) | 375 RCP | m |  |  |  | 58 |  | 20796.5039 |  | 7 | 7534.0206 | 4981.04 | 8281.4433 | 0 | 20796.5039
| 1 | 375 RCP | m | M | 1 | 1 | 58 | 68.6 | 3978.8 | 58 |  | 0 | 3978.8 | 0 | 0 | 3978.8 | SWP
| 2 | Sand | tonne | M | 1 | 1 | 41.76 | 24 | 1002.24 | 41.76 |  | 0 | 1002.24 | 0 | 0 | 1002.24 | QMS
| 3 | 10 Individual culverts each will take 6 hours to install, backfill & complete.
51.1 | 4 | Excavator - 25T | hr | P | 1 | 0.97 | 58 | 135 | 8072.1649 | 59.7938 | 6.6438 | 0 | 0 | 8072.1649 | 0 | 8072.1649 | 81
| 5 | Labour | hr | L | 3 | 0.97 | 58 | 42 | 7534.0206 | 179.3814 | 6.6438 | 7534.0206 | 0 | 0 | 0 | 7534.0206 | 81
| 6 | Plate Compactor | hr | P | 1 | 0.97 | 58 | 3.5 | 209.2784 | 59.7938 | 6.6438 | 0 | 0 | 209.2784 | 0 | 209.2784 | 81
52 | Line No 66 Item No C221(a) | 450 RCP | m |  |  |  | 44 |  | 17462.72 |  | 6 | 6026.087 | 4812.72 | 6623.913 | 0 | 17462.72
| 1 | 450 RCP FJ CL2 | m | M | 1 | 1 | 44 | 92.1 | 4052.4 | 44 |  | 0 | 4052.4 | 0 | 0 | 4052.4 | SWP
| 2 | Sand | tonne | M | 1 | 1 | 31.68 | 24 | 760.32 | 31.68 |  | 0 | 760.32 | 0 | 0 | 760.32 | QMS
| 3 | 8 Individual culverts each will take 6 hours to install, backfill & complete.
52.2 | 4 | Excavator - 25T | hr | P | 1 | 0.92 | 44 | 135 | 6456.5217 | 47.8261 | 5.314 | 0 | 0 | 6456.5217 | 0 | 6456.5217 | 81
| 5 | Labour | hr | L | 3 | 0.92 | 44 | 42 | 6026.087 | 143.4783 | 5.314 | 6026.087 | 0 | 0 | 0 | 6026.087 | 81
| 6 | Plate Compactor | hr | P | 1 | 0.92 | 44 | 3.5 | 167.3913 | 47.8261 | 5.314 | 0 | 0 | 167.3913 | 0 | 167.3913 | 81
53 | Line No 67 Item No C222(a) | Insitu RCBC Base Slab | cum |  |  |  | 57 |  | 28611.0196 |  |  | 0 | 19339.2196 | 0 | 9271.8 | 28611.0196
54 | 1 | Culvert 4S - 1200 x 450 (4.8m) | [6 empty] | 666.5351 |  | 2 | 0 | 450.5351 | 0 | 216 | 666.5351
54.1 | 2 | Area | m² |  |  |  | 8
| 3 | Sand | tonne | M | 1 | 1 | 0.8 | 24 | 19.2 | 0.8 |  | 0 | 19.2 | 0 | 0 | 19.2 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 9.6 | 9.1 | 87.36 | 9.6 |  | 0 | 87.36 | 0 | 0 | 87.36 | RSM
| 5 | Bar Chairs | each | M | 1 | 1 | 8.8889 | 0.8 | 7.1111 | 8.8889 |  | 0 | 7.1111 | 0 | 0 | 7.1111 | RSM
| 6 | N32 | m³ | M | 1 | 1 | 1.936 | 174 | 336.864 | 1.936 |  | 0 | 336.864 | 0 | 0 | 336.864 | C32
| 7 | Concrete Subbie | m² | S | 1 | 1 | 8 | 27 | 216 | 8 | 0.88889 | 0 | 0 | 0 | 216 | 216 | 182
8
55 | 9 | Culvert 4AB - 1200 x 450 (4.8m) | [6 empty] | 666.5351 |  | 2 | 0 | 450.5351 | 0 | 216 | 666.5351
55.1 | 10 | Area | m² |  |  |  | 8
| 11 | Sand | tonne | M | 1 | 1 | 0.8 | 24 | 19.2 | 0.8 |  | 0 | 19.2 | 0 | 0 | 19.2 | QMS
| 12 | SL72 | m² | M | 1 | 1 | 9.6 | 9.1 | 87.36 | 9.6 |  | 0 | 87.36 | 0 | 0 | 87.36 | RSM
| 13 | Bar Chairs | each | M | 1 | 1 | 8.8889 | 0.8 | 7.1111 | 8.8889 |  | 0 | 7.1111 | 0 | 0 | 7.1111 | RSM
| 14 | N32 | m³ | M | 1 | 1 | 1.936 | 174 | 336.864 | 1.936 |  | 0 | 336.864 | 0 | 0 | 336.864 | C32
| 15 | Concrete Subbie | m² | S | 1 | 1 | 8 | 27 | 216 | 8 | 0.88889 | 0 | 0 | 0 | 216 | 216 | 182
16
56 | 17 | Culvert 5E - 2/1200 x 450 (6m) | [6 empty] | 1499.704 |  | 3 | 0 | 1013.704 | 0 | 486 | 1499.704
56.1 | 18 | Area | m² |  |  |  | 18
| 19 | Sand | tonne | M | 1 | 1 | 1.8 | 24 | 43.2 | 1.8 |  | 0 | 43.2 | 0 | 0 | 43.2 | QMS
| 20 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 | 21.6 |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 21 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 | 20 |  | 0 | 16 | 0 | 0 | 16 | RSM
| 22 | N32 | m³ | M | 1 | 1 | 4.356 | 174 | 757.944 | 4.356 |  | 0 | 757.944 | 0 | 0 | 757.944 | C32
| 23 | Concrete Subbie | m² | S | 1 | 1 | 18 | 27 | 486 | 18 | 2 | 0 | 0 | 0 | 486 | 486 | 182
24
57 | 25 | Culvert 6D - 3/1200 x 600 (6m) | [6 empty] | 2332.8729 |  | 3 | 0 | 1576.8729 | 0 | 756 | 2332.8729
57.1 | 26 | Area | m² |  |  |  | 28
| 27 | Sand | tonne | M | 1 | 1 | 2.8 | 24 | 67.2 | 2.8 |  | 0 | 67.2 | 0 | 0 | 67.2 | QMS
| 28 | SL72 | m² | M | 1 | 1 | 33.6 | 9.1 | 305.76 | 33.6 |  | 0 | 305.76 | 0 | 0 | 305.76 | RSM
| 29 | Bar Chairs | each | M | 1 | 1 | 31.1111 | 0.8 | 24.8889 | 31.1111 |  | 0 | 24.8889 | 0 | 0 | 24.8889 | RSM
| 30 | N32 | m³ | M | 1 | 1 | 6.776 | 174 | 1179.024 | 6.776 |  | 0 | 1179.024 | 0 | 0 | 1179.024 | C32
| 31 | Concrete Subbie | m² | S | 1 | 1 | 28 | 27 | 756 | 28 | 1.037 | 0 | 0 | 0 | 756 | 756 | 182
32
58 | 33 | Culvert 6F - 2/1200 x 600 (6m) | [6 empty] | 1499.704 |  | 3 | 0 | 1013.704 | 0 | 486 | 1499.704
58.1 | 34 | Area | m² |  |  |  | 18
| 35 | Sand | tonne | M | 1 | 1 | 1.8 | 24 | 43.2 | 1.8 |  | 0 | 43.2 | 0 | 0 | 43.2 | QMS
| 36 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 | 21.6 |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 37 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 | 20 |  | 0 | 16 | 0 | 0 | 16 | RSM
| 38 | N32 | m³ | M | 1 | 1 | 4.356 | 174 | 757.944 | 4.356 |  | 0 | 757.944 | 0 | 0 | 757.944 | C32
| 39 | Concrete Subbie | m² | S | 1 | 1 | 18 | 27 | 486 | 18 | 2 | 0 | 0 | 0 | 486 | 486 | 182
40
59 | 41 | Culvert 6K - 2/1200 x 450 (4.8m) | [6 empty] | 1499.704 |  | 2 | 0 | 1013.704 | 0 | 486 | 1499.704
59.1 | 42 | Area | m² |  |  |  | 18
| 43 | Sand | tonne | M | 1 | 1 | 1.8 | 24 | 43.2 | 1.8 |  | 0 | 43.2 | 0 | 0 | 43.2 | QMS
| 44 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 | 21.6 |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 45 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 | 20 |  | 0 | 16 | 0 | 0 | 16 | RSM
| 46 | N32 | m³ | M | 1 | 1 | 4.356 | 174 | 757.944 | 4.356 |  | 0 | 757.944 | 0 | 0 | 757.944 | C32
| 47 | Concrete Subbie | m² | S | 1 | 1 | 18 | 27 | 486 | 18 | 1 | 0 | 0 | 0 | 486 | 486 | 182
48
60 | 49 | Culvert 6M - 2/1200 x 450 (4.8m) | [6 empty] | 1499.704 |  | 3 | 0 | 1013.704 | 0 | 486 | 1499.704
60.1 | 50 | Area | m² |  |  |  | 18
| 51 | Sand | tonne | M | 1 | 1 | 1.8 | 24 | 43.2 | 1.8 |  | 0 | 43.2 | 0 | 0 | 43.2 | QMS
| 52 | SL72 | m² | M | 1 | 1 | 21.6 | 9.1 | 196.56 | 21.6 |  | 0 | 196.56 | 0 | 0 | 196.56 | RSM
| 53 | Bar Chairs | each | M | 1 | 1 | 20 | 0.8 | 16 | 20 |  | 0 | 16 | 0 | 0 | 16 | RSM
| 54 | N32 | m³ | M | 1 | 1 | 4.356 | 174 | 757.944 | 4.356 |  | 0 | 757.944 | 0 | 0 | 757.944 | C32
| 55 | Concrete Subbie | m² | S | 1 | 1 | 18 | 27 | 486 | 18 | 2 | 0 | 0 | 0 | 486 | 486 | 182
56
61 | 57 | Culvert 6P - 1200 x 450 (4.8m) | [6 empty] | 666.5351 |  | 2 | 0 | 450.5351 | 0 | 216 | 666.5351
61.1 | 58 | Area | m² |  |  |  | 8
| 59 | Sand | tonne | M | 1 | 1 | 0.8 | 24 | 19.2 | 0.8 |  | 0 | 19.2 | 0 | 0 | 19.2 | QMS
| 60 | SL72 | m² | M | 1 | 1 | 9.6 | 9.1 | 87.36 | 9.6 |  | 0 | 87.36 | 0 | 0 | 87.36 | RSM
| 61 | Bar Chairs | each | M | 1 | 1 | 8.8889 | 0.8 | 7.1111 | 8.8889 |  | 0 | 7.1111 | 0 | 0 | 7.1111 | RSM
| 62 | N32 | m³ | M | 1 | 1 | 1.936 | 174 | 336.864 | 1.936 |  | 0 | 336.864 | 0 | 0 | 336.864 | C32
| 63 | Concrete Subbie | m² | S | 1 | 1 | 8 | 27 | 216 | 8 | 0.88889 | 0 | 0 | 0 | 216 | 216 | 182
64
62 | 65 | Culvert 6T - 1200 x 450 (6m) | [6 empty] | 916.4858 |  | 3 | 0 | 619.4858 | 0 | 297 | 916.4858
62.1 | 66 | Area | m² |  |  |  | 11
| 67 | Sand | tonne | M | 1 | 1 | 1.1 | 24 | 26.4 | 1.1 |  | 0 | 26.4 | 0 | 0 | 26.4 | QMS
| 68 | SL72 | m² | M | 1 | 1 | 13.2 | 9.1 | 120.12 | 13.2 |  | 0 | 120.12 | 0 | 0 | 120.12 | RSM
| 69 | Bar Chairs | each | M | 1 | 1 | 12.2222 | 0.8 | 9.7778 | 12.2222 |  | 0 | 9.7778 | 0 | 0 | 9.7778 | RSM
| 70 | N32 | m³ | M | 1 | 1 | 2.662 | 174 | 463.188 | 2.662 |  | 0 | 463.188 | 0 | 0 | 463.188 | C32
| 71 | Concrete Subbie | m² | S | 1 | 1 | 11 | 27 | 297 | 11 | 1.2222 | 0 | 0 | 0 | 297 | 297 | 182
72
63 | 73 | Culvert 4U 2/1200 x 600 (10.8m) Under Road | [6 empty] | 2949.4179 |  | 3 | 0 | 1993.6179 | 0 | 955.8 | 2949.4179
63.1 | 74 | Area | m² |  |  |  | 35.4
| 75 | Sand | tonne | M | 1 | 1 | 3.54 | 24 | 84.96 | 3.54 |  | 0 | 84.96 | 0 | 0 | 84.96 | QMS
| 76 | SL72 | m² | M | 1 | 1 | 42.48 | 9.1 | 386.568 | 42.48 |  | 0 | 386.568 | 0 | 0 | 386.568 | RSM
| 77 | Bar Chairs | each | M | 1 | 1 | 39.3333 | 0.8 | 31.4667 | 39.3333 |  | 0 | 31.4667 | 0 | 0 | 31.4667 | RSM
| 78 | N32 | m³ | M | 1 | 1 | 8.5668 | 174 | 1490.6232 | 8.5668 |  | 0 | 1490.6232 | 0 | 0 | 1490.6232 | C32
| 79 | Concrete Subbie | m² | S | 1 | 1 | 35.4 | 27 | 955.8 | 35.4 | 1.3111 | 0 | 0 | 0 | 955.8 | 955.8 | 182
80
64 | 81 | Culvert 4AA - 3/1200 x 450 (9.6m) Under Road | [6 empty] | 3682.6065 |  | 3 | 0 | 2489.2065 | 0 | 1193.4 | 3682.6065
64.1 | 82 | Area | m² |  |  |  | 44.2
| 83 | Sand | tonne | M | 1 | 1 | 4.42 | 24 | 106.08 | 4.42 |  | 0 | 106.08 | 0 | 0 | 106.08 | QMS
| 84 | SL72 | m² | M | 1 | 1 | 53.04 | 9.1 | 482.664 | 53.04 |  | 0 | 482.664 | 0 | 0 | 482.664 | RSM
| 85 | Bar Chairs | each | M | 1 | 1 | 49.1111 | 0.8 | 39.2889 | 49.1111 |  | 0 | 39.2889 | 0 | 0 | 39.2889 | RSM
| 86 | N32 | m³ | M | 1 | 1 | 10.6964 | 174 | 1861.1736 | 10.6964 |  | 0 | 1861.1736 | 0 | 0 | 1861.1736 | C32
| 87 | Concrete Subbie | m² | S | 1 | 1 | 44.2 | 27 | 1193.4 | 44.2 | 1.2278 | 0 | 0 | 0 | 1193.4 | 1193.4 | 182
88
65 | 89 | Culvert 5D - 2/1200 x 600 ((.6m) Under Road | [6 empty] | 2399.5264 |  | 5 | 0 | 1621.9264 | 0 | 777.6 | 2399.5264
65.1 | 90 | Area | m² |  |  |  | 28.8
| 91 | Sand | tonne | M | 1 | 1 | 2.88 | 24 | 69.12 | 2.88 |  | 0 | 69.12 | 0 | 0 | 69.12 | QMS
| 92 | SL72 | m² | M | 1 | 1 | 34.56 | 9.1 | 314.496 | 34.56 |  | 0 | 314.496 | 0 | 0 | 314.496 | RSM
| 93 | Bar Chairs | each | M | 1 | 1 | 32 | 0.8 | 25.6 | 32 |  | 0 | 25.6 | 0 | 0 | 25.6 | RSM
| 94 | N32 | m³ | M | 1 | 1 | 6.9696 | 174 | 1212.7104 | 6.9696 |  | 0 | 1212.7104 | 0 | 0 | 1212.7104 | C32
| 95 | Concrete Subbie | m² | S | 1 | 1 | 28.8 | 27 | 777.6 | 28.8 | 3.2 | 0 | 0 | 0 | 777.6 | 777.6 | 182
96
66 | 97 | Culvert 5M - 4/1200 x 600 (10.8m) Under Road | [6 empty] | 5748.8653 |  | 3 | 0 | 3885.8653 | 0 | 1863 | 5748.8653
66.1 | 98 | Area | m² |  |  |  | 69
| 99 | Sand | tonne | M | 1 | 1 | 6.9 | 24 | 165.6 | 6.9 |  | 0 | 165.6 | 0 | 0 | 165.6 | QMS
| 100 | SL72 | m² | M | 1 | 1 | 82.8 | 9.1 | 753.48 | 82.8 |  | 0 | 753.48 | 0 | 0 | 753.48 | RSM
| 101 | Bar Chairs | each | M | 1 | 1 | 76.6667 | 0.8 | 61.3333 | 76.6667 |  | 0 | 61.3333 | 0 | 0 | 61.3333 | RSM
| 102 | N32 | m³ | M | 1 | 1 | 16.698 | 174 | 2905.452 | 16.698 |  | 0 | 2905.452 | 0 | 0 | 2905.452 | C32
| 103 | Concrete Subbie | m² | S | 1 | 1 | 69 | 27 | 1863 | 69 | 1.5333 | 0 | 0 | 0 | 1863 | 1863 | 182
104
67 | 105 | Culvert 6B - 1200 x 450 (9.6m) Under Road | [6 empty] | 1291.4118 |  | 3 | 0 | 872.9118 | 0 | 418.5 | 1291.4118
67.1 | 106 | Area | m² |  |  |  | 15.5
| 107 | Sand | tonne | M | 1 | 1 | 1.55 | 24 | 37.2 | 1.55 |  | 0 | 37.2 | 0 | 0 | 37.2 | QMS
| 108 | SL72 | m² | M | 1 | 1 | 18.6 | 9.1 | 169.26 | 18.6 |  | 0 | 169.26 | 0 | 0 | 169.26 | RSM
| 109 | Bar Chairs | each | M | 1 | 1 | 17.2222 | 0.8 | 13.7778 | 17.2222 |  | 0 | 13.7778 | 0 | 0 | 13.7778 | RSM
| 110 | N32 | m³ | M | 1 | 1 | 3.751 | 174 | 652.674 | 3.751 |  | 0 | 652.674 | 0 | 0 | 652.674 | C32
| 111 | Concrete Subbie | m² | S | 1 | 1 | 15.5 | 27 | 418.5 | 15.5 | 1.7222 | 0 | 0 | 0 | 418.5 | 418.5 | 182
112
68 | 113 | Culvert 6V - 1200 x 450 (9.6m) Under Road | [6 empty] | 1291.4118 |  | 3 | 0 | 872.9118 | 0 | 418.5 | 1291.4118
68.1 | 114 | Area | m² |  |  |  | 15.5
| 115 | Sand | tonne | M | 1 | 1 | 1.55 | 24 | 37.2 | 1.55 |  | 0 | 37.2 | 0 | 0 | 37.2 | QMS
| 116 | SL72 | m² | M | 1 | 1 | 18.6 | 9.1 | 169.26 | 18.6 |  | 0 | 169.26 | 0 | 0 | 169.26 | RSM
| 117 | Bar Chairs | each | M | 1 | 1 | 17.2222 | 0.8 | 13.7778 | 17.2222 |  | 0 | 13.7778 | 0 | 0 | 13.7778 | RSM
| 118 | N32 | m³ | M | 1 | 1 | 3.751 | 174 | 652.674 | 3.751 |  | 0 | 652.674 | 0 | 0 | 652.674 | C32
| 119 | Concrete Subbie | m² | S | 1 | 1 | 15.5 | 27 | 418.5 | 15.5 | 1.7222 | 0 | 0 | 0 | 418.5 | 418.5 | 182
69 | Line No 68 Item No C222(b) | RCBC - 1200 x 450 | m |  |  |  | 100 |  | 71971.5 |  |  | 13419 | 40047.5 | 18505 | 0 | 71971.5
70 | 1 | Culvert 4S - 1200 x 450 (4.8m) | [6 empty] | 4074.5 |  | 1 | 882 | 1930 | 1262.5 | 0 | 4074.5
70.1 | 2 | Box Units to Stand | ea |  |  |  | 4
70.2 | 3 | Hand Placed Backfill | m3 |  |  |  | 15
| 4 | RCBC - 1200 x 450 | m | M | 1 | 1 | 4.8 | 387.5 | 1860 | 4.8 |  | 0 | 1860 | 0 | 0 | 1860 | SWC
70.3 | 5 | Excavator - 25T | hr | P | 1 | 2 | 4 | 135 | 270 | 2 | 0.22222 | 0 | 0 | 270 | 0 | 270 | 181
| 6 | Labour | hr | L | 3 | 2 | 4 | 42 | 252 | 6 | 0.22222 | 252 | 0 | 0 | 0 | 252 | 181
| 7 | Denso Tape | m | M | 1 | 1 | 14 | 5 | 70 | 14 |  | 0 | 70 | 0 | 0 | 70 | 181
70.4 | 8 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 0.55556 | 0 | 0 | 475 | 0 | 475 | 181
| 9 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 10 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 0.55556 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 11 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 0.55556 | 0 | 0 | 500 | 0 | 500 | 181
12
71 | 13 | Culvert 4AB - 1200 x 450 (4.8m) | [6 empty] | 4074.5 |  | 1 | 882 | 1930 | 1262.5 | 0 | 4074.5
71.1 | 14 | Box Units to Stand | ea |  |  |  | 4
71.2 | 15 | Hand Placed Backfill | m3 |  |  |  | 15
| 16 | RCBC - 1200 x 450 | m | M | 1 | 1 | 4.8 | 387.5 | 1860 | 4.8 |  | 0 | 1860 | 0 | 0 | 1860 | SWC
71.3 | 17 | Excavator - 25T | hr | P | 1 | 2 | 4 | 135 | 270 | 2 | 0.22222 | 0 | 0 | 270 | 0 | 270 | 181
| 18 | Labour | hr | L | 3 | 2 | 4 | 42 | 252 | 6 | 0.22222 | 252 | 0 | 0 | 0 | 252 | 181
| 19 | Denso Tape | m | M | 1 | 1 | 14 | 5 | 70 | 14 |  | 0 | 70 | 0 | 0 | 70 | 181
71.4 | 20 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 0.55556 | 0 | 0 | 475 | 0 | 475 | 181
| 21 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 22 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 0.55556 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 23 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 0.55556 | 0 | 0 | 500 | 0 | 500 | 181
24
72 | 25 | Culvert 5E - 2/1200 x 450 (6m) | [6 empty] | 8726 |  | 1 | 1638 | 4825 | 2263 | 0 | 8726
72.1 | 26 | Box Units to Stand | ea |  |  |  | 10
72.2 | 27 | Hand Placed Backfill | m3 |  |  |  | 24
| 28 | RCBC - 1200 x 450 | m | M | 1 | 1 | 12 | 387.5 | 4650 | 12 |  | 0 | 4650 | 0 | 0 | 4650 | SWC
72.3 | 29 | Excavator - 25T | hr | P | 1 | 2 | 10 | 135 | 675 | 5 | 0.55556 | 0 | 0 | 675 | 0 | 675 | 181
| 30 | Labour | hr | L | 3 | 2 | 10 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 31 | Denso Tape | m | M | 1 | 1 | 35 | 5 | 175 | 35 |  | 0 | 175 | 0 | 0 | 175 | 181
72.4 | 32 | Bobcat | hr | P | 1 | 3 | 24 | 95 | 760 | 8 | 0.88889 | 0 | 0 | 760 | 0 | 760 | 181
| 33 | Labour | hr | L | 3 | 3 | 24 | 42 | 1008 | 24 | 0.88889 | 1008 | 0 | 0 | 0 | 1008 | 181
| 34 | Plate Compactor | hr | P | 1 | 3 | 24 | 3.5 | 28 | 8 | 0.88889 | 0 | 0 | 28 | 0 | 28 | 181
| 35 | Water Cart - Hire | hr | P | 1 | 3 | 24 | 100 | 800 | 8 | 0.88889 | 0 | 0 | 800 | 0 | 800 | 181
36
73 | 37 | Culvert 6K - 2/1200 x 450 (4.8m) | [6 empty] | 6526.5 |  | 1 | 1134 | 3860 | 1532.5 | 0 | 6526.5
73.1 | 38 | Box Units to Stand | ea |  |  |  | 8
73.2 | 39 | Hand Placed Backfill | m3 |  |  |  | 15
| 40 | RCBC - 1200 x 450 | m | M | 1 | 1 | 9.6 | 387.5 | 3720 | 9.6 |  | 0 | 3720 | 0 | 0 | 3720 | SWC
73.3 | 41 | Excavator - 25T | hr | P | 1 | 2 | 8 | 135 | 540 | 4 | 0.44444 | 0 | 0 | 540 | 0 | 540 | 181
| 42 | Labour | hr | L | 3 | 2 | 8 | 42 | 504 | 12 | 0.44444 | 504 | 0 | 0 | 0 | 504 | 181
| 43 | Denso Tape | m | M | 1 | 1 | 28 | 5 | 140 | 28 |  | 0 | 140 | 0 | 0 | 140 | 181
73.4 | 44 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 0.55556 | 0 | 0 | 475 | 0 | 475 | 181
| 45 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 46 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 0.55556 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 47 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 0.55556 | 0 | 0 | 500 | 0 | 500 | 181
48
74 | 49 | Culvert 6M - 2/1200 x 450 (4.8m) | [6 empty] | 6526.5 |  | 1 | 1134 | 3860 | 1532.5 | 0 | 6526.5
74.1 | 50 | Box Units to Stand | ea |  |  |  | 8
74.2 | 51 | Hand Placed Backfill | m3 |  |  |  | 15
| 52 | RCBC - 1200 x 450 | m | M | 1 | 1 | 9.6 | 387.5 | 3720 | 9.6 |  | 0 | 3720 | 0 | 0 | 3720 | SWC
74.3 | 53 | Excavator - 25T | hr | P | 1 | 2 | 8 | 135 | 540 | 4 | 0.44444 | 0 | 0 | 540 | 0 | 540 | 181
| 54 | Labour | hr | L | 3 | 2 | 8 | 42 | 504 | 12 | 0.44444 | 504 | 0 | 0 | 0 | 504 | 181
| 55 | Denso Tape | m | M | 1 | 1 | 28 | 5 | 140 | 28 |  | 0 | 140 | 0 | 0 | 140 | 181
74.4 | 56 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 0.55556 | 0 | 0 | 475 | 0 | 475 | 181
| 57 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 58 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 0.55556 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 59 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 0.55556 | 0 | 0 | 500 | 0 | 500 | 181
60
75 | 61 | Culvert 6P - 1200 x 450 (4.8m) | [6 empty] | 4074.5 |  | 1 | 882 | 1930 | 1262.5 | 0 | 4074.5
75.1 | 62 | Box Units to Stand | ea |  |  |  | 4
75.2 | 63 | Hand Placed Backfill | m3 |  |  |  | 15
| 64 | RCBC - 1200 x 450 | m | M | 1 | 1 | 4.8 | 387.5 | 1860 | 4.8 |  | 0 | 1860 | 0 | 0 | 1860 | SWC
75.3 | 65 | Excavator - 25T | hr | P | 1 | 2 | 4 | 135 | 270 | 2 | 0.22222 | 0 | 0 | 270 | 0 | 270 | 181
| 66 | Labour | hr | L | 3 | 2 | 4 | 42 | 252 | 6 | 0.22222 | 252 | 0 | 0 | 0 | 252 | 181
| 67 | Denso Tape | m | M | 1 | 1 | 14 | 5 | 70 | 14 |  | 0 | 70 | 0 | 0 | 70 | 181
75.4 | 68 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 0.55556 | 0 | 0 | 475 | 0 | 475 | 181
| 69 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 70 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 0.55556 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 71 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 0.55556 | 0 | 0 | 500 | 0 | 500 | 181
72
76 | 73 | Culvert 6T - 1200 x 450 (6m) | [6 empty] | 5012 |  | 1 | 1071 | 2412.5 | 1528.5 | 0 | 5012
76.1 | 74 | Box Units to Stand | ea |  |  |  | 5
76.2 | 75 | Hand Placed Backfill | m3 |  |  |  | 18
| 76 | RCBC - 1200 x 450 | m | M | 1 | 1 | 6 | 387.5 | 2325 | 6 |  | 0 | 2325 | 0 | 0 | 2325 | SWC
76.3 | 77 | Excavator - 25T | hr | P | 1 | 2 | 5 | 135 | 337.5 | 2.5 | 0.27778 | 0 | 0 | 337.5 | 0 | 337.5 | 181
| 78 | Labour | hr | L | 3 | 2 | 5 | 42 | 315 | 7.5 | 0.27778 | 315 | 0 | 0 | 0 | 315 | 181
| 79 | Denso Tape | m | M | 1 | 1 | 17.5 | 5 | 87.5 | 17.5 |  | 0 | 87.5 | 0 | 0 | 87.5 | 181
76.4 | 80 | Bobcat | hr | P | 1 | 3 | 18 | 95 | 570 | 6 | 0.66667 | 0 | 0 | 570 | 0 | 570 | 181
| 81 | Labour | hr | L | 3 | 3 | 18 | 42 | 756 | 18 | 0.66667 | 756 | 0 | 0 | 0 | 756 | 181
| 82 | Plate Compactor | hr | P | 1 | 3 | 18 | 3.5 | 21 | 6 | 0.66667 | 0 | 0 | 21 | 0 | 21 | 181
| 83 | Water Cart - Hire | hr | P | 1 | 3 | 18 | 100 | 600 | 6 | 0.66667 | 0 | 0 | 600 | 0 | 600 | 181
84
77 | 85 | Culvert 4AA - 3/1200 x 450 (9.6m) Under Road | [6 empty] | 17957 |  | 2 | 2772 | 11580 | 3605 | 0 | 17957
77.1 | 86 | Box Units to Stand | ea |  |  |  | 24
77.2 | 87 | Hand Placed Backfill | m3 |  |  |  | 30
| 88 | RCBC - 1200 x 450 | m | M | 1 | 1 | 28.8 | 387.5 | 11160 | 28.8 |  | 0 | 11160 | 0 | 0 | 11160 | SWC
77.3 | 89 | Excavator - 25T | hr | P | 1 | 2 | 24 | 135 | 1620 | 12 | 1.3333 | 0 | 0 | 1620 | 0 | 1620 | 181
| 90 | Labour | hr | L | 3 | 2 | 24 | 42 | 1512 | 36 | 1.3333 | 1512 | 0 | 0 | 0 | 1512 | 181
| 91 | Denso Tape | m | M | 1 | 1 | 84 | 5 | 420 | 84 |  | 0 | 420 | 0 | 0 | 420 | 181
77.4 | 92 | Bobcat | hr | P | 1 | 3 | 30 | 95 | 950 | 10 | 1.1111 | 0 | 0 | 950 | 0 | 950 | 181
| 93 | Labour | hr | L | 3 | 3 | 30 | 42 | 1260 | 30 | 1.1111 | 1260 | 0 | 0 | 0 | 1260 | 181
| 94 | Plate Compactor | hr | P | 1 | 3 | 30 | 3.5 | 35 | 10 | 1.1111 | 0 | 0 | 35 | 0 | 35 | 181
| 95 | Water Cart - Hire | hr | P | 1 | 3 | 30 | 100 | 1000 | 10 | 1.1111 | 0 | 0 | 1000 | 0 | 1000 | 181
96
78 | 97 | Culvert 6B - 1200 x 450 (9.6m) Under Road | [6 empty] | 7500 |  | 1 | 1512 | 3860 | 2128 | 0 | 7500
78.1 | 98 | Box Units to Stand | ea |  |  |  | 8
78.2 | 99 | Hand Placed Backfill | m3 |  |  |  | 24
| 100 | RCBC - 1200 x 450 | m | M | 1 | 1 | 9.6 | 387.5 | 3720 | 9.6 |  | 0 | 3720 | 0 | 0 | 3720 | SWC
78.3 | 101 | Excavator - 25T | hr | P | 1 | 2 | 8 | 135 | 540 | 4 | 0.44444 | 0 | 0 | 540 | 0 | 540 | 181
| 102 | Labour | hr | L | 3 | 2 | 8 | 42 | 504 | 12 | 0.44444 | 504 | 0 | 0 | 0 | 504 | 181
| 103 | Denso Tape | m | M | 1 | 1 | 28 | 5 | 140 | 28 |  | 0 | 140 | 0 | 0 | 140 | 181
78.4 | 104 | Bobcat | hr | P | 1 | 3 | 24 | 95 | 760 | 8 | 0.88889 | 0 | 0 | 760 | 0 | 760 | 181
| 105 | Labour | hr | L | 3 | 3 | 24 | 42 | 1008 | 24 | 0.88889 | 1008 | 0 | 0 | 0 | 1008 | 181
| 106 | Plate Compactor | hr | P | 1 | 3 | 24 | 3.5 | 28 | 8 | 0.88889 | 0 | 0 | 28 | 0 | 28 | 181
| 107 | Water Cart - Hire | hr | P | 1 | 3 | 24 | 100 | 800 | 8 | 0.88889 | 0 | 0 | 800 | 0 | 800 | 181
108
79 | 109 | Culvert 6V - 1200 x 450 (9.6m) Under Road | [6 empty] | 7500 |  | 1 | 1512 | 3860 | 2128 | 0 | 7500
79.1 | 110 | Box Units to Stand | ea |  |  |  | 8
79.2 | 111 | Hand Placed Backfill | m3 |  |  |  | 24
| 112 | RCBC - 1200 x 450 | m | M | 1 | 1 | 9.6 | 387.5 | 3720 | 9.6 |  | 0 | 3720 | 0 | 0 | 3720 | SWC
79.3 | 113 | Excavator - 25T | hr | P | 1 | 2 | 8 | 135 | 540 | 4 | 0.44444 | 0 | 0 | 540 | 0 | 540 | 181
| 114 | Labour | hr | L | 3 | 2 | 8 | 42 | 504 | 12 | 0.44444 | 504 | 0 | 0 | 0 | 504 | 181
| 115 | Denso Tape | m | M | 1 | 1 | 28 | 5 | 140 | 28 |  | 0 | 140 | 0 | 0 | 140 | 181
79.4 | 116 | Bobcat | hr | P | 1 | 3 | 24 | 95 | 760 | 8 | 0.88889 | 0 | 0 | 760 | 0 | 760 | 181
| 117 | Labour | hr | L | 3 | 3 | 24 | 42 | 1008 | 24 | 0.88889 | 1008 | 0 | 0 | 0 | 1008 | 181
| 118 | Plate Compactor | hr | P | 1 | 3 | 24 | 3.5 | 28 | 8 | 0.88889 | 0 | 0 | 28 | 0 | 28 | 181
| 119 | Water Cart - Hire | hr | P | 1 | 3 | 24 | 100 | 800 | 8 | 0.88889 | 0 | 0 | 800 | 0 | 800 | 181
80 | Line No 69 Item No C222(b) | RCBC - 1200 x 600 | m |  |  |  | 114 |  | 80010.8333 |  |  | 11613 | 53500 | 14897.8333 | 0 | 80010.8333
81 | 1 | Culvert 6D - 3/1200 x 600 (6m) | [6 empty] | 11404.5 |  | 1 | 1701 | 7500 | 2203.5 | 0 | 11404.5
81.1 | 2 | Box Units to Stand | ea |  |  |  | 15
81.2 | 3 | Hand Placed Backfill | m3 |  |  |  | 18
| 4 | RCBC - 1200 x 600 | m | M | 1 | 1 | 18 | 400 | 7200 | 18 |  | 0 | 7200 | 0 | 0 | 7200 | SWC
81.3 | 5 | Excavator - 25T | hr | P | 1 | 2 | 15 | 135 | 1012.5 | 7.5 | 0.83333 | 0 | 0 | 1012.5 | 0 | 1012.5 | 181
| 6 | Labour | hr | L | 3 | 2 | 15 | 42 | 945 | 22.5 | 0.83333 | 945 | 0 | 0 | 0 | 945 | 181
| 7 | Denso Tape | m | M | 1 | 1 | 60 | 5 | 300 | 60 |  | 0 | 300 | 0 | 0 | 300 | 181
81.4 | 8 | Bobcat | hr | P | 1 | 3 | 18 | 95 | 570 | 6 | 0.66667 | 0 | 0 | 570 | 0 | 570 | 181
| 9 | Labour | hr | L | 3 | 3 | 18 | 42 | 756 | 18 | 0.66667 | 756 | 0 | 0 | 0 | 756 | 181
| 10 | Plate Compactor | hr | P | 1 | 3 | 18 | 3.5 | 21 | 6 | 0.66667 | 0 | 0 | 21 | 0 | 21 | 181
| 11 | Water Cart - Hire | hr | P | 1 | 3 | 18 | 100 | 600 | 6 | 0.66667 | 0 | 0 | 600 | 0 | 600 | 181
14
82 | 15 | Culvert 6F - 2/1200 x 600 (6m) | [6 empty] | 8252 |  | 1 | 1386 | 5000 | 1866 | 0 | 8252
82.1 | 16 | Box Units to Stand | ea |  |  |  | 10
82.2 | 17 | Hand Placed Backfill | m3 |  |  |  | 18
| 18 | RCBC - 1200 x 600 | m | M | 1 | 1 | 12 | 400 | 4800 | 12 |  | 0 | 4800 | 0 | 0 | 4800 | SWC
82.3 | 19 | Excavator - 25T | hr | P | 1 | 2 | 10 | 135 | 675 | 5 | 0.55556 | 0 | 0 | 675 | 0 | 675 | 181
| 20 | Labour | hr | L | 3 | 2 | 10 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 21 | Denso Tape | m | M | 1 | 1 | 40 | 5 | 200 | 40 |  | 0 | 200 | 0 | 0 | 200 | 181
82.4 | 22 | Bobcat | hr | P | 1 | 3 | 18 | 95 | 570 | 6 | 0.66667 | 0 | 0 | 570 | 0 | 570 | 181
| 23 | Labour | hr | L | 3 | 3 | 18 | 42 | 756 | 18 | 0.66667 | 756 | 0 | 0 | 0 | 756 | 181
| 24 | Plate Compactor | hr | P | 1 | 3 | 18 | 3.5 | 21 | 6 | 0.66667 | 0 | 0 | 21 | 0 | 21 | 181
| 25 | Water Cart - Hire | hr | P | 1 | 3 | 18 | 100 | 600 | 6 | 0.66667 | 0 | 0 | 600 | 0 | 600 | 181
28
83 | 29 | Culvert 4U 2/1200 x 600 (10.8m) Under Road | [6 empty] | 26159.3333 |  | 2 | 3612 | 18000 | 4547.3333 | 0 | 26159.3333
83.1 | 30 | Box Units to Stand | ea |  |  |  | 36
83.2 | 31 | Hand Placed Backfill | m3 |  |  |  | 32
| 32 | RCBC - 1200 x 600 | m | M | 1 | 1 | 43.2 | 400 | 17280 | 43.2 |  | 0 | 17280 | 0 | 0 | 17280 | SWC
83.3 | 33 | Excavator - 25T | hr | P | 1 | 2 | 36 | 135 | 2430 | 18 | 2 | 0 | 0 | 2430 | 0 | 2430 | 181
| 34 | Labour | hr | L | 3 | 2 | 36 | 42 | 2268 | 54 | 2 | 2268 | 0 | 0 | 0 | 2268 | 181
| 35 | Denso Tape | m | M | 1 | 1 | 144 | 5 | 720 | 144 |  | 0 | 720 | 0 | 0 | 720 | 181
83.4 | 36 | Bobcat | hr | P | 1 | 3 | 32 | 95 | 1013.3333 | 10.6667 | 1.1852 | 0 | 0 | 1013.3333 | 0 | 1013.3333 | 181
| 37 | Labour | hr | L | 3 | 3 | 32 | 42 | 1344 | 32 | 1.1852 | 1344 | 0 | 0 | 0 | 1344 | 181
| 38 | Plate Compactor | hr | P | 1 | 3 | 32 | 3.5 | 37.3333 | 10.6667 | 1.1852 | 0 | 0 | 37.3333 | 0 | 37.3333 | 181
| 39 | Water Cart - Hire | hr | P | 1 | 3 | 32 | 100 | 1066.6667 | 10.6667 | 1.1852 | 0 | 0 | 1066.6667 | 0 | 1066.6667 | 181
42
84 | 43 | Culvert 5D - 2/1200 x 600 ((.6m) Under Road | [6 empty] | 8252 |  | 1 | 1386 | 5000 | 1866 | 0 | 8252
84.1 | 44 | Box Units to Stand | ea |  |  |  | 10
84.2 | 45 | Hand Placed Backfill | m3 |  |  |  | 18
| 46 | RCBC - 1200 x 600 | m | M | 1 | 1 | 12 | 400 | 4800 | 12 |  | 0 | 4800 | 0 | 0 | 4800 | SWC
84.3 | 47 | Excavator - 25T | hr | P | 1 | 2 | 10 | 135 | 675 | 5 | 0.55556 | 0 | 0 | 675 | 0 | 675 | 181
| 48 | Labour | hr | L | 3 | 2 | 10 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 49 | Denso Tape | m | M | 1 | 1 | 40 | 5 | 200 | 40 |  | 0 | 200 | 0 | 0 | 200 | 181
84.4 | 50 | Bobcat | hr | P | 1 | 3 | 18 | 95 | 570 | 6 | 0.66667 | 0 | 0 | 570 | 0 | 570 | 181
| 51 | Labour | hr | L | 3 | 3 | 18 | 42 | 756 | 18 | 0.66667 | 756 | 0 | 0 | 0 | 756 | 181
| 52 | Plate Compactor | hr | P | 1 | 3 | 18 | 3.5 | 21 | 6 | 0.66667 | 0 | 0 | 21 | 0 | 21 | 181
| 53 | Water Cart - Hire | hr | P | 1 | 3 | 18 | 100 | 600 | 6 | 0.66667 | 0 | 0 | 600 | 0 | 600 | 181
56
85 | 57 | Culvert 5M - 4/1200 x 600 (10.8m) Under Road | [6 empty] | 25943 |  | 2 | 3528 | 18000 | 4415 | 0 | 25943
85.1 | 58 | Box Units to Stand | ea |  |  |  | 36
85.2 | 59 | Hand Placed Backfill | m3 |  |  |  | 30
| 60 | RCBC - 1200 x 600 | m | M | 1 | 1 | 43.2 | 400 | 17280 | 43.2 |  | 0 | 17280 | 0 | 0 | 17280 | SWC
85.3 | 61 | Excavator - 25T | hr | P | 1 | 2 | 36 | 135 | 2430 | 18 | 2 | 0 | 0 | 2430 | 0 | 2430 | 181
| 62 | Labour | hr | L | 3 | 2 | 36 | 42 | 2268 | 54 | 2 | 2268 | 0 | 0 | 0 | 2268 | 181
| 63 | Denso Tape | m | M | 1 | 1 | 144 | 5 | 720 | 144 |  | 0 | 720 | 0 | 0 | 720 | 181
85.4 | 64 | Bobcat | hr | P | 1 | 3 | 30 | 95 | 950 | 10 | 1.1111 | 0 | 0 | 950 | 0 | 950 | 181
| 65 | Labour | hr | L | 3 | 3 | 30 | 42 | 1260 | 30 | 1.1111 | 1260 | 0 | 0 | 0 | 1260 | 181
| 66 | Plate Compactor | hr | P | 1 | 3 | 30 | 3.5 | 35 | 10 | 1.1111 | 0 | 0 | 35 | 0 | 35 | 181
| 67 | Water Cart - Hire | hr | P | 1 | 3 | 30 | 100 | 1000 | 10 | 1.1111 | 0 | 0 | 1000 | 0 | 1000 | 181
86 | Line No 70 Item No C223(a) | Cast in situ headwalls | cum |  |  |  | 35 |  | 21000 |  | 4 | 0 | 0 | 0 | 21000 | 21000
| 1 | Concrete Sub-contract | m² | S | 1 | 1 | 35 | 600 | 21000 | 35 | 3.8889 | 0 | 0 | 0 | 21000 | 21000 | 72
87 | Line No 71 Item No C223(a) | 375 HW | ea |  |  |  | 1 |  | 621 |  | 1 | 126 | 360 | 135 | 0 | 621
| 1 | HW - 375 | each | M | 1 | 1 | 1 | 360 | 360 | 1 |  | 0 | 360 | 0 | 0 | 360 | SWH
87.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 1 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 81
| 3 | Labour | hr | L | 3 | 1 | 1 | 42 | 126 | 3 | 0.11111 | 126 | 0 | 0 | 0 | 126 | 81
88 | Line No 72 Item No C223(a) | 375 Sloping HW | ea |  |  |  | 18 |  | 15948 |  | 2 | 2268 | 11250 | 2430 | 0 | 15948
| 1 | HW - 375 Sloping | each | M | 1 | 1 | 18 | 625 | 11250 | 18 |  | 0 | 11250 | 0 | 0 | 11250 | SWH
88.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 18 | 135 | 2430 | 18 | 2 | 0 | 0 | 2430 | 0 | 2430 | 81
| 3 | Labour | hr | L | 3 | 1 | 18 | 42 | 2268 | 54 | 2 | 2268 | 0 | 0 | 0 | 2268 | 81
89 | Line No 73 Item No C223(a) | 450 Sloping HW | ea |  |  |  | 20 |  | 18120 |  | 3 | 2520 | 12900 | 2700 | 0 | 18120
| 1 | HW - 450 Sloping | each | M | 1 | 1 | 20 | 645 | 12900 | 20 |  | 0 | 12900 | 0 | 0 | 12900 | SWH
89.1 | 2 | Excavator - 25T | hr | P | 1 | 1 | 20 | 135 | 2700 | 20 | 2.2222 | 0 | 0 | 2700 | 0 | 2700 | 81
| 3 | Labour | hr | L | 3 | 1 | 20 | 42 | 2520 | 60 | 2.2222 | 2520 | 0 | 0 | 0 | 2520 | 81
90 | Line No 74 Item No C224(h) | B1 Kerb | m |  |  |  | 48 |  | 3994.1526 |  | 1 | 0 | 1054.1526 | 1500 | 1440 | 3994.1526
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 5.5814 | 181 | 1010.2326 | 5.5814 |  | 0 | 1010.2326 | 0 | 0 | 1010.2326 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 0.64 | 24 | 15.36 | 0.64 |  | 0 | 15.36 | 0 | 0 | 15.36 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.08 | 357 | 28.56 | 0.08 |  | 0 | 28.56 | 0 | 0 | 28.56 | 71
| 5 | Kerb Subbie (two) | m | S | 1 | 1 | 48 | 30 | 1440 | 48 | 0.24 | 0 | 0 | 0 | 1440 | 1440 | 71
| 6 | Float | LS | P | 1 | 1 | 1500 | 1 | 1500 | 1500 | 166.6667 | 0 | 0 | 1500 | 0 | 1500 | 71
91 | Line No 75 Item No C224(h) | SM5 Kerb | m |  |  |  | 62 |  | 4351.8967 |  | 1 | 0 | 991.8967 | 1500 | 1860 | 4351.8967
| 1 | Use Kerb Subbie. Allciv to supply sand & cement for slurry
| 2 | S32 - Kerb Mix | m³ | M | 1 | 1 | 5.1667 | 181 | 935.1667 | 5.1667 |  | 0 | 935.1667 | 0 | 0 | 935.1667 | CKM
| 3 | Sand | tonne | M | 1 | 1 | 0.82667 | 24 | 19.84 | 0.82667 |  | 0 | 19.84 | 0 | 0 | 19.84 | QMS
| 4 | Cement | tonne | M | 1 | 1 | 0.10333 | 357 | 36.89 | 0.10333 |  | 0 | 36.89 | 0 | 0 | 36.89 | 71
| 5 | Kerb Subbie (two) | m | S | 1 | 1 | 62 | 30 | 1860 | 62 | 0.31 | 0 | 0 | 0 | 1860 | 1860 | 71
| 6 | Float | LS | P | 1 | 1 | 1500 | 1 | 1500 | 1500 | 166.6667 | 0 | 0 | 1500 | 0 | 1500 | 71
92 | Line No 76 Item No C231(b) | Sub-soil | m |  |  |  | 1520 |  | 59161.7985 |  | 16 | 17238.5239 | 9977.28 | 31945.9946 | 0 | 59161.7985
| 1 | Excavate & install sub-soil drain at a rate of 100m per day. Use 300 trench and sand to backfill.
| 2 | Sub Soil Drain | m | M | 1 | 1 | 1520 | 2.5 | 3800 | 1520 |  | 0 | 3800 | 0 | 0 | 3800 | 87
| 3 | Sub Soil Flush Fittings | each | M | 1 | 1 | 30.4 | 25 | 760 | 30.4 |  | 0 | 760 | 0 | 0 | 760 | 87
| 4 | Sand | tonne | M | 1 | 1 | 225.72 | 24 | 5417.28 | 225.72 |  | 0 | 5417.28 | 0 | 0 | 5417.28 | QMS
92.1 | 5 | Excavator - 25T | hr | P | 1 | 11.11 | 1520 | 135 | 18469.847 | 136.8137 | 15.2015 | 0 | 0 | 18469.847 | 0 | 18469.847 | 87
| 6 | Labour | hr | L | 3 | 11.11 | 1520 | 42 | 17238.5239 | 410.441 | 15.2015 | 17238.5239 | 0 | 0 | 0 | 17238.5239 | 87
| 7 | Bobcat | hr | P | 1 | 11.11 | 1520 | 95 | 12997.2997 | 136.8137 | 15.2015 | 0 | 0 | 12997.2997 | 0 | 12997.2997 | 87
| 8 | Plate Compactor | hr | P | 1 | 11.11 | 1520 | 3.5 | 478.8479 | 136.8137 | 15.2015 | 0 | 0 | 478.8479 | 0 | 478.8479 | 87
93 | Line No 78 Item No | PAVEMENTS
94 | Line No 79 Item No C242 | Place only 2.3 | m3 |  |  |  | 1135 |  | 52163.0063 |  | 7 | 7723.3123 | 0 | 44439.694 | 0 | 52163.0063
| 1 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 2 | CBR45 - m3*Gravel Conversion Factor = tonnes to Haul & Place - Principal suplied material | tonne |  |  |  | 2724
95 | 3 | Grader | hr | P | 1 | 44.44 | 2724 | 135 | 8274.9775 | 61.2961 | 6.8107 | 0 | 0 | 8274.9775 | 0 | 8274.9775 | 62
| 4 | Truck & Dog | hr | P | 3 | 44.44 | 2724 | 145 | 26663.8164 | 183.8884 | 6.8107 | 0 | 0 | 26663.8164 | 0 | 26663.8164 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 44.44 | 2724 | 100 | 6129.613 | 61.2961 | 6.8107 | 0 | 0 | 6129.613 | 0 | 6129.613 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | 2724 | 55 | 3371.2871 | 61.2961 | 6.8107 | 0 | 0 | 3371.2871 | 0 | 3371.2871 | 62
| 7 | Labour | hr | L | 3 | 44.44 | 2724 | 42 | 7723.3123 | 183.8884 | 6.8107 | 7723.3123 | 0 | 0 | 0 | 7723.3123 | 62
96 | Line No 80 Item No C242 | Place Only 2.1 | m3 |  |  |  | 1490 |  | 63885.88 |  | 10 | 10930.3021 | 0 | 52955.5779 | 0 | 63885.88
| 1 | Haul, place, spread, compac680:691t & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 2 | CBR80 - m3*Gravel Conversion Factor = tonnes to Haul & Place - Principal suplied material |  |  |  |  | 3576
96.1 | 3 | Grader | hr | P | 1 | 66.67 | 3576 | 135 | 7241.0379 | 53.6373 | 5.9597 | 0 | 0 | 7241.0379 | 0 | 7241.0379 | 62
| 4 | Truck & Dog | hr | P | 4 | 66.67 | 3576 | 145 | 31109.6445 | 214.5493 | 5.9597 | 0 | 0 | 31109.6445 | 0 | 31109.6445 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 66.67 | 3576 | 100 | 5363.7318 | 53.6373 | 5.9597 | 0 | 0 | 5363.7318 | 0 | 5363.7318 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 3576 | 55 | 2950.0525 | 53.6373 | 5.9597 | 0 | 0 | 2950.0525 | 0 | 2950.0525 | 62
| 7 | Labour | hr | L | 3 | 66.67 | 3576 | 42 | 6758.3021 | 160.912 | 5.9597 | 6758.3021 | 0 | 0 | 0 | 6758.3021 | 62
8
| 9 | Final Trim
96.2 | 10 | Grader | hr | P | 1 | 300 | 9933.3333 | 135 | 4470 | 33.1111 | 3.679 | 0 | 0 | 4470 | 0 | 4470 | 63
| 11 | MW Roller | hr | P | 1 | 300 | 9933.3333 | 55 | 1821.1111 | 33.1111 | 3.679 | 0 | 0 | 1821.1111 | 0 | 1821.1111 | 63
| 12 | Labour | hr | L | 3 | 300 | 9933.3333 | 42 | 4172 | 99.3333 | 3.679 | 4172 | 0 | 0 | 0 | 4172 | 63
97 | Line No 81 Item No C244 | First Coat AMC5 | sqm |  |  |  | 9380 |  | 39396 |  | 1 | 0 | 0 | 0 | 39396 | 39396
| 1 | 7mm Primer Seal | m² | S | 1 | 1 | 9849 | 4 | 39396 | 9849 | 1094.3333 | 0 | 0 | 0 | 39396 | 39396 | 64
98 | Line No 82 Item No C244 | Second Coat | sqm |  |  |  | 9380 |  | 78595.02 |  | 1 | 0 | 0 | 0 | 78595.02 | 78595.02
| 1 | Seal Visit Two | m² | S | 1 | 1 | 9849 | 7.98 | 78595.02 | 9849 | 1094.3333 | 0 | 0 | 0 | 78595.02 | 78595.02 | 64
99 | Line No 83 Item No C261(a) | Pavement Markings - Longitudinal Lines | m |  |  |  | 3404 |  | 6808 |  | 1 | 0 | 0 | 0 | 6808 | 6808
| 1 | Line Marking | m² | S | 1 | 1 | 6808 | 1 | 6808 | 6808 |  | 0 | 0 | 0 | 6808 | 6808 | 66
100 | Line No 84 Item No C261(b) | Pavement Marking (Transverse etc) | LS |  |  |  | 1 |  | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000
| 1 | Line Marking | m² | S | 1 | 1 | 2000 | 1 | 2000 | 2000 |  | 0 | 0 | 0 | 2000 | 2000 | 66
101 | Line No 85 Item No C262(g) | Remove & reinstate exisiting signs & supports | LS |  |  |  | 1 |  | 840 |  | 2 | 840 | 0 | 0 | 0 | 840
| 1 | Labour | hr | L | 2 | 1 | 10 | 42 | 840 | 20 | 1.1111 | 840 | 0 | 0 | 0 | 840 | 67
102 | Line No 86 Item No C262 | Supply & Install all signs complete | ea |  |  |  | 26 |  | 5804.5 |  | 2 | 1092 | 4712.5 | 0 | 0 | 5804.5
| 1 | Signs Complete | each | M | 1 | 1 | 26 | 140 | 3640 | 26 |  | 0 | 3640 | 0 | 0 | 3640 | 67
102.1 | 2 | Labour | hr | L | 2 | 2 | 26 | 42 | 1092 | 26 | 1.4444 | 1092 | 0 | 0 | 0 | 1092 | 67
| 3 | N25 | m³ | M | 1 | 4 | 26 | 165 | 1072.5 | 26 |  | 0 | 1072.5 | 0 | 0 | 1072.5 | 67
103 | Line No 87 Item No C263(a) | Guide Posts | ea |  |  |  | 131 |  | 4585 |  | 3 | 0 | 4585 | 0 | 0 | 4585
| 1 | Guide Post | each | M | 1 | 1 | 131 | 35 | 4585 | 131 |  | 0 | 4585 | 0 | 0 | 4585 | 67
104 | Line No 89 Item No | MISCELLANEOUS
105 | Line No 90 Item No C273(a) | Grass seeding | sqm |  |  |  | 9200 |  | 24794 |  | 1 | 0 | 0 | 0 | 24794 | 24794
| 1 | Grass Seeding | m² | S | 1 | 1 | 10120 | 2.45 | 24794 | 10120 | 1.012 | 0 | 0 | 0 | 24794 | 24794 | 121
106 | Line No 91 Item No C306(a) | Sawcut Bitumen pavement | m |  |  |  | 53 |  | 1590 |  | 1 | 0 | 0 | 0 | 1590 | 1590
| 1 | Sawcut | m | S | 1 | 1 | 53 | 30 | 1590 | 53 | 0.23556 | 0 | 0 | 0 | 1590 | 1590 | 75
107 | Line No 92 Item No | Locate & Protect Services | LS |  |  |  | 1 |  | 2430 |  | 2 | 0 | 0 | 0 | 2430 | 2430
107.1 | 1 | Service Locator | hr | S | 1 | 1 | 18 | 135 | 2430 | 18 | 2 | 0 | 0 | 0 | 2430 | 2430 | 15
108 | Line No 93 Item No | As Constructed Plans | LS |  |  |  | 1 |  | 8325 |  | 5 | 8325 | 0 | 0 | 0 | 8325
108.1 | 1 | Surveyor | hr | L | 1 | 1 | 45 | 185 | 8325 | 45 | 5 | 8325 | 0 | 0 | 0 | 8325 | 11
VARIATIONS
109 | PV01 | Principal Supply of Precast Conrete Items | each |  |  |  | 1 |  | -116891.2 |  | 1 | 0 | -116891.2 | 0 | 0 | -116891.2
109.1 | 1 | 375 RCP | m | M | 1 | 1 | -58 | 68.6 | -3978.8 | -58 |  | 0 | -3978.8 | 0 | 0 | -3978.8 | SWP
109.2 | 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | -44 | 92.1 | -4052.4 | -44 |  | 0 | -4052.4 | 0 | 0 | -4052.4 | SWP
109.3 | 3 | RCBC - 1200 x 450 | m | M | 1 | 1 | -100 | 387.5 | -38750 | -100 |  | 0 | -38750 | 0 | 0 | -38750 | SWC
109.4 | 4 | RCBC - 1200 x 600 | m | M | 1 | 1 | -114 | 400 | -45600 | -114 |  | 0 | -45600 | 0 | 0 | -45600 | SWC
109.5 | 5 | HW - 375 | each | M | 1 | 1 | -1 | 360 | -360 | -1 |  | 0 | -360 | 0 | 0 | -360 | SWH
109.6 | 6 | HW - 375 Sloping | each | M | 1 | 1 | -18 | 625 | -11250 | -18 |  | 0 | -11250 | 0 | 0 | -11250 | SWH
109.7 | 7 | HW - 450 Sloping | each | M | 1 | 1 | -20 | 645 | -12900 | -20 |  | 0 | -12900 | 0 | 0 | -12900 | SWH
110 | PV02 | Additional 375RCP at chainage 230. | each |  |  |  | 1 |  | 991.3207 |  | 4 | 277.7575 | 84.3264 | 383.6947 | 245.5421 | 991.3207
110.1 |  | Install Only New RCP: | m |  |  |  | 4.88
| 2 | Sand | tonne | M | 1 | 1 | 3.5136 | 24 | 84.3264 | 3.5136 |  | 0 | 84.3264 | 0 | 0 | 84.3264 | QMS
110.2 | 4 | Excavator - 25T | hr | P | 1 | 0.97 | 1 | 135 | 139.1753 | 1.0309 | 0.11455 | 0 | 0 | 139.1753 | 0 | 139.1753 | 81
| 5 | Labour | hr | L | 3 | 0.97 | 1 | 42 | 129.8969 | 3.0928 | 0.11455 | 129.8969 | 0 | 0 | 0 | 129.8969 | 81
| 6 | Plate Compactor | hr | P | 1 | 0.97 | 1 | 3.5 | 3.6082 | 1.0309 | 0.11455 | 0 | 0 | 3.6082 | 0 | 3.6082 | 81
Install Only 375 Sloping Head Wall:
110.3 | 2 | Excavator - 25T | hr | P | 1 | 1 | 1 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 81
| 3 | Labour | hr | L | 3 | 1 | 1 | 42 | 126 | 3 | 0.11111 | 126 | 0 | 0 | 0 | 126 | 81
Place Only Type 2.1 Gravel:
110.4 | 1 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D. | m3 |  |  |  | 2.98
| 2 | CBR80 - m3*Gravel Conversion Factor = tonnes to Haul & Place - Principal suplied material | tonne |  |  |  | 7.152
110.5 | 3 | Grader | hr | P | 1 | 66.67 | 7.152 | 135 | 14.4821 | 0.10727 | 0.011919 | 0 | 0 | 14.4821 | 0 | 14.4821 | 62
| 4 | Truck & Dog | hr | P | 4 | 66.67 | 7.152 | 145 | 62.2193 | 0.4291 | 0.011919 | 0 | 0 | 62.2193 | 0 | 62.2193 | 62
| 5 | Water Cart - Hire | hr | P | 1 | 66.67 | 7.152 | 100 | 10.7275 | 0.10727 | 0.011919 | 0 | 0 | 10.7275 | 0 | 10.7275 | 62
| 6 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 7.152 | 55 | 5.9001 | 0.10727 | 0.011919 | 0 | 0 | 5.9001 | 0 | 5.9001 | 62
| 7 | Labour | hr | L | 3 | 66.67 | 7.152 | 42 | 13.5166 | 0.32182 | 0.011919 | 13.5166 | 0 | 0 | 0 | 13.5166 | 62
| 9 | Final Trim
110.6 | 10 | Grader | hr | P | 1 | 300 | 19.8667 | 135 | 8.94 | 0.066222 | 0.007358 | 0 | 0 | 8.94 | 0 | 8.94 | 63
| 11 | MW Roller | hr | P | 1 | 300 | 19.8667 | 55 | 3.6422 | 0.066222 | 0.007358 | 0 | 0 | 3.6422 | 0 | 3.6422 | 63
| 12 | Labour | hr | L | 3 | 300 | 19.8667 | 42 | 8.344 | 0.19867 | 0.007358 | 8.344 | 0 | 0 | 0 | 8.344 | 63
110.7 |  | Primer Seal: | m² |  |  |  | 19.52
| 1 | 7mm Primer Seal | m² | S | 1 | 1 | 20.496 | 4 | 81.984 | 20.496 | 0.010248 | 0 | 0 | 0 | 81.984 | 81.984 | 64
|  | Second Seal |  |  |  |  | 19.52
| 1 | Seal Visit Two | m² | S | 1 | 1 | 20.496 | 7.98 | 163.5581 | 20.496 | 0.010248 | 0 | 0 | 0 | 163.5581 | 163.5581 | 64
112 | PV04 | Revised Seal Design | m2 |  |  |  | 9380 |  | 10735.41 |  |  | 0 | 0 | 0 | 10735.41 | 10735.41
| 1 | Revised Seal Design | m² | S | 1 | 1 | 9849 | 1.09 | 10735.41 | 9849 |  | 0 | 0 | 0 | 10735.41 | 10735.41 | 64
113 | PV05 | Shape table drain chainage 523-725 | m3 |  |  |  | 251 | 2254.46 | 2072.8398 |  | 1 | 237.2187 | 0 | 1835.6211 | 0 | 2072.8398
113.1 | 1 | Excavator - 25T | hr | P | 1 | 44.44 | 251 | 135 | 762.4887 | 5.6481 | 0.62756 | 0 | 0 | 762.4887 | 0 | 762.4887 | 53
| 2 | Tipper | hr | P | 2 | 44.44 | 251 | 95 | 1073.1323 | 11.2961 | 0.62756 | 0 | 0 | 1073.1323 | 0 | 1073.1323 | 53
| 3 | Labour | hr | L | 1 | 44.44 | 251 | 42 | 237.2187 | 5.6481 | 0.62756 | 237.2187 | 0 | 0 | 0 | 237.2187 | 53
114 | PV06 | Nicol St - Revised pavement design | each |  |  |  | 1 |  | -36828.5961 |  | 0 | -5878.4408 | 154.224 | -31104.3793 | 0 | -36828.5961
114.1 | 1 | General Earthworks (Cut) | m3 |  |  |  | -524
114.2 | 2 | Excavator - 25T | hr | P | 1 | 43.54 | -524 | 135 | -1624.7129 | -12.0349 | -1.3372 | 0 | 0 | -1624.7129 | 0 | -1624.7129 | 53
| 3 | Tipper | hr | P | 3 | 43.54 | -524 | 95 | -3429.9495 | -36.1047 | -1.3372 | 0 | 0 | -3429.9495 | 0 | -3429.9495 | 53
| 4 | Labour | hr | L | 2 | 43.54 | -524 | 42 | -1010.9325 | -24.0698 | -1.3372 | -1010.9325 | 0 | 0 | 0 | -1010.9325 | 53
| 5 | Water Cart - Hire | hr | P | 1 | 43.54 | -524 | 100 | -1203.491 | -12.0349 | -1.3372 | 0 | 0 | -1203.491 | 0 | -1203.491 | 53
114.3 | 6 | Place Only 2.3 | m3 |  |  |  | -332
| 7 | Gravel to be hauled in tonnes = QTY * Gravel Conversion Factor | tonne |  |  |  | -796.8
114.4 | 8 | Grader | hr | P | 1 | 44.44 | -796.8 | 135 | -2420.5221 | -17.9298 | -1.9922 | 0 | 0 | -2420.5221 | 0 | -2420.5221 | 62
| 9 | Truck & Dog | hr | P | 3 | 44.44 | -796.8 | 145 | -7799.4599 | -53.7894 | -1.9922 | 0 | 0 | -7799.4599 | 0 | -7799.4599 | 62
| 10 | Water Cart - Hire | hr | P | 1 | 44.44 | -796.8 | 100 | -1792.9793 | -17.9298 | -1.9922 | 0 | 0 | -1792.9793 | 0 | -1792.9793 | 62
| 11 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | -796.8 | 55 | -986.1386 | -17.9298 | -1.9922 | 0 | 0 | -986.1386 | 0 | -986.1386 | 62
| 12 | Labour | hr | L | 3 | 44.44 | -796.8 | 42 | -2259.1539 | -53.7894 | -1.9922 | -2259.1539 | 0 | 0 | 0 | -2259.1539 | 62
114.5 | 13 | Place Only 2.1 | m3 |  |  |  | -282
| 14 | Gravel to be hauled in tonnes = QTY * Gravel Conversion Factor | tonne |  |  |  | -676.8
114.6 | 15 | Grader | hr | P | 1 | 44.44 | -676.8 | 135 | -2055.9856 | -15.2295 | -1.6922 | 0 | 0 | -2055.9856 | 0 | -2055.9856 | 62
| 16 | Truck & Dog | hr | P | 3 | 44.44 | -676.8 | 145 | -6624.8425 | -45.6886 | -1.6922 | 0 | 0 | -6624.8425 | 0 | -6624.8425 | 62
| 17 | Water Cart - Hire | hr | P | 1 | 44.44 | -676.8 | 100 | -1522.9523 | -15.2295 | -1.6922 | 0 | 0 | -1522.9523 | 0 | -1522.9523 | 62
| 18 | SD Roller - Wet (No Op) | hr | P | 1 | 44.44 | -676.8 | 55 | -837.6238 | -15.2295 | -1.6922 | 0 | 0 | -837.6238 | 0 | -837.6238 | 62
| 19 | Labour | hr | L | 3 | 44.44 | -676.8 | 42 | -1918.9199 | -45.6886 | -1.6922 | -1918.9199 | 0 | 0 | 0 | -1918.9199 | 62
| 20 | Final Trim (Layer thickness = 150mm) | m2
114.7 | 21 | Grader | hr | P | 1 | 300 | -1880 | 135 | -846 | -6.2667 | -0.6963 | 0 | 0 | -846 | 0 | -846 | 63
| 22 | MW Roller | hr | P | 1 | 300 | -1880 | 55 | -344.6667 | -6.2667 | -0.6963 | 0 | 0 | -344.6667 | 0 | -344.6667 | 63
| 23 | Labour | hr | L | 3 | 300 | -1880 | 42 | -789.6 | -18.8 | -0.6963 | -789.6 | 0 | 0 | 0 | -789.6 | 63
114.8 | 24 | Special Item - Take Up & Stabilise & Relay as Working Platform | m3 |  |  |  | 9
| 25 | Take Up the Gravel
| 26 | Excavator - 25T | hr | P | 1 | 40 | 9 | 135 | 30.375 | 0.225 | 0.025 | 0 | 0 | 30.375 | 0 | 30.375 | 53
| 27 | Tipper | hr | P | 2 | 40 | 9 | 95 | 42.75 | 0.45 | 0.025 | 0 | 0 | 42.75 | 0 | 42.75 | 53
| 28 | Labour | hr | L | 1 | 40 | 9 | 42 | 9.45 | 0.225 | 0.025 | 9.45 | 0 | 0 | 0 | 9.45 | 53
| 29 | Relay Gravel
| 30 | Excavator - 25T | hr | P | 1 | 27.778 | 9 | 135 | 43.7397 | 0.324 | 0.036 | 0 | 0 | 43.7397 | 0 | 43.7397 | 53
| 31 | Tipper | hr | P | 2 | 27.778 | 9 | 95 | 61.5595 | 0.64799 | 0.036 | 0 | 0 | 61.5595 | 0 | 61.5595 | 53
| 32 | Grader | hr | P | 1 | 27.778 | 9 | 135 | 43.7397 | 0.324 | 0.036 | 0 | 0 | 43.7397 | 0 | 43.7397 | 53
| 33 | SD Roller - Wet (No Op) | hr | P | 1 | 27.778 | 9 | 55 | 17.8199 | 0.324 | 0.036 | 0 | 0 | 17.8199 | 0 | 17.8199 | 53
| 34 | Stabilise (12kg / m2 spread rate)
114.9 | 35 | Cement | tonne | M | 1 | 0.012 | 0.432 | 357 | 154.224 | 0.432 |  | 0 | 154.224 | 0 | 0 | 154.224 | CSA
| 36 | Stabilising | m2 |  |  |  | 36
114.91 | 37 | CAT297 Stabiliser | hr | P | 1 | 66.67 | 36 | 66.07 | 35.676 | 0.53997 | 0.059997 | 0 | 0 | 35.676 | 0 | 35.676 | 68
| 38 | NH Grader | hr | P | 1 | 66.67 | 36 | 25.78 | 13.9205 | 0.53997 | 0.059997 | 0 | 0 | 13.9205 | 0 | 13.9205 | 68
| 39 | Water Cart - Hire | hr | P | 1 | 66.67 | 36 | 100 | 53.9973 | 0.53997 | 0.059997 | 0 | 0 | 53.9973 | 0 | 53.9973 | 68
| 40 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 36 | 55 | 29.6985 | 0.53997 | 0.059997 | 0 | 0 | 29.6985 | 0 | 29.6985 | 68
| 41 | UD Spreader | hr | P | 1 | 66.67 | 36 | 21.61 | 11.6688 | 0.53997 | 0.059997 | 0 | 0 | 11.6688 | 0 | 11.6688 | 68
| 42 | Labour | hr | L | 4 | 66.67 | 36 | 42 | 90.7155 | 2.1599 | 0.059997 | 90.7155 | 0 | 0 | 0 | 90.7155 | 68
115 | PV07 | Nicol St - Additional drain outlet | each |  |  |  | 50 |  | 3241.2213 |  | 2 | 1590 | 651.2213 | 1000 | 0 | 3241.2213
| 1 | DN150 uPVC SN8 | m | M | 1 | 1 | 50 | 9.09 | 454.5 | 50 |  | 0 | 454.5 | 0 | 0 | 454.5 | 81
| 2 | Sand | tonne | M | 1 | 1 | 8.1967 | 24 | 196.7213 | 8.1967 |  | 0 | 196.7213 | 0 | 0 | 196.7213 | QMS
115.1 | 3 | Excavator - 8T | hr | P | 1 | 5 | 50 | 100 | 1000 | 10 | 1.1111 | 0 | 0 | 1000 | 0 | 1000 | 81
| 4 | Labour | hr | L | 1 | 5 | 50 | 42 | 420 | 10 | 1.1111 | 420 | 0 | 0 | 0 | 420 | 81
| 5 | Foreman - Hourly | hr | L | 1 | 1 | 8 | 120 | 960 | 8 | 0.88889 | 960 | 0 | 0 | 0 | 960 | 902
| 6 | Engineer / CQR | hr | L | 1 | 1 | 2 | 105 | 210 | 2 | 0.22222 | 210 | 0 | 0 | 0 | 210 | 902
116 | PV08 | Nicol St - Subgrade pavement repairs | each |  |  |  | 1 |  | 10385.4605 |  | 2 | 1837.8834 | 4424.3904 | 4123.1867 | 0 | 10385.4605
116.1 | 24 | Special Item - Take Up & Stabilise & Relay as Working Platform | m3 |  |  |  | 96.4
| 25 | Take Up the Gravel
| 26 | Excavator - 25T | hr | P | 1 | 40 | 96.4 | 135 | 325.35 | 2.41 | 0.26778 | 0 | 0 | 325.35 | 0 | 325.35 | 53
| 27 | Tipper | hr | P | 2 | 40 | 96.4 | 95 | 457.9 | 4.82 | 0.26778 | 0 | 0 | 457.9 | 0 | 457.9 | 53
| 28 | Labour | hr | L | 1 | 40 | 96.4 | 42 | 101.22 | 2.41 | 0.26778 | 101.22 | 0 | 0 | 0 | 101.22 | 53
| 29 | Relay Gravel
| 30 | Excavator - 25T | hr | P | 1 | 27.778 | 96.4 | 135 | 468.5003 | 3.4704 | 0.3856 | 0 | 0 | 468.5003 | 0 | 468.5003 | 53
| 31 | Tipper | hr | P | 2 | 27.778 | 96.4 | 95 | 659.3707 | 6.9407 | 0.3856 | 0 | 0 | 659.3707 | 0 | 659.3707 | 53
| 32 | Grader | hr | P | 1 | 27.778 | 96.4 | 135 | 468.5003 | 3.4704 | 0.3856 | 0 | 0 | 468.5003 | 0 | 468.5003 | 53
| 33 | SD Roller - Wet (No Op) | hr | P | 1 | 27.778 | 96.4 | 55 | 190.8705 | 3.4704 | 0.3856 | 0 | 0 | 190.8705 | 0 | 190.8705 | 53
| 34 | Stabilise (12kg / m2 spread rate)
116.2 | 35 | Cement | tonne | M | 1 | 0.012 | 4.6272 | 357 | 1651.9104 | 4.6272 |  | 0 | 1651.9104 | 0 | 0 | 1651.9104 | CSA
| 36 | Stabilising |  |  |  |  | 385.6
116.3 | 37 | CAT297 Stabiliser | hr | P | 1 | 66.67 | 385.6 | 66.07 | 382.1298 | 5.7837 | 0.64263 | 0 | 0 | 382.1298 | 0 | 382.1298 | 68
| 38 | NH Grader | hr | P | 1 | 66.67 | 385.6 | 25.78 | 149.1041 | 5.7837 | 0.64263 | 0 | 0 | 149.1041 | 0 | 149.1041 | 68
| 39 | Water Cart - Hire | hr | P | 1 | 66.67 | 385.6 | 100 | 578.3711 | 5.7837 | 0.64263 | 0 | 0 | 578.3711 | 0 | 578.3711 | 68
| 40 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 385.6 | 55 | 318.1041 | 5.7837 | 0.64263 | 0 | 0 | 318.1041 | 0 | 318.1041 | 68
| 41 | UD Spreader | hr | P | 1 | 66.67 | 385.6 | 21.61 | 124.986 | 5.7837 | 0.64263 | 0 | 0 | 124.986 | 0 | 124.986 | 68
| 42 | Labour | hr | L | 4 | 66.67 | 385.6 | 42 | 971.6634 | 23.1348 | 0.64263 | 971.6634 | 0 | 0 | 0 | 971.6634 | 68
116.4 | 43 | Geotextiles: |  |  |  |  | 380
| 44 | TX160 - Geogrid | m2 | M | 1 | 1 | 456 | 5.03 | 2293.68 | 456 |  | 0 | 2293.68 | 0 | 0 | 2293.68 | 68
| 45 | A24 | m2 | M | 1 | 1 | 456 | 1.05 | 478.8 | 456 |  | 0 | 478.8 | 0 | 0 | 478.8 | 68
| 46 | Foreman - Hourly | hr | L | 1 | 1 | 2 | 120 | 240 | 2 | 0.22222 | 240 | 0 | 0 | 0 | 240 | 902
| 47 | Engineer / CQR | hr | L | 1 | 1 | 5 | 105 | 525 | 5 | 0.55556 | 525 | 0 | 0 | 0 | 525 | 902
117 | PV09 | Nicol St - Additional works to water services | each |  |  |  | 1 |  | 13500 |  | 1 | 0 | 0 | 0 | 13500 | 13500
| 1 | Water Subbie | item | S | 13500 | 1 | 1 | 1 | 13500 | 13500 | 0.11111 | 0 | 0 | 0 | 13500 | 13500 | 103
118 | PV10 | Wright Rd - Drainage works ch1300 | each |  |  |  | 1 |  | 5796 |  | 3 | 1122 | 0 | 3449 | 1225 | 5796
118.1 | 1 | Excavator - 25T | hr | P | 1 | 1 | 18 | 135 | 2430 | 18 | 2 | 0 | 0 | 2430 | 0 | 2430 | 53
| 2 | CAT297 | hr | P | 1 | 1 | 6 | 46.5 | 279 | 6 | 0.66667 | 0 | 0 | 279 | 0 | 279 | 53
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 1 | 4 | 55 | 220 | 4 | 0.44444 | 0 | 0 | 220 | 0 | 220 | 53
| 4 | Labour | hr | L | 1 | 1 | 4 | 42 | 168 | 4 | 0.44444 | 168 | 0 | 0 | 0 | 168 | 53
| 4 | Float | hr | P | 520 | 1 | 1 | 1 | 520 | 520 | 0.11111 | 0 | 0 | 520 | 0 | 520 | 53
| 5 | Engineer / CQR | hr | L | 1 | 1 | 6 | 105 | 630 | 6 | 0.66667 | 630 | 0 | 0 | 0 | 630 | 53
| 6 | Foreman - Hourly | hr | L | 1 | 1 | 2 | 120 | 240 | 2 | 0.22222 | 240 | 0 | 0 | 0 | 240 | 53
| 7 | Labour | hr | L | 1 | 1 | 2 | 42 | 84 | 2 | 0.22222 | 84 | 0 | 0 | 0 | 84 | 53
118.2 | 8 | Grass Seeding | hr | S | 1 | 1 | 500 | 2.45 | 1225 | 500 | 55.5556 | 0 | 0 | 0 | 1225 | 1225 | 53
119 | PV11 | Wright Rd - Additional culvert no.06 | each |  |  |  | 1 |  | 2127.1546 |  | 3 | 277.7575 | 1383.7184 | 383.6947 | 81.984 | 2127.1546
119.1 | 1 | Install Only New RCP: |  |  |  |  | 4.88
| 2 | 375 RCP | tonne | M | 1 | 1 | 0.72 | 68.6 | 49.392 | 0.72 |  | 0 | 49.392 | 0 | 0 | 49.392 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 3.5136 | 24 | 84.3264 | 3.5136 |  | 0 | 84.3264 | 0 | 0 | 84.3264 | QMS
119.2 | 4 | Excavator - 25T | hr | P | 1 | 0.97 | 1 | 135 | 139.1753 | 1.0309 | 0.11455 | 0 | 0 | 139.1753 | 0 | 139.1753 | 181
| 5 | Labour | hr | L | 3 | 0.97 | 1 | 42 | 129.8969 | 3.0928 | 0.11455 | 129.8969 | 0 | 0 | 0 | 129.8969 | 181
| 6 | Plate Compactor | hr | P | 1 | 0.97 | 1 | 3.5 | 3.6082 | 1.0309 | 0.11455 | 0 | 0 | 3.6082 | 0 | 3.6082 | 181
| 7 | Install Only 375 Sloping Head Wall:
| 2 | HW - 375 Sloping | tonne | M | 1 | 1 | 2 | 625 | 1250 | 2 |  | 0 | 1250 | 0 | 0 | 1250 | SWH
119.3 | 8 | Excavator - 25T | hr | P | 1 | 1 | 1 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 181
| 9 | Labour | hr | L | 3 | 1 | 1 | 42 | 126 | 3 | 0.11111 | 126 | 0 | 0 | 0 | 126 | 181
| 10 | Place Only Type 2.1 Gravel:
119.4 | 11 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D. | m3 |  |  |  | 2.98
| 12 | CBR80 - m3*Gravel Conversion Factor = tonnes to Haul & Place - Principal suplied material | tonne |  |  |  | 7.152
119.5 | 13 | Grader | hr | P | 1 | 66.67 | 7.152 | 135 | 14.4821 | 0.10727 | 0.011919 | 0 | 0 | 14.4821 | 0 | 14.4821 | 62
| 14 | Truck & Dog | hr | P | 4 | 66.67 | 7.152 | 145 | 62.2193 | 0.4291 | 0.011919 | 0 | 0 | 62.2193 | 0 | 62.2193 | 62
| 15 | Water Cart - Hire | hr | P | 1 | 66.67 | 7.152 | 100 | 10.7275 | 0.10727 | 0.011919 | 0 | 0 | 10.7275 | 0 | 10.7275 | 62
| 16 | SD Roller - Wet (No Op) | hr | P | 1 | 66.67 | 7.152 | 55 | 5.9001 | 0.10727 | 0.011919 | 0 | 0 | 5.9001 | 0 | 5.9001 | 62
| 17 | Labour | hr | L | 3 | 66.67 | 7.152 | 42 | 13.5166 | 0.32182 | 0.011919 | 13.5166 | 0 | 0 | 0 | 13.5166 | 62
| 18 | Final Trim | m²
119.6 | 19 | Grader | hr | P | 1 | 300 | 19.8667 | 135 | 8.94 | 0.066222 | 0.007358 | 0 | 0 | 8.94 | 0 | 8.94 | 63
| 20 | MW Roller | hr | P | 1 | 300 | 19.8667 | 55 | 3.6422 | 0.066222 | 0.007358 | 0 | 0 | 3.6422 | 0 | 3.6422 | 63
| 21 | Labour | hr | L | 3 | 300 | 19.8667 | 42 | 8.344 | 0.19867 | 0.007358 | 8.344 | 0 | 0 | 0 | 8.344 | 63
119.7 | 22 | Primer Seal: | m² |  |  |  | 19.52
| 23 | 7mm Primer Seal | m² | S | 1 | 1 | 20.496 | 4 | 81.984 | 20.496 | 2.2773 | 0 | 0 | 0 | 81.984 | 81.984 | 64
120 | PV12 | Wright Rd - Driveway works | each |  |  |  | 200 |  | 9750 |  | 4 | 0 | 4350 | 0 | 5400 | 9750
| 1 | Concrete Subbie | m² | S | 1 | 1 | 200 | 27 | 5400 | 200 |  | 0 | 0 | 0 | 5400 | 5400 | 71
| 2 | N32 | m3 | M | 1 | 1 | 25 | 174 | 4350 | 25 |  | 0 | 4350 | 0 | 0 | 4350 | C32
121 | PV13 | Nicol St - Kerb ramp reconstruction | each |  |  |  | 2 |  | 2270 |  | 2 | 0 | 870 | 0 | 1400 | 2270
| 22 | N32 | m3 | M | 1 | 1 | 5 | 174 | 870 | 5 |  | 0 | 870 | 0 | 0 | 870 | C32
| 23 | Pram Ramps | each | S | 1 | 1 | 2 | 700 | 1400 | 2 |  | 0 | 0 | 0 | 1400 | 1400 | 71
122 | PV14 | Nicol St - Removal of Unsuitable - Telstra Cable | each |  |  |  | 33.8 |  | 3117.6134 |  | 1 | 590.5843 | 0 | 2527.0292 | 0 | 3117.6134
122.1 | 1 | Excavator - 25T | hr | P | 1 | 10 | 33.8 | 135 | 456.3 | 3.38 | 0.37556 | 0 | 0 | 456.3 | 0 | 456.3 | 53
| 2 | Tipper | hr | P | 1 | 10 | 33.8 | 95 | 321.1 | 3.38 | 0.37556 | 0 | 0 | 321.1 | 0 | 321.1 | 53
| 3 | Labour | hr | L | 2 | 10 | 33.8 | 42 | 283.92 | 6.76 | 0.37556 | 283.92 | 0 | 0 | 0 | 283.92 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 10 | 33.8 | 100 | 338 | 3.38 | 0.37556 | 0 | 0 | 338 | 0 | 338 | 53
| 5 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D.
| 6 | Gravel to be hauled in tonnes = QTY*Gravel Conversion Factor | tonne |  |  |  | 81.12
122.2 | 7 | Grader | hr | P | 1 | 33.33 | 81.12 | 135 | 328.5689 | 2.4338 | 0.27043 | 0 | 0 | 328.5689 | 0 | 328.5689 | 62
| 8 | Truck & Dog | hr | P | 2 | 33.33 | 81.12 | 145 | 705.8146 | 4.8677 | 0.27043 | 0 | 0 | 705.8146 | 0 | 705.8146 | 62
| 9 | Water Cart - Hire | hr | P | 1 | 33.33 | 81.12 | 100 | 243.3843 | 2.4338 | 0.27043 | 0 | 0 | 243.3843 | 0 | 243.3843 | 62
| 10 | SD Roller - Wet (No Op) | hr | P | 1 | 33.33 | 81.12 | 55 | 133.8614 | 2.4338 | 0.27043 | 0 | 0 | 133.8614 | 0 | 133.8614 | 62
| 11 | Labour | hr | L | 3 | 33.33 | 81.12 | 42 | 306.6643 | 7.3015 | 0.27043 | 306.6643 | 0 | 0 | 0 | 306.6643 | 62
123 | PV15 | Wright Road - Scour & Batter Protection | each |  |  |  | 1
124 | PV15 a | Scour Protection | each |  |  |  | 18 |  | 8991.2997 |  | 6 | 34.0234 | 6264 | 263.2763 | 2430 | 8991.2997
124.1 | 1 | Excavator - 25T | hr | P | 1 | 22.22 | 18 | 135 | 109.3609 | 0.81008 | 2 | 0 | 0 | 109.3609 | 0 | 109.3609 | 53
| 2 | Tipper | hr | P | 2 | 22.22 | 18 | 95 | 153.9154 | 1.6202 | 2 | 0 | 0 | 153.9154 | 0 | 153.9154 | 53
| 3 | Labour | hr | L | 1 | 22.22 | 18 | 42 | 34.0234 | 0.81008 | 2 | 34.0234 | 0 | 0 | 0 | 34.0234 | 53
| 1 | Concrete Subbie | m² | S | 1 | 1 | 90 | 27 | 2430 | 90 | 3.3333 | 0 | 0 | 0 | 2430 | 2430 | 71
| 2 | N32 | m3 | M | 1 | 1 | 36 | 174 | 6264 | 36 |  | 0 | 6264 | 0 | 0 | 6264 | C32
125 | PV15 b | Drain Widening - Lot 130 | each |  |  |  | 200 |  | 3303.3303 |  | 1 | 378.0378 | 0 | 2925.2925 | 0 | 3303.3303
125.1 | 1 | Excavator - 25T | hr | P | 1 | 22.22 | 200 | 135 | 1215.1215 | 9.0009 | 1.0001 | 0 | 0 | 1215.1215 | 0 | 1215.1215 | 53
| 2 | Tipper | hr | P | 2 | 22.22 | 200 | 95 | 1710.171 | 18.0018 | 1.0001 | 0 | 0 | 1710.171 | 0 | 1710.171 | 53
| 3 | Labour | hr | L | 1 | 22.22 | 200 | 42 | 378.0378 | 9.0009 | 1.0001 | 378.0378 | 0 | 0 | 0 | 378.0378 | 53
126 | PV15 c | Batter Protection - Lot 130 | each |  |  |  | 2 | 3000 | 2641.5909 |  | 1 | 509.0909 | 132.5 | 2000 | 0 | 2641.5909
| 1 | Gabion Rock | hr | M | 1 | 1 | 5 | 26.5 | 132.5 | 5 |  | 0 | 132.5 | 0 | 0 | 132.5 | 53
126.1 | 1 | Excavator - 25T | hr | P | 1 | 0.33 | 2 | 135 | 818.1818 | 6.0606 | 0.6734 | 0 | 0 | 818.1818 | 0 | 818.1818 | 53
| 2 | Tipper | hr | P | 1 | 0.33 | 2 | 95 | 575.7576 | 6.0606 | 0.6734 | 0 | 0 | 575.7576 | 0 | 575.7576 | 53
| 3 | Labour | hr | L | 2 | 0.33 | 2 | 42 | 509.0909 | 12.1212 | 0.6734 | 509.0909 | 0 | 0 | 0 | 509.0909 | 53
| 4 | Water Cart - Hire | hr | P | 1 | 0.33 | 2 | 100 | 606.0606 | 6.0606 | 0.6734 | 0 | 0 | 606.0606 | 0 | 606.0606 | 53
127 | PV16 | Culvert Extension - Lot 30 | m |  |  |  | 2.4 |  | 3181.7676 |  | 3 | 756 | 1190.2676 | 1127.5 | 108 | 3181.7676
127.1 | 2 | Area | m² |  |  |  | 4
| 3 | Sand | tonne | M | 1 | 1 | 0.4 | 24 | 9.6 | 0.4 |  | 0 | 9.6 | 0 | 0 | 9.6 | QMS
| 4 | SL72 | m² | M | 1 | 1 | 4.8 | 9.1 | 43.68 | 4.8 |  | 0 | 43.68 | 0 | 0 | 43.68 | RSM
| 5 | Bar Chairs | each | M | 1 | 1 | 4.4444 | 0.8 | 3.5556 | 4.4444 |  | 0 | 3.5556 | 0 | 0 | 3.5556 | RSM
| 6 | N32 | m³ | M | 1 | 1 | 0.968 | 174 | 168.432 | 0.968 |  | 0 | 168.432 | 0 | 0 | 168.432 | C32
| 7 | Concrete Subbie | m² | S | 1 | 1 | 4 | 27 | 108 | 4 | 0.44444 | 0 | 0 | 0 | 108 | 108 | 182
8
127.2 | 2 | Box Units to Stand | ea |  |  |  | 2
127.3 | 3 | Hand Placed Backfill | m3 |  |  |  | 15
| 4 | RCBC - 1200 x 450 | m | M | 1 | 1 | 2.4 | 387.5 | 930 | 2.4 |  | 0 | 930 | 0 | 0 | 930 | SWC
127.4 | 5 | Excavator - 25T | hr | P | 1 | 2 | 2 | 135 | 135 | 1 | 0.11111 | 0 | 0 | 135 | 0 | 135 | 181
| 6 | Labour | hr | L | 3 | 2 | 2 | 42 | 126 | 3 | 0.11111 | 126 | 0 | 0 | 0 | 126 | 181
| 7 | Denso Tape | m | M | 1 | 1 | 7 | 5 | 35 | 7 |  | 0 | 35 | 0 | 0 | 35 | 181
127.5 | 8 | Bobcat | hr | P | 1 | 3 | 15 | 95 | 475 | 5 | 0.55556 | 0 | 0 | 475 | 0 | 475 | 181
| 9 | Labour | hr | L | 3 | 3 | 15 | 42 | 630 | 15 | 0.55556 | 630 | 0 | 0 | 0 | 630 | 181
| 10 | Plate Compactor | hr | P | 1 | 3 | 15 | 3.5 | 17.5 | 5 | 0.55556 | 0 | 0 | 17.5 | 0 | 17.5 | 181
| 11 | Water Cart - Hire | hr | P | 1 | 3 | 15 | 100 | 500 | 5 | 0.55556 | 0 | 0 | 500 | 0 | 500 | 181
12
128 | PV17 | Additional Drainage Works - Wright Road | item |  |  |  | 75 |  | 1238.7489 |  | 1 | 141.7642 | 0 | 1096.9847 | 0 | 1238.7489
128.1 | 1 | Excavator - 25T | hr | P | 1 | 22.22 | 75 | 135 | 455.6706 | 3.3753 | 0.37504 | 0 | 0 | 455.6706 | 0 | 455.6706 | 53
| 2 | Tipper | hr | P | 2 | 22.22 | 75 | 95 | 641.3141 | 6.7507 | 0.37504 | 0 | 0 | 641.3141 | 0 | 641.3141 | 53
| 3 | Labour | hr | L | 1 | 22.22 | 75 | 42 | 141.7642 | 3.3753 | 0.37504 | 141.7642 | 0 | 0 | 0 | 141.7642 | 53
| Line No. | Comment | Unit |  | No | Production | Quantity | Rate |  |  |  | Labour | Material | Plant | Subcontract | Total
9001 | Line No OH 1 Item No | Project Supervision | item |  |  |  | 1 |  | 33500 |  |  | 33500 | 0 | 0 | 0 | 33500
| 1 | Project Supervisor | week | L | 1 | 1 | 10 | 3350 | 33500 | 10 | 10 | 33500 | 0 | 0 | 0 | 33500 | 902
9002 | Line No OH 2 Item No | Crib Facilities | item |  |  |  | 1 |  | 16250 |  |  | 0 | 0 | 16250 | 0 | 16250
| 1 | Crib Facilities | week | P | 1 | 1 | 13 | 1250 | 16250 | 13 | 13 | 0 | 0 | 16250 | 0 | 16250 | 903
9003 | Line No OH 3 Item No | Insurance | item |  |  |  | 1 |  | 12000 |  |  | 0 | 0 | 0 | 12000 | 12000
| 1 | CAR | Item | S | 1 | 1 | 12000 | 1 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 12000 | 12000 | 904
9004 | Line No OH 4 Item No | Retention | item |  |  |  | 1 |  | 13500 |  |  | 0 | 0 | 0 | 13500 | 13500
| 1 | Retention Costs | Item | S | 1 | 1 | 13500 | 1 | 13500 | 13500 | 13500 | 0 | 0 | 0 | 13500 | 13500 | 904

## Resources
| Resource Name | Description | Type | Unit | Curr | Base Rate
Labour Resources | Concretor | Concretor | L | hr | AUD | 50
| Concretor - Labour |  | L | hr | AUD | 85
| Engineer / CQR |  | L | hr | AUD | 105
| Foreman - Hourly |  | L | hr | AUD | 120
| Labour | Labour | L | hr | AUD | 42
| Labour - RATE ONLY |  | L | hr | AUD | 58
| Operator | Plant Operator | L |  | AUD | 48
| PM |  | L | hr | AUD | 145
| Pipe Layer | Pipe Layer | L | hr | AUD | 65
| Pipelayer |  | L | hr | AUD | 75
| Project Engineer | Project Engineer - Weekly Rate | L | week | AUD | 3250
| Project Manager | Weekly Rate - Project Manager | L | week | AUD | 4250
| Project Supervisor | Project Supervisor | L | week | AUD | 3350
| Surveyor | Survey Team | L | hr | AUD | 185
| Traffic Controller | Traffic Controller with Vehicle | L | hr | AUD | 42
| WHSO | Work Place Health & Safety Officer | L | week | AUD | 3200
Material Resources | 100 Bend - 11.25 deg |  | M | each | AUD | 58
| 100 Bend - 22.5 deg |  | M | each | AUD | 58
| 100 Bend - 45 deg |  | M | each | AUD | 58
| 100 End Cap |  | M | each | AUD | 39
| 100 Gasket Set |  | M | each | AUD | 18.5
| 100 LD uPVC Electrical |  | M | m | AUD | 4.32
| 100 SV So-So |  | M | each | AUD | 248
| 100 x 100 Tee |  | M | each | AUD | 108.88
| 1050 Manhole per metre | 1050 pre-cast man hole rings (sewer / storm water) | M | m | AUD | 434.16
| 1050 Reducer Slab | 1050 Reducer Slab for 1050 Manhole | M | each | AUD | 218.86
| 1200 RCP FJ CL2 |  | M | m | AUD | 429.14
| 125 LD uPVC Electrical |  | M | m | AUD | 5.34
| 150 Bend - 11.25 deg |  | M | each | AUD | 89
| 150 Bend - 22.5 deg |  | M | each | AUD | 89
| 150 Bend - 45 deg |  | M | each | AUD | 89
| 150 Bend - 90 deg |  | M | each | AUD | 122
| 150 End Cap |  | M | each | AUD | 51
| 150 Gasket Set |  | M | m | AUD | 34
| 150 SN8 Sewer Pipe |  | M | m | AUD | 25
| 150 SV So-So |  | M | each | AUD | 420
| 150 Vari-Gib |  | M | each | AUD | 112
| 150 Water Meter - Helix |  | M | each | AUD | 1449.3
| 150 x 100 Tee |  | M | each | AUD | 257.32
| 150 x 150 Tee |  | M | each | AUD | 318.8
| 20mm Drainage Agg |  | M | ton | AUD | 33.5
| 300 RCP |  | M | m | AUD | 55
| 300 RCP FJ CL3 |  | M | m | AUD | 48.72
| 375 RCP |  | M | m | AUD | 68.6
| 375 RCP FJ CL3 |  | M | m | AUD | 71.92
| 375 Sloping Headwall |  | M | each | AUD | 400
| 40 HD uPVC Electrical |  | M | m | AUD | 1.98
| 40mm Drainage Agg |  | M | ton | AUD | 27.5
| 450 RCP FJ CL2 |  | M | m | AUD | 92.1
| 450 RCP FJ CL4 |  | M | m | AUD | 115.06
| 50 HD uPVC Electrical |  | M | m | AUD | 3
| 50 uPVC Communications |  | M | m | AUD | 2.32
| 525 RCP FJ CL2 |  | M | m | AUD | 105.79
| 63 HD VX Electrical |  | M | m | AUD | 3.85
| 675 RCP FJ CL3 |  | M | m | AUD | 203.21
| 750 HW |  | M | each | AUD | 725
| 750 RCP |  | M | m | AUD | 175
| 80 uPVC Communications |  | M | m | AUD | 4.62
| 900 RCP FJ CL2 |  | M | m | AUD | 259.81
| A24 | A24 - Bidum | M | m² | AUD | 1.05
| A34 |  | M | m² | AUD | 2.5
| A64 | A64 Bidum | M | m² | AUD | 2.49
| Abel Flex |  | M | m | AUD | 3
| Bar Chairs |  | M | each | AUD | 0.8
| Bollard - Plain |  | M | each | AUD | 250
| Bolts |  | M | each | AUD | 7.5
| Bro Pit - 1C1T | Bro Pit 1 Chamber, 1 Trough | M | each | AUD | 1346.26
| Bro Pit - 1C2T | Bro Pit - 1 Chamber, 2 Trough | M | each | AUD | 1709.44
| CBR15 | CBR15 Road Base | M | tonne | AUD | 27.8
| CBR45 | CBR45 Road Base | M | tonne | AUD | 28.3
| CBR80 | CBR80 Road Base - Delivered | M | tonne | AUD | 28.8
| Cast Iron Lid & Surround | Cast Iron Lid (Class D) & Surround for Man Holes | M | each | AUD | 419.97
| Cement | Bulk GP / GB Cement | M | tonne | AUD | 357
| Cement - 2 Tonne Bag | Cement Powder - 2 Tonne Bag | M | tonne | AUD | 240
| Cement - GP Bulk |  | M | tonne | AUD | 293
| Cold Mix AC |  | M | tonne | AUD | 180
| Crusher Dust - Delivered |  | M | tonne | AUD | 21.8
| DN100 uPVC PN18 |  | M | m | AUD | 13.67
| DN100 uPVC SN10 |  | M | m | AUD | 4.35
| DN100 uPVC SN8 |  | M | m | AUD | 9.09
| DN150 uPVC PN16 |  | M | m | AUD | 19.17
| DN150 uPVC PN18 |  | M | m | AUD | 26.67
| DN150 uPVC SN8 |  | M | m | AUD | 9.09
| DN25 PE100 PN12.5 | 50m Roll | M | Item | AUD | 30
| DN32 PE100 PN12.5 | 50m Roll | M | m | AUD | 50
| DN40 PE100 ON12.5 | 50m Roll | M | Item | AUD | 71.74
| DN50 PE100 PN12.5 | 50m Roll | M | Item | AUD | 120.5
| DN63 PE100 PN12.5 | 50m roll | M | Item | AUD | 184.29
| DN63 PE80B SDR11 (Gas) | 110m Roll | M | Item | AUD | 518.45
| DN90 PE100 PN12.5 | 90 PE - 100m roll | M | Item | AUD | 633.14
| Daneley Joints |  | M | each | AUD | 65
| Delineation |  | M | Item | AUD | 12000
| Denso Tape | Denso Tape | M | m | AUD | 5
| Dowels |  | M | each | AUD | 8
| Drainage Agg | Drainage Aggregate | M | tonne | AUD | 37.5
| Draw Rope - Conduits |  | M | m | AUD | 0.11
| Electrical Pit - Precast |  | M | each | AUD | 1800
| Ferrule & Bonnet - 25mm |  | M | each | AUD | 73.97
| Ferrule & Bonnet - 40mm |  | M | each | AUD | 164.31
| Ferrule & Bonnet - 50mm |  | M | each | AUD | 220.46
| Fire Booster Assembly |  | M | each | AUD | 3640.84
| Fire Booster Cabinet |  | M | each | AUD | 1597.57
| Form Boards |  | M | m | AUD | 5
| Form Ply |  | M | m² | AUD | 10
| GCL |  | M | m² | AUD | 7.2
| Gabion Rock | Gabion Rock (150 - 300) | M | tonne | AUD | 26.5
| Gates |  | M | each | AUD | 900
| General Fill | General Fill | M | tonne | AUD | 19
| General Fill (CBR15) | CBR 15 General Fill | M | tonne | AUD | 18
| Grate & Frame |  | M | each | AUD | 1000
| Guide Post |  | M | each | AUD | 35
| HW - 1200 x 450 RCBC |  | M | each | AUD | 2342.34
| HW - 2400 x 900 RCBC |  | M | each | AUD | 5347.16
| HW - 3/1200 x 300 RCBC |  | M | each | AUD | 2484.3
| HW - 300 |  | M | each | AUD | 320
| HW - 375 | Head Wall 375 RCP | M | each | AUD | 360
| HW - 375 Sloping |  | M | each | AUD | 625
| HW - 450 |  | M | each | AUD | 313.5
| HW - 450 Sloping |  | M | each | AUD | 645
| HW - 600 x 375 RCBC |  | M | each | AUD | 804.44
| HW - 675 |  | M | each | AUD | 396.31
| HW - 750 x 450 RCBC |  | M | each | AUD | 946.4
| HW 1200 x 600 RCBC |  | M | each | AUD | 2342.34
| Hard Cover - Electrical |  | M | m | AUD | 2.7
| Hazard Board |  | M | each | AUD | 750
| Hose Cock |  | M | each | AUD | 75
| Hydrant Riser |  | M | each | AUD | 230
| Hydrant Riser - 100 Dual |  | M | each | AUD | 614.3
| Hydrant Riser 150 Dual |  | M | each | AUD | 1046.6
| Kerb Adaptors |  | M | each | AUD | 75
| MDPE Junctions |  | M | each | AUD | 391.4
| Marker Post |  | M | each | AUD | 35
| N20 | N20 Concrete | M |  | AUD | 180
| N25 | N25 Concrete | M | m³ | AUD | 165
| N32 | N32 Concrete | M | m³ | AUD | 174
| PN10 : 200 DiaPE100 | DN200 - PE100 MDPE Pipe | M | m | AUD | 22.9
| Pickets | Star Pickets | M | each | AUD | 6
| Pugmill |  | M | tonne | AUD | 2.5
| RCBC - 1200 x 300 |  | M | m | AUD | 393.36
| RCBC - 1200 x 375 |  | M | each | AUD | 417.6
| RCBC - 1200 x 450 |  | M | m | AUD | 387.5
| RCBC - 1200 x 600 |  | M | m | AUD | 400
| RCBC - 2400 x 900 |  | M | m | AUD | 1176.34
| RCBC - 3600 x 900 | RCBC Crown Unit - 3600 x 900 | M | each | AUD | 1755.6
| RCBC - 600 x 300 |  | M | each | AUD | 273.13
| RCBC - 750 x 450 |  | M | m | AUD | 159.43
| RCBC - 900 x 300 |  | M | each | AUD | 313.2
| RCBC 600 x 375 |  | M | m | AUD | 152.82
| Rag Bolt |  | M | each | AUD | 425
| Rag Bolt - Small |  | M | each | AUD | 300
| Reinforcing Steel |  | M | tonne | AUD | 2200
| S32 - Exposed Aggregate |  | M | m³ | AUD | 260
| S32 - Kerb Mix | S32 - Kerb Mix | M | m³ | AUD | 181
| SL72 | SL72 - Reinforcing Mesh | M | m² | AUD | 9.1
| SL82 | SL82 Reinforcing Mesh | M | m² | AUD | 12.3
| Sand | Bedding Sand | M | tonne | AUD | 24
| Sand Bags |  | M | each | AUD | 1
| Signs - General | General signs & delineation for traffic control. | M | Item | AUD | 3500
| Signs Complete |  | M | each | AUD | 140
| Silt Fence | Silt Fence | M | m | AUD | 2
| Single Check Detector |  | M | each | AUD | 3630.96
| Small Signs |  | M | each | AUD | 350
| Small Tools |  | M | Item | AUD | 1
| Stabilised Sand | Stabilised Sand | M | m³ | AUD | 165
| Sub Soil Drain |  | M | m | AUD | 2.5
| Sub Soil Flush Fittings |  | M | each | AUD | 25
| TX160 - Geogrid |  | M | m² | AUD | 5.03
| Tack Coat |  | M | m² | AUD | 1.5
| Tapping Band - 100 x 25 |  | M | each | AUD | 36.3
| Tapping Band - 100 x 50 |  | M | each | AUD | 57.62
| Tapping Band 100 x 40 |  | M | each | AUD | 57.62
| Type A Sewer Junction |  | M | each | AUD | 110
| Valve Box & Surround |  | M | each | AUD | 150
| Water Meter Interface |  | M | each | AUD | 378.47
| Wheel Stops | Pre-cast wheel stops | M | each | AUD | 68.83
| DG14 |  | M | tonne | AUD | 299
Plant Resources | A25 |  | P | hr | AUD | 185
| Back Hoe | Backhoe - Wet Hire | P | hr | AUD | 95
| Backhoe |  | P | hr | AUD | 100
| Bobcat | Bobcat - Wet Hire | P | hr | AUD | 95
| Bobcat - RATE ONLY |  | P | hr | AUD | 115
| Bomag 124DH | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | P | hr | AUD | 26.46
| Bomag 124DH (Stand Down) | Stand Down SD Roller | P | hr | AUD | 10.75
| CAT297 | CAT297C MTL - No Operator | P | hr | AUD | 46.5
| CAT297 Stabiliser | CAT297 Stabiliser - No operator | P | hr | AUD | 66.07
| CAT311 | CAT311D - 12T Excavator (No Operator) | P | hr | AUD | 48
| Container |  | P | week | AUD | 40
| Crane Truck |  | P | day | AUD | 360
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 1250
| D6 | D6 Dozer | P | hr | AUD | 185
| Dual Grade Laser |  | P | week | AUD | 277
| Excavator - 15T | 15T Excavator - Wet Hire | P | hr | AUD | 115
| Excavator - 25T | 25T Excavator - Wet Hire | P | hr | AUD | 135
| Excavator - 30T | 30T Excavator - Wet Hire | P | hr | AUD | 135
| Excavator - 8T | 8T Excavator - Wet Hire | P | hr | AUD | 100
| Excavator 25T - RATE ONLY |  | P | hr | AUD | 162.5
| Excavator < 24 RATE ONLY |  | P | hr | AUD | 143.75
| FAE Mixer | FAE Mixer with Tractor | P | day | AUD | 2800
| Float |  | P | LS | AUD | 1
| Ford Utility | Ford Ranger 4WD Utility | P | hr | AUD | 11.67
| Generator |  | P | week | AUD | 350
| Grader | Grader - Wet Hire | P | hr | AUD | 135
| Grader - RATE ONLY |  | P | hr | AUD | 168.75
| MW Roller | MW Roller (Wet No Op) | P | hr | AUD | 55
| NH Grader | New Holland Compact Grader - No Operator | P | hr | AUD | 25.78
| PF Roller | Pad Foot Roller - Dry | P | day | AUD | 365
| PF Roller Wet - No OP |  | P | hr | AUD | 58
| Plant Float - Allciv |  | P | hr | AUD | 7
| Plate Compactor | Plate Compactor - Dry Hire | P | hr | AUD | 3.5
| Rock Breaker | Excavator - Wet Hire with Rock Breaker | P | hr | AUD | 85
| SD Roller | SD Roller - Dry | P | day | AUD | 365
| SD Roller - RATE ONLY |  | P | hr | AUD | 95
| SD Roller - Wet (No Op) | SD Roller Wet Hire - No Operator | P | hr | AUD | 55
| Scraper - RATE ONLY |  | P | hr | AUD | 406.25
| Spreader Truck - 30T | Spreader Truck - 30T | P | day | AUD | 1250
| T&D - RATE ONLY |  | P | hr | AUD | 181.25
| Tipper | Tipper (Wet Hire) | P | hr | AUD | 95
| Tipper - Allciv | Tipper - Allciv (No Driver) | P | hr | AUD | 42.79
| Toyota Utility | Toyota Landcruiser 100 Utility | P | hr | AUD | 17
| Trench Roller |  | P | hr | AUD | 15
| Truck & Dog | Truck & Dog - Wet Hire | P | hr | AUD | 145
| Truck - RATE ONLY |  | P | hr | AUD | 106.25
| UD Spreader | UD Spreader Truck - No Driver | P | hr | AUD | 21.61
| UD Spreader - Daily |  | P | day | AUD | 198
| Ute - Hire |  | P | day | AUD | 125
| Variable Message Board | Variable Message Board | P | day | AUD | 100
| WC - Allciv | Water Cart Allciv - No Operator | P | hr | AUD | 42.79
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 100
| Water Cart - RATE ONLY |  | P | hr | AUD | 118.75
Sub-Contract Resources | 10mm Seal | 10mm Spary Seal | S | m² | AUD | 3.19
| 14mm Primerseal | 14mm Primerseal | S | m² | AUD | 4.61
| 7mm Primer Seal | 7mm Primer Seal | S | m² | AUD | 4
| AMC0 Prime |  | S | m² | AUD | 1.5
| Accommodation | Accommodation & 3 meals Rate | S | day | AUD | 125
| Broons - Day One | Broons Impact Roller First day hire | S | day | AUD | 15400
| Broons - Day Two + | Broons Impact Roller - Daily hire after day one | S | day | AUD | 5240
| CAR | CAR Insurance | S | Item | AUD | 1
| CBR Test |  | S | each | AUD | 400
| CCTV |  | S | Item | AUD | 1
| Concrete Cylinders | Cylinders - Set of Three | S | each | AUD | 150
| Concrete Hole Cutting |  | S | each | AUD | 350
| Concrete Sub-contract | Concrete Sub-contractor (Slab on Ground) | S | m² | AUD | 600
| Concrete Subbie | Slab on Ground | S | m² | AUD | 27
| Conduit Subbie |  | S | LS | AUD | 1
| Council Fee |  | S | Item | AUD | 1
| Fencing Subbie |  | S | LS | AUD | 1
| Field Density |  | S | each | AUD | 45
| Final Seal |  | S | m² | AUD | 2.91
| Geotech Level One |  | S | hr | AUD | 120
| Grass Seeding |  | S | m² | AUD | 2.45
| Gravel Properties Testing |  | S | each | AUD | 390
| Grinder |  | S | day | AUD | 8500
| HDPE Liner |  | S | Item | AUD | 26553
| Kerb Subbie |  | S | m | AUD | 20
| Kerb Subbie (two) |  | S | m | AUD | 30
| Lab Compaction |  | S | each | AUD | 120
| Manhole Builder (1-2m) |  | S | LS | AUD | 1
| Manhole Builder (2-3m) |  | S | each | AUD | 5500
| PE Welder |  | S | each | AUD | 50
| PL | PL Insurance | S | Item | AUD | 6250
| Pavement Subbie |  | S | Item | AUD | 1
| Pavement Test |  | S | each | AUD | 180
| Pit Builder | Contract Rate per pit | S | each | AUD | 3750
| Pit Builder - Modify | Modify Manholes | S | each | AUD | 2500
| Plumber |  | S | hr | AUD | 85
| Pot Holes R Us |  | S | tonne | AUD | 600
| Power |  | S | Item | AUD | 5000
| Pram Ramps |  | S | each | AUD | 700
| Profiling Subbie |  | S | Item | AUD | 2100
| Retention Costs |  | S | Item | AUD | 1
| Revised Seal Design |  | S | m² | AUD | 1.09
| SAMI Seal |  | S | m² | AUD | 7.81
| Safety Rails |  | S | m | AUD | 195
| Sand Replacements | Field Density via Sand Replacement Method | S | each | AUD | 145
| Sawcut |  | S | m | AUD | 30
| Seal Visit Eight |  | S | m² | AUD | 5.56
| Seal Visit Five |  | S | m² | AUD | 4.89
| Seal Visit Four |  | S | m² | AUD | 6.67
| Seal Visit One | 7mm Primer Seal | S | m² | AUD | 9.54
| Seal Visit Seven |  | S | m² | AUD | 4.27
| Seal Visit Six |  | S | m² | AUD | 4.54
| Seal Visit Three |  | S | m² | AUD | 4.37
| Seal Visit Two |  | S | m² | AUD | 7.98
| Security Fence | Security Fence - Three Strand Barb & Crank | S | m | AUD | 66
| Service Locator |  | S | hr | AUD | 135
| Sewer Subbie |  | S | LS | AUD | 1
| Soil Tests |  | S | Item | AUD | 1650
| Steel Fixing |  | S | tonne | AUD | 2200
| Stone Pitching |  | S | m² | AUD | 75
| Sub Soil Clean Out - Inst |  | S | each | AUD | 143
| Survey - Boundary Pegs |  | S | each | AUD | 45
| Temporary Fencing |  | S | m | AUD | 8
| Tip Fees | Tip fees per ton of waste | S | tonne | AUD | 25
| Traffic Control Crew | 2 x TC's + Ute, Signs & Comms | S | hr | AUD | 102.16
| Traffic Ute |  | S | hr | AUD | 25
| Turf Subbie |  | S | m² | AUD | 7
| WHS | WHS Insurance / Levy | S | Item | AUD | 1
| Water Subbie |  | S | LS | AUD | 1
| DG10 |  | S | tonne | AUD | 275.7
| Line Marking |  | S | m² | AUD | 1
|  | Gravel MDD (tonnes per compacted cubic metre) | 2.22
|  | Gravel OMC (% water at OMC in tonnes) | 8%
|  | Wastage Factor (% wastage in tonnes) | 10%
|  | Gravel Conversion Factor (Sum of above) | 2.4

## Model Inputs
WBS | DESCRIPTION | TYPE | MODEL INPUT | UOM
5 | NICOL ST - PROSERPINE
6 | Quality System Documents & Records | Q | 1 | LS
7 | Quality Verification & Control | Q | 1 | LS
8 | Site Establishment & Disestablishment | Q | 1 | LS
9 | Preparation of Environmrntal Management Plan | Q | 1 | LS
10 | Control of Traffic | Q | 1 | LS
10.1 | Traffic Controller | P | 0.11 | hr
11 | Provision of Temporary Roadways, Sidetracks & Detours | Q | 1 | LS
12 | Temporary Erosion & Sedimentation Control | Q | 1 | LS
12.1 | Silt Fence | Q | 500 | m
12.2 | Labour | Q | 50 | hr
13 | Clearing & Grubbing | Q | 1 | LS
13.1 | Excavator - 25T | P | 0.06 | hr
14 | Removal & Stockpiling of Topsoil for Re-use | Q | 20 | cum
14.1 | Excavator - 25T | P | 20 | hr
15 | General Earthworks (Cut) | Q | 1045 | cum
15.1 | Excavator - 25T | P | 43.54 | hr
16 | Replace unsuitable material below subgrade with select material complete (Provisional) | Q | 10 | cum
17.1 | Excavator - 25T | P | 10 | hr
17.2 | Grader | P | 33.33 | hr
18 | Alteration to Exisiting Stormwater Structures | Q | 1 | LS
18.1 | Labour | L | 0.5 | hr
19 | Concrete Barrier Kerb (B1) | Q | 308 | m
20 | 100mm slotted corrugated lastic pipe | Q | 260 | m
20.1 | Excavator - 25T | P | 11.11 | hr
20.2 | Cleanout Structures | Q | 6 | ea
21 | Supply stabilising Agent | Q | 34 | tonne
22 | Mixing & Spreading of stabilising agent | Q | 1893 | sqm
22.1 | CAT297 Stabiliser | P | 66.67 | hr
23 | Place only 2.3 | Q | 758 | cum
23.1 | Grader | P | 44.44 | hr
24 | Place only 2.1 | Q | 282 | cum
24.1 | Grader | P | 44.44 | hr
24.2 | Grader | P | 300 | hr
25 | Special Item - Take up existing gravel, stabilise & relay as working platform | Q | 483 | m3
25.1 | CAT297 Stabiliser | P | 66.67 | hr
26 | AMC5 | Q | 1661 | sqm
27 | DG14 AC | Q | 195 | tonne
28 | Industrial Invert Crossing | Q | 15 | ea
28.1 | Excavator - 25T | P | 10 | hr
29 | Grass Seeding | Q | 1000 | sqm
30 | Sawcut bitumous pavement | Q | 30 | 0
31 | Remove existing pavement & dispose offsite | Q | 1661 | m2
31.1 | Grader | P | 300 | hr
31.2 | Excavator - 25T | P | 415.25 | hr
32 | Locate & Protect services | Q | 1 | LS
33 | As Constructed Plans | Q | 1 | LS
34 | WRIGHTS ROAD (STRATHDICKIE)
35 | Quality System Documents & Records | Q | 1 | LS
36 | Quality Verification & Control | Q | 1 | LS
37 | Site Establishment & Disestablishment | Q | 1 | LS
38 | Preparation of Environmrntal Management Plan | Q | 1 | LS
39 | Control of Traffic | Q | 1 | LS
40 | Provision of Temporary Roadways, Sidetracks & Detours | Q | 1 | LS
41 | Temporary Erosion & Sedimentation Control | Q | 1 | LS
41.1 | Bobcat | P | 10 | hr
42 | Clearing & Grubbing | Q | 1 | LS
42.1 | Grader | P | 0.06 | hr
43 | Special Item - Demolition of structures(concrete slabs, culverts pipes) | Q | 1 | LS
43.1 | Excavator - 25T | P | 0.03 | hr
44 | Removal & Stockpiling of Topsoil for Re-use | Q | 700 | cum
44.1 | Excavator - 25T | P | 33.33 | hr
44.2 | General Earthworks (Cut) | Q | 1220 | cum
44.3 | Excavator - 25T | P | 44.44 | hr
45 | General Earthworks (Fill) | Q | 410 | cum
45.1 | Grader | P | 44.44 | hr
46 | Replace unsuitable material below subgrade with select material complete (Provisional) | Q | 10 | cum
46.1 | Excavator - 25T | P | 10 | hr
46.2 | Grader | P | 33.33 | hr
47 | Excavation in Roak (Unrippable) | Q | 5 | cum
48 | Minor Rural Accesses | Q | 36 | ea
49 | Excavation for stromwater structures | Q | 300 | cum
49.1 | Excavator - 25T | P | 20 | hr
50 | Removal / Demolition of Drainage Components | Q | 1 | LS
51 | 375 RCP | Q | 58 | m
51.1 | Excavator - 25T | P | 0.97 | hr
52 | 450 RCP | Q | 44 | m
52.2 | Excavator - 25T | P | 0.92 | hr
53 | Insitu RCBC Base Slab | Q | 57 | cum
54 | Culvert 4S - 1200 x 450 (4.8m) | Q | 0 | 0
54.1 | Area | Q | 8 | m²
55 | Culvert 4AB - 1200 x 450 (4.8m) | Q | 0 | 0
55.1 | Area | Q | 8 | m²
56 | Culvert 5E - 2/1200 x 450 (6m) | Q | 0 | 0
56.1 | Area | Q | 18 | m²
57 | Culvert 6D - 3/1200 x 600 (6m) | Q | 0 | 0
57.1 | Area | Q | 28 | m²
58 | Culvert 6F - 2/1200 x 600 (6m) | Q | 0 | 0
58.1 | Area | Q | 18 | m²
59 | Culvert 6K - 2/1200 x 450 (4.8m) | Q | 0 | 0
59.1 | Area | Q | 18 | m²
60 | Culvert 6M - 2/1200 x 450 (4.8m) | Q | 0 | 0
60.1 | Area | Q | 18 | m²
61 | Culvert 6P - 1200 x 450 (4.8m) | Q | 0 | 0
61.1 | Area | Q | 8 | m²
62 | Culvert 6T - 1200 x 450 (6m) | Q | 0 | 0
62.1 | Area | Q | 11 | m²
63 | Culvert 4U 2/1200 x 600 (10.8m) Under Road | Q | 0 | 0
63.1 | Area | Q | 35.4 | m²
64 | Culvert 4AA - 3/1200 x 450 (9.6m) Under Road | Q | 0 | 0
64.1 | Area | Q | 44.2 | m²
65 | Culvert 5D - 2/1200 x 600 ((.6m) Under Road | Q | 0 | 0
65.1 | Area | Q | 28.8 | m²
66 | Culvert 5M - 4/1200 x 600 (10.8m) Under Road | Q | 0 | 0
66.1 | Area | Q | 69 | m²
67 | Culvert 6B - 1200 x 450 (9.6m) Under Road | Q | 0 | 0
67.1 | Area | Q | 15.5 | m²
68 | Culvert 6V - 1200 x 450 (9.6m) Under Road | Q | 0 | 0
68.1 | Area | Q | 15.5 | m²
69 | RCBC - 1200 x 450 | Q | 0 | m
70 | Culvert 4S - 1200 x 450 (4.8m) | Q | 0 | 0
70.1 | Box Units to Stand | Q | 4 | ea
70.2 | Hand Placed Backfill | Q | 15 | m3
70.3 | Excavator - 25T | P | 2 | hr
70.4 | Bobcat | P | 3 | hr
71 | Culvert 4AB - 1200 x 450 (4.8m) | Q | 0 | 0
71.1 | Box Units to Stand | Q | 4 | ea
71.2 | Hand Placed Backfill | Q | 15 | m3
71.3 | Excavator - 25T | P | 2 | hr
71.4 | Bobcat | P | 3 | hr
72 | Culvert 5E - 2/1200 x 450 (6m) | Q | 0 | 0
72.1 | Box Units to Stand | Q | 10 | ea
72.2 | Hand Placed Backfill | Q | 24 | m3
72.3 | Excavator - 25T | P | 2 | hr
72.4 | Bobcat | P | 3 | hr
73 | Culvert 6K - 2/1200 x 450 (4.8m) | Q | 0 | 0
73.1 | Box Units to Stand | Q | 8 | ea
73.2 | Hand Placed Backfill | Q | 15 | m3
73.3 | Excavator - 25T | P | 2 | hr
73.4 | Bobcat | P | 3 | hr
74 | Culvert 6M - 2/1200 x 450 (4.8m) | Q | 0 | 0
74.1 | Box Units to Stand | Q | 8 | ea
74.2 | Hand Placed Backfill | Q | 15 | m3
74.3 | Excavator - 25T | P | 2 | hr
74.4 | Bobcat | P | 3 | hr
75 | Culvert 6P - 1200 x 450 (4.8m) | Q | 0 | 0
75.1 | Box Units to Stand | Q | 4 | ea
75.2 | Hand Placed Backfill | Q | 15 | m3
75.3 | Excavator - 25T | P | 2 | hr
75.4 | Bobcat | P | 3 | hr
76 | Culvert 6T - 1200 x 450 (6m) | Q | 0 | 0
76.1 | Box Units to Stand | Q | 5 | ea
76.2 | Hand Placed Backfill | Q | 18 | m3
76.3 | Excavator - 25T | P | 2 | hr
76.4 | Bobcat | P | 3 | hr
77 | Culvert 4AA - 3/1200 x 450 (9.6m) Under Road | Q | 0 | 0
77.1 | Box Units to Stand | Q | 24 | ea
77.2 | Hand Placed Backfill | Q | 30 | m3
77.3 | Excavator - 25T | P | 2 | hr
77.4 | Bobcat | P | 3 | hr
78 | Culvert 6B - 1200 x 450 (9.6m) Under Road | Q | 0 | 0
78.1 | Box Units to Stand | Q | 8 | ea
78.2 | Hand Placed Backfill | Q | 24 | m3
78.3 | Excavator - 25T | P | 2 | hr
78.4 | Bobcat | P | 3 | hr
79 | Culvert 6V - 1200 x 450 (9.6m) Under Road | Q | 0 | 0
79.1 | Box Units to Stand | Q | 8 | ea
79.2 | Hand Placed Backfill | Q | 24 | m3
79.3 | Excavator - 25T | P | 2 | hr
79.4 | Bobcat | P | 3 | hr
80 | RCBC - 1200 x 600 | Q | 0 | m
81 | Culvert 6D - 3/1200 x 600 (6m) | Q | 0 | 0
81.1 | Box Units to Stand | Q | 15 | ea
81.2 | Hand Placed Backfill | Q | 18 | m3
81.3 | Excavator - 25T | P | 2 | hr
81.4 | Bobcat | P | 3 | hr
82 | Culvert 6F - 2/1200 x 600 (6m) | Q | 0 | 0
82.1 | Box Units to Stand | Q | 10 | ea
82.2 | Hand Placed Backfill | Q | 18 | m3
82.3 | Excavator - 25T | P | 2 | hr
82.4 | Bobcat | P | 3 | hr
83 | Culvert 4U 2/1200 x 600 (10.8m) Under Road | Q | 0 | 0
83.1 | Box Units to Stand | Q | 36 | ea
83.2 | Hand Placed Backfill | Q | 32 | m3
83.3 | Excavator - 25T | P | 2 | hr
83.4 | Bobcat | P | 3 | hr
84 | Culvert 5D - 2/1200 x 600 ((.6m) Under Road | Q | 0 | 0
84.1 | Box Units to Stand | Q | 10 | ea
84.2 | Hand Placed Backfill | Q | 18 | m3
84.3 | Excavator - 25T | P | 2 | hr
84.4 | Bobcat | P | 3 | hr
85 | Culvert 5M - 4/1200 x 600 (10.8m) Under Road | Q | 0 | 0
85.1 | Box Units to Stand | Q | 36 | ea
85.2 | Hand Placed Backfill | Q | 30 | m3
85.3 | Excavator - 25T | P | 2 | hr
85.4 | Bobcat | P | 3 | hr
86 | Cast in situ headwalls | Q | 35 | cum
87 | 375 HW | Q | 1 | ea
87.1 | Excavator - 25T | P | 1 | hr
88 | 375 Sloping HW | Q | 18 | ea
88.1 | Excavator - 25T | P | 1 | hr
89 | 450 Sloping HW | Q | 20 | ea
89.1 | Excavator - 25T | P | 1 | hr
90 | B1 Kerb | Q | 48 | m
91 | SM5 Kerb | Q | 62 | m
92 | Sub-soil | Q | 1520 | m
92.1 | Excavator - 25T | P | 11.11 | hr
93 | PAVEMENTS | Q | 0 | 0
94 | Place only 2.3 | Q | 1135 | m3
95 | Grader | P | 44.44 | hr
96 | Place Only 2.1 | Q | 1490 | m3
96.1 | Grader | P | 66.67 | hr
96.2 | Grader | P | 300 | hr
97 | First Coat AMC5 | Q | 9380 | sqm
98 | Second Coat | Q | 9380 | sqm
99 | Pavement Markings - Longitudinal Lines | Q | 3404 | m
100 | Pavement Marking (Transverse etc) | Q | 1 | LS
101 | Remove & reinstate exisiting signs & supports | Q | 1 | LS
102 | Supply & Install all signs complete | Q | 26 | ea
102.1 | Labour | L | 2 | hr
103 | Guide Posts | Q | 131 | ea
104 | MISCELLANEOUS
105 | Grass seeding | Q | 9200 | sqm
106 | Sawcut Bitumen pavement | Q | 53 | m
107 | Locate & Protect Services | Q | 0 | LS
107.1 | Service Locator | P | 18 | hr
108 | As Constructed Plans | Q | 0 | LS
108.1 | Surveyor | P | 45 | hr
109 | Principal Supply of Precast Conrete Items | Q | 0 | each
109.1 | 375 RCP | Q | -58 | m
109.2 | 450 RCP FJ CL2 | Q | -44 | m
109.3 | RCBC - 1200 x 450 | Q | -100 | m
109.4 | RCBC - 1200 x 600 | Q | -114 | m
109.5 | HW - 375 | Q | -1 | each
109.6 | HW - 375 Sloping | Q | -18 | each
109.7 | HW - 450 Sloping | Q | -20 | each
110 | Additional 375RCP at chainage 230. | Q | 0 | each
110.1 | Install Only New RCP: | Q | 4.88 | m
110.2 | Excavator - 25T | P | 0.97 | hr
110.3 | Excavator - 25T | P | 1 | hr
110.4 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D. | Q | 2.98 | m3
110.5 | Grader | P | 66.67 | hr
110.6 | Grader | P | 300 | hr
110.7 | Primer Seal: | Q | 19.52 | m²
112 | Revised Seal Design | Q | 9380 | m2
113 | Shape table drain chainage 523-725 | Q | 251 | m3
113.1 | Excavator - 25T | P | 44.44 | hr
114 | Nicol St - Revised pavement design | Q | 0 | each
114.1 | General Earthworks (Cut) | Q | -524 | m3
114.2 | Excavator - 25T | P | 43.54 | hr
114.3 | Place Only 2.3 | Q | -332 | m3
114.4 | Grader | P | 44.44 | hr
114.5 | Place Only 2.1 | Q | -282 | m3
114.6 | Grader | P | 44.44 | hr
114.7 | Grader | P | 300 | hr
114.8 | Special Item - Take Up & Stabilise & Relay as Working Platform | Q | 9 | m3
114.9 | Cement | Q | 0.012 | tonne
114.91 | CAT297 Stabiliser | P | 66.67 | hr
115 | Nicol St - Additional drain outlet | Q | 50 | each
115.1 | Excavator - 8T | P | 5 | hr
116 | Nicol St - Subgrade pavement repairs | Q | 0 | each
116.1 | Special Item - Take Up & Stabilise & Relay as Working Platform | Q | 96.4 | m3
116.2 | Cement | Q | 0.012 | tonne
116.3 | CAT297 Stabiliser | P | 66.67 | hr
116.4 | Geotextiles: | Q | 380 | 0
117 | Nicol St - Additional works to water services | Q | 1 | each
118 | Wright Rd - Drainage works ch1300 | Q | 0 | each
118.1 | Excavator - 25T | P | 18 | hr
118.2 | Grass Seeding | Q | 500 | hr
119 | Wright Rd - Additional culvert no.06 | Q | 0 | each
119.1 | Install Only New RCP: | Q | 4.88 | 0
119.2 | Excavator - 25T | P | 0.97 | hr
119.3 | Excavator - 25T | P | 1 | hr
119.4 | Haul, place, spread, compact & trim (No supply). Round trip of one hour to Foxdale & back to Proserpine. Haul in T&D. | Q | 2.98 | m3
119.5 | Grader | P | 66.67 | hr
119.6 | Grader | P | 300 | hr
119.7 | Primer Seal: | Q | 19.52 | m²
120 | Wright Rd - Driveway works | Q | 200 | each
121 | Nicol St - Kerb ramp reconstruction | Q | 2 | each
122 | Nicol St - Removal of Unsuitable - Telstra Cable | Q | 33.8 | each
122.1 | Excavator - 25T | P | 10 | hr
122.2 | Grader | P | 33.33 | hr
123 | Wright Road - Scour & Batter Protection | Q | 0 | each
124 | Scour Protection | Q | 18 | each
124.1 | Excavator - 25T | P | 22.22 | hr
125 | Drain Widening - Lot 130 | Q | 200 | each
125.1 | Excavator - 25T | P | 22.22 | hr
126 | Batter Protection - Lot 130 | Q | 2 | each
126.1 | Excavator - 25T | P | 0.33 | hr
127 | Culvert Extension - Lot 30 | Q | 0 | m
127.1 | Area | Q | 4 | m²
127.2 | Box Units to Stand | Q | 2 | ea
127.3 | Hand Placed Backfill | Q | 15 | m3
127.4 | Excavator - 25T | P | 2 | hr
127.5 | Bobcat | P | 3 | hr
128 | Additional Drainage Works - Wright Road | Q | 75 | item
128.1 | Excavator - 25T | P | 22.22 | hr
9001 | Project Supervision | Q | 1 | item
9002 | Crib Facilities | Q | 1 | item
9003 | Insurance | Q | 1 | item
9004 | Retention | Q | 1 | item

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | 2013-01-26 | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Work Hours Per Day |  | 9
Start Date |  | 2011-09-05

## Program Links
WBS | TASK | Duration | Predecessors | Successors | Budget | %C Claim 01 | %C Claim 02 | %C Claim 03 | %C Claim 04 | %C Claim 05 | %C Claim 06 | %C Claim 07 | %C Claim 08 | %C Claim 09 | %C Claim 10
3 | Contract Award | 0 |  | 6,9,33,34,37,107
4 | Practical Completion | 0 | 32,106,103,7,10,11,28,35,38,39
5 | NICOL ST - PROSERPINE | 0 |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
6 | Quality System Documents & Records | 5 | 3 | 8,7 | 3250 | 0% | 60% | 70% | 70% | 85% | 90% | 90% | 100% | 100% | 100%
7 | Quality Verification & Control | 0 | 6 | 4 | 11750 | 0% | 60% | 70% | 70% | 85% | 90% | 90% | 100% | 100% | 100%
8 | Site Establishment & Disestablishment | 5 | 6 | 11,12,31,10 | 13900 | 0% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Preparation of Environmrntal Management Plan | 5 | 3 | 12 | 3250 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Control of Traffic | 35 | 8 | 4 | 15829.5455 | 0% | 60% | 70% | 70% | 85% | 90% | 95% | 100% | 100% | 100%
11 | Provision of Temporary Roadways, Sidetracks & Detours | 0 | 8,31 | 4 | 6600 | 0% | 60% | 70% | 70% | 85% | 90% | 100% | 100% | 100% | 100%
12 | Temporary Erosion & Sedimentation Control | 2 | 8,9 | 13 | 5050 | 0% | 60% | 70% | 70% | 85% | 90% | 90% | 100% | 100% | 100%
13 | Clearing & Grubbing | 2 | 12 | 14 | 11683.3333 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Removal & Stockpiling of Topsoil for Re-use | 1 | 13 | 15,17 | 272 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | General Earthworks (Cut) | 3 | 14 | 16,30SS | 14496.5549 | 0% | 40.77% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | Replace unsuitable material below subgrade with select material complete (Provisional) | 1 | 15,30 | 24,20SS,111,113,119 | 922.3708 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
18 | Alteration to Exisiting Stormwater Structures | 1 | 14112 | 18 | 1036 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | Concrete Barrier Kerb (B1) | 2 | 22,19,17 | 23,27 | 14424.1456 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
20 | 100mm slotted corrugated lastic pipe | 3 | 22 | 18112 | 10119.7822 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
21 | Supply stabilising Agent | 1 | 16SS | 21 | 12138 | 0% | 10.59% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | Mixing & Spreading of stabilising agent | 4 | 20114 | 22 | 12392.6621 | 0% | 10.57% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
23 | Place only 2.3 | 5 | 24,21 | 18,19 | 34836.6157 | 0% | 28.89% | 28.89% | 28.89% | 100% | 100% | 100% | 100% | 100% | 100%
24 | Place only 2.1 | 3 | 18118 | 25 | 14940.5907 | 0% | 0% | 0% | 0% | 33.33% | 100% | 100% | 100% | 100% | 100%
25 | Special Item - Take up existing gravel, stabilise & relay as working platform | 7 | 16111 | 22 | 34310.9398 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | AMC5 | 1 | 23,27 | 26FS+5 days,28,29 | 16638.237 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
27 | DG14 AC | 1 | 25FS+5 days,29 | 32 | 58305 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
28 | Industrial Invert Crossing | 7 | 18 | 25,118FF | 40993.6877 | 0% | 0% | 33.33% | 33.33% | 46.67% | 100% | 100% | 100% | 100% | 100%
29 | Grass Seeding | 1 | 25 | 4 | 2695 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
30 | Sawcut bitumous pavement | 1 | 25 | 26 | 900 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
31 | Remove existing pavement & dispose offsite | 1 | 15SS | 16 | 3708.45 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
32 | Locate & Protect services | 2 | 8 | 11 | 2025 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
33 | As Constructed Plans | 3 | 26 | 4 | 4995 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
34 | WRIGHTS ROAD (STRATHDICKIE) | 0 | 3
35 | Quality System Documents & Records | 5 | 3 | 36,109,35 | 6500 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
36 | Quality Verification & Control | 0 | 34 | 4 | 15080 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
37 | Site Establishment & Disestablishment | 5 | 34,37,107 | 40105 | 13100 | 80% | 80% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100%
38 | Preparation of Environmrntal Management Plan | 5 | 3 | 36 | 3250 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
39 | Control of Traffic | 28 | 40 | 4 | 10024 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
40 | Provision of Temporary Roadways, Sidetracks & Detours | 0 | 40 | 4 | 2100 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
41 | Temporary Erosion & Sedimentation Control | 6 | 36 | 39,38,41 | 10950 | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
42 | Clearing & Grubbing | 2 | 40105 | 42 | 9066.6667 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
43 | Special Item - Demolition of structures(concrete slabs, culverts pipes) | 4 | 41 | 43 | 13800 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
44 | Removal & Stockpiling of Topsoil for Re-use | 3 | 42 | 45,44 | 7707.7708 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
44.2 | General Earthworks (Cut) | 4 | 43 | 45FF | 10075.1575 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
45 | General Earthworks (Fill) | 2 | 43,44FF | 46,49,53 | 6310.5311 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
46 | Replace unsuitable material below subgrade with select material complete (Provisional) | 1 | 45 | 93 | 922.3708 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
48 | Minor Rural Accesses | 4 | 91FF,104 | 89 | 13464 | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
49 | Excavation for stromwater structures | 2 | 49 | 110 | 7362 | 71.33% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
50 | Removal / Demolition of Drainage Components | 6 | 45 | 48,50 | 2100 | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
51 | 375 RCP | 7 | 49 | 51,86,108 | 20796.5039 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
52 | 450 RCP | 6 | 50108110 | 88 | 17462.72 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
53 | Insitu RCBC Base Slab | 0 |  |  |  | 47.37% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
54 | Culvert 4S - 1200 x 450 (4.8m) | 2 | 45 | 54,69 | 666.5351
55 | Culvert 4AB - 1200 x 450 (4.8m) | 2 | 53 | 70FS+3 days,55 | 666.5351
56 | Culvert 5E - 2/1200 x 450 (6m) | 3 | 54 | 71FS+3 days,56 | 1499.704
57 | Culvert 6D - 3/1200 x 600 (6m) | 3 | 55 | 80FS+3 days,57 | 2332.8729
58 | Culvert 6F - 2/1200 x 600 (6m) | 3 | 56 | 81FS+3 days,58 | 1499.704
59 | Culvert 6K - 2/1200 x 450 (4.8m) | 2 | 57 | 72FS+3 days,59 | 1499.704
60 | Culvert 6M - 2/1200 x 450 (4.8m) | 3 | 58 | 73FS+3 days,60 | 1499.704
61 | Culvert 6P - 1200 x 450 (4.8m) | 2 | 59 | 74FS+3 days,61 | 666.5351
62 | Culvert 6T - 1200 x 450 (6m) | 3 | 60 | 75FS+3 days,62 | 916.4858
63 | Culvert 4U 2/1200 x 600 (10.8m) Under Road | 3 | 61 | 82FS+3 days,63 | 2949.4179
64 | Culvert 4AA - 3/1200 x 450 (9.6m) Under Road | 3 | 62 | 76FS+3 days,64 | 3682.6065
65 | Culvert 5D - 2/1200 x 600 ((.6m) Under Road | 5 | 63 | 83FS+3 days,65 | 2399.5264
66 | Culvert 5M - 4/1200 x 600 (10.8m) Under Road | 3 | 64 | 84FS+3 days,66 | 5748.8653
67 | Culvert 6B - 1200 x 450 (9.6m) Under Road | 3 | 65 | 77FS+3 days,67 | 1291.4118
68 | Culvert 6V - 1200 x 450 (9.6m) Under Road | 3 | 66 | 78FS+3 days | 1291.4118
69 | RCBC - 1200 x 450 | 0 |  |  |  | 14.4% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
70 | Culvert 4S - 1200 x 450 (4.8m) | 1 | 53 | 70 | 4074.5
71 | Culvert 4AB - 1200 x 450 (4.8m) | 1 | 54FS+3 days,69 | 71 | 4074.5
72 | Culvert 5E - 2/1200 x 450 (6m) | 1 | 55FS+3 days,70 | 80 | 8726
73 | Culvert 6K - 2/1200 x 450 (4.8m) | 1 | 58FS+3 days,81 | 73 | 6526.5
74 | Culvert 6M - 2/1200 x 450 (4.8m) | 1 | 59FS+3 days,72 | 74 | 6526.5
75 | Culvert 6P - 1200 x 450 (4.8m) | 1 | 60FS+3 days,73 | 75 | 4074.5
76 | Culvert 6T - 1200 x 450 (6m) | 1 | 61FS+3 days,74 | 82 | 5012
77 | Culvert 4AA - 3/1200 x 450 (9.6m) Under Road | 2 | 63FS+3 days,82 | 83 | 17957
78 | Culvert 6B - 1200 x 450 (9.6m) Under Road | 1 | 66FS+3 days,84 | 78 | 7500
79 | Culvert 6V - 1200 x 450 (9.6m) Under Road | 1 | 67FS+3 days,77 | 85 | 7500
80 | RCBC - 1200 x 600 | 0 |  | 80 |  | 35.79% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
81 | Culvert 6D - 3/1200 x 600 (6m) | 1 | 56FS+3 days,79,71 | 81 | 11404.5
82 | Culvert 6F - 2/1200 x 600 (6m) | 1 | 57FS+3 days,80 | 72 | 8252
83 | Culvert 4U 2/1200 x 600 (10.8m) Under Road | 2 | 62FS+3 days,75 | 76 | 26159.3333
84 | Culvert 5D - 2/1200 x 600 ((.6m) Under Road | 1 | 64FS+3 days,76 | 84 | 8252
85 | Culvert 5M - 4/1200 x 600 (10.8m) Under Road | 2 | 65FS+3 days,83 | 77 | 25943
86 | Cast in situ headwalls | 4 | 78,88FF | 93115 | 21000 | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
87 | 375 HW | 1 | 50 | 87 | 621 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
88 | 375 Sloping HW | 2 | 86 | 88 | 15948 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
89 | 450 Sloping HW | 3 | 87,51 | 85FF | 18120 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
90 | B1 Kerb | 1 | 91,47 | 90 | 3994.1526 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
91 | SM5 Kerb | 1 | 89 | 94 | 4351.8967 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
92 | Sub-soil | 16 | 93 | 47FF,89,104FF | 59161.7985 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
93 | PAVEMENTS | 0
94 | Place only 2.3 | 7 | 46,85 | 91 | 52163.0063 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
96 | Place Only 2.1 | 10 | 90 | 95 | 63885.88 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
97 | First Coat AMC5 | 1 | 94109 | 99,96FS+5 days,103 | 39396 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
98 | Second Coat | 1 | 95FS+5 days | 97FS+5 days | 78595.02 | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
99 | Pavement Markings - Longitudinal Lines | 1 | 96FS+5 days | 98 | 6808 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
100 | Pavement Marking (Transverse etc) | 1 | 97 | 106 | 2000 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
101 | Remove & reinstate exisiting signs & supports | 2 | 95 | 100 | 840 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
102 | Supply & Install all signs complete | 2 | 99 | 101 | 5804.5 | 0% | 0% | 0% | 0% | 96.15% | 100% | 100% | 100% | 100% | 100%
103 | Guide Posts | 3 | 100 | 106 | 4585 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
104 | MISCELLANEOUS | 0
105 | Grass seeding | 1 | 95 | 4 | 24794 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
106 | Sawcut Bitumen pavement | 1 | 91FF | 47 | 1590 | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
107 | Locate & Protect Services | 2 | 36 | 41 | 2430 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
108 | As Constructed Plans | 5 | 98117125101 | 4 | 8325 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
109 | Principal Supply of Precast Conrete Items | 1 | 3 | 36 | -116891.2 | 41.9% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
110 | Additional 375RCP at chainage 230. | 4 | 50 | 51 | 991.3207 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
112 | Revised Seal Design | 0 | 34 | 95 | 10735.41 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
113 | Shape table drain chainage 523-725 | 1 | 48 | 51 | 2072.8398 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
114 | Nicol St - Revised pavement design | 0 | 16 | 24 | -36828.5961 | 0% | 0% | 18% | 18% | 88% | 100% | 100% | 100% | 100% | 100%
115 | Nicol St - Additional drain outlet | 2 | 19 | 17 | 3241.2213 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
116 | Nicol St - Subgrade pavement repairs | 2 | 16119 | 114 | 10385.4605 | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
117 | Nicol St - Additional works to water services | 1 | 113 | 21 | 13500 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
118 | Wright Rd - Drainage works ch1300 | 3 | 85 | 116121 | 5796 | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
119 | Wright Rd - Additional culvert no.06 | 3 | 115 | 117 | 2127.1546 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
120 | Wright Rd - Driveway works | 4 | 116 | 106 | 9750 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
121 | Nicol St - Kerb ramp reconstruction | 2 | 27FF | 23 | 2270 | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
122 | Nicol St - Removal of Unsuitable - Telstra Cable | 1 | 16 | 113 | 3117.6134 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
123 | Wright Road - Scour & Batter Protection | 0
124 | Scour Protection | 6 | 115 | 122 | 8991.2997 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
125 | Drain Widening - Lot 130 | 1 | 121 | 123 | 3303.3303 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
126 | Batter Protection - Lot 130 | 1 | 122 | 124 | 2641.5909 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
127 | Culvert Extension - Lot 30 | 3 | 123 | 125 | 3181.7676 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 41.67% | 41.67%
128 | Additional Drainage Works - Wright Road | 1 | 124 | 106 | 1238.7489 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%

## Budget & Revenue
Portfolio WBS | Item No | Description | Unit | Tender Budget | Tender Quantity | Contract Quantity | Tender Rate | Tender Total | Contract Total | Claim 01 | % C - Claim 01 | Claim 02 | % C - Claim 02 | Claim 03 | % C - Claim 03 | Claim 04 | % C - Claim 04 | Claim 05 | % C - Claim 05 | Claim 06 | % C - Claim 06 | Claim 07 | % C - Claim 07 | Claim 08 | % C - Claim 08 | Claim 09 | % C - Claim 09 | Claim 10 | % C - Claim 10 | Revenue Sep-11 | Revenue Oct -11 | Revenue Nov-11 | Revenue Dec-11 | Revenue Jan-12 | Revenue Feb-12 | Revenue Mar-12 | Revenue May-12 | Revenue Jul-12 | Revenue Dec-12
Contract Items
5 |  | NICOL ST - PROSERPINE
6 | QCP1 | Quality System Documents & Records | LS | 3250 | 1 | 1 | 3999.73 | 3999.73 | 3999.73 |  | 0% | 0.6 | 60% | 0.7 | 70% | 0.7 | 70% | 0.85 | 85% | 0.9 | 90% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2399.838 | 2799.811 | 2799.811 | 3399.7705 | 3599.757 | 3599.757 | 3999.73 | 3999.73 | 3999.73
7 | QCP1 | Quality Verification & Control | LS | 11750 | 1 | 1 | 14460.56 | 14460.56 | 14460.56 |  | 0% | 0.6 | 60% | 0.7 | 70% | 0.7 | 70% | 0.85 | 85% | 0.9 | 90% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 8676.336 | 10122.392 | 10122.392 | 12291.476 | 13014.504 | 13014.504 | 14460.56 | 14460.56 | 14460.56
8 | C101(b) | Site Establishment & Disestablishment | LS | 13900 | 1 | 1 | 17106.54 | 17106.54 | 17106.54 |  | 0% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 13685.232 | 13685.232 | 13685.232 | 17106.54 | 17106.54 | 17106.54 | 17106.54 | 17106.54 | 17106.54
9 |  | Preparation of Environmrntal Management Plan | LS | 3250 | 1 | 1 | 3999.73 | 3999.73 | 3999.73 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73
ROAD & EARTHWORKS
10 | C201 (a) | Control of Traffic | LS | 15829.5455 | 1 | 1 | 20115.57 | 20115.57 | 20115.57 |  | 0% | 0.6 | 60% | 0.7 | 70% | 0.7 | 70% | 0.85 | 85% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 12069.342 | 14080.899 | 14080.899 | 17098.2345 | 18104.013 | 19109.7915 | 20115.57 | 20115.57 | 20115.57
11 | C201 (b) | Provision of Temporary Roadways, Sidetracks & Detours | LS | 6600 | 1 | 1 | 8122.53 | 8122.53 | 8122.53 |  | 0% | 0.6 | 60% | 0.7 | 70% | 0.7 | 70% | 0.85 | 85% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 4873.518 | 5685.771 | 5685.771 | 6904.1505 | 7310.277 | 8122.53 | 8122.53 | 8122.53 | 8122.53
12 | C211(a) | Temporary Erosion & Sedimentation Control | LS | 5050 | 1 | 1 | 6214.97 | 6214.97 | 6214.97 |  | 0% | 0.6 | 60% | 0.7 | 70% | 0.7 | 70% | 0.85 | 85% | 0.9 | 90% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 3728.982 | 4350.479 | 4350.479 | 5282.7245 | 5593.473 | 5593.473 | 6214.97 | 6214.97 | 6214.97
13 | C212 (a) | Clearing & Grubbing | LS | 11683.3333 | 1 | 1 | 15272.91 | 15272.91 | 15272.91 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 15272.91 | 15272.91 | 15272.91 | 15272.91 | 15272.91 | 15272.91 | 15272.91 | 15272.91 | 15272.91
14 | C213(a) | Removal & Stockpiling of Topsoil for Re-use | cum | 272 | 20 | 20 | 16.74 | 334.8 | 334.8 |  | 0% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 334.8 | 334.8 | 334.8 | 334.8 | 334.8 | 334.8 | 334.8 | 334.8 | 334.8
15 | C213(b) | General Earthworks (Cut) | cum | 14496.5549 | 1045 | 1045 | 17.07 | 17838.15 | 17838.15 |  | 0% | 426 | 40.77% | 1045 | 100% | 1045 | 100% | 1045 | 100% | 1045 | 100% | 1045 | 100% | 1045 | 100% | 1045 | 100% | 1045 | 100% | 0 | 7271.82 | 17838.15 | 17838.15 | 17838.15 | 17838.15 | 17838.15 | 17838.15 | 17838.15 | 17838.15
16 | C213(d) | Replace unsuitable material below subgrade with select material complete (Provisional) | cum | 922.3708 | 10 | 10 | 92.23 | 922.3 | 922.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 10 | 100% | 10 | 100% | 10 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 922.3 | 922.3 | 922.3
STORMWATER DRAINAGE
18 |  | Alteration to Exisiting Stormwater Structures | LS | 1036 | 1 | 1 | 1688.5 | 1688.5 | 1688.5 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 1688.5 | 1688.5 | 1688.5 | 1688.5 | 1688.5 | 1688.5 | 1688.5 | 1688.5 | 1688.5
19 | C224(h) | Concrete Barrier Kerb (B1) | m | 14424.1456 | 308 | 308 | 57.64 | 17753.12 | 17753.12 |  | 0% |  | 0% |  | 0% |  | 0% | 308 | 100% | 308 | 100% | 308 | 100% | 308 | 100% | 308 | 100% | 308 | 100% | 0 | 0 | 0 | 0 | 17753.12 | 17753.12 | 17753.12 | 17753.12 | 17753.12 | 17753.12
20 | C232(b) | 100mm slotted corrugated lastic pipe | m | 10119.7822 | 260 | 260 | 47.9 | 12454 | 12454 |  | 0% | 260 | 100% | 260 | 100% | 260 | 100% | 260 | 100% | 260 | 100% | 260 | 100% | 260 | 100% | 260 | 100% | 260 | 100% | 0 | 12454 | 12454 | 12454 | 12454 | 12454 | 12454 | 12454 | 12454 | 12454
20.2 | C232(c) | Cleanout Structures | ea | 858 | 6 | 6 | 175.99 | 1055.94 | 1055.94 |  | 0% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 0 | 1055.94 | 1055.94 | 1055.94 | 1055.94 | 1055.94 | 1055.94 | 1055.94 | 1055.94 | 1055.94
PAVEMENTS
21 | C241(a) | Supply stabilising Agent | tonne | 12138 | 34 | 34 | 439.35 | 14937.9 | 14937.9 |  | 0% | 3.6 | 10.59% | 34 | 100% | 34 | 100% | 34 | 100% | 34 | 100% | 34 | 100% | 34 | 100% | 34 | 100% | 34 | 100% | 0 | 1581.66 | 14937.9 | 14937.9 | 14937.9 | 14937.9 | 14937.9 | 14937.9 | 14937.9 | 14937.9
22 | C242(b) | Mixing & Spreading of stabilising agent | sqm | 12392.6621 | 1893 | 1893 | 7.66 | 14500.38 | 14500.38 |  | 0% | 200 | 10.57% | 1893 | 100% | 1893 | 100% | 1893 | 100% | 1893 | 100% | 1893 | 100% | 1893 | 100% | 1893 | 100% | 1893 | 100% | 0 | 1532 | 14500.38 | 14500.38 | 14500.38 | 14500.38 | 14500.38 | 14500.38 | 14500.38 | 14500.38
23 | C242 | Place only 2.3 | cum | 34836.6157 | 758 | 758 | 56.55 | 42864.9 | 42864.9 |  | 0% | 219 | 28.89% | 219 | 28.89% | 219 | 28.89% | 758 | 100% | 758 | 100% | 758 | 100% | 758 | 100% | 758 | 100% | 758 | 100% | 0 | 12384.45 | 12384.45 | 12384.45 | 42864.9 | 42864.9 | 42864.9 | 42864.9 | 42864.9 | 42864.9
24 | C242 | Place only 2.1 | cum | 14940.5907 | 282 | 282 | 65.2 | 18386.4 | 18386.4 |  | 0% |  | 0% |  | 0% |  | 0% | 94 | 33.33% | 282 | 100% | 282 | 100% | 282 | 100% | 282 | 100% | 282 | 100% | 0 | 0 | 0 | 0 | 6128.8 | 18386.4 | 18386.4 | 18386.4 | 18386.4 | 18386.4
25 | C242 | Special Item - Take up existing gravel, stabilise & relay as working platform | m3 | 34310.9398 | 483 | 483 | 58.78 | 28390.74 | 28390.74 |  | 0% | 483 | 100% | 483 | 100% | 483 | 100% | 483 | 100% | 483 | 100% | 483 | 100% | 483 | 100% | 483 | 100% | 483 | 100% | 0 | 28390.74 | 28390.74 | 28390.74 | 28390.74 | 28390.74 | 28390.74 | 28390.74 | 28390.74 | 28390.74
26 | C244(a) | AMC5 | sqm | 16638.237 | 1661 | 1661 | 12.33 | 20480.13 | 20480.13 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 20480.13 | 20480.13 | 20480.13 | 20480.13
27 | C245(c) | DG14 AC | tonne | 58305 | 195 | 195 | 367.97 | 71754.15 | 71754.15 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 195 | 100% | 195 | 100% | 195 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71754.15 | 71754.15 | 71754.15
MISCELLANEOUS
28 | C271(c) | Industrial Invert Crossing | ea | 40993.6877 | 15 | 15 | 3363.36 | 50450.4 | 50450.4 |  | 0% |  | 0% | 5 | 33.33% | 5 | 33.33% | 7 | 46.67% | 15 | 100% | 15 | 100% | 15 | 100% | 15 | 100% | 15 | 100% | 0 | 0 | 16816.8 | 16816.8 | 23543.52 | 50450.4 | 50450.4 | 50450.4 | 50450.4 | 50450.4
29 | C273(a) | Grass Seeding | sqm | 2695 | 1000 | 1000 | 3.32 | 3320 | 3320 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3320 | 3320 | 3320
30 | C306(a) | Sawcut bitumous pavement |  | 900 | 30 | 30 | 36.92 | 1107.6 | 1107.6 |  | 0% | 30 | 100% | 30 | 100% | 30 | 100% | 30 | 100% | 30 | 100% | 30 | 100% | 30 | 100% | 30 | 100% | 30 | 100% | 0 | 1107.6 | 1107.6 | 1107.6 | 1107.6 | 1107.6 | 1107.6 | 1107.6 | 1107.6 | 1107.6
31 | C306(b) | Remove existing pavement & dispose offsite | m2 | 3708.45 | 1661 | 1661 | 2.76 | 4584.36 | 4584.36 |  | 0% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 1661 | 100% | 0 | 4584.36 | 4584.36 | 4584.36 | 4584.36 | 4584.36 | 4584.36 | 4584.36 | 4584.36 | 4584.36
32 |  | Locate & Protect services | LS | 2025 | 1 | 1 | 2492.14 | 2492.14 | 2492.14 |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2492.14 | 2492.14 | 2492.14 | 2492.14 | 2492.14 | 2492.14 | 2492.14 | 2492.14 | 2492.14
33 |  | As Constructed Plans | LS | 4995 | 1 | 1 | 6147.28 | 6147.28 | 6147.28 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6147.28 | 6147.28 | 6147.28
|  | TOTAL NICOL ST | [5 empty] | 420755.73
34 |  | WRIGHTS ROAD (STRATHDICKIE)
35 | QP1 | Quality System Documents & Records | LS | 6500 | 1 | 1 | 7999.46 | 7999.46 | 7999.46 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 7999.46 | 7999.46 | 7999.46 | 7999.46 | 7999.46 | 7999.46 | 7999.46 | 7999.46 | 7999.46 | 7999.46
36 | QCP1 | Quality Verification & Control | LS | 15080 | 1 | 1 | 18558.75 | 18558.75 | 18558.75 | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 9279.375 | 18558.75 | 18558.75 | 18558.75 | 18558.75 | 18558.75 | 18558.75 | 18558.75 | 18558.75 | 18558.75
37 | C101(b) | Site Establishment & Disestablishment | LS | 13100 | 1 | 1 | 16121.99 | 16121.99 | 16121.99 | 0.8 | 80% | 0.8 | 80% | 0.9 | 90% | 0.9 | 90% | 0.9 | 90% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 12897.592 | 12897.592 | 14509.791 | 14509.791 | 14509.791 | 16121.99 | 16121.99 | 16121.99 | 16121.99 | 16121.99
38 |  | Preparation of Environmrntal Management Plan | LS | 3250 | 1 | 1 | 3999.73 | 3999.73 | 3999.73 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73 | 3999.73
ROAD & EARTHWORKS
39 | C201 (a) | Control of Traffic | LS | 10024 | 1 | 1 | 42109.16 | 42109.16 | 42109.16 | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 21054.58 | 42109.16 | 42109.16 | 42109.16 | 42109.16 | 42109.16 | 42109.16 | 42109.16 | 42109.16 | 42109.16
40 | C201 (b) | Provision of Temporary Roadways, Sidetracks & Detours | LS | 2100 | 1 | 1 | 2584.44 | 2584.44 | 2584.44 | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1292.22 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44
41 | C211(a) | Temporary Erosion & Sedimentation Control | LS | 10950 | 1 | 1 | 13476.02 | 13476.02 | 13476.02 | 0.7 | 70% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 9433.214 | 13476.02 | 13476.02 | 13476.02 | 13476.02 | 13476.02 | 13476.02 | 13476.02 | 13476.02 | 13476.02
42 | C212 (a) | Clearing & Grubbing | LS | 9066.6667 | 1 | 1 | 12041.25 | 12041.25 | 12041.25 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 12041.25 | 12041.25 | 12041.25 | 12041.25 | 12041.25 | 12041.25 | 12041.25 | 12041.25 | 12041.25 | 12041.25
43 | C212(a) | Special Item - Demolition of structures(concrete slabs, culverts pipes) | LS | 13800 | 1 | 1 | 18342.15 | 18342.15 | 18342.15 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 18342.15 | 18342.15 | 18342.15 | 18342.15 | 18342.15 | 18342.15 | 18342.15 | 18342.15 | 18342.15 | 18342.15
44 | C213(a) | Removal & Stockpiling of Topsoil for Re-use | cum | 7707.7708 | 700 | 700 | 13.55 | 9485 | 9485 | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 700 | 100% | 9485 | 9485 | 9485 | 9485 | 9485 | 9485 | 9485 | 9485 | 9485 | 9485
44.2 | C213(b) | General Earthworks (Cut) | cum | 10075.1575 | 1220 | 1220 | 10.16 | 12395.2 | 12395.2 | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 1220 | 100% | 12395.2 | 12395.2 | 12395.2 | 12395.2 | 12395.2 | 12395.2 | 12395.2 | 12395.2 | 12395.2 | 12395.2
45 | C213(c) | General Earthworks (Fill) | cum | 6310.5311 | 410 | 410 | 18.94 | 7765.4 | 7765.4 | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 410 | 100% | 7765.4 | 7765.4 | 7765.4 | 7765.4 | 7765.4 | 7765.4 | 7765.4 | 7765.4 | 7765.4 | 7765.4
46 | C213(d) | Replace unsuitable material below subgrade with select material complete (Provisional) | cum | 922.3708 | 10 | 10 | 92.23 | 922.3 | 922.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | C213(e) | Excavation in Roak (Unrippable) | cum | 425 | 5 | 5 | 85 | 425 | 425 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 |  | Minor Rural Accesses | ea | 13464 | 36 | 36 | 460.28 | 16570.08 | 16570.08 | 27 | 75% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 12427.56 | 16570.08 | 16570.08 | 16570.08 | 16570.08 | 16570.08 | 16570.08 | 16570.08 | 16570.08 | 16570.08
| C223(a) | STORMWATER DRAINAGE
49 | C220(a) | Excavation for stromwater structures | cum | 7362 | 300 | 300 | 30.2 | 9060 | 9060 | 214 | 71.33% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 6462.8 | 9060 | 9060 | 9060 | 9060 | 9060 | 9060 | 9060 | 9060 | 9060
50 |  | Removal / Demolition of Drainage Components | LS | 2100 | 1 | 1 | 2584.44 | 2584.44 | 2584.44 | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2067.552 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44 | 2584.44
51 | C221(a) | 375 RCP | m | 20796.5039 | 58 | 58 | 442.42 | 25660.36 | 25660.36 | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 58 | 100% | 25660.36 | 25660.36 | 25660.36 | 25660.36 | 25660.36 | 25660.36 | 25660.36 | 25660.36 | 25660.36 | 25660.36
52 | C221(a) | 450 RCP | m | 17462.72 | 44 | 44 | 489.71 | 21547.24 | 21547.24 | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 44 | 100% | 21547.24 | 21547.24 | 21547.24 | 21547.24 | 21547.24 | 21547.24 | 21547.24 | 21547.24 | 21547.24 | 21547.24
53 | C222(a) | Insitu RCBC Base Slab | cum | 28611.0196 | 57 | 57 | 617.74 | 35211.18 | 35211.18 | 27 | 47.37% | 57 | 100% | 57 | 100% | 57 | 100% | 57 | 100% | 57 | 100% | 57 | 100% | 57 | 100% | 57 | 100% | 57 | 100% | 16678.98 | 35211.18 | 35211.18 | 35211.18 | 35211.18 | 35211.18 | 35211.18 | 35211.18 | 35211.18 | 35211.18
69 | C222(b) | RCBC - 1200 x 450 | m | 71971.5 | 100 | 100 | 885.74 | 88574 | 88574 | 14.4 | 14.4% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 100 | 100% | 12754.656 | 88574 | 88574 | 88574 | 88574 | 88574 | 88574 | 88574 | 88574 | 88574
80 | C222(b) | RCBC - 1200 x 600 | m | 80010.8333 | 114 | 114 | 863.75 | 98467.5 | 98467.5 | 40.8 | 35.79% | 114 | 100% | 114 | 100% | 114 | 100% | 114 | 100% | 114 | 100% | 114 | 100% | 114 | 100% | 114 | 100% | 114 | 100% | 35241 | 98467.5 | 98467.5 | 98467.5 | 98467.5 | 98467.5 | 98467.5 | 98467.5 | 98467.5 | 98467.5
86 | C223(a) | Cast in situ headwalls | cum | 21000 | 35 | 35 | 738.41 | 25844.35 | 25844.35 |  | 0% |  | 0% | 28 | 80% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 0 | 0 | 20675.48 | 25844.35 | 25844.35 | 25844.35 | 25844.35 | 25844.35 | 25844.35 | 25844.35
87 | C223(a) | 375 HW | ea | 621 | 1 | 1 | 764.26 | 764.26 | 764.26 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 764.26 | 764.26 | 764.26 | 764.26 | 764.26 | 764.26 | 764.26 | 764.26
88 | C223(a) | 375 Sloping HW | ea | 15948 | 18 | 18 | 1090.39 | 19627.02 | 19627.02 | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 19627.02 | 19627.02 | 19627.02 | 19627.02 | 19627.02 | 19627.02 | 19627.02 | 19627.02 | 19627.02 | 19627.02
89 | C223(a) | 450 Sloping HW | ea | 18120 | 20 | 20 | 1115 | 22300 | 22300 | 10 | 50% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 11150 | 22300 | 22300 | 22300 | 22300 | 22300 | 22300 | 22300 | 22300 | 22300
90 | C224(h) | B1 Kerb | m | 3994.1526 | 48 | 48 | 102.41 | 4915.68 | 4915.68 |  | 0% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 48 | 100% | 0 | 4915.68 | 4915.68 | 4915.68 | 4915.68 | 4915.68 | 4915.68 | 4915.68 | 4915.68 | 4915.68
91 | C224(h) | SM5 Kerb | m | 4351.8967 | 62 | 62 | 86.38 | 5355.56 | 5355.56 |  | 0% |  | 0% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 62 | 100% | 0 | 0 | 5355.56 | 5355.56 | 5355.56 | 5355.56 | 5355.56 | 5355.56 | 5355.56 | 5355.56
92 | C231(b) | Sub-soil | m | 59161.7985 | 1520 | 1520 | 47.9 | 72808 | 72808 |  | 0% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 1520 | 100% | 0 | 72808 | 72808 | 72808 | 72808 | 72808 | 72808 | 72808 | 72808 | 72808
93 |  | PAVEMENTS
94 | C242 | Place only 2.3 | cum | 52163.0063 | 1135 | 1135 | 56.56 | 64195.6 | 64195.6 |  | 0% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 1135 | 100% | 0 | 64195.6 | 64195.6 | 64195.6 | 64195.6 | 64195.6 | 64195.6 | 64195.6 | 64195.6 | 64195.6
96 | C242 | Place Only 2.1 | cum | 63885.88 | 1490 | 1490 | 52.77 | 78627.3 | 78627.3 |  | 0% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 1490 | 100% | 0 | 78627.3 | 78627.3 | 78627.3 | 78627.3 | 78627.3 | 78627.3 | 78627.3 | 78627.3 | 78627.3
97 | C244 | First Coat AMC5 | sqm | 39396 | 9380 | 9380 | 5.17 | 48494.6 | 48494.6 |  | 0% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 0 | 48494.6 | 48494.6 | 48494.6 | 48494.6 | 48494.6 | 48494.6 | 48494.6 | 48494.6 | 48494.6
98 | C244 | Second Coat | sqm | 78595.02 | 9380 | 9380 | 10.31 | 96707.8 | 96707.8 |  | 0% |  | 0% |  | 0% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 9380 | 100% | 0 | 0 | 0 | 96707.8 | 96707.8 | 96707.8 | 96707.8 | 96707.8 | 96707.8 | 96707.8
99 | C261(a) | Pavement Markings - Longitudinal Lines | m | 6808 | 3404 | 3404 | 2.46 | 8373.84 | 8373.84 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 3404 | 100% | 3404 | 100% | 3404 | 100% | 3404 | 100% | 3404 | 100% | 0 | 0 | 0 | 0 | 0 | 8373.84 | 8373.84 | 8373.84 | 8373.84 | 8373.84
100 | C261(b) | Pavement Marking (Transverse etc) | LS | 2000 | 1 | 1 | 2461.37 | 2461.37 | 2461.37 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 2461.37 | 2461.37 | 2461.37 | 2461.37 | 2461.37
101 | C262(g) | Remove & reinstate exisiting signs & supports | LS | 840 | 1 | 1 | 1033.78 | 1033.78 | 1033.78 |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 1033.78 | 1033.78 | 1033.78 | 1033.78 | 1033.78 | 1033.78
102 | C262 | Supply & Install all signs complete | ea | 5804.5 | 26 | 26 | 274.75 | 7143.5 | 7143.5 |  | 0% |  | 0% |  | 0% |  | 0% | 25 | 96.15% | 26 | 100% | 26 | 100% | 26 | 100% | 26 | 100% | 26 | 100% | 0 | 0 | 0 | 0 | 6868.75 | 7143.5 | 7143.5 | 7143.5 | 7143.5 | 7143.5
103 | C263(a) | Guide Posts | ea | 4585 | 131 | 131 | 43.07 | 5642.17 | 5642.17 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 131 | 100% | 131 | 100% | 131 | 100% | 131 | 100% | 131 | 100% | 0 | 0 | 0 | 0 | 0 | 5642.17 | 5642.17 | 5642.17 | 5642.17 | 5642.17
104 |  | MISCELLANEOUS
105 | C273(a) | Grass seeding | sqm | 24794 | 9200 | 9200 | 3.32 | 30544 | 30544 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 9200 | 100% | 9200 | 100% | 9200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30544 | 30544 | 30544
106 | C306(a) | Sawcut Bitumen pavement | m | 1590 | 53 | 53 | 36.92 | 1956.76 | 1956.76 |  | 0% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 53 | 100% | 0 | 1956.76 | 1956.76 | 1956.76 | 1956.76 | 1956.76 | 1956.76 | 1956.76 | 1956.76 | 1956.76
107 |  | Locate & Protect Services | LS | 2430 | 1 | 1 | 2990.57 | 2990.57 | 2990.57 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 2990.57 | 2990.57 | 2990.57 | 2990.57 | 2990.57 | 2990.57 | 2990.57 | 2990.57 | 2990.57 | 2990.57
108 |  | As Constructed Plans | LS | 8325 | 1 | 1 | 10245.46 | 10245.46 | 10245.46 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10245.46 | 10245.46 | 10245.46
|  | TOTAL WRIGHTS ROAD | [5 empty] | 973932.27
Variations
109 | PV01 | Principal Supply of Precast Conrete Items | each | -116891.2 | 1 | 1 | -116891.2 | -116891.2 | -116891.2 | 0.419 | 41.9% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | -48977.4128 | -116891.2 | -116891.2 | -116891.2 | -116891.2 | -116891.2 | -116891.2 | -116891.2 | -116891.2 | -116891.2
110 | PV02 | Additional 375RCP at chainage 230. | each | 991.3207 | 1 | 1 | 3695.45 | 3695.45 | 3695.45 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 3695.45 | 3695.45 | 3695.45 | 3695.45 | 3695.45 | 3695.45 | 3695.45 | 3695.45
112 | PV04 | Revised Seal Design | each | 10735.41 | 1 | 1 | 10224.2 | 10224.2 | 10224.2 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 10224.2 | 10224.2 | 10224.2 | 10224.2 | 10224.2 | 10224.2 | 10224.2 | 10224.2
113 | PV05 | Shape table drain chainage 523-725 | each | 2072.8398 | 1 | 1 | 2550.16 | 2550.16 | 2550.16 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 2550.16 | 2550.16 | 2550.16 | 2550.16 | 2550.16 | 2550.16 | 2550.16 | 2550.16
114 | PV06 | Nicol St - Revised pavement design | each | -36828.5961 | 1 | 1 | -45576.66 | -45576.66 | -45576.66 |  | 0% |  | 0% | 0.18 | 18% | 0.18 | 18% | 0.88 | 88% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | -8203.7988 | -8203.7988 | -40107.4608 | -45576.66 | -45576.66 | -45576.66 | -45576.66 | -45576.66
115 | PV07 | Nicol St - Additional drain outlet | each | 3241.2213 | 1 | 1 | 4171.66 | 4171.66 | 4171.66 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 4171.66 | 4171.66 | 4171.66 | 4171.66 | 4171.66 | 4171.66 | 4171.66 | 4171.66
116 | PV08 | Nicol St - Subgrade pavement repairs | each | 10385.4605 | 1 | 1 | 10033.79 | 10033.79 | 10033.79 |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 10033.79 | 10033.79 | 10033.79 | 10033.79 | 10033.79 | 10033.79 | 10033.79 | 10033.79
117 | PV09 | Nicol St - Additional works to water services | each | 13500 | 1 | 1 | 15224 | 15224 | 15224 |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 15224 | 15224 | 15224 | 15224 | 15224 | 15224
118 | PV10 | Wright Rd - Drainage works ch1300 | each | 5796 | 1 | 1 | 6610 | 6610 | 6610 |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 6610 | 6610 | 6610 | 6610 | 6610 | 6610
119 | PV11 | Wright Rd - Additional culvert no.06 | each | 2127.1546 | 1 | 1 | 4698.3 | 4698.3 | 4698.3 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.3 | 4698.3
120 | PV12 | Wright Rd - Driveway works | each | 9750 | 1 | 1 | 11090 | 11090 | 11090 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11090 | 11090 | 11090
121 | PV13 | Nicol St - Kerb ramp reconstruction | each | 2270 | 2 | 2 | 2435 | 4870 | 4870 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 4870 | 4870 | 4870 | 4870 | 4870
122 | PV14 | Nicol St - Removal of Unsuitable - Telstra Cable | each | 3117.6134 | 1 | 1 | 5695.71 | 5695.71 | 5695.71 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5695.71 | 5695.71 | 5695.71
124 | PV15 a | Wright Road - Scour Protection | each | 8991.2997 | 18 | 18 | 1370 | 24660 | 24660 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 18 | 100% | 18 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24660 | 24660
125 | PV15 b | Wright Road - Drain Widening - Lot 130 | each | 3303.3303 | 1 | 1 | 5510 | 5510 | 5510 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5510 | 5510 | 5510
126 | PV15 c | Wright Road - Batter Protection - Lot 130 | each | 2641.5909 | 1 | 1 | 4240 | 4240 | 4240 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4240 | 4240
127 | PV16 | Culvert Extension - Lot 30 | m | 3181.7676 | 2.4 | 2.4 | 8940 | 21456 | 21456 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 41.67% | 1 | 41.67% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8940 | 8940
128 | PV17 | Additional Drainage Works - Wright Road | item | 1238.7489 | 1 | 1 | 2000 | 2000 | 2000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000
|  | Total, all contract items and variations |  | 1047448.2045 |  |  |  | 1368949.41 | 1368949.41 | [20 empty] | 243615.4962 | 797937.18 | 907815.2262 | 1009691.8962 | 1079972.1662 | 1139547.444 | 1161845.6055 | 1310547.81 | 1353086.11 | 1355086.11

## Portfolio WBS
Portfolio WBS | Description | Quantity | UOM | BAC | BAC Rate | Final Qty (AQ) | Final Cost (AC) | Final Rate | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 124 | hrs | 22940 | 185 | 121 | 23188.92 | 185.6942 | 12 | 2220 | 0 | 720 | 0 | 24 | 4440 | 38 | 7669.1 | 7030 | 56 | 10360 | 62 | 12165 | 11470 | 68 | 12580 | 70 | 13592.52 | 12950 | 84 | 15540 | 70 | 13592.52 | 12950 | 96 | 17760 | 81 | 15710.37 | 14985 | 104 | 19240 | 100 | 19270.52 | 18500 | 124 | 22940 | 121 | 20342.92 | 22385 | 124 | 22940 | 121 | 20567.32 | 22385 | 124 | 22940 | 121 | 23188.92 | 22385 | 124 | 22940 | 121 | 23188.92 | 22385 | 124 | 22940 | 121 | 23188.92 | 22940
13 | QA Testing | 1 | item | 33460 | 33460 | 1 | 5728.34 | 6448 | 0.1 | 3346 | 0.1 | 0 | 3346 | 0.2 | 6692 | 0.25 | 1600 | 8365 | 0.4 | 13384 | 0.4 | 2769.54 | 13384 | 0.6 | 20076 | 0.4 | 2769.54 | 13384 | 0.7 | 23422 | 0.75 | 4151.44 | 25095 | 0.9 | 30114 | 0.75 | 4151.44 | 25095 | 1 | 33460 | 1 | 5728.34 | 33460 | 1 | 33460 | 1 | 5728.34 | 33460 | 1 | 33460 | 1 | 5728.34 | 33460 | 1 | 33460 | 1 | 5728.34 | 33460 | 1 | 33460 | 1 | 5728.34 | 33460 | 1 | 33460 | 1 | 5728.34 | 33460
15 | Service Locations | 18 | hrs | 4455 | 247.5 | 3.5 | 857.5 | 245.1429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 130 | 0 | 18 | 4455 | 0 | 130 | 0 | 18 | 4455 | 0 | 130 | 0 | 18 | 4455 | 0 | 130 | 0 | 18 | 4455 | 3.5 | 857.5 | 866.25 | 18 | 4455 | 3.5 | 857.5 | 866.25 | 18 | 4455 | 3.5 | 857.5 | 866.25 | 18 | 4455 | 3.5 | 857.5 | 866.25 | 18 | 4455 | 3.5 | 857.5 | 4455
22 | Disposal offsite - Clearing waste | 1 | item | 20750 | 20750 | 1 | 13933.58 | 13934 | 0 | 0 | 0 | 0 | 0 | 0.5 | 10375 | 0.25 | 3641.75 | 5187.5 | 1 | 20750 | 1 | 13933.58 | 20750 | 1 | 20750 |  | 13933.58 | 0 | 1 | 20750 |  | 13933.58 | 0 | 1 | 20750 |  | 13933.58 | 0 | 1 | 20750 |  | 13933.58 | 0 | 1 | 20750 | 1 | 13933.58 | 20750 | 1 | 20750 | 1 | 13933.58 | 20750 | 1 | 20750 | 1 | 13933.58 | 20750 | 1 | 20750 | 1 | 13933.58 | 20750 | 1 | 20750 | 1 | 13933.58 | 20750
31 | Strip Topsoil to Stockpile | 720 | m3 | 7979.7708 | 11.083 | 730 | 72746.43 | 99.6521 | 700 | 7758.1105 | 650 | 65243.68 | 7203.9597 | 700 | 7758.1105 | 700 | 70756.18 | 7758.1105 | 700 | 7758.1105 | 700 | 70756.18 | 7758.1105 | 700 | 7758.1105 | 700 | 70756.18 | 7758.1105 | 700 | 7758.1105 | 700 | 70756.18 | 7758.1105 | 700 | 7758.1105 | 720 | 71161.18 | 7979.7708 | 720 | 7979.7708 | 720 | 71161.18 | 7979.7708 | 720 | 7979.7708 | 730 | 71161.18 | 8090.6009 | 720 | 7979.7708 | 730 | 72746.43 | 8090.6009 | 720 | 7979.7708 | 730 | 72746.43 | 8090.6009 | 720 | 7979.7708 | 730 | 72746.43 | 8090.6009 | 720 | 7979.7708 | 730 | 72746.43 | 7979.7708
41 | Demolition works | 1 | item | 15900 | 15900 | 1 | 5217.475 | 5217 | 0 | 0 | 0 | 0 | 0 | 0.5 | 7950 | 0.5 | 2852.475 | 7950 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900 | 1 | 15900 | 1 | 5217.475 | 15900
53 | Cut to Spoil | 2265 | m3 | 62682.6249 | 27.6744 | 2265 | 43727.4897 | 19.3055 | 200 | 5534.8896 | 60 | 1276.8 | 1660.4669 | 1800 | 49814.0065 | 1580 | 30926.475 | 43725.6279 | 1800 | 49814.0065 | 1730 | 33731.475 | 47876.7952 | 1800 | 49814.0065 | 1730 | 33731.475 | 47876.7952 | 2050 | 56732.6185 | 1980 | 38619.5897 | 54795.4072 | 2265 | 62682.6249 | 2060 | 40212.4897 | 57009.363 | 2265 | 62682.6249 | 2060 | 40527.4897 | 57009.363 | 2265 | 62682.6249 | 2265 | 42327.4897 | 62682.6249 | 2265 | 62682.6249 | 2265 | 43727.4897 | 62682.6249 | 2265 | 62682.6249 | 2265 | 43727.4897 | 62682.6249 | 2265 | 62682.6249 | 2265 | 43727.4897 | 62682.6249 | 2265 | 62682.6249 | 2265 | 43727.4897 | 62682.6249
55 | Place General Fill | 410 | m3 | 6310.5311 | 15.3915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 0 | 410 | 6310.5311 | 0 | 0 | 6310.5311
61 | Subgrade Preparation | 11813 | m2 | 13464 | 1.1398 | 11813 | 26831.6 | 2.2714 | 4000 | 4559.0451 | 0 | 0 | 0 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464 | 11813 | 13464 | 11813 | 26831.6 | 13464
62 | Place & Compact Gravel | 8796 | tonne | 128112.8632 | 14.5649 | 8796 | 159414.47 | 18.1235 | 1000 | 14564.9003 | 56 | 1127.92 | 815.6344 | 6196 | 90244.1224 | 6180 | 114398.01 | 90011.084 | 6196 | 90244.1224 | 7370 | 134531.66 | 107343.3153 | 6196 | 90244.1224 | 7580 | 138382.37 | 110401.9444 | 8000 | 116519.2025 | 8635 | 152631.495 | 125767.9142 | 8796 | 128112.8632 | 8796 | 158813.52 | 128112.8632 | 8796 | 128112.8632 | 8796 | 158990.27 | 128112.8632 | 8796 | 128112.8632 | 8796 | 159414.47 | 128112.8632 | 8796 | 128112.8632 | 8796 | 159414.47 | 128112.8632 | 8796 | 128112.8632 | 8796 | 159414.47 | 128112.8632 | 8796 | 128112.8632 | 8796 | 159414.47 | 128112.8632 | 8796 | 128112.8632 | 8796 | 159414.47 | 128112.8632
63 | Trim All Layers | 23626 | m2 | 10504.9636 | 0.44464 | 23626 | 7087.515 | 0.30001 | 4000 | 1778.5429 | 0 | 0 | 0 | 18760 | 8341.3661 | 18760 | 3453.6 | 8341.3661 | 18760 | 8341.3661 | 18760 | 3453.6 | 8341.3661 | 18760 | 8341.3661 | 18760 | 3453.6 | 8341.3661 | 21190 | 9421.8309 | 21190 | 5602.815 | 9421.8309 | 23626 | 10504.9636 | 21190 | 5602.815 | 9421.8309 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636 | 23626 | 10504.9636 | 23626 | 7087.515 | 10504.9636
64 | Sweep & Prime / Primer seal or Seal | 20421 | m2 | 145692.1931 | 7.1344 | 20421 | 131081.82 | 6.419 | 0 | 0 | 0 | 0 | 0 | 9380 | 66920.9525 | 9380 | 69005.5 | 66920.9525 | 9380 | 66920.9525 | 9380 | 69005.5 | 66920.9525 | 18760 | 133841.905 | 18760 | 125506.06 | 133841.905 | 18760 | 133841.905 |  | 125506.06 | 0 | 18760 | 133841.905 |  | 125506.06 | 0 | 20421 | 145692.1931 |  | 125506.06 | 0 | 20421 | 145692.1931 | 20421 | 125506.06 | 145692.1931 | 20421 | 145692.1931 | 20421 | 131081.82 | 145692.1931 | 20421 | 145692.1931 | 20421 | 131081.82 | 145692.1931 | 20421 | 145692.1931 | 20421 | 131081.82 | 145692.1931 | 20421 | 145692.1931 | 20421 | 131081.82 | 145692.1931
65 | Asphalt | 195 | tonne | 58305 | 299 | 267.4 | 80088.974 | 299.5101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 58305 | 267.4 | 0 | 79952.6 | 195 | 58305 | 267.4 | 80088.974 | 79952.6 | 195 | 58305 | 267.4 | 80088.974 | 79952.6 | 195 | 58305 | 267.4 | 80088.974 | 79952.6 | 195 | 58305 | 267.4 | 80088.974 | 58305
66 | Linemarking | 1 | item | 8808 | 8808 | 1 | 2580 | 2580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8808 | 0 | 0 | 0 | 1 | 8808 | 1 | 2580 | 8808 | 1 | 8808 | 1 | 2580 | 8808 | 1 | 8808 | 1 | 2580 | 8808 | 1 | 8808 | 1 | 2580 | 8808 | 1 | 8808 | 1 | 2580 | 8808 | 1 | 8808 | 1 | 2580 | 8808 | 1 | 8808 | 1 | 2580 | 8808
67 | Install Road Furniture | 1 | item | 11229.5 | 11229.5 | 1 | 6897.4 | 22190 | 0.5 | 5614.75 | 0.5 | 0 | 5614.75 | 0.5 | 5614.75 | 0.55 | 0 | 6176.225 | 0.5 | 5614.75 | 0.55 | 810 | 6176.225 | 1 | 11229.5 | 0.75 | 4862.5 | 8422.125 | 1 | 11229.5 | 1 | 6261.1 | 11229.5 | 1 | 11229.5 | 1 | 6826.7 | 11229.5 | 1 | 11229.5 | 1 | 6897.4 | 11229.5 | 1 | 11229.5 | 1 | 6897.4 | 11229.5 | 1 | 11229.5 | 1 | 6897.4 | 11229.5 | 1 | 11229.5 | 1 | 6897.4 | 11229.5 | 1 | 11229.5 | 1 | 6897.4 | 11229.5 | 1 | 11229.5 | 1 | 6897.4 | 11229.5
68 | Insitu Stabilisation of Subgrade | 1893 | m2 | 30573.1555 | 16.1506 | 1893 | 47892.13 | 25.2995 | 0 | 0 | 0 | 225 | 0 | 350 | 5652.7229 | 655 | 16695.645 | 10578.6671 | 1893 | 30573.1555 | 1893 | 47297.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47297.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47297.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47297.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555 | 1893 | 30573.1555 | 1893 | 47892.13 | 30573.1555
71 | Place Kerb & Channel / Inverts | 418 | m | 23438.71 | 56.0735 | 418 | 30901.95 | 73.9282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 48 | 2691.5265 | 48 | 3520 | 2691.5265 | 233 | 13065.1183 | 48 | 3520 | 2691.5265 | 418 | 23438.71 | 48 | 4081.25 | 2691.5265 | 418 | 23438.71 | 86 | 6346.95 | 4822.3183 | 418 | 23438.71 | 418 | 30901.95 | 23438.71 | 418 | 23438.71 | 418 | 30901.95 | 23438.71 | 418 | 23438.71 | 418 | 30901.95 | 23438.71 | 418 | 23438.71 | 418 | 30901.95 | 23438.71 | 418 | 23438.71 | 418 | 30901.95 | 23438.71 | 418 | 23438.71 | 418 | 30901.95 | 23438.71
72 | Form & Pour Headwalls | 35 | m3 | 21000 | 600 | 35 | 6696.985 | 191.3429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 12000 | 18 | 3440.325 | 10800 | 35 | 21000 | 25 | 4851.985 | 15000 | 35 | 21000 | 25 | 4851.985 | 15000 | 35 | 21000 | 25 | 4851.985 | 15000 | 35 | 21000 | 25 | 4851.985 | 15000 | 35 | 21000 | 35 | 4851.985 | 21000 | 35 | 21000 | 35 | 4851.985 | 21000 | 35 | 21000 | 35 | 6696.985 | 21000 | 35 | 21000 | 35 | 6696.985 | 21000 | 35 | 21000 | 35 | 6696.985 | 21000
73 | Form & Place Footpath | 517 | m2 | 15824.8109 | 30.6089 | 517 | 11570 | 22.3791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 517 | 15824.8109 | 160 | 3600 | 4897.427 | 517 | 15824.8109 | 517 | 11570 | 15824.8109 | 517 | 15824.8109 | 517 | 11570 | 15824.8109 | 517 | 15824.8109 | 517 | 11570 | 15824.8109 | 517 | 15824.8109 | 517 | 11570 | 15824.8109 | 517 | 15824.8109 | 517 | 11570 | 15824.8109
75 | Saw Cutting/Joint sealing | 83 | m | 3526 | 42.4819 | 83 | 4008.49 | 48.2892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 254.8916 | 6 | 269.28 | 254.8916 | 6 | 254.8916 | 6 | 269.28 | 254.8916 | 83 | 3526 | 15 | 711.18 | 637.2289 | 83 | 3526 | 83 | 4008.49 | 3526 | 83 | 3526 | 83 | 4008.49 | 3526 | 83 | 3526 | 83 | 4008.49 | 3526 | 83 | 3526 | 83 | 4008.49 | 3526 | 83 | 3526 | 83 | 4008.49 | 3526 | 83 | 3526 | 83 | 4008.49 | 3526 | 83 | 3526 | 83 | 4008.49 | 3526
81 | > 450 | 102.48 | m | 41052.6443 | 400.5918 | 102 | 34010.8 | 327.8529 | 50 | 20029.5884 | 43.92 | 14553.385 | 17593.9904 | 102.48 | 41052.6443 | 102.48 | 32464.275 | 41052.6443 | 102.48 | 41052.6443 | 102.48 | 32464.275 | 41052.6443 | 102.48 | 41052.6443 | 102.48 | 32464.275 | 41052.6443 | 102.48 | 41052.6443 | 102.48 | 33440.8 | 41052.6443 | 102.48 | 41052.6443 | 102.48 | 33440.8 | 41052.6443 | 102.48 | 41052.6443 | 102.48 | 33440.8 | 41052.6443 | 102.48 | 41052.6443 | 102 | 33440.8 | 40860.3603 | 102.48 | 41052.6443 | 102 | 33440.8 | 40860.3603 | 102.48 | 41052.6443 | 102 | 33440.8 | 40860.3603 | 102.48 | 41052.6443 | 102 | 33440.8 | 40860.3603 | 102.48 | 41052.6443 | 102 | 34010.8 | 41052.6443
87 | Supply & Place Subsoil Drainage | 1780 | m | 63795.6598 | 35.8403 | 1780 | 19291.025 | 10.8376 | 0 | 0 | 0 | 0 | 0 | 500 | 17920.1291 | 875 | 9624.465 | 31360.226 | 1410 | 50534.7642 | 930 | 10214.465 | 33331.4402 | 1780 | 63795.6598 | 930 | 10214.465 | 33331.4402 | 1780 | 63795.6598 | 1660 | 18262.525 | 59494.8288 | 1780 | 63795.6598 | 1660 | 18262.525 | 59494.8288 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598 | 1780 | 63795.6598 | 1780 | 19291.025 | 63795.6598
103 | Water Sub-Contractor | 1 | item | 13500 | 13500 | 1 | 13840 | 13840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500 | 1 | 13500 | 1 | 13840 | 13500
121 | Landscaping Sub-contractors | 10200 | m2 | 27489 | 2.695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 10200 | 27489 |  | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 0 | 10200 | 27489 | 0 | 0 | 27489
141 | Traffic Controllers | 933 | hrs | 27953.5455 | 29.9609 | 110 | 21548.605 | 56.8636 | 200 | 5992.1855 | 45 | 7903.41 | 1348.2417 | 400 | 11984.371 | 72 | 15179.52 | 2157.1868 | 600 | 17976.5566 | 76 | 15497.67 | 2277.0305 | 800 | 23968.7421 | 76 | 15497.67 | 2277.0305 | 840 | 25167.1792 | 100 | 19127.455 | 2996.0928 | 880 | 26365.6163 | 110 | 21548.605 | 3295.702 | 920 | 27564.0534 | 110 | 21548.605 | 3295.702 | 933 | 27953.5455 | 110 | 21548.605 | 3295.702 | 933 | 27953.5455 | 110 | 21548.605 | 3295.702 | 933 | 27953.5455 | 110 | 21548.605 | 3295.702 | 933 | 27953.5455 | 110 | 21548.605 | 3295.702 | 933 | 27953.5455 | 110 | 21548.605 | 27953.5455
151 | Supply & Place Silt fences | 560 | m | 16000 | 28.5714 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 |  | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 0 | 560 | 16000 | 0 | 0 | 16000
181 | Supply & Place Box Culverts | 214 | m | 64479.5137 | 301.3061 | 214 | 59053.1702 | 275.9486 | 70 | 21091.4297 | 70 | 19480.19 | 21091.4297 | 160 | 48208.9822 | 135 | 38187.17 | 40676.3288 | 214 | 64479.5137 | 154 | 42587.17 | 46401.1454 | 214 | 64479.5137 | 206 | 56447.17 | 62069.0646 | 214 | 64479.5137 | 206 | 56447.17 | 62069.0646 | 214 | 64479.5137 | 206 | 56447.17 | 62069.0646 | 214 | 64479.5137 | 206 | 56447.17 | 62069.0646 | 214 | 64479.5137 | 214 | 56447.17 | 64479.5137 | 214 | 64479.5137 | 214 | 56447.17 | 64479.5137 | 214 | 64479.5137 | 214 | 56447.17 | 64479.5137 | 214 | 64479.5137 | 214 | 59053.1702 | 64479.5137 | 214 | 64479.5137 | 214 | 59053.1702 | 64479.5137
182 | Supply Base Slabs | 57 | m3 | 9379.8 | 164.5579 | 57 | 11490 | 338.0351 | 28 | 4607.6211 | 23 | 0 | 3784.8316 | 53 | 8721.5684 | 53 | 0 | 8721.5684 | 53 | 8721.5684 | 53 | 11490 | 8721.5684 | 53 | 8721.5684 | 53 | 11490 | 8721.5684 | 53 | 8721.5684 | 53 | 11490 | 8721.5684 | 53 | 8721.5684 | 53 | 11490 | 8721.5684 | 53 | 8721.5684 | 53 | 11490 | 8721.5684 | 57 | 9379.8 | 57 | 11490 | 9379.8 | 57 | 9379.8 | 57 | 11490 | 9379.8 | 57 | 9379.8 | 57 | 11490 | 9379.8 | 57 | 9379.8 | 57 | 11490 | 9379.8 | 57 | 9379.8 | 57 | 11490 | 9379.8
902 | Project Supervision | 26 | week | 55235 | 2124.4231 | 17 | 49348.4995 | 2869.0588 | 4 | 8497.6923 | 4.4 | 12970.12 | 9347.4615 | 12 | 25493.0769 | 12.2 | 35735.185 | 25917.9615 | 15 | 31866.3462 | 13.52 | 39554.665 | 28722.2 | 17 | 36115.1923 | 13.5 | 39899.615 | 28679.7115 | 19 | 40364.0385 | 14.7 | 43042.1095 | 31229.0192 | 22 | 46737.3077 | 16 | 46146.6595 | 33990.7692 | 26 | 55235 | 16.5 | 47158.2945 | 35052.9808 | 26 | 55235 | 17 | 47409.6295 | 36115.1923 | 26 | 55235 | 17 | 47625.0595 | 36115.1923 | 26 | 55235 | 17 | 47625.0595 | 36115.1923 | 26 | 55235 | 17 | 48774.0195 | 36115.1923 | 26 | 55235 | 17 | 49348.4995 | 55235
903 | Project Facilities | 13 | week | 16250 | 1250 | 13 | 11252.71 | 614.7692 | 2 | 2500 | 2 | 729.39 | 2500 | 6 | 7500 | 6 | 4316.95 | 7500 | 12 | 15000 | 10 | 9551.79 | 12500 | 13 | 16250 | 10 | 9892.69 | 12500 | 13 | 16250 | 10 | 10745.11 | 12500 | 13 | 16250 | 10 | 11027.91 | 12500 | 13 | 16250 | 10 | 11133.96 | 12500 | 13 | 16250 | 13 | 11133.96 | 16250 | 13 | 16250 | 13 | 11133.96 | 16250 | 13 | 16250 | 13 | 11133.96 | 16250 | 13 | 16250 | 13 | 11252.71 | 16250 | 13 | 16250 | 13 | 11252.71 | 16250
904 | Project Insurance, Fees & Levies | 1 | item | 25500 | 25500 | 1 | 5722.72 | 5723 | 0.5 | 12750 | 0.75 | 3922 | 19125 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500 | 1 | 25500 | 1 | 5722.72 | 25500
905 | small tools | 1 | item | 0 | 0 | 1 | 5849.178 | 5849 | 0.2 | 0 | 0.2 | 3377.058 | 0 | 0.3 | 0 | 0.3 | 3810.448 | 0 | 0.4 | 0 | 0.4 | 4399.798 | 0 | 0.5 | 0 | 0.5 | 4469.298 | 0 | 0.7 | 0 | 0.7 | 5479.218 | 0 | 0.9 | 0 | 0.9 | 5744.188 | 0 | 1 | 0 | 1 | 5837.818 | 0 | 1 | 0 | 1 | 5837.818 | 0 | 1 | 0 | 1 | 5837.818 | 0 | 1 | 0 | 1 | 5837.818 | 0 | 1 | 0 | 1 | 5849.178 | 0 | 1 | 0 | 1 | 5849.178 | 0
907 | Site Establishment | 1 | item | 13800 | 13800 | 1 | 10703.96 | 10704 | 0.5 | 6900 | 0.5 | 5153.88 | 6900 | 1 | 13800 | 0.9 | 9205.99 | 12420 | 1 | 13800 | 0.95 | 10026.46 | 13110 | 1 | 13800 | 1 | 10026.46 | 13800 | 1 | 13800 | 1 | 10401.46 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800 | 1 | 13800 | 1 | 10703.96 | 13800
C25 | 25 Mpa | 100 | m3 | 16421.2284 | 164.2123 | 24 | 3904.88 | 171.625 | 0 | 0 | 0 | 0 | 0 | 50 | 8210.6142 | 7 | 1214.48 | 1149.486 | 80 | 13136.9827 | 9.6 | 1649.48 | 1576.4379 | 80 | 13136.9827 | 9.6 | 1649.48 | 1576.4379 | 80 | 13136.9827 | 11 | 1649.48 | 1806.3351 | 80 | 13136.9827 | 16 | 2623.88 | 2627.3965 | 80 | 13136.9827 | 16 | 2623.88 | 2627.3965 | 100 | 16421.2284 | 24 | 2623.88 | 3941.0948 | 100 | 16421.2284 | 24 | 3904.88 | 3941.0948 | 100 | 16421.2284 | 24 | 3904.88 | 3941.0948 | 100 | 16421.2284 | 24 | 3904.88 | 3941.0948 | 100 | 16421.2284 | 24 | 3904.88 | 16421.2284
C32 | 32 Mpa | 120 | m3 | 26112.3192 | 217.6027 | 259 | 46335.42 | 178.0734 | 40 | 8704.1064 | 23.5 | 4207.2 | 5113.6625 | 80 | 17408.2128 | 115 | 20954.32 | 25024.3059 | 80 | 17408.2128 | 136 | 24312.4 | 29593.9618 | 80 | 17408.2128 | 139 | 24869.2 | 30246.7697 | 80 | 17408.2128 | 166 | 29756.4 | 36122.0416 | 80 | 17408.2128 | 249 | 44698.4 | 54183.0623 | 117 | 25459.5112 | 254 | 45508 | 55271.0756 | 120 | 26112.3192 | 259 | 45508 | 56359.0889 | 120 | 26112.3192 | 259 | 45508 | 56359.0889 | 120 | 26112.3192 | 259 | 45666 | 56359.0889 | 120 | 26112.3192 | 259 | 46335.42 | 56359.0889 | 120 | 26112.3192 | 259 | 46335.42 | 26112.3192
CKM | Kerb Mix | 43 | m3 | 8427.7248 | 195.9936 | 30 | 5390.78 | 179.7 | 0 | 0 | 0 | 31.28 | 0 | 0 | 0 | 0 | 31.28 | 0 | 4.8 | 940.7693 | 0 | 31.28 | 0 | 25 | 4899.84 | 0 | 31.28 | 0 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 5879.808 | 43 | 8427.7248 | 30 | 5390.78 | 8427.7248
CSA | Cement Powder (Stabilising) | 34 | tonne | 22220.8224 | 653.5536 | 37 | 12410 | 335.4054 | 0 | 0 | 0 | 0 | 0 | 12 | 7842.6432 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 24181.4832 | 34 | 22220.8224 | 37 | 12410 | 22220.8224
QM2.3 | 2.3 | 100 | tonne | 0 | 0 | 80.66 | 3182.03 | 39.4495 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 80.66 | 3182.03 | 0 | 100 | 0 | 80.66 | 3182.03 | 0 | 100 | 0 | 80.66 | 3182.03 | 0 | 100 | 0 | 80.66 | 3182.03 | 0 | 100 | 0 | 80.66 | 3182.03 | 0 | 100 | 0 | 80.66 | 3182.03 | 0 | 100 | 0 | 80.66 | 3182.03 | 0
QMS | Sand | 455 | m3 | 11300.5768 | 24.8364 | 375 | 4651.9454 | 24.8827 | 250 | 6209.1082 | 188 | 0 | 4669.2493 | 380 | 9437.8444 | 295 | 2674.7594 | 7326.7476 | 380 | 9437.8444 | 295 | 2674.7594 | 7326.7476 | 380 | 9437.8444 | 330 | 3589.7194 | 8196.0228 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 9313.6622 | 455 | 11300.5768 | 375 | 4651.9454 | 11300.5768
RSM | Mesh | 1032 | m2 | 10988.8547 | 10.6481 | 1032 | 15444.99 | 7.4293 | 600 | 6388.869 | 440 | 11024.79 | 4685.1706 | 600 | 6388.869 | 512 | 11604.79 | 5451.8349 | 600 | 6388.869 | 512 | 11604.79 | 5451.8349 | 600 | 6388.869 | 512 | 11604.79 | 5451.8349 | 1032 | 10988.8547 | 748 | 13347.29 | 7964.79 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547 | 1032 | 10988.8547 | 1032 | 15444.99 | 10988.8547
SWC | RCBC | 2 | each | 6535 | 3267.5 | 2 | 920 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6535 | 2 | 0 | 6535 | 2 | 6535 | 2 | 0 | 6535 | 2 | 6535 | 2 | 0 | 6535 | 2 | 6535 | 2 | 920 | 6535 | 2 | 6535 | 2 | 920 | 6535
SWH | Headwalls | 2 | each | 1250 | 625 | 2 | 1141.81 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1250 | 2 | 0 | 1250 | 2 | 1250 | 2 | 551.81 | 1250 | 2 | 1250 | 2 | 1141.81 | 1250 | 2 | 1250 | 2 | 1141.81 | 1250 | 2 | 1250 | 2 | 1141.81 | 1250
SWP | RCP | 2 | each | 49.392 | 24.696 | 2 | 5576.5 | 448.5 | 0 | 0 | 0 | 4679.5 | 0 | 2 | 49.392 | 1 | 5159.5 | 24.696 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392 | 2 | 49.392 | 2 | 5576.5 | 49.392

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | Total | Portfolio WBS
Portfolio WBS 011
2011-09-30 | Survey Team Inv - CBW 69121779 | Surveyor |  | 1 | 720 | 720 | 11
2011-10-21 | Survey Team Inv - SI36314511 | Field Survey |  | 1 | 6949.1 | 6949.1 | 11
2011-11-23 | Survey Team Inv No - SI 3632332 | Field Survey |  | 1 | 4495.9 | 4495.9 | 11
2011-12-14 | Inv No - SI3633890 | Field Survey |  | 1 | 1427.52 | 1427.52 | 11
2012-02-22 | Field Survey. Inv No - SI3638505 | Field Survey |  | 1 | 1727.85 | 1727.85 | 11
2012-02-24 | Field Survey. Inv No - SI3638696 | Field Survey |  | 1 | 390 | 390 | 11
2012-03-12 | Field Survey. Inv No - SI3639263 | Field Survey |  | 1 | 3560.15 | 3560.15 | 11
2012-04-19 | Inv No - SI3641201 | Field Survey |  | 1 | 1072.4 | 1072.4 | 11
2012-05-23 | Field Survey,. Inv No - SI3643635 | Field Survey |  | 1 | 224.4 | 224.4 | 11
2012-06-15 | Field Survey. Inv No SI3644749 | Field Survey |  | 1 | 1102.6 | 1102.6 | 11
2012-06-15 | Inv No - SI3644748 | Survey - Construction |  | 1 | 1519 | 1519 | 11
| Subtotal for 011 |  |  |  |  | 23188.92
Portfolio WBS 013
2011-10-28 | Inv 69122014 | Field Density |  | 1 | 1600 | 1600 | 13
2011-11-30 | Inv No - 106834 | Field Density |  | 1 | 1169.54 | 1169.54 | 13
2012-01-19 | Inv No CBW: 69122458 | Moisture Density |  | 1 | 820 | 820 | 13
2012-01-31 | Inv No - 107485 | Field Density |  | 1 | 561.9 | 561.9 | 13
2012-03-31 | Inv No - 108207 | Field Density |  | 1 | 1576.9 | 1576.9 | 13
| Subtotal for 013 |  |  |  |  | 6448.34
Portfolio WBS 015
2011-11-07 | Inv - 102663 | Service Locator |  | 1 | 130 | 130 | 15
2012-04-23 | Sevice Locator & Labour. Inv No - 0153 | Service Locator |  | 1 | 727.5 | 727.5 | 15
| Subtotal for 015 |  |  |  |  | 857.5
Portfolio WBS 022
2011-10-31 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 22
2011-10-31 | ( Grader Hire ) | Scott Mackenzie | hr | 6 | 145 | 870 | 22
2011-10-31 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 22
2011-10-31 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 22
2011-10-31 | Backhoe ( Wet ) | Tom Hurst | hr | 6.5 | 85 | 552.5 | 22
2011-10-31 | Tipper/ Water Cart | Tom Hurst | hr | 6.5 | 90 | 585 | 22
2011-10-31 | Tipper Hire | Michael Biles | hr | 3 | 125 | 375 | 22
2011-10-31 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 8 | 26.46 | 211.68 | 22
2011-10-31 | Ford Ranger 4WD Utility | Ford Utility | hr | 11 | 11.67 | 128.37 | 22
2011-11-01 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 22
2011-11-01 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 22
2011-11-01 | Body Truck | Tom Hurst | hr | 5.5 | 85 | 467.5 | 22
2011-11-01 | Tipper Hire | Michael Biles | hr | 8 | 95 | 760 | 22
2011-11-01 | Backhoe | Tom Hurst | hr | 5.5 | 55 | 302.5 | 22
2011-11-02 | Backhoe ( Dry ) | Tom Hurst | hr | 8 | 55 | 440 | 22
2011-11-02 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 22
2011-11-02 | Backhoe | Tom Hurst | hr | 8 | 85 | 680 | 22
2011-11-02 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 22
2011-11-02 | Tipper Hire | Michael Biles | hr | 8 | 95 | 760 | 22
2011-11-02 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 22
2011-11-03 | Backhoe ( Wet ) | Tom Hurst | hr | 8 | 90 | 720 | 22
2011-11-03 | Tipper ( standown ) | Michael Biles | hr | 8 | 95 | 760 | 22
2011-11-03 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 22
2011-11-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 22
2011-11-03 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 1 | 26.46 | 26.46 | 22
2011-11-03 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 22
2011-11-03 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 22
2011-11-03 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 6 | 90 | 540 | 22
2011-11-04 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 22
2011-11-04 | Leading Hand | Labour | hr | 8.5 | 44.2 | 375.7 | 22
2011-11-04 | Tipper Hire | Michael Biles | hr | 8 | 95 | 760 | 22
2011-11-04 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 22
2011-11-04 | Backhoe ( Wet) | Tom Hurst | hr | 8 | 90 | 720 | 22
| Subtotal for 022 |  |  |  |  | 13933.58
Portfolio WBS 031
2011-09-07 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-07 | T/Trailor Met Area | Michael Biles | hr | 4.5 | 125 | 562.5 | 31
2011-09-07 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-07 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-07 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 31
2011-09-07 | 140 G Grader | Berry Excavations | hr | 8.5 | 140 | 1190 | 31
2011-09-07 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-07 | Tipper/ Water Cart | Tom Hurst | hr | 3.5 | 85 | 297.5 | 31
2011-09-07 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-07 | truck Hire | Michael Biles | hr | 5 | 95 | 475 | 31
2011-09-08 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-08 | Tipper/ Water Cart | Tom Hurst | hr | 5 | 85 | 425 | 31
2011-09-08 | 140 G Grader | Berry Excavations | hr | 4 | 140 | 560 | 31
2011-09-08 | Tipper | Michael Biles | hr | 5 | 95 | 475 | 31
2011-09-08 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 31
2011-09-08 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-08 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-09 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-09 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-09 | Tipper | Michael Biles | hr | 7.5 | 95 | 712.5 | 31
2011-09-09 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 31
2011-09-09 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-09 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-09 | 11T Excavator | Shannons Excavations | hr | 7.5 | 110 | 825 | 31
2011-09-09 | 140 G Grader | Berry Excavations | hr | 8 | 100 | 800 | 31
2011-09-09 | Tipper/ Water Cart | Tom Hurst | hr | 7.5 | 85 | 637.5 | 31
2011-09-10 | Tipper | Michael Biles | hr | 8 | 95 | 760 | 31
2011-09-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-10 | 140 G Grader | Berry Excavations | hr | 8 | 100 | 800 | 31
2011-09-10 | 11T Excavator | Shannons Excavations | hr | 8 | 110 | 880 | 31
2011-09-10 | Tipper/ Water Cart | Tom Hurst | hr | 8 | 90 | 720 | 31
2011-09-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-10 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 31
2011-09-10 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 31
2011-09-10 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-11 | 140 G Grader | Berry Excavations | hr | 10 | 100 | 1000 | 31
2011-09-11 | Tipper/ Water Cart | Tom Hurst | hr | 2 | 90 | 180 | 31
2011-09-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-12 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 31
2011-09-12 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 31
2011-09-12 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 31
2011-09-12 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-12 | 140 G Grader | Berry Excavations | hr | 10 | 100 | 1000 | 31
2011-09-12 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 31
2011-09-12 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-13 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-13 | 140 G Grader | Berry Excavations | hr | 10 | 100 | 1000 | 31
2011-09-13 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 31
2011-09-13 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-13 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 31
2011-09-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 31
2011-09-14 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-14 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 31
2011-09-14 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-14 | Labour Hire | Labour | hr | 10 | 10.5 | 105 | 31
2011-09-14 | 140 G Grader | Berry Excavations | hr | 10 | 100 | 1000 | 31
2011-09-14 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-14 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-15 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-15 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 31
2011-09-15 | Labour Hire | Labour | hr | 10 | 10.5 | 105 | 31
2011-09-15 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-15 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-15 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 31
2011-09-16 | Tipper/ Water Cart | Tom Hurst | hr | 8.5 | 90 | 765 | 31
2011-09-16 | 140 G Grader | Berry Excavations | hr | 8 | 100 | 800 | 31
2011-09-16 | 11T Excavator | Shannons Excavations | hr | 8 | 110 | 880 | 31
2011-09-16 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-16 | Labour Hire | Labour | hr | 8 | 10.5 | 84 | 31
2011-09-16 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 31
2011-09-16 | Tipper | Michael Biles | hr | 8 | 95 | 760 | 31
2011-09-16 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-17 | Tipper | Michael Biles | hr | 8 | 95 | 760 | 31
2011-09-17 | 11T Excavator | Shannons Excavations | hr | 8 | 110 | 880 | 31
2011-09-17 | Tipper/ Water Cart | Tom Hurst | hr | 8 | 60 | 480 | 31
2011-09-17 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-17 | Labour Hire | Labour | hr | 8 | 10.5 | 84 | 31
2011-09-17 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-17 | 140 G Grader | Berry Excavations | hr | 1 | 100 | 100 | 31
2011-09-18 | Tipper/ Water Cart | Tom Hurst | hr | 2 | 60 | 120 | 31
2011-09-18 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 31
2011-09-19 | Labour Hire | Labour | hr | 10 | 10.5 | 105 | 31
2011-09-19 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 31
2011-09-19 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-19 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-19 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-20 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-20 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 31
2011-09-20 | Labour Hire | Labour | hr | 7.5 | 10.5 | 78.75 | 31
2011-09-20 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-20 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 31
2011-09-20 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 31
2011-09-21 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 31
2011-09-21 | 140 G Grader | Berry Excavations | hr | 3 | 100 | 300 | 31
2011-09-21 | Labour Hire | Labour | hr | 8 | 10.5 | 84 | 31
2011-09-21 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-21 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 31
2011-09-21 | Tipper | Michael Biles | hr | 6.5 | 95 | 617.5 | 31
2011-09-21 | 11T Excavator | Shannons Excavations | hr | 6.5 | 110 | 715 | 31
2011-09-22 | 11T Excavator | Shannons Excavations | hr | 8 | 110 | 880 | 31
2011-09-22 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-22 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 31
2011-09-22 | Tipper | Michael Biles | hr | 8 | 95 | 760 | 31
2011-09-23 | Tipper/ Water Cart | Tom Hurst | hr | 4 | 90 | 360 | 31
2011-09-23 | 11T Excavator | Shannons Excavations | hr | 2 | 110 | 220 | 31
2011-09-23 | 140 G Grader | Berry Excavations | hr | 1 | 100 | 100 | 31
2011-09-24 | Tipper/ Water Cart | Tom Hurst | hr | 2.5 | 90 | 225 | 31
2011-09-26 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-27 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-28 | Tipper/ Water Cart | Tom Hurst | hr | 9 | 90 | 810 | 31
2011-09-29 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 31
2011-09-30 | Bobcat - Wet Hire From the 8/09/2011 to 30/09/2011 | Bobcat |  | 1 | 4696.71 | 4696.71 | 31
2011-10-03 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-05 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-06 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-07 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 3.5 | 95 | 332.5 | 31
2011-10-10 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-11 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-12 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-13 | 11T Excavator | Shannons Excavations | hr | 5 | 110 | 550 | 31
2011-10-13 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2011-10-14 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 2 | 95 | 190 | 31
2011-10-14 | 11T Excavator | Shannons Excavations | hr | 4 | 110 | 440 | 31
2011-10-15 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 2 | 100 | 200 | 31
2011-10-17 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 31
2012-02-22 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 4.5 | 90 | 405 | 31
2012-05-02 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 31
2012-05-11 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 31
2012-05-11 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 31
2012-05-11 | Tipper Hire | Bernie Currey | hr | 6 | 65 | 390 | 31
2012-05-11 | ( Bobcat Hire ) | Bernie Currey | hr | 7 | 95 | 665 | 31
| Subtotal for 031 |  |  |  |  | 72746.43
Portfolio WBS 041
2011-10-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 41
2011-10-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 41
2011-10-11 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 41
2011-10-11 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 8.5 | 90 | 765 | 41
2011-10-11 | 140 G Grader | Berry Excavations | hr | 8 | 135 | 1080 | 41
2011-11-10 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 41
2011-11-11 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 9 | 100 | 900 | 41
2011-11-11 | ( 7 Tonne Excavator ) | Berry Excavations | hr | 9 | 110 | 990 | 41
| Subtotal for 041 |  |  |  |  | 5217.475
Portfolio WBS 053
2011-09-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-09-06 | standby | Michael Biles | hr | 3 | 45 | 135 | 53
2011-09-06 | Leading Hand | Labour | hr | 3 | 44.2 | 132.6 | 53
2011-09-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-09-06 | Truck Hire | Michael Biles | hr | 2 | 95 | 190 | 53
2011-09-06 | Labour HIre | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-09-06 | 11T Excavator - Labour Rate Float excavator from Dysart | Shannons Excavations | hr | 3.5 | 40 | 140 | 53
2011-09-06 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-09-06 | Tipper/ Water Cart | Tom Hurst | hr | 3 | 85 | 255 | 53
2011-10-12 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-12 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-12 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 9.5 | 90 | 855 | 53
2011-10-12 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-12 | Water Tipper | Humphries | hr | 10 | 150 | 1500 | 53
2011-10-12 | 140 G Grader | Berry Excavations | hr | 8.5 | 110 | 935 | 53
2011-10-13 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-13 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-13 | Water Tipper | Humphries | hr | 10.5 | 150 | 1575 | 53
2011-10-13 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-13 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-13 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-14 | 140 G Grader | Berry Excavations | hr | 6 | 135 | 810 | 53
2011-10-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-10-14 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 6.5 | 90 | 585 | 53
2011-10-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-10-14 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 53
2011-10-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-10-15 | 140 G Grader | Berry Excavations | hr | 3 | 135 | 405 | 53
2011-10-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-10-15 | (10 tipper ) | Pollards Earthmoving | hr | 3 | 95 | 285 | 53
2011-10-15 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 3 | 90 | 270 | 53
2011-10-15 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2011-10-17 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 53
2011-10-17 | (10 tipper ) | Pollards Earthmoving | hr | 6.5 | 95 | 617.5 | 53
2011-10-17 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 7 | 90 | 630 | 53
2011-10-17 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 53
2011-10-17 | 140 G Grader | Berry Excavations | hr | 7 | 135 | 945 | 53
2011-10-20 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2011-10-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2011-10-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 53
2011-10-25 | 21 Tonne Excavator | Berry Excavations | hr | 3 | 110 | 330 | 53
2011-10-26 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 7.5 | 90 | 675 | 53
2011-10-26 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 9.5 | 90 | 855 | 53
2011-10-26 | 21 Tonne Excavator | Berry Excavations | hr | 9 | 135 | 1215 | 53
2011-10-26 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-26 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 53
2011-10-26 | 140 G Grader | Berry Excavations | hr | 4.25 | 110 | 467.5 | 53
2011-10-26 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-27 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-27 | 21 Tonne Excavator | Berry Excavations | hr | 8.5 | 135 | 1147.5 | 53
2011-10-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2011-10-27 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 9 | 90 | 810 | 53
2011-10-27 | (10 tipper ) | Pollards Earthmoving | hr | 4.5 | 95 | 427.5 | 53
2011-10-27 | Lovell Earthmoving ( 10m Tipper ) (2) | Lovell Earthmoving | hr | 9 | 90 | 810 | 53
2011-10-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 53
2011-10-28 | (10 tipper ) | Pollards Earthmoving | hr | 5.5 | 95 | 522.5 | 53
2011-10-28 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 53
2011-10-28 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 8.5 | 90 | 765 | 53
2011-10-28 | Lovell Earthmoving ( 10 m Tipper ) (2) | Lovell Earthmoving | hr | 8.5 | 90 | 765 | 53
2011-10-28 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2011-10-28 | 21 Tonne Excavator | Berry Excavations | hr | 8.5 | 135 | 1147.5 | 53
2011-10-29 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2011-10-29 | 21 Tonne Excavator | Berry Excavations | hr | 4.5 | 135 | 607.5 | 53
2011-10-29 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2011-10-29 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 5 | 90 | 450 | 53
2011-10-29 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 53
2011-10-31 | (10 tipper ) | Pollards Earthmoving | hr | 6 | 95 | 570 | 53
2011-10-31 | 21 Tonne Excavator | Berry Excavations | hr | 6.5 | 135 | 877.5 | 53
2011-10-31 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-10-31 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 53
2011-11-08 | ( Bobcat Hire ) | Bernie Currey | hr | 10.5 | 95 | 997.5 | 53
2011-11-09 | ( Bobcat Hire ) | Bernie Currey | hr | 10.5 | 95 | 997.5 | 53
2011-11-09 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 9 | 90 | 810 | 53
2012-01-09 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-01-09 | Taylors Earthmoving ( 25t Excavator ) | Taylors Earthmoving | hr | 7.5 | 130 | 975 | 53
2012-01-09 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 9 | 95 | 855 | 53
2012-01-24 | Backhoe Hire | Mcdowall Earthmoving | hr | 9 | 90 | 810 | 53
2012-01-24 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-01-24 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 53
2012-01-24 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 53
2012-01-25 | Backhoe Hire | Mcdowall Earthmoving | hr | 5.75 | 90 | 517.5 | 53
2012-01-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-01-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 53
2012-01-30 | Labour Hire | Labour | hr | 1.499 | 35.35 | 52.9896 | 53
2012-01-30 | Backhoe Hire | Mcdowall Earthmoving | hr | 4.5 | 90 | 405 | 53
2012-01-30 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 53
2012-02-09 | Backhoe Hire | Mcdowall Earthmoving | hr | 3.5 | 90 | 315 | 53
2012-02-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-02-10 | Backhoe Hire | Mcdowall Earthmoving | hr | 3.5 | 90 | 315 | 53
2012-02-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 53
2012-02-22 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-02-22 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 53
2012-02-22 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 5.2 | 90 | 468 | 53
2012-03-21 | Backhoe Hire | Mcdowall Earthmoving | hr | 3.5 | 90 | 315 | 53
2012-04-27 | 8t Excavator Hire | Copp & Co | hr | 9 | 105 | 945 | 53
2012-04-27 | Truck Hire | Copp & Co | hr | 9 | 95 | 855 | 53
2012-05-30 | 8t Excavator Hire | Copp & Co | hr | 7 | 105 | 735 | 53
2012-05-30 | Truck Hire | Copp & Co | hr | 7 | 95 | 665 | 53
| Subtotal for 053 |  |  |  |  | 43727.4897
Portfolio WBS 061
2011-10-01 | Cart Concrete from Airport Inv - 698 | Truck - RATE ONLY |  | 1 | 3750 | 3750 | 61
2011-10-01 | Truck & Dog - Wet Hire Cart Concrete From Airport to Walls | Truck & Dog |  | 1 | 3750 | 3750 | 61
2011-10-01 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 61
2011-10-01 | Tipper | Michael Biles | hr | 6 | 125 | 750 | 61
2011-10-01 | 140 G Grader | Berry Excavations | hr | 8 | 100 | 800 | 61
2011-10-01 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 61
2011-10-01 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 61
2011-10-01 | Tipper/ Water Cart | Tom Hurst | hr | 7 | 90 | 630 | 61
2011-10-03 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 4.5 | 95 | 427.5 | 61
2011-10-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-03 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 61
2011-10-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-03 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 90 | 900 | 61
2011-10-03 | 140 G Grader | Berry Excavations | hr | 8 | 110 | 880 | 61
2011-10-03 | Plant Hire Tractor Profiler | Tractor Profiler | day | 1 | 1500 | 1500 | 61
2011-10-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-04 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-04 | Tipper/ Water Cart | Tom Hurst | hr | 10.5 | 120 | 1260 | 61
2011-10-04 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-04 | 140 G Grader | Berry Excavations | hr | 10 | 100 | 1000 | 61
2011-10-04 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 61
2011-10-04 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-04 | Plant Hire Tractor Profiler | Tractor Profiler | day | 1 | 1500 | 1500 | 61
2011-10-04 | Tipper Hire | Michael Biles | hr | 5 | 45 | 225 | 61
2011-10-05 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 61
2011-10-05 | Semi Side Tipper Hire | Raymond s Truck Hire | hr | 10 | 80 | 800 | 61
2011-10-05 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 61
2011-10-05 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 120 | 1140 | 61
2011-10-06 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-06 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-06 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 61
2011-10-06 | Backhoe | Tom Hurst | hr | 2 | 55 | 110 | 61
2011-10-06 | Tipper/ Water Cart | Tom Hurst | hr | 10.5 | 120 | 1260 | 61
2011-10-06 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 61
2011-10-06 | Tipper Hire standown | Michael Biles | hr | 5 | 45 | 225 | 61
2011-10-06 | Tipper Hire | Michael Biles | hr | 4 | 130 | 520 | 61
| Subtotal for 061 |  |  |  |  | 26831.6
Portfolio WBS 062
2011-09-08 | Tipper | Michael Biles | hr | 5 | 95 | 475 | 62
2011-09-08 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 2 | 26.46 | 52.92 | 62
2011-09-30 | 140 G Grader | Berry Excavations | hr | 6 | 100 | 600 | 62
2011-10-05 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-05 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-07 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-10-07 | Tipper/ Water Cart | Tom Hurst | hr | 7.5 | 120 | 900 | 62
2011-10-07 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-10-07 | Tipper Hire | Michael Biles | hr | 8 | 125 | 1000 | 62
2011-10-07 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-08 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5.5 | 95 | 522.5 | 62
2011-10-10 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 120 | 1140 | 62
2011-10-10 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-10 | Tipper Hire | Michael Biles | hr | 10 | 125 | 1250 | 62
2011-10-10 | Backhoe | Tom Hurst | hr | 1 | 55 | 55 | 62
2011-10-11 | Tipper Hire | Michael Biles | hr | 10.5 | 125 | 1312.5 | 62
2011-10-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-11 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 120 | 1200 | 62
2011-10-11 | Water Tipper | Humphries | hr | 10.25 | 150 | 1537.5 | 62
2011-10-11 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-12 | Tipper/ Water Cart | Tom Hurst | hr | 10.5 | 120 | 1260 | 62
2011-10-12 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-12 | Excavator 5.5 t Inv - 258231 | Excavator - 8T | bcm | 1 | 1490.71 | 1490.71 | 62
2011-10-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-12 | Tipper Hire | Michael Biles | hr | 10.5 | 125 | 1312.5 | 62
2011-10-12 | Tipper/ Water Cart | Tom Hurst | hr | 1 | 55 | 55 | 62
2011-10-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-13 | Tipper/ Water Cart | Tom Hurst | hr | 10.5 | 120 | 1260 | 62
2011-10-13 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-13 | Tipper Hire | Michael Biles | hr | 10.5 | 125 | 1312.5 | 62
2011-10-13 | Tipper/ Water Cart | Tom Hurst | hr | 10.5 | 120 | 1260 | 62
2011-10-13 | Backhoe | Tom Hurst | hr | 3 | 55 | 165 | 62
2011-10-14 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 6 | 95 | 570 | 62
2011-10-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2011-10-14 | 140 G Grader | Berry Excavations | hr | 3 | 135 | 405 | 62
2011-10-14 | Tipper Hire | Michael Biles | hr | 5 | 125 | 625 | 62
2011-10-14 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-10-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2011-10-14 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 3 | 90 | 270 | 62
2011-10-14 | Water Tipper | Humphries | hr | 1 | 60 | 60 | 62
2011-10-14 | Water Tipper | Humphries | hr | 5 | 150 | 750 | 62
2011-10-14 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2011-10-14 | Backhoe | Tom Hurst | hr | 4 | 120 | 480 | 62
2011-10-15 | (10 tipper ) | Pollards Earthmoving | hr | 1.5 | 95 | 142.5 | 62
2011-10-15 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 1 | 90 | 90 | 62
2011-10-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-15 | 140 G Grader | Berry Excavations | hr | 1.5 | 135 | 202.5 | 62
2011-10-15 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 2.5 | 100 | 250 | 62
2011-10-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-15 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-17 | 140 G Grader | Berry Excavations | hr | 1.5 | 135 | 202.5 | 62
2011-10-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-17 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-17 | Water Tipper | Humphries | hr | 10 | 150 | 1500 | 62
2011-10-17 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 120 | 1140 | 62
2011-10-17 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-17 | BackHoe | Berry Excavations | hr | 7 | 110 | 770 | 62
2011-10-17 | Lovell Earthmoving ( 10m Tipper) | Lovell Earthmoving | hr | 1 | 90 | 90 | 62
2011-10-17 | (10 tipper ) | Pollards Earthmoving | hr | 1 | 95 | 95 | 62
2011-10-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-17 | Backhoe | Tom Hurst | hr | 2 | 55 | 110 | 62
2011-10-18 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 3 | 90 | 270 | 62
2011-10-18 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2011-10-18 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 6 | 95 | 570 | 62
2011-10-18 | Plate Compactor - Dry Hire Inv - 258806 | Plate Compactor |  | 1 | 640 | 640 | 62
2011-10-19 | 12 T Excavator | Shannons Excavations | hr | 5 | 110 | 550 | 62
2011-10-19 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 4.5 | 95 | 427.5 | 62
2011-10-19 | ( Grader Hire ) | Scott Mackenzie | hr | 10 | 145 | 1450 | 62
2011-10-19 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 4 | 95 | 380 | 62
2011-10-19 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 10 | 90 | 900 | 62
2011-10-19 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 62
2011-10-19 | Truck Hire / Water Cart - Brad | Doyawanna Truck Hire | hr | 3 | 95 | 285 | 62
2011-10-19 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-19 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 62
2011-10-19 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-19 | Backhoe | Tom Hurst | hr | 4.5 | 55 | 247.5 | 62
2011-10-20 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 10 | 90 | 900 | 62
2011-10-20 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 62
2011-10-20 | ( Grader Hire ) | Scott Mackenzie | hr | 10 | 145 | 1450 | 62
2011-10-20 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-20 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-20 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 9.5 | 95 | 902.5 | 62
2011-10-20 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 62
2011-10-20 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 120 | 1140 | 62
2011-10-20 | 12 T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 62
2011-10-20 | ( Tipper ) | Michael Biles | hr | 9.5 | 125 | 1187.5 | 62
2011-10-21 | Ford Ranger 4WD Utility | Ford Utility | hr | 4.5 | 11.67 | 52.515 | 62
2011-10-21 | ( Grader Hire ) | Scott Mackenzie | hr | 4.5 | 145 | 652.5 | 62
2011-10-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2011-10-21 | Leading Hand | Labour | hr | 4.5 | 44.2 | 198.9 | 62
2011-10-21 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 62
2011-10-22 | ( Tipper ) | Michael Biles | hr | 6.5 | 95 | 617.5 | 62
2011-10-22 | 12 T Excavator | Shannons Excavations | hr | 5 | 110 | 550 | 62
2011-10-22 | Ford Ranger 4WD Utility | Ford Utility | hr | 8.5 | 11.67 | 99.195 | 62
2011-10-22 | Leading Hand | Labour | hr | 8.5 | 44.2 | 375.7 | 62
2011-10-22 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 62
2011-10-22 | Tipper/ Water Cart | Tom Hurst | hr | 6.5 | 85 | 552.5 | 62
2011-10-22 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-22 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 5.5 | 90 | 495 | 62
2011-10-22 | ( Grader Hire ) | Scott Mackenzie | hr | 8.5 | 145 | 1232.5 | 62
2011-10-23 | Water Cart Hire 20/10/2011 Inv - 124232 | Water Cart - Hire |  | 6.5 | 95 | 617.5 | 62
2011-10-24 | ( Tipper ) | Michael Biles | hr | 8.5 | 125 | 1062.5 | 62
2011-10-24 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 120 | 1140 | 62
2011-10-24 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 9.5 | 95 | 902.5 | 62
2011-10-24 | ( Grader Hire ) | Scott Mackenzie | hr | 10.5 | 145 | 1522.5 | 62
2011-10-24 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-10-24 | Tipper Hire | Michael Biles | hr | 1 | 95 | 95 | 62
2011-10-24 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 62
2011-10-24 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 62
2011-10-24 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-10-25 | 140 G Grader | Berry Excavations | hr | 7 | 135 | 945 | 62
2011-10-25 | Tipper/ Water Cart | Tom Hurst | hr | 4 | 55 | 220 | 62
2011-10-25 | ( Grader Hire ) | Scott Mackenzie | hr | 10 | 145 | 1450 | 62
2011-10-25 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 62
2011-10-25 | Tipper ( Bernie driver ) | Michael Biles | hr | 9.5 | 125 | 1187.5 | 62
2011-10-25 | ( Water Truck ) | Talbots | hr | 6 | 95 | 570 | 62
2011-10-25 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 9.5 | 90 | 855 | 62
2011-10-25 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10 | 95 | 950 | 62
2011-10-25 | From the 3/10/2011 to the 24/10/2011 Inv - 259535 | Bobcat |  | 1 | 1876 | 1876 | 62
2011-10-25 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-10-25 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 62
2011-10-25 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 120 | 1140 | 62
2011-10-26 | ( Truck & Dog ) | Michael Biles | hr | 9.5 | 125 | 1187.5 | 62
2011-10-26 | ( Water Truck ) | Talbots | hr | 5 | 95 | 475 | 62
2011-10-26 | Tipper/ Water Cart | Tom Hurst | hr | 9 | 120 | 1080 | 62
2011-10-26 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 62
2011-10-26 | 11 Tonne Excavator | Shannons Excavations | hr | 8 | 110 | 880 | 62
2011-10-26 | ( Grader Hire ) | Scott Mackenzie | hr | 10 | 145 | 1450 | 62
2011-10-26 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-26 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-10-26 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10 | 95 | 950 | 62
2011-10-26 | Tom Hurst ( Backhoe ) | Tom Hurst | hr | 2.5 | 55 | 137.5 | 62
2011-10-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 62
2011-10-26 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 8 | 90 | 720 | 62
2011-10-26 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-26 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-27 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-27 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 10 | 26.46 | 264.6 | 62
2011-10-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-27 | Ford Ranger 4WD Utility | Ford Utility | hr | 6 | 11.67 | 70.02 | 62
2011-10-27 | Backhoe (Dry) | Tom Hurst | hr | 6.5 | 55 | 357.5 | 62
2011-10-27 | Tipper/ Water Cart | Tom Hurst | hr | 10 | 85 | 850 | 62
2011-10-27 | ( Truck & Dog ) | Michael Biles | hr | 4 | 125 | 500 | 62
2011-10-27 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10 | 95 | 950 | 62
2011-10-27 | ( Grader Hire ) | Scott Mackenzie | hr | 10 | 145 | 1450 | 62
2011-10-27 | Leading Hand | Labour | hr | 6 | 44.2 | 265.2 | 62
2011-10-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-27 | 12 T Excavator | Shannons Excavations | hr | 6 | 110 | 660 | 62
2011-10-28 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-10-28 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-10-28 | (10 tipper ) | Pollards Earthmoving | hr | 3 | 95 | 285 | 62
2011-10-28 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2011-10-28 | Leading Hand | Labour | hr | 4 | 44.2 | 176.8 | 62
2011-10-28 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 62
2011-10-28 | 11 Tonne Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 62
2011-10-28 | Tipper Hire | Michael Biles | hr | 2 | 125 | 250 | 62
2011-10-28 | Water Tipper | Humphries | hr | 1 | 60 | 60 | 62
2011-10-28 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 10 | 26.46 | 264.6 | 62
2011-10-28 | ( Grader Hire ) | Scott Mackenzie | hr | 10 | 145 | 1450 | 62
2011-10-28 | ( Truck & Dog ) | Michael Biles | hr | 8 | 95 | 760 | 62
2011-10-28 | ( Water Truck ) | Talbots | hr | 5.5 | 95 | 522.5 | 62
2011-10-28 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 62
2011-10-28 | Tom Hurst ( Backhoe ) | Tom Hurst | hr | 4 | 55 | 220 | 62
2011-10-29 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 62
2011-10-29 | Water Tipper | Humphries | hr | 1 | 60 | 60 | 62
2011-10-29 | Body Truck | Tom Hurst | hr | 5 | 85 | 425 | 62
2011-10-29 | Tipper Hire | Michael Biles | hr | 3.5 | 125 | 437.5 | 62
2011-10-29 | Tipper Hire | Michael Biles | hr | 3 | 95 | 285 | 62
2011-10-29 | Backhoe ( Wet ) | Tom Hurst | hr | 8.5 | 90 | 765 | 62
2011-10-29 | 12 T Excavator | Shannons Excavations | hr | 6.5 | 110 | 715 | 62
2011-10-29 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 11 | 95 | 1045 | 62
2011-10-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-10-29 | Leading Hand | Labour | hr | 10.5 | 44.2 | 464.1 | 62
2011-10-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 62
2011-10-30 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10 | 95 | 950 | 62
2011-10-31 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 7.5 | 95 | 712.5 | 62
2011-10-31 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2011-10-31 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 62
2011-10-31 | ( Truck & Dog ) | Michael Biles | hr | 5.5 | 125 | 687.5 | 62
2011-10-31 | Plate Compactor - Dry Hire From the 28/09/2011 to the 31/10/2011 Inv - 260724 | Plate Compactor |  | 1 | 362.56 | 362.56 | 62
2011-10-31 | Multi Roller ( Flexi Hire ) (16 Tonne) From the 19/10/2011 to the 31/10/2011 Inv - 260722 | Multi Roller |  | 1 | 3930 | 3930 | 62
2011-10-31 | Water Tipper | Humphries | hr | 1 | 60 | 60 | 62
2011-10-31 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 62
2011-10-31 | Bobcat - Wet Hire Fro mthe 30/09/2011 to the 31/10/2011 Inv- 260720 | Bobcat |  | 1 | 5103 | 5103 | 62
2011-10-31 | Double Drum Roller (8 Tonne) From the 13/10/2011 to the 31/10/2011 Inv - 260723 | Multi Roller |  | 1 | 4650 | 4650 | 62
2011-11-01 | Fuel for Multi Tyre Roller Inv No 261472 | Diesel Fuel |  | 59 | 2.2 | 129.8 | 62
2011-11-02 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 62
2011-11-02 | Tipper (Wet Hire) Docket No 7825 Inv - 6780 | Tipper |  | 1 | 487.5 | 487.5 | 62
2011-11-02 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 62
2011-11-02 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 62
2011-11-02 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 62
2011-11-03 | Concrete Saw From the 3/11/2011 to the 3/11/2011 Inv - 261733 | Sawcut |  | 1 | 164.63 | 164.63 | 62
2011-11-07 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 62
2011-11-08 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 8.5 | 95 | 807.5 | 62
2011-11-08 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 62
2011-11-09 | Hire from the 2/11/2011 to the 4/11/2011 Inv- 262359 | Vibrating Rammer |  | 1 | 311.58 | 311.58 | 62
2011-11-09 | Hired From the 8/11/2011 to the 9/11/2011 Inv - 262428 | Generator |  | 1 | 205.88 | 205.88 | 62
2011-11-09 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 4.5 | 95 | 427.5 | 62
2011-11-11 | Skid Steer Loader ( Flexi Hire ) From the 31/10/2011 to the 10/11/2011 | Skid Steer Loader |  | 1 | 1975.11 | 1975.11 | 62
2011-11-11 | Hired form the 31/10/2011 to the 10/11/2011 | Generator |  | 1 | 575.97 | 575.97 | 62
2011-11-14 | Plate Compactor - Dry Hire From the 31/10/2011 to the 10/11/2011 Inv - 262883 | Plate Compactor |  | 1 | 789.28 | 789.28 | 62
2011-11-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-11-25 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2011-11-25 | ( Bobcat Hire ) | Bernie Currey | hr | 7.5 | 95 | 712.5 | 62
2011-11-25 | Vibrating Plate ( Flexi Hire ) | Plate Compactor | hr | 1 | 71 | 71 | 62
2011-11-25 | Truck Hire | Bernie Currey | hr | 6 | 65 | 390 | 62
2011-11-28 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-11-28 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-11-28 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 62
2011-11-28 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 4 | 95 | 380 | 62
2011-11-28 | Truck Hire | Bernie Currey | hr | 4 | 65 | 260 | 62
2011-11-28 | ( Bobcat Hire ) | Bernie Currey | hr | 9.5 | 95 | 902.5 | 62
2011-11-30 | Hire from the 31/10/2011 to the 30/11/2011 Inv No - 265609 | Double Drum Roller |  | 1 | 8064 | 8064 | 62
2011-12-06 | Bedding Sand Inv No- 4428 | Sand |  | 1 | 168.18 | 168.18 | 62
2011-12-06 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-06 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2011-12-22 | Hire from the 21/12/2011 to the 22/12/2011 Inv No 268438 | Vibrating Rammer |  | 1 | 159.03 | 159.03 | 62
2011-12-27 | Water Cart Hire 27/12/11 to 1/1/12 - Inv 2013 | Water Cart - Hire |  | 6.5 | 100 | 650 | 62
2011-12-31 | Double Drum Roller ( Flexi Hire ) Hired from the 30/11/2011 to the 31/12/2011 Inv No 269588 | Double Drum Roller |  | 1 | 2520 | 2520 | 62
2012-01-09 | Micheal Biles ( Truck & Dog ) | Michael Biles | hr | 8 | 125 | 1000 | 62
2012-01-09 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10 | 95 | 950 | 62
2012-01-09 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-01-09 | Labour Hire. ( Concrete Supervisor ) | Labour | hr | 6 | 57.7 | 346.2 | 62
2012-01-10 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 9.5 | 95 | 902.5 | 62
2012-01-10 | ( Bobcat Hire ) | Bernie Currey | hr | 4 | 95 | 380 | 62
2012-01-11 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 9 | 95 | 855 | 62
2012-01-12 | Semi Side Tipper Hire | Raymond s Truck Hire | hr | 6.5 | 125 | 812.5 | 62
2012-01-12 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10.5 | 95 | 997.5 | 62
2012-01-12 | Semi Side Tipper Hire | Raymond s Truck Hire | hr | 7.5 | 125 | 937.5 | 62
2012-01-12 | Truck & Dog Hire | Michael Biles | hr | 9 | 95 | 855 | 62
2012-01-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 62
2012-01-13 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 2 | 95 | 190 | 62
2012-01-24 | S.A & M.L Mackenzie Grader Hire | Mackenzie Grader Hire | hr | 3 | 145 | 435 | 62
2012-01-31 | SD Roller - Dry . Hired from the 02/01/2012 to the 26/01/2012. Inv No - 272213 | SD Roller |  | 1 | 5040 | 5040 | 62
2012-02-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-13 | Backhoe Hire | Mcdowall Earthmoving | hr | 2.5 | 90 | 225 | 62
2012-02-13 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 62
2012-02-15 | Water Truck Hire | Berry Excavations | hr | 7.5 | 100 | 750 | 62
2012-02-21 | Water Truck Hire | Berry Excavations | hr | 9 | 100 | 900 | 62
2012-02-21 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-02-22 | Water Truck Hire | Berry Excavations | hr | 9 | 100 | 900 | 62
2012-02-22 | Pollard ( Truck & Dog ) | Pollards Earthmoving | hr | 6 | 140 | 840 | 62
2012-02-22 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-02-22 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 62
2012-02-23 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 62
2012-02-23 | Water Truck Hire | Berry Excavations | hr | 8 | 100 | 800 | 62
2012-02-28 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 62
2012-02-29 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-02-29 | Humphries ( Grader Hire ) | Humphries | hr | 3 | 100 | 300 | 62
2012-03-01 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 62
2012-04-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-04-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
2012-04-02 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 62
| Subtotal for 062 |  |  |  |  | 159414.47
Portfolio WBS 063
2011-10-17 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 63
2011-10-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2011-10-17 | 12 T Excavator | Shannons Excavations | hr | 6 | 110 | 660 | 63
2011-10-17 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 6 | 90 | 540 | 63
2011-10-17 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 63
2011-10-18 | 12 T Excavator | Shannons Excavations | hr | 2.5 | 110 | 275 | 63
2011-10-29 | ( Grader Hire ) | Scott Mackenzie | hr | 10.5 | 145 | 1522.5 | 63
2012-01-21 | Labour Hire ( People Resourcing ) | Labour | hr | 2 | 40.97 | 81.94 | 63
2012-01-21 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 63
2012-01-21 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 63
2012-01-23 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 63
2012-01-23 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 63
2012-01-23 | Excavator 7 Tonne | Berry Excavations | hr | 6 | 110 | 660 | 63
2012-01-23 | S.A & M.L Mackenzie Grader Hire | Mackenzie Grader Hire | hr | 3 | 145 | 435 | 63
2012-01-23 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 63
2012-01-25 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 63
2012-03-03 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2012-03-03 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 63
2012-03-05 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-03-05 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 63
2012-03-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-03-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-03-06 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 63
2012-03-31 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 63
2012-03-31 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 63
| Subtotal for 063 |  |  |  |  | 7087.515
Portfolio WBS 064
2011-10-31 | Primer Seal - Inv 265044 Wrights Rd | Seal Visit |  | 9518 | 7.25 | 69005.5 | 64
2011-12-08 | 10mm Aggregate | Seal Visit |  | 9708 | 5.82 | 56500.56 | 64
2012-05-01 | Inv No - AQMKB4009-001 | Primerseal |  | 1 | 5100 | 5100 | 64
2012-05-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 64
2012-05-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 64
2012-05-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 64
2012-05-10 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 64
2012-05-10 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 64
2012-05-11 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 64
| Subtotal for 064 |  |  |  |  | 131081.82
Portfolio WBS 065
2012-05-14 | Asphalt. Inv No - 6053291 RI | Asphalt |  | 54.5 | 299.51 | 16323.295 | 65
2012-05-14 | Inv No - 6053291 RI | Asphalt |  | 212.9 | 299.51 | 63765.679 | 65
| Subtotal for 065 |  |  |  |  | 80088.974
Portfolio WBS 066
2012-02-29 | Inv No - 20422 | Line Marking |  | 1 | 2580 | 2580 | 66
| Subtotal for 066 |  |  |  |  | 2580
Portfolio WBS 067
2011-11-02 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 9 | 90 | 810 | 67
2011-12-18 | ( Truck Hire ) | Bernie Currey | hr | 2 | 65 | 130 | 67
2011-12-18 | ( Bobcat Hire ) | Bernie Currey | hr | 9.5 | 95 | 902.5 | 67
2011-12-19 | ( Bobcat Hire ) | Bernie Currey | hr | 9.5 | 95 | 902.5 | 67
2011-12-19 | ( Truck Hire ) | Bernie Currey | hr | 5 | 65 | 325 | 67
2011-12-20 | Excavator P & H Gourlay | Hyundai Excavator | hr | 8 | 80 | 640 | 67
2011-12-20 | ( Bobcat Hire ) | Bernie Currey | hr | 5.5 | 95 | 522.5 | 67
2011-12-21 | ( Bobcat Hire ) | Bernie Currey | hr | 2 | 95 | 190 | 67
2011-12-21 | Excavator P & H Gourlay | Hyundai Excavator | hr | 5.5 | 80 | 440 | 67
2012-01-17 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 67
2012-01-17 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 67
2012-01-17 | ( Bobcat Hire ) | Bernie Currey | hr | 3 | 95 | 285 | 67
2012-01-17 | Leading Hand | Labour | hr | 6 | 44.2 | 265.2 | 67
2012-01-17 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 67
2012-01-17 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 67
2012-02-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 67
2012-02-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 67
2012-03-21 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 67
2012-03-21 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 67
| Subtotal for 067 |  |  |  |  | 6897.4
Portfolio WBS 068
2011-09-25 | Tipper/ Water Cart | Tom Hurst | hr | 2.5 | 90 | 225 | 68
2011-10-20 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 68
2011-10-20 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 2.5 | 66.07 | 165.175 | 68
2011-10-25 | UD Spreader Truck - No Driver | UD Spreader | hr | 1 | 21.61 | 21.61 | 68
2011-10-25 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 1.5 | 66.07 | 99.105 | 68
2011-10-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 68
2011-10-25 | Labour Hire | Labour | hr | 3.5 | 35.35 | 123.725 | 68
2011-10-25 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 68
2011-10-31 | Grader - Wet Hire Inv - 8942199 | Grader |  | 1 | 15778.23 | 15778.23 | 68
2011-11-03 | Plant Hire Tractor Profiler | Tractor Profiler | day | 1 | 2500 | 2500 | 68
2011-11-03 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 68
2011-11-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
2011-11-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
2011-11-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 68
2011-11-04 | Hire from the 4/11/2011 to the 4/11/2011 Inv - 261914 | Sawcut |  | 1 | 164.63 | 164.63 | 68
2011-11-04 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-11-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 68
2011-11-04 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 68
2011-11-04 | Plant Hire Tractor Profiler | Tractor Profiler | day | 1 | 2500 | 2500 | 68
2011-11-05 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 68
2011-11-07 | Pad Foot Roller - Dry From the 3/11/2011 to the 4/11/2011 Inv - 262005 | PF Roller |  | 1 | 1166 | 1166 | 68
2011-11-08 | Forklift Inv - 21118 | Forklift |  | 1 | 300 | 300 | 68
2011-11-09 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 68
2011-11-09 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 68
2011-11-09 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 68
2011-11-09 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 68
2011-11-09 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-09 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 68
2011-11-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-11-10 | UD Spreader Truck - No Driver | UD Spreader | hr | 7 | 21.61 | 151.27 | 68
2011-11-10 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 4 | 95 | 380 | 68
2011-11-10 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 68
2011-11-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-11-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-11-10 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-11-11 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 7 | 66.07 | 462.49 | 68
2011-11-11 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 68
2011-11-11 | UD Spreader Truck - No Driver | UD Spreader | hr | 7 | 21.61 | 151.27 | 68
2011-11-11 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 68
2011-11-11 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 9.5 | 95 | 902.5 | 68
2011-11-11 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 68
2011-11-11 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 68
2011-11-11 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 68
2011-11-11 | Leading Hand | Labour | hr | 9 | 44.2 | 397.8 | 68
2011-11-11 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 68
2011-11-12 | UD Spreader Truck - No Driver | UD Spreader | hr | 6.5 | 21.61 | 140.465 | 68
2011-11-12 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 6.5 | 66.07 | 429.455 | 68
2011-11-12 | ( 7 Tonne Excavator ) | Berry Excavations | hr | 4.75 | 110 | 522.5 | 68
2011-11-12 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 68
2011-11-12 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 7.5 | 95 | 712.5 | 68
2011-11-12 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-12 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-12 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-12 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-12 | Leading Hand | Labour | hr | 6.5 | 44.2 | 287.3 | 68
2011-11-12 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-14 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 9 | 95 | 855 | 68
2011-11-15 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-11-15 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 68
2011-11-15 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 68
2011-11-15 | ( Bobcat Hire ) | Bernie Currey | hr | 4 | 40 | 160 | 68
2011-11-15 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 68
2011-11-15 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 68
2011-11-15 | Ecavator (7 Tonne ) | Berry Excavations | hr | 4 | 110 | 440 | 68
2011-11-15 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 68
2011-11-16 | Ecavator (7 Tonne ) | Berry Excavations | hr | 6 | 140 | 840 | 68
2011-11-16 | Leading Hand | Labour | hr | 8.5 | 44.2 | 375.7 | 68
2011-11-16 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 68
2011-11-16 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 68
2011-11-16 | Inv - 263194 | Quick Cut Saw |  | 1 | 890.4 | 890.4 | 68
2011-11-16 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 68
2011-11-16 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 68
2011-11-16 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 68
2011-11-16 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 68
2011-11-16 | Tipper | Bernie Currey | hr | 5 | 65 | 325 | 68
2011-11-16 | ( MoultyTyres Roller ) | Tutt Bryant | day | 1 | 365 | 365 | 68
2011-11-16 | UD Spreader Truck - No Driver | UD Spreader | hr | 3 | 21.61 | 64.83 | 68
2011-11-21 | Pad Foot Roller Inv- 263716 | PF Roller |  | 1 | 2705 | 2705 | 68
2012-03-21 | Stabilised Sand. Inv No - 67145154 | Stabilised Sand |  | 5 | 119 | 595 | 68
| Subtotal for 068 |  |  |  |  | 47892.13
Portfolio WBS 071
2011-10-26 | 11 Tonne Excavator | Shannons Excavations | hr | 2 | 110 | 220 | 71
2011-10-26 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 2 | 90 | 180 | 71
2011-11-01 | Inv 49 | Concrete Subbie |  | 1 | 3120 | 3120 | 71
2012-01-24 | Leading Hand | Labour | hr | 5.5 | 44.2 | 243.1 | 71
2012-01-24 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 71
2012-01-24 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 71
2012-02-15 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 71
2012-02-15 | ( Bobcat Hire ) | Bernie Currey | hole | 4.5 | 95 | 427.5 | 71
2012-02-15 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 71
2012-02-15 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 71
2012-02-15 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 71
2012-02-21 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 71
2012-02-22 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 71
2012-03-01 | Set Pharr & Finish Drain. Drain outlet outside McDowells. Inv No - 956521 | Concrete Subbie |  | 1 | 780 | 780 | 71
2012-03-01 | Crossovers & Driveway. Inv No - 956521 | Concrete Subbie |  | 1 | 18775 | 18775 | 71
2012-03-21 | Inv No - 198339 | Kerb Subbie |  | 1 | 5000 | 5000 | 71
| Subtotal for 071 |  |  |  |  | 30901.95
Portfolio WBS 072
2011-11-07 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 2 | 95 | 190 | 72
2011-11-07 | ( Bobcat Hire ) | Bernie Currey | hr | 3 | 95 | 285 | 72
2011-11-07 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 72
2011-11-07 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 72
2011-11-08 | Leading Hand | Labour | hr | 9.5 | 44.2 | 419.9 | 72
2011-11-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-08 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-09 | Leading Hand | Labour | hr | 9.5 | 44.2 | 419.9 | 72
2011-11-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 72
2011-11-21 | Leading Hand | Labour | hr | 6.5 | 44.2 | 287.3 | 72
2011-11-21 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 72
2011-12-13 | N32 Concrete Inv No 8787 | N32 |  | 1 | 390 | 390 | 72
2011-12-13 | Truck Hire | Bernie Currey | hr | 1.5 | 65 | 97.5 | 72
2011-12-13 | ( Bobcat Hire ) | Bernie Currey | hr | 5 | 95 | 475 | 72
2011-12-16 | N32 Concrete Inv No 8844 | N32 |  | 1 | 170.76 | 170.76 | 72
2011-12-17 | N32 Concrete Inv No - 66998739 | N32 |  | 1 | 278.4 | 278.4 | 72
2012-06-01 | Set Place & Finish of Concrete Driveway. Inv No - 956535 | Concrete Subbie |  | 1 | 1845 | 1845 | 72
| Subtotal for 072 |  |  |  |  | 6696.985
Portfolio WBS 073
2012-03-01 | Set & Place Pram Rämp. Inv No - 956521 | Concrete Subbie |  | 1 | 3600 | 3600 | 73
2012-04-01 | Set & Place Driveways. Inv No - 956525 | Concrete Subbie |  | 1 | 7970 | 7970 | 73
| Subtotal for 073 |  |  |  |  | 11570
Portfolio WBS 075
2011-11-07 | Concrete Sub-contractor (Slab on Ground) Saw Cutting 30.6m - 80mm Deep Inv - 1403 | Concrete Sub-contract |  | 1 | 269.28 | 269.28 | 75
2012-01-24 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 75
2012-01-30 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 75
2012-01-30 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 75
2012-02-09 | Labour Hire | Labour | hr | 3 | 35.35 | 106.05 | 75
2012-02-09 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 75
2012-02-10 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-02-10 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-02-10 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 1 | 90 | 90 | 75
2012-02-15 | Fuel .Hired on the 15/02/2012. Inv No - 274134 | Generator |  | 1 | 64.1 | 64.1 | 75
2012-02-21 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 75
2012-02-21 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 75
2012-02-21 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 75
2012-02-22 | Breaker Points & Fuel. & Damage Waiver. Hired from the 20/02/12 - 22/02/12. Inv No - 274731 | Generator |  | 1 | 243.71 | 243.71 | 75
2012-02-22 | Humphries ( Grader ) Dry Hire | Humphries | hr | 9 | 100 | 900 | 75
2012-02-23 | Humphries ( Grader ) Dry Hire | Humphries | hr | 9 | 100 | 900 | 75
2012-02-28 | Hired on the 15/02/2012. Inv No - 274134 | Drill Hammer |  | 1 | 39 | 39 | 75
| Subtotal for 075 |  |  |  |  | 4008.49
Portfolio WBS 081
2011-09-08 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 81
2011-09-08 | Labour Hire | Labour | hr | 1 | 35.35 | 35.35 | 81
2011-09-08 | Leading Hand | Labour | hr | 2.5 | 44.2 | 110.5 | 81
2011-09-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 81
2011-09-13 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 81
2011-09-14 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 81
2011-09-14 | Leading Hand | Labour | hr | 10.5 | 44.2 | 464.1 | 81
2011-09-15 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-15 | Plate Compactor - Dry Hire Inv - 254219 | Plate Compactor |  | 1 | 362.55 | 362.55 | 81
2011-09-15 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-16 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-09-16 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 81
2011-09-17 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 81
2011-09-17 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 81
2011-09-17 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-09-19 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-19 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 81
2011-09-19 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-19 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-20 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-20 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 81
2011-09-20 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 81
2011-09-20 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-20 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 81
2011-09-20 | 140 G Grader | Berry Excavations | hr | 7.5 | 100 | 750 | 81
2011-09-20 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-21 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 81
2011-09-21 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-21 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 81
2011-09-21 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 81
2011-09-21 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-22 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-09-22 | Labour Hire | Labour | hr | 8 | 10.5 | 84 | 81
2011-09-22 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 81
2011-09-22 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 81
2011-09-23 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 81
2011-09-23 | Labour Hire | Labour | hr | 8 | 10.5 | 84 | 81
2011-09-23 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 81
2011-09-23 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 81
2011-09-26 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-26 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-27 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-28 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-09-28 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-09-29 | Leading Hand | Labour | hr | 10.5 | 44.2 | 464.1 | 81
2011-09-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 81
2011-09-30 | Leading Hand | Labour | hr | 9 | 44.2 | 397.8 | 81
2011-09-30 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 81
2011-10-01 | Leading Hand | Labour | hr | 7 | 44.2 | 309.4 | 81
2011-10-03 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-10-04 | Concrete saw Qui, Diamond Blade 14IN Inv - 255016 | Sawcut |  | 1 | 329.28 | 329.28 | 81
2011-10-04 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-10-10 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 81
2011-10-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-10-10 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-10-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-10-11 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-10-11 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 81
2011-10-12 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 81
2011-10-12 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 81
2011-10-13 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 81
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 81
2011-10-13 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 81
2011-10-13 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 81
2011-10-13 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 81
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 81
2011-10-13 | 12 T Excavator | Shannons Excavations | hr | 5 | 110 | 550 | 81
2011-10-14 | Tipper Hire | Michael Biles | hr | 3 | 95 | 285 | 81
2011-10-14 | Tipper/ Water Cart | Tom Hurst | hr | 4 | 85 | 340 | 81
2011-10-14 | 12 T Excavator | Shannons Excavations | hr | 4 | 110 | 440 | 81
2011-10-15 | Water Tipper | Humphries | hr | 2 | 60 | 120 | 81
2011-10-15 | Tipper/ Water Cart | Tom Hurst | hr | 5.5 | 85 | 467.5 | 81
2011-10-15 | 12 T Excavator | Shannons Excavations | hr | 5 | 110 | 550 | 81
2011-10-15 | Backhoe (Wet) | Tom Hurst | hr | 5 | 90 | 450 | 81
2011-10-15 | Backhoe (Dry) | Tom Hurst | hr | 4 | 55 | 220 | 81
2011-10-17 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 4 | 90 | 360 | 81
2011-10-17 | 12 T Excavator | Shannons Excavations | hr | 4 | 110 | 440 | 81
2011-10-18 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2011-10-18 | Backhoe (Wet) | Tom Hurst | hr | 6 | 90 | 540 | 81
2011-10-18 | Leading Hand | Labour | hr | 6 | 44.2 | 265.2 | 81
2011-10-18 | 12 T Excavator | Shannons Excavations | hr | 6 | 110 | 660 | 81
2011-10-18 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 6 | 90 | 540 | 81
2011-10-18 | Ford Ranger 4WD Utility | Ford Utility | hr | 6 | 11.67 | 70.02 | 81
2011-10-19 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 81
2011-10-19 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 81
2011-10-19 | 12 T Excavator | Shannons Excavations | hr | 5 | 110 | 550 | 81
2011-10-24 | 12 T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 81
2011-10-25 | 11 Tonne Excavator | Shannons Excavations | hr | 6 | 110 | 660 | 81
2011-10-25 | Leading Hand | Labour | hr | 6.5 | 44.2 | 287.3 | 81
2011-10-26 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 81
2011-10-27 | Ford Ranger 4WD Utility | Ford Utility | hr | 4 | 11.67 | 46.68 | 81
2011-10-27 | 12 T Excavator | Shannons Excavations | hr | 4 | 110 | 440 | 81
2011-10-28 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 81
2012-01-13 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 6 | 95 | 570 | 81
2012-01-30 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 81
2012-01-31 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 81
2012-11-01 | Backhoe Hire | Terry Flanagan | hr | 6 | 95 | 570 | 81
| Subtotal for 081 |  |  |  |  | 34010.8
Portfolio WBS 087
2011-10-05 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 87
2011-10-05 | Tipper Hire | Michael Biles | hr | 10.5 | 130 | 1365 | 87
2011-10-05 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 87
2011-10-05 | Leading Hand | Labour | hr | 10 | 44.2 | 442 | 87
2011-10-05 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 87
2011-10-06 | Plant Hire Tractor Profiler | Tractor Profiler | day | 1 | 1500 | 1500 | 87
2011-10-06 | Leading Hand | Labour | hr | 10.5 | 44.2 | 464.1 | 87
2011-10-06 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 87
2011-10-06 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2011-10-07 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 87
2011-10-07 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 87
2011-10-07 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 87
2011-10-08 | Labour Hire | Labour | hr | 6 | 35.35 | 212.1 | 87
2011-10-08 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 87
2011-10-08 | Leading Hand | Labour | hr | 6 | 44.2 | 265.2 | 87
2011-10-13 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 87
2011-10-13 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 87
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 87
2011-10-13 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 87
2011-10-13 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 87
2011-10-13 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 87
2011-10-14 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 87
2011-10-14 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 87
2011-10-14 | Leading Hand | Labour | hr | 8 | 44.2 | 353.6 | 87
2011-10-15 | Labour Hire | Labour | hr | 5.5 | 35.35 | 194.425 | 87
2011-10-15 | Leading Hand | Labour | hr | 5.5 | 44.2 | 243.1 | 87
2011-10-15 | Ford Ranger 4WD Utility | Ford Utility | hr | 5.5 | 11.67 | 64.185 | 87
2011-10-17 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 87
2011-10-17 | Leading Hand | Labour | hr | 5 | 44.2 | 221 | 87
2011-10-17 | Ford Ranger 4WD Utility | Ford Utility | hr | 5 | 11.67 | 58.35 | 87
2011-10-18 | Ford Ranger 4WD Utility | Ford Utility | hr | 2.5 | 11.67 | 29.175 | 87
2011-10-18 | Labour Hire | Labour | hr | 2.5 | 35.35 | 88.375 | 87
2011-10-18 | Leading Hand | Labour | hr | 2.5 | 44.2 | 110.5 | 87
2011-10-24 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2011-10-24 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 87
2011-10-24 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 87
2011-10-25 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 87
2011-11-24 | Drainage Aggregate Docket No 14916 Inv 19789 | Drainage Agg |  | 1 | 590 | 590 | 87
2012-01-09 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 8 | 90 | 720 | 87
2012-01-09 | Berry Excavator ( 7 t Excavator ) | Berry Excavations | hr | 8 | 110 | 880 | 87
2012-01-09 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 87
2012-01-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-01-09 | Labour Hire. ( Concrete Supervisor ) | Labour | hr | 3.5 | 57.7 | 201.95 | 87
2012-01-09 | Float | Berry Excavations | hr | 1 | 120 | 120 | 87
2012-01-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-01-10 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 9 | 90 | 810 | 87
2012-01-10 | Berry Excavator ( 7 t Excavator ) | Berry Excavations | hr | 8.75 | 110 | 962.5 | 87
2012-01-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-01-10 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 87
2012-01-10 | Labour Hire ( People Resourcing ) | Labour | hr | 9.5 | 40.97 | 389.215 | 87
2012-01-11 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 87
2012-01-11 | Labour Hire ( People Resourcing ) | Labour | hr | 9 | 40.97 | 368.73 | 87
2012-01-11 | Berry Excavator ( 7 t Excavator ) | Berry Excavations | hr | 7.5 | 110 | 825 | 87
2012-01-11 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 8 | 90 | 720 | 87
2012-03-06 | Drainage Aggregate. Inv No - 20487 | Drainage Agg |  | 1 | 1028.5 | 1028.5 | 87
| Subtotal for 087 |  |  |  |  | 19291.025
Portfolio WBS 103
2011-12-23 | Inv 132 | Water Subbie |  | 1 | 13840 | 13840 | 103
| Subtotal for 103 |  |  |  |  | 13840
Portfolio WBS 141
2011-09-05 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 141
2011-09-05 | Labour HIre | Labour | hr | 5 | 35.35 | 176.75 | 141
2011-09-05 | Leading Hand | Labour | hr | 6.5 | 44.2 | 287.3 | 141
2011-09-05 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 141
2011-09-05 | General signs & delineation for traffic control. Inv- 8193019 | Signs - General |  | 1 | 3628.13 | 3628.13 | 141
2011-09-05 | General signs & delineation for traffic control. Inv - IN-8196974 | Signs - General |  | 1 | 1203.48 | 1203.48 | 141
2011-09-06 | General signs & delineation for traffic control. Inv - 8194707 | Signs - General |  | 1 | 590.25 | 590.25 | 141
2011-09-08 | Labour HIre | Labour | hr | 10 | 35.35 | 353.5 | 141
2011-09-08 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 141
2011-09-12 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 141
2011-09-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 141
2011-09-13 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 141
2011-09-13 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 141
2011-10-05 | General signs & delineation for traffic control. Inv - IN-8196973 | Signs - General |  | 1 | 2020.72 | 2020.72 | 141
2011-10-13 | General signs & delineation for traffic control. Inv - IN-81498139 | Signs - General |  | 1 | 1647 | 1647 | 141
2011-10-17 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2011-10-18 | General signs & delineation for traffic control. Inv - In-8198707 | Signs - General |  | 1 | 2044 | 2044 | 141
2011-10-20 | XH Stackable Barriers Inv - 259020 | Traffic Controller |  | 1 | 291.79 | 291.79 | 141
2011-10-27 | Labour Hire | Labour | hr | 7.5 | 35.35 | 265.125 | 141
2011-10-28 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2011-10-31 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2011-11-02 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 141
2012-01-05 | General signs & delineation for traffic control . Inv No - 8207984 | Signs - General |  | 1 | 2304.16 | 2304.16 | 141
2012-01-09 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2012-01-11 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 141
2012-01-23 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2012-01-24 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2012-02-16 | General signs & delineation for traffic control. Inv No - 8208844 | Signs - General |  | 1 | 1487.08 | 1487.08 | 141
2012-02-20 | Inv No - 8212900 | Signs - General |  | 1 | 368.47 | 368.47 | 141
2012-02-22 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 141
2012-02-23 | Labour Hire | Labour | hr | 6.5 | 35.35 | 229.775 | 141
| Subtotal for 141 |  |  |  |  | 21548.605
Portfolio WBS 181
2011-09-13 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 2 | 26.46 | 52.92 | 181
2011-09-14 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3 | 26.46 | 79.38 | 181
2011-09-15 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3.5 | 26.46 | 92.61 | 181
2011-09-20 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 4.5 | 26.46 | 119.07 | 181
2011-09-21 | Tipper ( standown ) | Michael Biles | hr | 3.5 | 45 | 157.5 | 181
2011-09-21 | 11 T Excavator | Shannons Excavations | hr | 3.5 | 110 | 385 | 181
2011-09-21 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3.5 | 26.46 | 92.61 | 181
2011-09-22 | 11 T Excavator | Shannons Excavations | hr | 2 | 110 | 220 | 181
2011-09-22 | 140 G Grader | Berry Excavations | hr | 3 | 100 | 300 | 181
2011-09-22 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3.5 | 26.46 | 92.61 | 181
2011-09-22 | Tipper ( standown ) | Michael Biles | hr | 2 | 45 | 90 | 181
2011-09-23 | Tipper/ Water Cart | Tom Hurst | hr | 4 | 85 | 340 | 181
2011-09-23 | Ford Ranger 4WD Utility | Ford Utility | hr | 8 | 11.67 | 93.36 | 181
2011-09-23 | Truck Hire | Michael Biles | hr | 5 | 95 | 475 | 181
2011-09-23 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 2 | 26.46 | 52.92 | 181
2011-09-23 | Tipper | Michael Biles | hr | 3.5 | 125 | 437.5 | 181
2011-09-23 | 11 T Excavator | Shannons Excavations | hr | 6 | 110 | 660 | 181
2011-09-26 | Tipper | Michael Biles | hr | 5 | 95 | 475 | 181
2011-09-26 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 181
2011-09-26 | 140 G Grader | Berry Excavations | hr | 1 | 100 | 100 | 181
2011-09-26 | tipper ( standown) | Michael Biles | hr | 5 | 45 | 225 | 181
2011-09-26 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3.5 | 26.46 | 92.61 | 181
2011-09-26 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 181
2011-09-26 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 181
2011-09-27 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-09-27 | 140 G Grader | Berry Excavations | hr | 1 | 100 | 100 | 181
2011-09-27 | tipper ( standown) | Michael Biles | hr | 4 | 45 | 180 | 181
2011-09-27 | Tipper | Michael Biles | hr | 6 | 95 | 570 | 181
2011-09-27 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 181
2011-09-27 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3.5 | 26.46 | 92.61 | 181
2011-09-27 | Labour Hire ( Driving own car ) | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-09-27 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 181
2011-09-27 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 181
2011-09-28 | Truck Hire | Michael Biles | hr | 6 | 95 | 570 | 181
2011-09-28 | Standown | Michael Biles | hr | 4 | 45 | 180 | 181
2011-09-28 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 10 | 26.46 | 264.6 | 181
2011-09-28 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 181
2011-09-28 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 181
2011-09-28 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-09-28 | 140 G Grader | Berry Excavations | hr | 1 | 100 | 100 | 181
2011-09-28 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 181
2011-09-28 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-09-29 | Tipper | Michael Biles | hr | 10 | 95 | 950 | 181
2011-09-29 | Ford Ranger 4WD Utility | Ford Utility | hr | 10.5 | 11.67 | 122.535 | 181
2011-09-29 | 140 G Grader | Berry Excavations | hr | 3 | 100 | 300 | 181
2011-09-29 | 11T Excavator | Shannons Excavations | hr | 10.5 | 110 | 1155 | 181
2011-09-29 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 3.5 | 26.46 | 92.61 | 181
2011-09-29 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 181
2011-09-29 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 181
2011-09-30 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 5 | 95 | 475 | 181
2011-09-30 | Tipper/ Water Cart | Tom Hurst | hr | 9 | 90 | 810 | 181
2011-09-30 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 181
2011-09-30 | Labour Hire | Labour | hr | 9 | 35.35 | 318.15 | 181
2011-09-30 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 181
2011-09-30 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 9 | 26.46 | 238.14 | 181
2011-09-30 | Ford Ranger 4WD Utility | Ford Utility | hr | 9 | 11.67 | 105.03 | 181
2011-09-30 | 11T Excavator | Shannons Excavations | hr | 9 | 110 | 990 | 181
2011-09-30 | Tipper | Michael Biles | hr | 9 | 95 | 855 | 181
2011-10-01 | Ford Ranger 4WD Utility | Ford Utility | hr | 7 | 11.67 | 81.69 | 181
2011-10-01 | Set & Pour Culverts | Concrete Subbie |  | 1 | 3680 | 3680 | 181
2011-10-01 | Tipper | Michael Biles | hr | 1 | 125 | 125 | 181
2011-10-01 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-10-01 | Bomag 124DH-3 SD Roller (3.5 T) - No Operator | Bomag 124DH | hr | 7 | 26.46 | 185.22 | 181
2011-10-01 | Hire of Traffic Lights | Traffic lights | day | 1 | 125 | 125 | 181
2011-10-01 | 11T Excavator | Shannons Excavations | hr | 6.5 | 110 | 715 | 181
2011-10-03 | Tipper Hire Standby | Michael Biles | hr | 5 | 45 | 225 | 181
2011-10-03 | Tipper Hire | Michael Biles | hr | 5 | 95 | 475 | 181
2011-10-03 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-10-03 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 181
2011-10-03 | Tipper/ Water Cart | Tom Hurst | hr | 1 | 90 | 90 | 181
2011-10-03 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 181
2011-10-03 | Ford Ranger 4WD Utility | Ford Utility | hr | 9.5 | 11.67 | 110.865 | 181
2011-10-04 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 181
2011-10-04 | Labour Hire | Labour | hr | 10 | 35.35 | 353.5 | 181
2011-10-04 | Labour Hire | Labour | hr | 4.5 | 35.35 | 159.075 | 181
2011-10-04 | Ford Ranger 4WD Utility | Ford Utility | hr | 10 | 11.67 | 116.7 | 181
2011-10-05 | 11T Excavator | Shannons Excavations | hr | 10 | 110 | 1100 | 181
2011-10-05 | Labour Hire | Labour | hr | 5 | 35.35 | 176.75 | 181
2011-10-05 | Bobcat/Tipper Hire | Mcdowall Earthmoving | hr | 3 | 90 | 270 | 181
2011-10-06 | Ford Ranger 4WD Utility | Ford Utility | hr | 10.5 | 11.67 | 122.535 | 181
2011-10-06 | Labour Hire | Labour | hr | 7 | 35.35 | 247.45 | 181
2011-10-06 | 11T Excavator | Shannons Excavations | hr | 7.5 | 110 | 825 | 181
2011-10-07 | 11T Excavator | Shannons Excavations | hr | 8 | 110 | 880 | 181
2011-10-08 | Tipper Hire | Michael Biles | hr | 6 | 95 | 570 | 181
2011-10-08 | 11T Excavator | Shannons Excavations | hr | 6 | 110 | 660 | 181
2011-10-12 | 24 * 75MM * 10 MTR Denso Tape 24RL/CRRRTN, 18 * 100MM * 10 MTR Denso Tape Inv - 1578224 | Tapping Band - 100 x 25 |  | 1 | 1170.66 | 1170.66 | 181
2011-10-13 | 5.5 T Excavator Inv - 256406 | Excavator - 8T |  | 1 | 1469.28 | 1469.28 | 181
2011-10-18 | Concrete Saw Qui, Diamond Blade 14 In Inv 258875 | Sawcut |  | 1 | 164.63 | 164.63 | 181
2011-10-25 | Leading Hand | Labour | hr | 4 | 44.2 | 176.8 | 181
2011-10-25 | 11 Tonne Excavator | Shannons Excavations | hr | 4 | 110 | 440 | 181
2011-10-27 | Leading Hand | Labour | hr | 4 | 44.2 | 176.8 | 181
2011-10-28 | Tipper/ Water Cart | Tom Hurst | hr | 9.5 | 90 | 855 | 181
2011-11-01 | Inv 49 | Conduit Subbie |  | 1 | 4400 | 4400 | 181
2011-12-01 | Wrights Rd - Inv 956506 | Concrete Subbie |  | 1 | 13860 | 13860 | 181
2012-08-01 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 181
2012-08-01 | Labour Hire (Achieve Group) | Labour | hr | 8.5 | 34.81 | 295.885 | 181
2012-08-01 | Concrete Sub-Contractor | Labour | hr | 8.5 | 45 | 382.5 | 181
2012-08-02 | Labour Hire | Labour | hr | 9.5 | 35.35 | 335.825 | 181
2012-08-02 | Labour Hire (Achieve Group) | Labour | hr | 9.5 | 34.81 | 330.695 | 181
2012-08-02 | Concrete Sub-Contractor | Labour | hr | 9.5 | 45 | 427.5 | 181
2012-08-03 | Concrete Sub-Contractor | Labour | hr | 4 | 45 | 180 | 181
2012-08-03 | Over Time Hours | Labour | hr | 1.586 | 45.7 | 72.4802 | 181
2012-08-03 | Labour Hire | Labour | hr | 4 | 35.35 | 141.4 | 181
2012-08-03 | Labour Hire (Achieve Group) | Labour | hr | 4 | 34.81 | 139.24 | 181
| Subtotal for 181 |  |  |  |  | 59053.1702
Portfolio WBS 182
2011-11-01 | Slab on Ground - Inv 49 | Concrete Subbie |  | 1 | 11490 | 11490 | 182
| Subtotal for 182 |  |  |  |  | 11490
Portfolio WBS 902
2011-09-05 | Project Supervisor | Supervisor | hr | 8.5 | 68.99 | 586.415 | 902
2011-09-06 | Project Supervisor | Supervisor | hr | 3 | 68.99 | 206.97 | 902
2011-09-07 | Project Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-08 | Project Supervisor | Supervisor | hr | 11 | 68.99 | 758.89 | 902
2011-09-09 | Project Supervisor | Supervisor | hr | 9 | 68.99 | 620.91 | 902
2011-09-10 | Project Supervisor | Supervisor | hr | 8.5 | 68.99 | 586.415 | 902
2011-09-12 | Project Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-13 | Project Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-14 | Project Supervisor | Supervisor | hr | 10.5 | 68.99 | 724.395 | 902
2011-09-15 | Project Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-16 | Project Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2011-09-20 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-21 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-22 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-23 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-26 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-27 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-28 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-09-29 | Supervisor | Supervisor | hr | 10.5 | 68.99 | 724.395 | 902
2011-09-30 | Supervisor | Supervisor | hr | 9 | 68.99 | 620.91 | 902
2011-10-01 | Supervisor | Supervisor | hr | 7 | 68.99 | 482.93 | 902
2011-10-03 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-04 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-05 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-06 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-07 | Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2011-10-10 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-11 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-10-11 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-12 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-12 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-10-13 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-13 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-13 | Project Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2011-10-13 | Project Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2011-10-14 | Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2011-10-14 | Project Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-15 | Supervisor | Supervisor | hr | 1 | 68.99 | 68.99 | 902
2011-10-15 | Project Supervisor | Supervisor | hr | 6 | 68.99 | 413.94 | 902
2011-10-17 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-17 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-10-18 | Supervisor | Supervisor | hr | 8.5 | 68.99 | 586.415 | 902
2011-10-19 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-20 | Work Place Health & Safety Officer | WHSO | week | 6 | 45 | 270 | 902
2011-10-20 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-21 | Supervisor | Supervisor | hr | 4.5 | 68.99 | 310.455 | 902
2011-10-24 |  | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-25 | Project supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-25 | Project Supervisor | Supervisor | hr | 10.5 | 68.99 | 724.395 | 902
2011-10-26 | Project supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-26 | Project Supervisor | Supervisor | hr | 10.5 | 68.99 | 724.395 | 902
2011-10-27 | Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-27 | Project Supervisor | Supervisor | hr | 10.5 | 68.99 | 724.395 | 902
2011-10-28 | Project supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2011-10-28 | Leading Hand | Labour | hr | 4 | 44.2 | 176.8 | 902
2011-10-28 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-10-29 | Project Supervisor | Supervisor | hr | 5.5 | 68.99 | 379.445 | 902
2011-10-31 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-11-02 | (Foreman ) | Supervisor | day | 0.4 | 580 | 232 | 902
2011-11-08 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-11-09 | Project Supervisor | Supervisor | hr | 4.5 | 68.99 | 310.455 | 902
2011-11-10 | Project Supervisor | Supervisor | hr | 7.5 | 68.99 | 517.425 | 902
2011-11-11 | Project Supervisor | Supervisor | hr | 9.5 | 68.99 | 655.405 | 902
2011-11-12 | Project Supervisor | Supervisor | hr | 6.5 | 68.99 | 448.435 | 902
2011-11-16 | Project Supervisor | Supervisor | hr | 4 | 68.99 | 275.96 | 902
2011-11-25 | Project Supervisor | Supervisor | hr | 4 | 68.99 | 275.96 | 902
2011-11-28 | Project Supervisor | Supervisor | hr | 6.5 | 68.99 | 448.435 | 902
2011-12-06 | Project Supervisor | Supervisor | hr | 5 | 68.99 | 344.95 | 902
2012-01-09 | Project Supervisor | Supervisor | hr | 9.55 | 68.99 | 658.8545 | 902
2012-01-10 | Project Supervisor | Supervisor | hr | 4.5 | 68.99 | 310.455 | 902
2012-01-11 | Project Supervisor | Supervisor | hr | 5 | 68.99 | 344.95 | 902
2012-01-12 | Project Supervisor | Supervisor | hr | 5 | 68.99 | 344.95 | 902
2012-01-13 | Project Supervisor | Supervisor | hr | 1 | 68.99 | 68.99 | 902
2012-01-21 | Project Supervisor | Supervisor | hr | 6.5 | 68.99 | 448.435 | 902
2012-01-23 | Project Supervisor | Supervisor | hr | 2 | 68.99 | 137.98 | 902
2012-01-24 | Project Supervisor | Supervisor | hr | 5 | 68.99 | 344.95 | 902
2012-01-25 | Project Supervisor | Supervisor | hr | 4 | 68.99 | 275.96 | 902
2012-01-30 | Project Supervisor | Supervisor | hr | 2 | 68.99 | 137.98 | 902
2012-01-31 | Project Supervisor | Supervisor | hr | 1 | 68.99 | 68.99 | 902
2012-02-15 | Project Supervisor | Supervisor | hr | 8.5 | 68.99 | 586.415 | 902
2012-02-21 | Project Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2012-02-22 | Project Supervisor | Supervisor | hr | 10 | 68.99 | 689.9 | 902
2012-02-23 | Project Supervisor | Supervisor | hr | 6.5 | 68.99 | 448.435 | 902
2012-02-27 | Project Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 902
2012-02-28 | Project Supervisor | Supervisor | hr | 4 | 68.99 | 275.96 | 902
2012-03-03 | Project Supervisor | Supervisor | hr | 3.5 | 68.99 | 241.465 | 902
2012-03-05 | Project Supervisor | Supervisor | hr | 3.5 | 68.99 | 241.465 | 902
2012-03-06 | Project Supervisor | Supervisor | hr | 3.5 | 68.99 | 241.465 | 902
2012-03-31 | Project Supervisor | Supervisor | hr | 4 | 71.81 | 287.24 | 902
2012-04-01 | Project Supervisor | Supervisor | hr | 2.5 | 71.81 | 179.525 | 902
2012-04-02 | Project Supervisor | Supervisor | hr | 1 | 71.81 | 71.81 | 902
2012-05-10 | Project Supervisor | Supervisor | hr | 3 | 71.81 | 215.43 | 902
2012-10-23 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-10-25 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
2012-11-01 | Project Supervisor | Supervisor | hr | 8 | 71.81 | 574.48 | 902
| Subtotal for 902 |  |  |  |  | 49348.4995
Portfolio WBS 903
2011-09-14 | Inv - 33292388 Notice of road Works | site establishment |  | 1 | 85.41 | 85.41 | 903
2011-09-30 | Generator 17 KVA Inv - 256405 | Generator |  | 1 | 369.98 | 369.98 | 903
2011-09-30 | Site Office & Tiolet, 1 Pump out during project. Inv 256402 | Crib Facilities |  | 1 | 274 | 274 | 903
2011-10-28 | Bottled Water | Water |  | 1 | 275.5 | 275.5 | 903
2011-10-31 | Site Office & Tiolet, 1 Pump out during project. From the 30/09/2011 to the 31/10/2011 Inv - 260719 | Crib Facilities |  | 1 | 277.76 | 277.76 | 903
2011-10-31 | Lunch Room Inv - 8942189. | Crib Facilities |  | 1 | 837 | 837 | 903
2011-10-31 | 17KVA GEN From the 30/08/2011m to the 25/10/2011 20 KVA GEN From the 25/10/2011 ton thev 31/10/2011 Plus Fuel Inv 260721 | Generator |  | 1 | 2197.3 | 2197.3 | 903
2011-11-01 | Inv 49 | Concrete Subbie |  | 1 | 1080 | 1080 | 903
2011-11-03 | Truck Hire / Water Cart | Doyawanna Truck Hire | hr | 10 | 95 | 950 | 903
2011-11-03 | (Foreman ) | Supervisor | day | 1 | 580 | 580 | 903
2011-11-04 | (Foreman ) | Supervisor | day | 0.6 | 580 | 348 | 903
2011-11-05 | (Foreman ) | Supervisor | day | 0.3 | 580 | 174 | 903
2011-11-07 | From the 7/11/2011 to jthe 7/11/2011 Inv 262126 | Generator |  | 1 | 53.71 | 53.71 | 903
2011-11-23 | Broken Cables | Telstra |  | 1 | 821.12 | 821.12 | 903
2011-11-30 | Luch Rooms Hire from the 31/10/2011 to the 4/11/2011 Inv No - 9066665 | Crib Facilities |  | 1 | 1228.01 | 1228.01 | 903
2011-12-20 | Inv No - 4428 | Float |  | 1 | 170.45 | 170.45 | 903
2011-12-21 | Float from Wrights Road to 52 Kookaburra Drive Inv no 4428 | Float |  | 1 | 170.45 | 170.45 | 903
2012-01-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 903
2012-01-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 903
2012-01-17 | Leading Hand | Labour | hr | 2 | 44.2 | 88.4 | 903
2012-01-17 | Labour Hire | Labour | hr | 2 | 35.35 | 70.7 | 903
2012-01-17 | Project Supervisor | Supervisor | hr | 8 | 68.99 | 551.92 | 903
2012-02-27 | Labour Hire | Labour | hr | 8 | 35.35 | 282.8 | 903
2012-03-21 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 903
2012-03-21 | Labour Hire | Labour | hr | 1.5 | 35.35 | 53.025 | 903
2012-10-25 | Backhoe Hire | Terry Flanagan | hr | 1.25 | 95 | 118.75 | 903
| Subtotal for 903 |  |  |  |  | 11252.71
Portfolio WBS 904
2011-09-20 | Construction Risk Insurance | Insurances |  | 1 | 3922 | 3922 | 904
2011-10-25 | From the 3/10/2011 to the 24/10/2011 Inv - 259535 | Insurances |  | 1 | 213.12 | 213.12 | 904
2011-10-31 | Multityre Roller 16 Tonne From the 19/10/2011 to the 31/10/2011 Damage Waiver Inv - 260722 | Insurances |  | 1 | 435.6 | 435.6 | 904
2011-10-31 | Double Drum( 8 Tonne) Roller Damage Waiver Inv - 260723 | Insurances |  | 1 | 540 | 540 | 904
2011-10-31 | Damage Waiver From the 30/09/2011 to the 31/10/2011 Inv - 260720 | Insurances |  | 1 | 612 | 612 | 904
| Subtotal for 904 |  |  |  |  | 5722.72
Portfolio WBS 905
2011-09-01 | Inv - 08244843 Tripod Builders 1830mm | Small Tools |  | 1 | 90.9 | 90.9 | 905
2011-09-01 | Inv- 8467/23690 Level Spirit Stanley, Marker Artline, Bar Crow Mumme. | Small Tools |  | 1 | 91.43 | 91.43 | 905
2011-09-07 | Inv 349-132720 2 x UHF Hand held radios | Small Tools |  | 1 | 290 | 290 | 905
2011-09-11 | Inv - 7932 Lifting Chain | Small Tools |  | 1 | 340.91 | 340.91 | 905
2011-09-13 | Inv - 8467/23921 | Small Tools |  | 1 | 60.62 | 60.62 | 905
2011-09-20 | Docket No 8467/24055 | Small Tools |  | 1 | 46.11 | 46.11 | 905
2011-09-20 | Docket No 8237479 | Small Tools |  | 1 | 32.418 | 32.418 | 905
2011-09-22 | Docket No 8467/24101 ( Star Pickets ) | Small Tools |  | 1 | 110.88 | 110.88 | 905
2011-09-28 | Hessian Sandbag 140Z Inv - 8276828 | Small Tools |  | 1 | 25.27 | 25.27 | 905
2011-09-28 | Barrow,Protecta.Toilet Roll Inv - 8276816 | Small Tools |  | 1 | 144.52 | 144.52 | 905
2011-09-30 | concrete Saw, Diamond Blade, Vibrating Rammer Inv - 256404 | Small Tools |  | 1 | 2144 | 2144 | 905
2011-10-05 | Tape Duct, Shackles, Chain Inv - 8467/24375 | Small Tools |  | 1 | 142.31 | 142.31 | 905
2011-10-05 | Spray & Mark Pink Inv - 8285404 | Small Tools |  | 24 | 6.13 | 147.12 | 905
2011-10-06 | First Aid Kit Protector (2) Inv - 8467/24412 | Small Tools |  | 1 | 36.36 | 36.36 | 905
2011-10-19 | Tape Duct,Spray Paint Inv - 8467/24721 | Small Tools |  | 1 | 76.84 | 76.84 | 905
2011-10-30 | Inv - 8467/25013 | Small Tools |  | 1 | 30.76 | 30.76 | 905
2011-11-07 | Hessian SandBags Inv No 8325336 | Small Tools |  | 1 | 21.06 | 21.06 | 905
2011-11-07 | BrickLayers Line Tape measure Inv No - 21263879 | Small Tools |  | 1 | 140.22 | 140.22 | 905
2011-11-08 | Denso Tape Inv No - 1588189 | Small Tools |  | 1 | 263.64 | 263.64 | 905
2011-11-09 | Knife Machette Inv No 21263960 | Small Tools |  | 1 | 35.04 | 35.04 | 905
2011-11-11 | Earmuffs Bolster Brickies Inv No - 21264074 | Small Tools |  | 1 | 69.5 | 69.5 | 905
2011-11-24 | Spray & Mark White Inv - 8308013 | Small Tools |  | 1 | 59.89 | 59.89 | 905
2011-12-08 | Poly Guyco Line Inv No - 212641001 | Small Tools |  | 1 | 69.5 | 69.5 | 905
2012-01-11 | DWV PVC Test Opening, Connector Jenco Inv No-8467/26778 | Small Tools |  | 1 | 27.7 | 27.7 | 905
2012-01-11 | DWV Juntion. Inv No - 21266184 | Small Tools |  | 1 | 27.91 | 27.91 | 905
2012-01-12 | Tape Measure, Fence Posts. Inv No 21266259 | Small Tools |  | 1 | 178.91 | 178.91 | 905
2012-01-21 | Cement. Inv No - 21266266 | Small Tools |  | 40 | 9.45 | 378 | 905
2012-01-25 | Medalist Club Hammer, Mattock, Shovel, Star Picket ect. Inv No - 21256664 | Small Tools |  | 1 | 397.4 | 397.4 | 905
2012-02-06 | Clean wipes, Cable Ties, Tape Measur, Cleaner, Steel Round Dowel. Inv No - 21267018 | Small Tools |  | 1 | 158.52 | 158.52 | 905
2012-02-21 | PVC Pipe, PVC Fittings,Tape Duct, Cable Ties. Inv No - 21267574 | Small Tools |  | 1 | 81.86 | 81.86 | 905
2012-02-22 | PVC Pipe Non Pressure DWV. Inv No 21267620 | Small Tools |  | 1 | 24.59 | 24.59 | 905
2012-03-07 | Rain Coats, Star Pickets. Inv No - 21268078 | Small Tools |  | 1 | 93.63 | 93.63 | 905
2012-10-24 | Mortar Cement. Inv No - 21275783 | Small Tools |  | 1 | 11.36 | 11.36 | 905
| Subtotal for 905 |  |  |  |  | 5849.178
Portfolio WBS 907
2011-09-01 | Float Excavator & Roller from Dysart to Wrights Rd - Inv 36191 | Float |  | 1 | 1800 | 1800 | 907
2011-09-07 | Inv - 1311 Container Tropic | site establishment |  | 1 | 100 | 100 | 907
2011-09-19 | 2 Weeks Accommodation - Tom Dalton | Accommodation |  | 1 | 1373.27 | 1373.27 | 907
2011-09-25 | Labour, Cart Agg pipe from Townsville | Michael Biles | hr | 3.5 | 125 | 437.5 | 907
2011-09-30 | Advertising Notice to Wrights Road Inv 73924 | site establishment |  | 1 | 65.1 | 65.1 | 907
2011-09-30 | Inv- 8817829 Lunch Room 17/08/9/2011 to the 30/09/2011 | site establishment |  | 1 | 1378.01 | 1378.01 | 907
2011-10-10 | 140 G Grader | Berry Excavations | hr | 2 | 100 | 200 | 907
2011-10-10 | Saddle Pipe Galv Inv - 21262929 | Small Tools |  | 1 | 25.77 | 25.77 | 907
2011-10-10 | 21 Tonne Excavator Inv - 4827 | Float |  | 1 | 272.73 | 272.73 | 907
2011-10-10 | White Knight Squirts , Tape Jointing, Cable Ties Inv - 21262925 | Small Tools |  | 1 | 47.27 | 47.27 | 907
2011-10-10 | Screws Tex Hd, Nut Setter Inv - 21262934 | Small Tools |  | 1 | 29.13 | 29.13 | 907
2011-10-10 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 907
2011-10-10 | Labour Hire | Labour | hr | 8.5 | 35.35 | 300.475 | 907
2011-10-12 | Saddle Pipe Galv Inv - 20429569 | Small Tools |  | 1 | 33.5 | 33.5 | 907
2011-10-13 | Oil Premium 2 stroke Inv 21263048 | Small Tools |  | 1 | 12.68 | 12.68 | 907
2011-10-17 | 5.5 T Digger Inv - 258686 | Bobcat |  | 1 | 250 | 250 | 907
2011-10-17 | Saddles Pipe Galv Inv - 20429751 | Small Tools |  | 1 | 20.63 | 20.63 | 907
2011-10-23 | 12 H Grader Inv - 0037050 | site establishment |  | 1 | 1130 | 1130 | 907
2011-10-23 | Tractor Mixer Inv - 37049 | site establishment |  | 1 | 1300 | 1300 | 907
2011-10-24 | DWV Level Invert Taper Inv- 21263405 | Small Tools |  | 1 | 26.27 | 26.27 | 907
2011-10-27 | Accommodation & 3 meals Rate From the 26/10/2011 to the 27/10/2011 Inv - 56446 | Accommodation |  | 1 | 103.18 | 103.18 | 907
2011-11-08 | Tipper - Allciv (No Driver) | Tipper - Allciv | hr | 10.5 | 42.79 | 449.295 | 907
2011-11-08 | Labour Hire | Labour | hr | 10.5 | 35.35 | 371.175 | 907
2012-01-09 | Float Steel Roller from Kelsey Crk to Nich Str. Inv N o - 4474 | Float |  | 1 | 125 | 125 | 907
2012-01-09 | Folat Excavator from Bloomsbury to Nicol St. Inv No- 4474 | Float |  | 2 | 125 | 250 | 907
2012-02-12 | Pick up of Roller ( Wright Rd - Bowen ). Inv No - 1534 | Float |  | 2.75 | 110 | 302.5 | 907
| Subtotal for 907 |  |  |  |  | 10703.96
Portfolio WBS C25
2011-10-01 | Bulk GP / GB Cement Inv - 8003 | Cement |  | 6.4 | 133.2 | 852.48 | C25
2011-10-06 | Bulk GP / GB Cement Inv 8041 | Cement |  | 1 | 362 | 362 | C25
2011-11-05 | Docket No 54662729 Inv- 66918006 | C25 |  | 1 | 435 | 435 | C25
2012-02-14 | N25 Concrete. Inv No - 670179822 | N25 |  | 1 | 974.4 | 974.4 | C25
2012-05-05 | N25 Concrete. Inv No - 67213404 | N25 |  | 1 | 1281 | 1281 | C25
| Subtotal for C25 |  |  |  |  | 3904.88
Portfolio WBS C32
2011-09-27 | Docket No - 03294/03293 | Cement |  | 8 | 178.2 | 1425.6 | C32
2011-09-30 | Inv - 66854343 | C32 |  | 1 | 878.4 | 878.4 | C32
2011-09-30 | Inv - 66854344 | C32 |  | 1 | 1903.2 | 1903.2 | C32
2011-10-04 | Inv - 66860218 | C32 |  | 1 | 1812 | 1812 | C32
2011-10-08 | Inv - 66865430 | C32 |  | 1 | 308.4 | 308.4 | C32
2011-10-08 | Inv - 66865431 | C32 |  | 1 | 846.4 | 846.4 | C32
2011-10-08 | Inv - 66865432 | C32 |  | 1 | 1688.4 | 1688.4 | C32
2011-10-08 | Inv - 66865429 | C32 |  | 1 | 1261 | 1261 | C32
2011-10-11 | Inv - 66872219 | C32 |  | 1 | 1030.4 | 1030.4 | C32
2011-10-15 | Inv - 66876691 | C32 |  | 1 | 2994.8 | 2994.8 | C32
2011-10-15 | Inv - 66876690 | C32 |  | 5 | 119 | 595 | C32
2011-10-18 | Inv - 66884900 | C32 |  | 1 | 1669 | 1669 | C32
2011-10-25 | Adjustment U/Charge ( Inv -7979 on the 3/10/2011 ) Inv - 8183 | Cement |  | 1 | 55.76 | 55.76 | C32
2011-10-25 | Adjustment of ( U/Charge Inv 7920 on the 27/09/2011 ) Inv - 81821 | Cement |  | 1 | 4.8 | 4.8 | C32
2011-10-25 | Bulk GP / GB Cement Dock 3548 Inv - 8184 | Cement |  | 5 | 197.6 | 988 | C32
2011-10-26 | Bulk GP / GB CementDocket No 3566 Inv - 8200 | Cement |  | 1 | 483.96 | 483.96 | C32
2011-10-26 | Inv - 66901114 | C32 |  | 1 | 680.4 | 680.4 | C32
2011-10-28 | Inv - 66905030 | C32 |  | 1 | 2112.8 | 2112.8 | C32
2011-10-31 |  | C32 |  | 1 | 216 | 216 | C32
2011-11-05 | Dock No 54687885 Inv - 66918007 | C32 |  | 1 | 294.6 | 294.6 | C32
2011-11-09 | N32 Concrete - Inv QM7984285 | N32 |  | 1 | 452.4 | 452.4 | C32
2011-11-11 | Bulk GP / GB Cement Docket No 3783 Inv - 8402 | Cement |  | 1 | 264.72 | 264.72 | C32
2011-11-12 | Docket No 54715802 Inv - 66929927 | C32 |  | 1 | 279.6 | 279.6 | C32
2011-11-15 | Bulk GP / GB CementDocket No 54747683 Inv - 66937484 | C32 |  | 3.4 | 185 | 629 | C32
2011-11-18 | Bulk GP / GB Cement Dock No 3825 Inv- 8506 | Cement |  | 1 | 327.36 | 327.36 | C32
2011-11-26 | Inv No 66955608 | C32 |  | 1 | 307.2 | 307.2 | C32
2011-11-26 | Inv No 66955609 | C32 |  | 1 | 803.2 | 803.2 | C32
2011-12-10 | N32 Concrete Inv No - 66983957 | N32 |  | 1 | 556.8 | 556.8 | C32
2012-01-17 | Inv No - 9056 | N20 |  | 1 | 214.4 | 214.4 | C32
2012-01-29 | N32 Concrete. Inv No 67052229 | N32 |  | 1 | 1770 | 1770 | C32
2012-01-31 | N32 Concrete. Inv No - 67054144 | N32 |  | 1 | 2902.8 | 2902.8 | C32
2012-02-11 | N32 Concrete. Dock No 55176067,55477003,55179257,55184537,55185299,55187388,55188248,55193256,55194038,55194627,55195603. Inv No 67071217 | N32 |  | 1 | 7633.4 | 7633.4 | C32
2012-02-16 | N32 Concrete.Inv No - QM8185005 | N32 |  | 1 | 778 | 778 | C32
2012-02-18 | 32 Mpa. Inv No - 67085711 | C32 |  | 1 | 1256.5 | 1256.5 | C32
2012-02-18 | 32 Mpa. Inv No - 67085713 | C32 |  | 1 | 2572.5 | 2572.5 | C32
2012-02-21 | N32 Concrete. Inv No - 67093069 | N32 |  | 1 | 353.2 | 353.2 | C32
2012-02-25 | Inv No 67098839 | N32 |  | 1 | 1628.4 | 1628.4 | C32
2012-02-29 | N32 Concrete. Inv No - 93 87 | N32 |  | 4 | 180 | 720 | C32
2012-03-03 | N32 Concrete. Inv No - 67444211 | N32 |  | 1 | 809.6 | 809.6 | C32
2012-06-19 | N32 Concrete. Inv No - QM8467653 | N32 |  | 1 | 158 | 158 | C32
2012-08-01 | N32 Concrete. Inv No 010412 | N32 |  | 3.6 | 185.95 | 669.42 | C32
| Subtotal for C32 |  |  |  |  | 46335.42
Portfolio WBS CKM
2011-09-28 | Bulk GP / GB Cement Inv - 8276816 | Cement |  | 4 | 7.82 | 31.28 | CKM
2012-01-25 | Inv No - QM8136150 | Kerb Machine |  | 1 | 5359.5 | 5359.5 | CKM
| Subtotal for CKM |  |  |  |  | 5390.78
Portfolio WBS CSA
2011-10-14 | Cement Builders Inv - 94498393 | Cement - GP Bulk |  | 34 | 365 | 12410 | CSA
| Subtotal for CSA |  |  |  |  | 12410
Portfolio WBS QM2.3
2012-02-17 | 80.66 T 2.3 Road Base. Inv No - 5107 | Roadbase |  | 1 | 3182.03 | 3182.03 | QM2.3
| Subtotal for QM2.3 |  |  |  |  | 3182.03
Portfolio WBS QMS
2011-10-03 | Bedding Sand Docket No 35602 Inv - 4225 | Sand |  | 11.26 | 13.64 | 153.5864 | QMS
2011-10-03 | Bedding Sand Dock No 35598 Inv - 4225 | Sand |  | 10.48 | 13.64 | 142.9472 | QMS
2011-10-07 | Bedding Sand Docket No 35645 Inv - 4225 | Sand |  | 25 | 13.64 | 341 | QMS
2011-10-15 | Dock 3491 Inv - 8118 | Sand |  | 1 | 292 | 292 | QMS
2011-10-21 | Bedding Sand For Nicole Street Docket No 35854 Inv - 4225 | Sand |  | 14.46 | 16.403 | 237.1874 | QMS
2011-10-24 | Docket No 35869 Inv - 4225 | Sand |  | 11.36 | 13.64 | 154.9504 | QMS
2011-10-24 | Bedding Sand Docket No 35879 Inv - 4225 | Sand |  | 12.32 | 16.883 | 207.9986 | QMS
2011-10-25 | Bedding Sand Dock 3555 Inv - 8181 | Sand |  | 1 | 292 | 292 | QMS
2011-10-27 | Bedding Sand Docket No 35929 Inv 4225 | Sand |  | 6.44 | 19.848 | 127.8211 | QMS
2011-10-28 | Bedding Sand Inv - 66905031 | Sand |  | 1 | 595 | 595 | QMS
2011-10-28 | Bedding Sand for Nicol Street Docket No 35940 Inv - 4225 | Sand |  | 6.62 | 19.678 | 130.2684 | QMS
2011-12-19 | Stabilised Sand - Inv 8867 | Stabilised Sand |  | 1 | 914.96 | 914.96 | QMS
2012-01-09 | Bedding Sand. Inv No - 4474 | Sand |  | 48.58 | 13.64 | 662.6312 | QMS
2012-01-11 | Bedding Sand. Inv No - 4474 | Sand |  | 23.43 | 13.64 | 319.5852 | QMS
2012-01-23 | Bedding Sand. Inv No - 4474 | Sand |  | 2.2 | 36.368 | 80.0096 | QMS
| Subtotal for QMS |  |  |  |  | 4651.9454
Portfolio WBS RSM
2011-09-20 | Inv - 20428288 | Reinforcing Steel |  | 1 | 3246.36 | 3246.36 | RSM
2011-09-26 | Inv - 20428832 | Steel Fixing |  | 1 | 5904.9 | 5904.9 | RSM
2011-09-29 | Inv - | Steel Fixing |  | 1 | 441.72 | 441.72 | RSM
2011-09-29 | inv - 20428967 | Steel Fixing |  | 1 | 1431.81 | 1431.81 | RSM
2011-10-13 | Inv - 19656 | Reinforcing Steel |  | 1 | 580 | 580 | RSM
2012-01-24 | NF 72 Ribmesh & Delivery Fee. Inv 20286 | Ribmesh |  | 1 | 1742.5 | 1742.5 | RSM
2012-02-09 | NF 82 Quare Ribmesh. Inv No - 20354 | Ribmesh |  | 1 | 867 | 867 | RSM
2012-02-15 | NF 82 Suare Ribmesh. Inv No - 20380 | Ribmesh |  | 1 | 293.1 | 293.1 | RSM
2012-02-22 | Inv No - 20424 | Ribmesh |  | 1 | 937.6 | 937.6 | RSM
| Subtotal for RSM |  |  |  |  | 15444.99
Portfolio WBS SWC
2012-08-03 | RCBC - 1200 x 450. Inv No - 21342 | RCBC - 1200 x 450 |  | 2 | 460 | 920 | SWC
| Subtotal for SWC |  |  |  |  | 920
Portfolio WBS SWH
2012-05-24 | Inv No - 00236844 | 375 Sloping Headwall |  | 1 | 551.81 | 551.81 | SWH
2012-06-20 | Inv No - 21056 | 375 Sloping Headwall |  | 1 | 590 | 590 | SWH
| Subtotal for SWH |  |  |  |  | 1141.81
Portfolio WBS SWP
2011-09-23 | Drainage Aggregate Inv - CD 201205677 | Drainage Agg |  | 1 | 4679.5 | 4679.5 | SWP
2011-10-24 | Bulk GP / GB Cement 2.4m - 375mm 2 FJ RC Pipies | Cement |  | 1 | 480 | 480 | SWP
2011-11-03 | 375mm RCP Docket No 14944 Inv 19818 | Wing Walls |  | 1 | 417 | 417 | SWP
| Subtotal for SWP |  |  |  |  | 5576.5
| Grand Total |  |  |  |  | 1021520.0918