## Estimate
| Line No. | Resource Name | Unit | Type | No | Production | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
[9 empty] | 2108483.7421 |  |  | 210805.2414 | 346340.6814 | 119999.5045 | 1431338.3149 | 2108483.7421
| Line No 10 Item No Item | ROADWORKS AND DRAINAGE
5 | Line No 13 Item No 1101.1 | ROADWORKS AND DRAINAGE Site establishment and disestablishment | Lump |  |  |  | 1 |  | 12000 |  | 5 | 0 | 0 | 0 | 12000 | 12000
| 1 | CAR | Item | S | 1 | 1 | 12000 | 1 | 12000 | 12000 | 12000 | 0 | 0 | 0 | 12000 | 12000 | 904
| Line No 23 Item No 2000 | Drainage, Retaining Structures & Protective Treatments
| Line No 24 Item No 2120 | Supply of Precast Concrete Pipe Culverts in accordance with AS 4058 - Exposure Class B1, and Installation of Culverts to MRS03
6 | Line No 25 Item No 2121.2 | Drainage, Retaining Structures & Protective TreatmentsSupply of Precast Concrete Pipe Culverts in accordance with AS 4058 - Exposure Class B1, and Installation of Culverts to MRS03Supply and installation of concrete pipe culvert components, Class 2, RRJ, 375mm diameter with saltwater cover | m |  |  |  | 63.4 |  | 9401.586 |  | 2 | 1217.28 | 6472.506 | 1711.8 | 0 | 9401.586
| 1 | Purchase Materials:
| 2 | 375 RCP | m | M | 1 | 1 | 63.4 | 96.09 | 6092.106 |  |  | 0 | 6092.106 | 0 | 0 | 6092.106 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 15.85 | 24 | 380.4 |  |  | 0 | 380.4 | 0 | 0 | 380.4 | QMS
| 4 | Install:
6.01 | 5 | Excavator - 15T | hr | P | 1 | 5 | 63.4 | 125 | 1585 | 12.68 | 12.68 | 0 | 0 | 1585 | 0 | 1585 | 81
| 6 | Labour | hr | L | 2 | 5 | 63.4 | 48 | 1217.28 | 25.36 | 12.68 | 1217.28 | 0 | 0 | 0 | 1217.28 | 81
| 7 | Plate Compactor | hr | P | 1 | 5 | 63.4 | 10 | 126.8 | 12.68 | 12.68 | 0 | 0 | 126.8 | 0 | 126.8 | 81
7 | Line No 26 Item No 2121.4 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 450mm diameter with saltwater cover | m |  |  |  | 26.8 |  | 4610.404 |  | 1 | 514.56 | 3372.244 | 723.6 | 0 | 4610.404
| 1 | Purchase Materials:
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 26.8 | 119.83 | 3211.444 |  |  | 0 | 3211.444 | 0 | 0 | 3211.444 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 6.7 | 24 | 160.8 |  |  | 0 | 160.8 | 0 | 0 | 160.8 | QMS
| 4 | Install:
7.01 | 5 | Excavator - 15T | hr | P | 1 | 5 | 26.8 | 125 | 670 | 5.36 | 5.36 | 0 | 0 | 670 | 0 | 670 | 81
| 6 | Labour | hr | L | 2 | 5 | 26.8 | 48 | 514.56 | 10.72 | 5.36 | 514.56 | 0 | 0 | 0 | 514.56 | 81
| 7 | Plate Compactor | hr | P | 1 | 5 | 26.8 | 10 | 53.6 | 5.36 | 5.36 | 0 | 0 | 53.6 | 0 | 53.6 | 81
8 | Line No 27 Item No 2121.6 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 525mm diameter with saltwater cover | m |  |  |  | 70.7 |  | 13652.17 |  | 2 | 1357.44 | 10385.83 | 1908.9 | 0 | 13652.17
| 1 | Purchase Materials:
| 2 | 525 RCP FJ CL2 | m | M | 1 | 1 | 70.7 | 140.9 | 9961.63 |  |  | 0 | 9961.63 | 0 | 0 | 9961.63 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 17.675 | 24 | 424.2 |  |  | 0 | 424.2 | 0 | 0 | 424.2 | SWP
| 4 | Install:
8.01 | 5 | Excavator - 15T | hr | P | 1 | 5 | 70.7 | 125 | 1767.5 | 14.14 | 14.14 | 0 | 0 | 1767.5 | 0 | 1767.5 | 82
| 6 | Labour | hr | L | 2 | 5 | 70.7 | 48 | 1357.44 | 28.28 | 14.14 | 1357.44 | 0 | 0 | 0 | 1357.44 | 82
| 7 | Plate Compactor | hr | P | 1 | 5 | 70.7 | 10 | 141.4 | 14.14 | 14.14 | 0 | 0 | 141.4 | 0 | 141.4 | 82
9 | Line No 28 Item No 2121.8 | Supply and installation of concrete pipe culvert components, Class 2,RRJ, 600mm diameter with saltwater cover | m |  |  |  | 31.7 |  | 7442.526 |  | 1 | 608.64 | 5977.986 | 855.9 | 0 | 7442.526
| 1 | Purchase Materials:
| 2 | 600 RCP RRJ CL2 | m | M | 1 | 1 | 31.7 | 182.58 | 5787.786 |  |  | 0 | 5787.786 | 0 | 0 | 5787.786 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 7.925 | 24 | 190.2 |  |  | 0 | 190.2 | 0 | 0 | 190.2 | QMS
| 4 | Install:
9.01 | 5 | Excavator - 15T | hr | P | 1 | 5 | 31.7 | 125 | 792.5 | 6.34 | 6.34 | 0 | 0 | 792.5 | 0 | 792.5 | 82
| 6 | Labour | hr | L | 2 | 5 | 31.7 | 48 | 608.64 | 12.68 | 6.34 | 608.64 | 0 | 0 | 0 | 608.64 | 82
| 7 | Plate Compactor | hr | P | 1 | 5 | 31.7 | 10 | 63.4 | 6.34 | 6.34 | 0 | 0 | 63.4 | 0 | 63.4 | 82
| Line No 29 Item No 2190 | Supply of Stormwater Drainage Pipe Culverts in accordance with AS/NZS 5065, and installation of Culverts to MRS03
10 | Line No 30 Item No 2191.1 | Supply of Stormwater Drainage Pipe Culverts in accordance with AS/NZS 5065, and installation of Culverts to MRS03 - Supply of Stormwater Drainage Pipe Culverts in accordance with AS/NZS 5065, and installation of Culverts to MRS03 - Supply and installation of BlackMAX stormwater pipe, Class SN8, 150 mm diameter | m |  |  |  | 315 |  | 33138 |  | 7 | 6048 | 19215 | 7875 | 0 | 33768
| 1 | Purchase Materials:
| 2 | 150 Black Max SN8 | m | M | 1 | 1 | 315 | 55 | 17325 |  |  | 0 | 17325 | 0 | 0 | 17325 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 78.75 | 24 | 1890 |  |  | 0 | 1890 | 0 | 0 | 1890 | QMS
| 4 | Install:
10.01 | 5 | Excavator - 15T | hr | P | 1 | 5 | 315 | 125 | 7875 | 63 | 63 | 0 | 0 | 7875 | 0 | 7875 | 81
| 6 | Labour | hr | L | 2 | 5 | 315 | 48 | 6048 | 126 | 63 | 6048 | 0 | 0 | 0 | 6048 | 81
| 7 | Plate Compactor | hr | P | 1 | 5 | 315 | 10 | 630 | 63 | 63 | 0 | 0 | 630 | 0 | 630 | 81
| Line No 31 Item No 2260 | Supply and Installation of Drainage Components
11 | Line No 32 Item No 2261.1 | Supply and Installation of Drainage Components - Supply and install 600mm flood flap | each |  |  |  | 1 |  | 2788 |  | 1 | 288 | 2500 | 0 | 0 | 2788
| 1 | Flood Flap | item | M | 1 | 1 | 1 | 2500 | 2500 |  |  | 0 | 2500 | 0 | 0 | 2500 | SWL
11.01 | 2 | Labour | hr | L | 2 | 0.33333 | 1 | 48 | 288 | 6 | 3 | 288 | 0 | 0 | 0 | 288 | 85
| Line No 33 Item No 2300 | Concrete in Culverts and End Structures, MRS03
11.5 | Line No 34 Item No 2308 | Concrete in Culverts and End Structures, MRS03 - End structures to culverts, reinforced concrete | m3 |  |  |  | 1 |  | 950 |  | 1 | 0 | 0 | 0 | 950 | 950
| 1 | Reinforced Concrete - CUM | m³ | S | 1 | 1 | 1 | 950 | 950 | 9 | 9 | 0 | 0 | 0 | 950 | 950 | 72
12 | Line No 35 Item No 2313 | Concrete in Culverts and End Structures, MRS03 - Aprons to culverts, reinforced concrete | m3 |  |  |  | 1 |  | 950 |  | 1 | 0 | 0 | 0 | 950 | 950
| 1 | Reinforced Concrete - CUM | m³ | S | 1 | 1 | 1 | 950 | 950 | 9 | 9 | 0 | 0 | 0 | 950 | 950 | 72
| Line No 37 Item No 2400 | Pavement Drainage, MRS03
13 | Line No 38 Item No 2404.1 | Pavement Drainage, MRS03 Concrete kerb and channel, barrier (B2) | m |  |  |  | 66 |  | 3396.8 |  | 1 | 0 | 888.8 | 198 | 2310 | 3396.8
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 4.4 | 202 | 888.8 |  |  | 0 | 888.8 | 0 | 0 | 888.8 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 66 | 35 | 2310 | 9 | 9 | 0 | 0 | 0 | 2310 | 2310 | 71
13.01 | 3 | Grader | hr | P | 1 | 45 | 66 | 135 | 198 | 1.4667 | 1.4667 | 0 | 0 | 198 | 0 | 198 | 71
14 | Line No 39 Item No 2404.3 | Pavement Drainage, MRS03 Type 1 main roads flush kerb (300x200) | m |  |  |  | 377 |  | 19808.2547 |  | 1 | 0 | 5482.2547 | 1131 | 13195 | 19808.2547
| 1 | S32 - Kerb Mix | m³ | M | 1 | 1 | 27.1399 | 202 | 5482.2547 |  |  | 0 | 5482.2547 | 0 | 0 | 5482.2547 | CKM
| 2 | Kerb Subbie | m | S | 1 | 1 | 377 | 35 | 13195 | 9 | 9 | 0 | 0 | 0 | 13195 | 13195 | 71
14.01 | 3 | Grader | hr | P | 1 | 45 | 377 | 135 | 1131 | 8.3778 | 8.3778 | 0 | 0 | 1131 | 0 | 1131 | 71
15 | Line No 40 Item No 2413.1 | Pavement Drainage, MRS03 3450x1500 ecosol RSF 500 GPT with class B lid | each |  |  |  | 1 |  | 32670 |  | 1 | 0 | 26170 | 0 | 6500 | 32670
| 1 | GPT | Item | M | 1 | 1 | 1 | 26170 | 26170 |  |  | 0 | 26170 | 0 | 0 | 26170 | SWPC
| 2 | GPT Installation | item | S | 1 | 1 | 1 | 6500 | 6500 | 9 | 9 | 0 | 0 | 0 | 6500 | 6500 | 86
16 | Line No 41 Item No 2413.2 | Pavement Drainage, MRS03 600x600 RKO pit with riser 600x600 V-Grate & Concrete Surround | each |  |  |  | 8 |  | 27200 |  | 16 | 0 | 0 | 0 | 27200 | 27200
| 1 | WDC | Item | S | 3400 | 1 | 8 | 1 | 27200 | 489600 | 144 | 0 | 0 | 0 | 27200 | 27200 | 85
17 | Line No 42 Item No 2413.4 | Pavement Drainage, MRS03 - Concrete gullies, Drainway 0TP/X maxflow grate, standard | each |  |  |  | 1 |  | 3950 |  | 1 | 0 | 0 | 0 | 3950 | 3950
| 1 | WDC | Item | S | 3950 | 1 | 1 | 1 | 3950 | 11850 | 3 | 0 | 0 | 0 | 3950 | 3950 | 85
18 | Line No 43 Item No 2141.2 | Pavement Drainage, MRS03 - Concrete manhole with 600dia access lid (major) | each |  |  |  | 1 |  | 3950 |  | 3 | 0 | 0 | 0 | 3950 | 3950
| 1 | WDC | Item | S | 3950 | 1 | 1 | 1 | 3950 | 106650 | 27 | 0 | 0 | 0 | 3950 | 3950 | 85
| Line No 44 Item No 2500 | Subsurface Drainage MRS03
19 | Line No 45 Item No 2501.1 | Subsurface Drainage MRS03 - Subsoil drains, Type C, 100 mm diameter including outlets and flush points | m |  |  |  | 390 |  | 15382.5425 |  | 6 | 5184 | 3448.5425 | 6750 | 0 | 15382.5425
| 1 | Purchase Materials:
| 2 | Sub Soil Drain | m | M | 1 | 1 | 498.03 | 3.3 | 1643.499 |  |  | 0 | 1643.499 | 0 | 0 | 1643.499 | 87
| 3 | Sub Soil Flush Fittings | each | M | 1 | 1 | 13.3699 | 65 | 869.0435 |  |  | 0 | 869.0435 | 0 | 0 | 869.0435 | 87
| 4 | Sand | tonne | M | 1 | 1 | 39 | 24 | 936 |  |  | 0 | 936 | 0 | 0 | 936 | QMS
| 5 | install:
19.01 | 6 | Excavator - 15T | hr | P | 1 | 7.2222 | 390 | 125 | 6750 | 54 | 54 | 0 | 0 | 6750 | 0 | 6750 | 87
| 7 | Labour | hr | L | 2 | 7.2222 | 390 | 48 | 5184 | 108 | 54 | 5184 | 0 | 0 | 0 | 5184 | 87
| Line No 47 Item No 2600 | Protective Treatments, MRS03
20 | Line No 48 Item No 2631.1 | Protective Treatments, MRS03 - Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 1.2m wide | m2 |  |  |  | 188 |  | 13898.4741 |  | 4 | 360.96 | 7164.3141 | 357.2 | 6016 | 13898.4741
| 1 | Purchase Materials:
| 2 | N32 | m³ | M | 1 | 1 | 20.6798 | 198 | 4094.5991 |  |  | 0 | 4094.5991 | 0 | 0 | 4094.5991 | C25
| 3 | SL82 | m² | M | 1 | 1 | 244.4 | 6.5 | 1588.6 |  |  | 0 | 1588.6 | 0 | 0 | 1588.6 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 20.6798 | 24 | 496.315 |  |  | 0 | 496.315 | 0 | 0 | 496.315 | QMS
| 5 | Black Plastic | m² | M | 1 | 1 | 244.4 | 1.25 | 305.5 |  |  | 0 | 305.5 | 0 | 0 | 305.5 | RSM
| 6 | Curing Oil | litre | M | 1 | 1 | 188 | 3.35 | 629.8 |  |  | 0 | 629.8 | 0 | 0 | 629.8 | RSM
| 7 | Bar Chairs - 40mm | Item | M | 1 | 1 | 5 | 9.9 | 49.5 |  |  | 0 | 49.5 | 0 | 0 | 49.5 | RSM
| 8 | Prep & Install:
20.01 | 9 | Bobcat | hr | P | 1 | 50 | 188 | 95 | 357.2 | 3.76 | 3.76 | 0 | 0 | 357.2 | 0 | 357.2 | 73
| 10 | Labour | hr | L | 2 | 50 | 188 | 48 | 360.96 | 7.52 | 3.76 | 360.96 | 0 | 0 | 0 | 360.96 | 73
| 11 | Place & Finish
| 12 | Concrete Subbie | m² | S | 1 | 1 | 188 | 32 | 6016 | 33.84 | 33.84 | 0 | 0 | 0 | 6016 | 6016 | 73
21 | Line No 49 Item No 2631.2 | Protective Treatments, MRS03 - Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 2.0m wide | m2 |  |  |  | 38.1 |  | 2816.5272 |  | 1 | 73.152 | 1451.7852 | 72.39 | 1219.2 | 2816.5272
| 1 | Purchase Materials:
| 2 | N32 | m³ | M | 1 | 1 | 4.191 | 198 | 829.8097 |  |  | 0 | 829.8097 | 0 | 0 | 829.8097 | C25
| 3 | SL82 | m² | M | 1 | 1 | 49.53 | 6.5 | 321.945 |  |  | 0 | 321.945 | 0 | 0 | 321.945 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 4.191 | 24 | 100.583 |  |  | 0 | 100.583 | 0 | 0 | 100.583 | QMS
| 5 | Black Plastic | m² | M | 1 | 1 | 49.53 | 1.25 | 61.9125 |  |  | 0 | 61.9125 | 0 | 0 | 61.9125 | RSM
| 6 | Curing Oil | litre | M | 1 | 1 | 38.1 | 3.35 | 127.635 |  |  | 0 | 127.635 | 0 | 0 | 127.635 | RSM
| 7 | Bar Chairs - 40mm | Item | M | 1 | 1 | 1 | 9.9 | 9.9 |  |  | 0 | 9.9 | 0 | 0 | 9.9 | RSM
| 8 | Prep & Install:
21.01 | 9 | Bobcat | hr | P | 1 | 50 | 38.1 | 95 | 72.39 | 0.762 | 0.762 | 0 | 0 | 72.39 | 0 | 72.39 | 73
| 10 | Labour | hr | L | 2 | 50 | 38.1 | 48 | 73.152 | 1.524 | 0.762 | 73.152 | 0 | 0 | 0 | 73.152 | 73
| 11 | Place & Finish
| 12 | Concrete Subbie | m² | S | 1 | 1 | 38.1 | 32 | 1219.2 | 6.858 | 6.858 | 0 | 0 | 0 | 1219.2 | 1219.2 | 73
22 | Line No 50 Item No 2631.5 | Protective Treatments, MRS03 - Hand-placed concrete paving, 170mm thick, N32/20 with SL82 mesh central with exposed aggregate finish (incl. joints as detailed) | m2 |  |  |  | 240 |  | 34443.1896 |  | 5 | 460.8 | 17926.3896 | 456 | 15600 | 34443.1896
| 1 | Purchase Materials:
| 2 | S32 - Exposed Aggregate | m³ | M | 1 | 1 | 44.8766 | 312 | 14001.4959 |  |  | 0 | 14001.4959 | 0 | 0 | 14001.4959 | E32
| 3 | SL82 | m² | M | 1 | 1 | 312 | 6.5 | 2028 |  |  | 0 | 2028 | 0 | 0 | 2028 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 26.3997 | 24 | 633.5937 |  |  | 0 | 633.5937 | 0 | 0 | 633.5937 | QMS
| 5 | Black Plastic | m² | M | 1 | 1 | 312 | 1.25 | 390 |  |  | 0 | 390 | 0 | 0 | 390 | RSM
| 6 | Curing Oil | litre | M | 1 | 1 | 240 | 3.35 | 804 |  |  | 0 | 804 | 0 | 0 | 804 | RSM
| 7 | Bar Chairs - 40mm | Item | M | 1 | 1 | 7 | 9.9 | 69.3 |  |  | 0 | 69.3 | 0 | 0 | 69.3 | RSM
| 8 | Prep & Install:
22.01 | 9 | Bobcat | hr | P | 1 | 50 | 240 | 95 | 456 | 4.8 | 4.8 | 0 | 0 | 456 | 0 | 456 | 73
| 10 | Labour | hr | L | 2 | 50 | 240 | 48 | 460.8 | 9.6 | 4.8 | 460.8 | 0 | 0 | 0 | 460.8 | 73
| 11 | Place & Finish
| 12 | Concrete Subbie (Exposed) | m² | S | 1 | 1 | 240 | 65 | 15600 | 43.2 | 43.2 | 0 | 0 | 0 | 15600 | 15600 | 73
| Line No 52 Item No 2700 | Retaining Walls, MRS03
23 | Line No 53 Item No 2712 | Retaining Walls, MRS03 - Natural local stone mass gravity wall. 500mm thick, vertical face including footing (1m x 400mm thick) and rear drainage | m2 |  |  |  | 677 |  | 456355.226 |  | 91 | 16476.0123 | 87299.8423 | 35492.1661 | 317087.2054 | 456355.226
| 1 | Purchase Materials:
| 2 | Bent Steel | item | M | 1 | 1 | 2.5 | 2200 | 5500 |  |  | 0 | 5500 | 0 | 0 | 5500 | RSB
| 3 | SL82 | m² | M | 1 | 1 | 1027.009 | 6.5 | 6675.5585 |  |  | 0 | 6675.5585 | 0 | 0 | 6675.5585 | RSM
| 4 | N32 | m³ | M | 1 | 1 | 234.9879 | 198 | 46527.5946 |  |  | 0 | 46527.5946 | 0 | 0 | 46527.5946 | C20
| 5 | Drainage Agg | tonne | M | 1 | 1 | 396.1381 | 42.5 | 16835.8689 |  |  | 0 | 16835.8689 | 0 | 0 | 16835.8689 | QMR
| 6 | A24 | m² | M | 1 | 1 | 2399.965 | 1.05 | 2519.9633 |  |  | 0 | 2519.9633 | 0 | 0 | 2519.9633 | 222
| 7 | Dowels | each | M | 1 | 1 | 62.002 | 8 | 496.0161 |  |  | 0 | 496.0161 | 0 | 0 | 496.0161 | RSB
| 8 | Dowel Sleeves | each | M | 1 | 1 | 62.002 | 1.4 | 86.8028 |  |  | 0 | 86.8028 | 0 | 0 | 86.8028 | RSB
| 9 | 50 HD uPVC Electrical | m | M | 1 | 1 | 109.9919 | 3 | 329.9756 |  |  | 0 | 329.9756 | 0 | 0 | 329.9756 | ETC
| 10 | Sub Soil Drain | m | M | 1 | 1 | 627.4328 | 3.3 | 2070.5283 |  |  | 0 | 2070.5283 | 0 | 0 | 2070.5283 | 87
| 11 | Sub Soil Flush Fittings | each | M | 1 | 1 | 27.0001 | 65 | 1755.0052 |  |  | 0 | 1755.0052 | 0 | 0 | 1755.0052 | 87
| 12 | Sub Soil Flush Fittings | each | M | 1 | 1 | 47.6358 | 65 | 3096.327 |  |  | 0 | 3096.327 | 0 | 0 | 3096.327 | 87
| 13 | Abel Flex | m | M | 1 | 1 | 677 | 1.1 | 744.7 |  |  | 0 | 744.7 | 0 | 0 | 744.7 | RSB
| 14 | Bar Chairs - 125mm | Item | M | 1 | 1 | 27.0001 | 24.5 | 661.502 |  |  | 0 | 661.502 | 0 | 0 | 661.502 | RSB
| 15 | Place & Finish Footings:
| 16 | Concretor - Footings | m | S | 1 | 1 | 569.8653 | 95 | 54137.2054 | 128.2197 | 128.2197 | 0 | 0 | 0 | 54137.2054 | 54137.2054 | 135
| 17 | Place & Finish Walls:
| 18 | Rock Wall Builder < 1400 | m² | S | 1 | 1 | 677 | 350 | 236950 | 812.4 | 812.4 | 0 | 0 | 0 | 236950 | 236950 | 132
| 20 | Excavator - 15T | hr | P | 1 | 1 | 120.0142 | 125 | 15001.7727 | 120.0142 | 120.0142 | 0 | 0 | 15001.7727 | 0 | 15001.7727 | 132
| 21 | Cartage - Rock | Item | S | 650 | 1 | 40 | 1 | 26000 | 26000 | 40 | 0 | 0 | 0 | 26000 | 26000 | QMR
| 22 | Subsoil Drains:
23.01 | 23 | Excavator - 15T | hr | P | 1 | 7.222 | 627.4328 | 125 | 10859.7481 | 86.878 | 86.878 | 0 | 0 | 10859.7481 | 0 | 10859.7481 | 87
| 24 | Labour | hr | L | 2 | 7.222 | 627.4328 | 48 | 8340.2866 | 173.756 | 86.878 | 8340.2866 | 0 | 0 | 0 | 8340.2866 | 87
| 25 | Drainage Aggregate:
23.02 | 26 | Bobcat | hr | P | 1 | 10 | 396.1381 | 95 | 3763.3119 | 39.6138 | 39.6138 | 0 | 0 | 3763.3119 | 0 | 3763.3119 | 132
| 27 | Labour | hr | L | 2 | 10 | 396.1381 | 48 | 3802.9257 | 79.2276 | 39.6138 | 3802.9257 | 0 | 0 | 0 | 3802.9257 | 132
| 28 | Backfill:
23.03 | 29 | Bobcat | hr | P | 1 | 15 | 677 | 95 | 4287.6667 | 45.1333 | 45.1333 | 0 | 0 | 4287.6667 | 0 | 4287.6667 | 52
| 30 | Trench Roller | hr | P | 1 | 15 | 677 | 35 | 1579.6667 | 45.1333 | 45.1333 | 0 | 0 | 1579.6667 | 0 | 1579.6667 | 52
| 31 | Labour | hr | L | 2 | 15 | 677 | 48 | 4332.8 | 90.2667 | 45.1333 | 4332.8 | 0 | 0 | 0 | 4332.8 | 52
| Line No 55 Item No 3000 | Earthworks
24 | Line No 59 Item No 3201 | Earthworks - Road excavation, all materials to reprofile the subgrade level | m3 |  |  |  | 380 |  | 3690.2222 |  | 1 | 1216 | 0 | 2474.2222 | 0 | 3690.2222
| 1 | Subgrade Preparation:
24.01 | 2 | Grader | hr | P | 1 | 150 | 1266.6667 | 135 | 1140 | 8.4444 | 8.4444 | 0 | 0 | 1140 | 0 | 1140 | 61
| 3 | PF Roller Wet - No OP | hr | P | 1 | 150 | 1266.6667 | 58 | 489.7778 | 8.4444 | 8.4444 | 0 | 0 | 489.7778 | 0 | 489.7778 | 61
| 4 | Water Cart - Hire | hr | P | 1 | 150 | 1266.6667 | 100 | 844.4444 | 8.4444 | 8.4444 | 0 | 0 | 844.4444 | 0 | 844.4444 | 61
| 5 | Labour | hr | L | 3 | 150 | 1266.6667 | 48 | 1216 | 25.3333 | 8.4444 | 1216 | 0 | 0 | 0 | 1216 | 61
25 | Line No 60 Item No 3201.2 | Earthworks - Allotment excavation to Revised RL (3.9 - 3.7) | m3 |  |  |  | 1000 |  | 10548.3871 |  | 2 | 2322.5806 | 0 | 8225.8065 | 0 | 10548.3871
25.01 | 1 | Excavator - 25T | hr | P | 1 | 62 | 1000 | 125 | 2016.129 | 16.129 | 16.129 | 0 | 0 | 2016.129 | 0 | 2016.129 | 54
| 2 | Tipper | hr | P | 2 | 62 | 1000 | 95 | 3064.5161 | 32.2581 | 16.129 | 0 | 0 | 3064.5161 | 0 | 3064.5161 | 54
| 3 | Bobcat | hr | P | 1 | 62 | 1000 | 95 | 1532.2581 | 16.129 | 16.129 | 0 | 0 | 1532.2581 | 0 | 1532.2581 | 54
| 4 | Water Cart - Hire | hr | P | 1 | 62 | 1000 | 100 | 1612.9032 | 16.129 | 16.129 | 0 | 0 | 1612.9032 | 0 | 1612.9032 | 54
| 5 | Labour | hr | L | 3 | 62 | 1000 | 48 | 2322.5806 | 48.3871 | 16.129 | 2322.5806 | 0 | 0 | 0 | 2322.5806 | 54
| Line No 61 Item No 3300 | Earthworks, Embankment, MRS04
26 | Line No 62 Item No 3301.2 | Earthworks, Embankment, MRS04 - Re-trim allotments to revised FL | m2 |  |  |  | 9000 |  | 9925.7143 |  | 3 | 2468.5714 | 0 | 7457.1429 | 0 | 9925.7143
26.01 | 1 | Grader | hr | P | 1 | 350 | 9000 | 135 | 3471.4286 | 25.7143 | 25.7143 | 0 | 0 | 3471.4286 | 0 | 3471.4286 | 59
| 2 | Water Cart - Hire | hr | P | 1 | 350 | 9000 | 100 | 2571.4286 | 25.7143 | 25.7143 | 0 | 0 | 2571.4286 | 0 | 2571.4286 | 59
| 3 | SD Roller - Wet (No Op) | hr | P | 1 | 350 | 9000 | 55 | 1414.2857 | 25.7143 | 25.7143 | 0 | 0 | 1414.2857 | 0 | 1414.2857 | 59
| 4 | Labour | hr | L | 2 | 350 | 9000 | 48 | 2468.5714 | 51.4286 | 25.7143 | 2468.5714 | 0 | 0 | 0 | 2468.5714 | 59
| Line No 64 Item No 4100 | Unbound Pavements, MRS05
27 | Line No 65 Item No 4103.1 | Unbound Pavements, MRS05 - Base, unbound pavement, Type 2, Subtype 2.1 | m3 |  |  |  | 125 |  | 15087.8611 |  | 1 | 648 | 10500 | 3939.8611 | 0 | 16887.8611
| 1 | Purchase Materials:
| 2 | CBR80 | tonne | M | 1 | 1 | 300 | 31 | 9300 |  |  | 0 | 9300 | 0 | 0 | 9300 | QM2.1
| 3 | Pugmill | tonne | M | 1 | 1 | 300 | 4 | 1200 |  |  | 0 | 1200 | 0 | 0 | 1200 | QM2.1
| 4 | Installation:
27.01 | 5 | Grader | hr | P | 1 | 44.4444 | 300 | 135 | 911.25 | 6.75 | 6.75 | 0 | 0 | 911.25 | 0 | 911.25 | 62
| 6 | Water Cart - Hire | hr | P | 1 | 44.4444 | 300 | 100 | 675 | 6.75 | 6.75 | 0 | 0 | 675 | 0 | 675 | 62
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 44.4444 | 300 | 55 | 371.25 | 6.75 | 6.75 | 0 | 0 | 371.25 | 0 | 371.25 | 62
| 8 | MW Roller | hr | P | 1 | 44.4444 | 300 | 55 | 371.25 | 6.75 | 6.75 | 0 | 0 | 371.25 | 0 | 371.25 | 62
| 9 | Labour | hr | L | 2 | 44.4444 | 300 | 48 | 648 | 13.5 | 6.75 | 648 | 0 | 0 | 0 | 648 | 62
| 10 | Final Trim:
27.02 | 11 | Grader | hr | P | 1 | 150 | 833.3333 | 135 | 750 | 5.5556 | 5.5556 | 0 | 0 | 750 | 0 | 750 | 63
| 12 | Water Cart - Hire | hr | P | 1 | 150 | 833.3333 | 100 | 555.5556 | 5.5556 | 5.5556 | 0 | 0 | 555.5556 | 0 | 555.5556 | 63
| 13 | MW Roller | hr | P | 1 | 150 | 833.3333 | 55 | 305.5556 | 5.5556 | 5.5556 | 0 | 0 | 305.5556 | 0 | 305.5556 | 63
| 14 | Labour | hr | L | 2 | 44.4444 | 833.3333 | 48 | 1800 | 37.5 | 18.75 | 1800 | 0 | 0 | 0 | 1800 | 63
28 | Line No 66 Item No 4104.2 | Unbound Pavements, MRS05 - Subbase, unbound pavement, Type 2, Subtype 2.3 | m3 |  |  |  | 190 |  | 23360.7837 |  | 2 | 1700.264 | 15960 | 5700.5197 | 0 | 23360.7837
| 1 | Purchase Materials:
| 2 | CBR80 | tonne | M | 1 | 1 | 456 | 31 | 14136 |  |  | 0 | 14136 | 0 | 0 | 14136 | QM2.3
| 3 | Pugmill | tonne | M | 1 | 1 | 456 | 4 | 1824 |  |  | 0 | 1824 | 0 | 0 | 1824 | QM2.3
| 4 | Installation:
28.01 | 5 | Grader | hr | P | 1 | 44.444 | 456 | 135 | 1385.1139 | 10.2601 | 10.2601 | 0 | 0 | 1385.1139 | 0 | 1385.1139 | 62
| 6 | Water Cart - Hire | hr | P | 1 | 44.444 | 456 | 100 | 1026.0103 | 10.2601 | 10.2601 | 0 | 0 | 1026.0103 | 0 | 1026.0103 | 62
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 44.444 | 456 | 55 | 564.3056 | 10.2601 | 10.2601 | 0 | 0 | 564.3056 | 0 | 564.3056 | 62
| 8 | MW Roller | hr | P | 1 | 44.444 | 456 | 55 | 564.3056 | 10.2601 | 10.2601 | 0 | 0 | 564.3056 | 0 | 564.3056 | 62
| 9 | Labour | hr | L | 2 | 44.444 | 456 | 48 | 984.9698 | 20.5202 | 10.2601 | 984.9698 | 0 | 0 | 0 | 984.9698 | 62
| 10 | Final Trim:
28.02 | 11 | Grader | hr | P | 1 | 170 | 1266.6667 | 135 | 1005.8824 | 7.451 | 7.451 | 0 | 0 | 1005.8824 | 0 | 1005.8824 | 63
| 12 | Water Cart - Hire | hr | P | 1 | 170 | 1266.6667 | 100 | 745.098 | 7.451 | 7.451 | 0 | 0 | 745.098 | 0 | 745.098 | 63
| 13 | MW Roller | hr | P | 1 | 170 | 1266.6667 | 55 | 409.8039 | 7.451 | 7.451 | 0 | 0 | 409.8039 | 0 | 409.8039 | 63
| 14 | Labour | hr | L | 2 | 170 | 1266.6667 | 48 | 715.2941 | 14.902 | 7.451 | 715.2941 | 0 | 0 | 0 | 715.2941 | 63
29 | Line No 67 Item No 4104.4 | Unbound Pavements, MRS05 - Subbase, unbound pavement, Type 2, Subtype 2.3 under 170mm Concrete | m3 |  |  |  | 36 |  | 6019.8834 |  | 1 | 709.6345 | 3024 | 2286.2489 | 0 | 6019.8834
| 1 | Purchase Materials:
| 2 | CBR80 | tonne | M | 1 | 1 | 86.4 | 31 | 2678.4 |  |  | 0 | 2678.4 | 0 | 0 | 2678.4 | QM2.3
| 3 | Pugmill | tonne | M | 1 | 1 | 86.4 | 4 | 345.6 |  |  | 0 | 345.6 | 0 | 0 | 345.6 | QM2.3
| 4 | Installation:
29.01 | 5 | Grader | hr | P | 1 | 33.333 | 86.4 | 135 | 349.9235 | 2.592 | 2.592 | 0 | 0 | 349.9235 | 0 | 349.9235 | 62
| 6 | Water Cart - Hire | hr | P | 1 | 33.333 | 86.4 | 100 | 259.2026 | 2.592 | 2.592 | 0 | 0 | 259.2026 | 0 | 259.2026 | 62
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 33.333 | 86.4 | 55 | 142.5614 | 2.592 | 2.592 | 0 | 0 | 142.5614 | 0 | 142.5614 | 62
| 8 | MW Roller | hr | P | 1 | 33.333 | 86.4 | 55 | 142.5614 | 2.592 | 2.592 | 0 | 0 | 142.5614 | 0 | 142.5614 | 62
| 9 | Labour | hr | L | 2 | 33.333 | 86.4 | 48 | 248.8345 | 5.1841 | 2.592 | 248.8345 | 0 | 0 | 0 | 248.8345 | 62
| 10 | Final Trim:
29.02 | 11 | Grader | hr | P | 1 | 50 | 240 | 135 | 648 | 4.8 | 4.8 | 0 | 0 | 648 | 0 | 648 | 63
| 12 | Water Cart - Hire | hr | P | 1 | 50 | 240 | 100 | 480 | 4.8 | 4.8 | 0 | 0 | 480 | 0 | 480 | 63
| 13 | MW Roller | hr | P | 1 | 50 | 240 | 55 | 264 | 4.8 | 4.8 | 0 | 0 | 264 | 0 | 264 | 63
| 14 | Labour | hr | L | 2 | 50 | 240 | 48 | 460.8 | 9.6 | 4.8 | 460.8 | 0 | 0 | 0 | 460.8 | 63
| Line No 68 Item No 5100 | Sprayed Bituminous Surfacing (Excluding Emulsion), MRS11
30 | Line No 69 Item No 5141.1 | Sprayed Bituminous Surfacing (Excluding Emulsion), MRS11 - Sprayed bituminous surfacing, including supply of binder, including supply of additives, including supply and spreading of precoated cover aggregates. 7mm Primerseal, MC5 1.0L/m2, 175m2/m3 | m2 |  |  |  | 955 |  | 17548.125 |  | 1 | 0 | 0 | 0 | 17548.125 | 17548.125
| 1 | Primer Seal - SP1 | m² | S | 1 | 1 | 1002.75 | 17.5 | 17548.125 | 4.5124 | 4.5124 | 0 | 0 | 0 | 17548.125 | 17548.125 | 64
| Line No 70 Item No 5600 | Asphalt Surfacing, Brisbane City Council Asphalt Specification S310
31 | Line No 71 Item No 5602.1 | Asphalt Surfacing, Brisbane City Council Asphalt Specification S310 - Asphalt Surfacing, Brisbane City Council Asphalt Specification S310 - AC10 Type 2 mix | tonne |  |  |  | 80 |  | 39160 |  | 1 | 0 | 0 | 0 | 39160 | 39160
| 1 | DG10 | tonne | S | 1 | 1 | 88 | 445 | 39160 | 3.96 | 3.96 | 0 | 0 | 0 | 39160 | 39160 | 65
| Line No 73 Item No 6140 | Roadside Structures, MRS16A
| Line No 74 Item No 6161.1 | Ballistrade guardrail (NOT INCLUDED. BY OWNERS)
32 | Line No 75 Item No 6161.3 | Roadside Structures, MRS16A - Stair Risers and treads (Hardwood & Stainless - Provisional) | Item |  |  |  | 1 |  | 84579.6 |  | 13 | 0 | 9699.6 | 0 | 74880 | 84579.6
| 1 | Purchase Materials:
| 2 | N40 | m³ | M | 1 | 1 | 35.2 | 198 | 6969.6 |  |  | 0 | 6969.6 | 0 | 0 | 6969.6 | 121
| 3 | SL82 | m² | M | 1 | 1 | 420 | 6.5 | 2730 |  |  | 0 | 2730 | 0 | 0 | 2730 | 121
| 4 | Form & Place:
| 5 | Concretor - Stairs | each | S | 13 | 1 | 1 | 5760 | 74880 | 1521 | 117 | 0 | 0 | 0 | 74880 | 74880 | 121
| Line No 76 Item No 9000 | Miscellaneous Works
32.5 | Line No 78 Item No 9001 | Compliance testing | Lump |  |  |  | 1 |  | 57531 |  | 0 | 28800 | 0 | 0 | 28731 | 57531
| 1 | Compaction Test:
| 2 | Field Density (subgrade) | each | S | 1 | 1 | 4 | 172 | 688 | 4 | 4 | 0 | 0 | 0 | 688 | 688 | 13
| 3 | Field Density (subgrade) | each | S | 1 | 1 | 4 | 172 | 688 | 4 | 4 | 0 | 0 | 0 | 688 | 688 | 13
| 4 | Field Density (subgrade) | each | S | 1 | 1 | 4 | 172 | 688 | 4 | 4 | 0 | 0 | 0 | 688 | 688 | 13
| 5 | Field Density (subgrade) | each | S | 1 | 1 | 8 | 172 | 1376 | 8 | 8 | 0 | 0 | 0 | 1376 | 1376 | 13
| 6 | Field Density (subgrade) | each | S | 1 | 1 | 2 | 172 | 344 | 2 | 2 | 0 | 0 | 0 | 344 | 344 | 13
| 7 | Field Density (subgrade) | each | S | 1 | 1 | 2 | 172 | 344 | 2 | 2 | 0 | 0 | 0 | 344 | 344 | 13
| 8 | Field Density (subgrade) | each | S | 1 | 1 | 12 | 172 | 2064 | 12 | 12 | 0 | 0 | 0 | 2064 | 2064 | 13
| 9 | Field Density (subgrade) | each | S | 1 | 1 | 12 | 172 | 2064 | 12 | 12 | 0 | 0 | 0 | 2064 | 2064 | 13
| 12 | Concrete Cylinders | each | S | 1 | 1 | 24 | 225 | 5400 | 24 | 24 | 0 | 0 | 0 | 5400 | 5400 | 13
| 13 | Concrete Cylinders | each | S | 1 | 1 | 24 | 225 | 5400 | 24 | 24 | 0 | 0 | 0 | 5400 | 5400 | 13
| 14 | Concrete Cylinders | each | S | 1 | 1 | 6 | 225 | 1350 | 6 | 6 | 0 | 0 | 0 | 1350 | 1350 | 13
| 15 | Concrete Cylinders | each | S | 1 | 1 | 2 | 225 | 450 | 2 | 2 | 0 | 0 | 0 | 450 | 450 | 13
| 16 | Concrete Cylinders | each | S | 1 | 1 | 6 | 225 | 1350 | 6 | 6 | 0 | 0 | 0 | 1350 | 1350 | 13
| 17 | Concrete Cylinders | each | S | 1 | 1 | 2 | 225 | 450 | 2 | 2 | 0 | 0 | 0 | 450 | 450 | 13
| 18 | Concrete Cylinders | each | S | 1 | 1 | 2 | 225 | 450 | 2 | 2 | 0 | 0 | 0 | 450 | 450 | 13
| 19 | Concrete Cylinders | each | S | 1 | 1 | 1 | 225 | 225 | 1 | 1 | 0 | 0 | 0 | 225 | 225 | 13
| 20 | Concrete Cylinders | each | S | 1 | 1 | 24 | 225 | 5400 | 24 | 24 | 0 | 0 | 0 | 5400 | 5400 | 13
| 22 | Project Administrator | hr | L | 1 | 1 | 600 | 48 | 28800 | 600 | 600 | 28800 | 0 | 0 | 0 | 28800 | 916
33 | Line No 79 Item No 9002 | Survey Set Out | Lump |  |  |  | 1 |  | 15945 |  | 0 | 0 | 0 | 0 | 15945 | 15945
| 1 | Survey | Item | S | 15945 | 1 | 1 | 1 | 15945 | 15945 | 1 | 0 | 0 | 0 | 15945 | 15945 | 11
34 | Line No 80 Item No 9002 | Preparation of "As constructed" drawings for submission | Lump |  |  |  | 1 |  | 7390 |  | 5 | 0 | 0 | 0 | 7390 | 7390
| 1 | Survey | Item | S | 7390 | 1 | 1 | 1 | 7390 | 332550 | 45 | 0 | 0 | 0 | 7390 | 7390 | 12
35 | Line No 81 Item No 9051 | Locate and protect services - general | Lump |  |  |  | 1 |  | 1998 |  | 2 | 0 | 0 | 0 | 1998 | 1998
| 1 | Service Locator | hr | S | 14.8 | 1 | 1 | 135 | 1998 | 219.04 | 14.8 | 0 | 0 | 0 | 1998 | 1998 | 15
| Line No 84 Item No Item | WATER PRESSURE MAINS
| Line No 85 Item No 9300 | Water Reticulation
| Line No 86 Item No 9304 | Supply OPVC pressure pipe, RRJ, (C.I.O.D. compatible) PN 16
36 | Line No 87 Item No 9304.1 | WATER PRESSURE MAINS - Water Reticulation - Supply OPVC pressure pipe, RRJ, (C.I.O.D. compatible) PN 16 100mm dia | m |  |  |  | 253 |  | 3795 |  | 4 | 0 | 0 | 0 | 3795 | 3795
| 1 | WDC | Item | S | 15 | 1 | 253 | 1 | 3795 | 506.25 | 33.75 | 0 | 0 | 0 | 3795 | 3795 | 103
| Line No 88 Item No 9311 | Supply sluice valves, C.I. to AS 2544, PN 16, counterclockwise to close c/w spindle cap incl. F.B.E./Rilsan coating, incl 316 S/S Flange insertion set (FL-FL)
37 | Line No 89 Item No 9311.1 | WATER PRESSURE MAINS Supply sluice valves, C.I. to AS 2544, PN 16, counterclockwise to close c/w spindle cap incl. F.B.E./Rilsan coating, incl 316 S/S Flange insertion set (FL-FL) 100mm dia | Each |  |  |  | 6 |  | 8100 |  | 0 | 0 | 0 | 0 | 8100 | 8100
| 1 | WDC | Item | S | 1350 | 1 | 6 | 1 | 8100 | 0 |  | 0 | 0 | 0 | 8100 | 8100 | 103
| Line No 90 Item No 9320 | Supply bends, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681 (SOC-SOC)
38 | Line No 91 Item No 9320.2 | WATER PRESSURE MAINS - Supply bends, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681 (SOC-SOC) 100mm x 22½o | Each |  |  |  | 2 |  | 240 |  | 0 | 0 | 0 | 0 | 240 | 240
| 1 | WDC | Item | S | 120 | 1 | 2 | 1 | 240 | 0 |  | 0 | 0 | 0 | 240 | 240 | 103
39 | Line No 92 Item No 9320.3 | WATER PRESSURE MAINS - 100mm x 45o | Each |  |  |  | 3 |  | 360 |  | 0 | 0 | 0 | 0 | 360 | 360
| 1 | WDC | Item | S | 120 | 1 | 3 | 1 | 360 | 0 |  | 0 | 0 | 0 | 360 | 360 | 103
40 | Line No 93 Item No 9320.4 | WATER PRESSURE MAINS - 100mm x 90o | Each |  |  |  | 2 |  | 280 |  | 0 | 0 | 0 | 0 | 280 | 280
| 1 | WDC | Item | S | 140 | 1 | 2 | 1 | 280 | 0 |  | 0 | 0 | 0 | 280 | 280 | 103
| Line No 94 Item No 9340 | Supply tees, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set for flange ends
41 | Line No 95 Item No 9343.1 | WATER PRESSURE MAINS - Supply tees, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set for flange ends - 100 x 100mm (FL-FLxFL) | Each |  |  |  | 3 |  | 840 |  | 0 | 0 | 0 | 0 | 840 | 840
| 1 | WDC | Item | S | 280 | 1 | 3 | 1 | 840 | 0 |  | 0 | 0 | 0 | 840 | 840 | 103
| Line No 96 Item No 9360 | Supply hydrant tee, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set (SOC-SOCxFL)
42 | Line No 97 Item No 9360.1 | WATER PRESSURE MAINS -Supply hydrant tee, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set (SOC-SOCxFL) - 100x80? | Each |  |  |  | 2 |  | 560 |  | 0 | 0 | 0 | 0 | 560 | 560
| 1 | WDC | Item | S | 280 | 1 | 2 | 1 | 560 | 0 |  | 0 | 0 | 0 | 560 | 560 | 103
43 | Line No 98 Item No 9361.1 | WATER PRESSURE MAINS -Supply spring hydrant incl. F.B.E./Rilsan coating | Each |  |  |  | 2 |  | 600 |  | 0 | 0 | 0 | 0 | 600 | 600
| 1 | WDC | Item | S | 300 | 1 | 2 | 1 | 600 | 0 |  | 0 | 0 | 0 | 600 | 600 | 103
44 | Line No 99 Item No 9362.2 | WATER PRESSURE MAINS - Supply hydrant risers 80?x300mm (FL-FL) (Provisional, if ordered) | Each |  |  |  | 2 |  | 260 |  | 0 | 0 | 0 | 0 | 260 | 260
| 1 | WDC | Item | S | 130 | 1 | 2 | 1 | 260 | 0 |  | 0 | 0 | 0 | 260 | 260 | 103
45 | Line No 100 Item No 9363.1 | WATER PRESSURE MAINS - Supply hydrant cover boxes | Each |  |  |  | 2 |  | 200 |  | 0 | 0 | 0 | 0 | 200 | 200
| 1 | WDC | Item | S | 100 | 1 | 2 | 1 | 200 | 0 |  | 0 | 0 | 0 | 200 | 200 | 103
46 | Line No 101 Item No 9364.1 | WATER PRESSURE MAINS - Install cover boxes to hydrants incl. supply of margin sets & bedding bricks & markers | Each |  |  |  | 2 |  | 1040 |  | 0 | 0 | 0 | 0 | 1040 | 1040
| 1 | WDC | Item | S | 520 | 1 | 2 | 1 | 1040 | 0 |  | 0 | 0 | 0 | 1040 | 1040 | 103
| Line No 102 Item No 9391 | Supply connectors (FL-SOC) DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set
47 | Line No 103 Item No 9391.1 | WATER PRESSURE MAINS - Supply connectors (FL-SOC) DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set - 100? | Each |  |  |  | 7 |  | 700 |  | 0 | 0 | 0 | 0 | 700 | 700
| 1 | WDC | Item | S | 100 | 1 | 7 | 1 | 700 | 0 |  | 0 | 0 | 0 | 700 | 700 | 103
| Line No 104 Item No 9400 | Supply gibault joints
48 | Line No 105 Item No 9401.2 | WATER PRESSURE MAINS - Supply gibault joints 150mm dia | Each |  |  |  | 2 |  | 500 |  | 0 | 0 | 0 | 0 | 500 | 500
| 1 | WDC | Item | S | 250 | 1 | 2 | 1 | 500 | 0 |  | 0 | 0 | 0 | 500 | 500 | 103
| Line No 106 Item No 9470 | House Connection Services (Refer MRC Std Dwg A3-00840) including supply and installation of 100 mm tapping band, main cock and poly pipe to property boundary
49 | Line No 107 Item No 9470.1 | WATER PRESSURE MAINS - House Connection Services (Refer MRC Std Dwg A3-00840) including supply and installation of 100 mm tapping band, main cock and poly pipe to property boundary - 32mm single (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each |  |  |  | 7 |  | 2800 |  | 3 | 0 | 0 | 0 | 2800 | 2800
| 1 | WDC | Item | S | 400 | 1 | 7 | 1 | 2800 | 8400 | 21 | 0 | 0 | 0 | 2800 | 2800 | 103
50 | Line No 108 Item No 9470.2 | WATER PRESSURE MAINS - 32mm single under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each |  |  |  | 2 |  | 4000 |  | 2 | 0 | 0 | 0 | 4000 | 4000
| 1 | WDC | Item | S | 2000 | 1 | 2 | 1 | 4000 | 36000 | 18 | 0 | 0 | 0 | 4000 | 4000 | 103
51 | Line No 109 Item No 9470.3 | WATER PRESSURE MAINS - 32mm dual (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each |  |  |  | 4 |  | 1920 |  | 1 | 0 | 0 | 0 | 1920 | 1920
| 1 | WDC | Item | S | 480 | 1 | 4 | 1 | 1920 | 1920 | 4 | 0 | 0 | 0 | 1920 | 1920 | 103
52 | Line No 110 Item No 9470.4 | WATER PRESSURE MAINS - 32mm dual under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each |  |  |  | 3 |  | 6240 |  | 3 | 0 | 0 | 0 | 6240 | 6240
| 1 | WDC | Item | S | 2080 | 1 | 3 | 1 | 6240 | 56160 | 27 | 0 | 0 | 0 | 6240 | 6240 | 103
| Line No 111 Item No 9523 | WATER PRESSURE MAINS - Excavate, lay, bed, joint and backfill OPVC pressure pipe, RRJ main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835)
53 | Line No 112 Item No 9523.1 | WATER PRESSURE MAINS - Excavate, lay, bed, joint and backfill OPVC pressure pipe, RRJ main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835) - 100mm dia | m |  |  |  | 253 |  | 20240 |  | 5 | 0 | 0 | 0 | 20240 | 20240
| 1 | WDC | Item | S | 80 | 1 | 253 | 1 | 20240 | 3036 | 37.95 | 0 | 0 | 0 | 20240 | 20240 | 103
54 | Line No 113 Item No | WATER PRESSURE MAINS - Supply & Installation of 100mm diameter water meter with an 80mm bypass line as per detail A of U13481.001-122(B) | item |  |  |  | 1 |  | 9600 |  | 1 | 0 | 0 | 0 | 9600 | 9600
| 1 | WDC | Item | S | 9600 | 1 | 1 | 1 | 9600 | 86400 | 9 | 0 | 0 | 0 | 9600 | 9600 | 103
| Line No 114 Item No 9525 | Extra Over Items
55 | Line No 115 Item No 9526 | WATER PRESSURE MAINS - Dewatering of trench extra to Items 9521 - 9524 (Provisional, if ordered) | m |  |  |  | 253 |  | 3795 |  | 0 | 0 | 0 | 0 | 3795 | 3795
| 1 | WDC | Item | S | 15 | 1 | 253 | 1 | 3795 | 0 |  | 0 | 0 | 0 | 3795 | 3795 | 103
56 | Line No 116 Item No 9527.1 | WATER PRESSURE MAINS - Supply and placing of approved sand filling 150 - 300mm above top of pipe (Type 1 construction) (Provisional, if ordered) | m³ |  |  |  | 25 |  | 1375 |  | 0 | 0 | 0 | 0 | 1375 | 1375
| 1 | WDC | Item | S | 55 | 1 | 25 | 1 | 1375 | 0 |  | 0 | 0 | 0 | 1375 | 1375 | 103
57 | Line No 117 Item No 9529.1 | WATER PRESSURE MAINS - Supply and Install Fire Booster (Provisional, if ordered) MARINA ITEM | Each |  |  |  | 1 |  | 17266.88 |  | 1 | 0 | 0 | 0 | 17266.88 | 17266.88
| 1 | WDC | Item | S | 17266.88 | 1 | 1 | 1 | 17266.88 | 155401.92 | 9 | 0 | 0 | 0 | 17266.88 | 17266.88 | 103
58 | Line No 118 Item No 9531.2 | WATER PRESSURE MAINS - Concrete Grade N20 in place for thrust blocks | m³ |  |  |  | 5 |  | 1750 |  | 0 | 0 | 0 | 0 | 1750 | 1750
| 1 | WDC | Item | S | 350 | 1 | 5 | 1 | 1750 | 0 |  | 0 | 0 | 0 | 1750 | 1750 | 103
59 | Line No 119 Item No 9596 | WATER PRESSURE MAINS - Flushing and chlorination of mains including supply of chlorine | Lump |  |  |  | 1 |  | 1000 |  | 3 | 0 | 0 | 0 | 1000 | 1000
| 1 | WDC | Item | S | 1000 | 1 | 1 | 1 | 1000 | 27000 | 27 | 0 | 0 | 0 | 1000 | 1000 | 103
60 | Line No 120 Item No 9597 | WATER PRESSURE MAINS - Testing of water mains including supply of pressurising equipment, gauges and fittings | Lump |  |  |  | 1 |  | 1500 |  | 1 | 0 | 0 | 0 | 1500 | 1500
| 1 | WDC | Item | S | 1500 | 1 | 1 | 1 | 1500 | 13500 | 9 | 0 | 0 | 0 | 1500 | 1500 | 103
61 | Line No 121 Item No 9598.1 | WATER PRESSURE MAINS - Connection to existing Council main, 100mm dia (incl. Council fees) | Lump |  |  |  | 1 |  | 2000 |  | 1 | 0 | 0 | 0 | 2000 | 2000
| 1 | WDC | Item | S | 2000 | 1 | 1 | 1 | 2000 | 18000 | 9 | 0 | 0 | 0 | 2000 | 2000 | 103
| Line No 124 Item No Item | PRESSURE SEWER SYSTEM
| Line No 125 Item No 9600 | Sewers and Manholes, MCC 7
| Line No 126 Item No 9601 | Supply and Delivery of uPVC sewer pipe, Class 16, complying with AS 1260, suitable for socket joints
62 | Line No 127 Item No 9601.2 | PRESSURE SEWER SYSTEM - Supply and Delivery of uPVC sewer pipe, Class 16, complying with AS 1260, suitable for socket joints - 225mm dia. | m |  |  |  | 5.3 |  | 201.4 |  | 1 | 0 | 0 | 0 | 201.4 | 201.4
| 1 | WDC | Item | S | 38 | 1 | 5.3 | 1 | 201.4 | 201.4 | 5.3 | 0 | 0 | 0 | 201.4 | 201.4 | 95
| Line No 128 Item No 9615 | Trench excavation in soil for 225mm dia. sewers, including excavation for manholes, jump ups, slope drops, vertical drops, backfilling, disposal of spoil and restoration.
63 | Line No 129 Item No 9615.1 | PRESSURE SEWER SYSTEM - Trench excavation in soil for 225mm dia. sewers, including excavation for manholes, jump ups, slope drops, vertical drops, backfilling, disposal of spoil and restoration. Depth Range 0.5-1.5m inclusive | m |  |  |  | 5.3 |  | 265 |  | 1 | 0 | 0 | 0 | 265 | 265
| 1 | WDC | Item | S | 50 | 1 | 5.3 | 1 | 265 | 265 | 5.3 | 0 | 0 | 0 | 265 | 265 | 95
| Line No 130 Item No 9620 | PRESSURE SEWER SYSTEM - Lay, bed and joint sewer pipe including main and specials, supply and place sand bedding to 150mm above top of pipe (Type 1 construction, WRC Std drawing D-0030) and testing of finished pipeline, including CCTV Survey and Report.
64 | Line No 131 Item No 9620.2 | PRESSURE SEWER SYSTEM - Lay, bed and joint sewer pipe including main and specials, supply and place sand bedding to 150mm above top of pipe (Type 1 construction, WRC Std drawing D-0030) and testing of finished pipeline, including CCTV Survey and Report. - 225mm dia. | m |  |  |  | 5.3 |  | 1325 |  | 1 | 0 | 0 | 0 | 1325 | 1325
| 1 | WDC | Item | S | 250 | 1 | 5.3 | 1 | 1325 | 1325 | 5.3 | 0 | 0 | 0 | 1325 | 1325 | 95
65 | Line No 132 Item No 9640.1 | PRESSURE SEWER SYSTEM - Concrete N20 in place for pipe bedding, surrounds, stops, blocks, cover slab incl. steel reinforcement where specified incl. supply of all materials (Provisional, if ordered) | m³ |  |  |  | 2 |  | 1000 |  | 0 | 0 | 0 | 0 | 1000 | 1000
| 1 | WDC | Item | S | 500 | 1 | 2 | 1 | 1000 | 0 |  | 0 | 0 | 0 | 1000 | 1000 | 95
66 | Line No 133 Item No 9650.1 | PRESSURE SEWER SYSTEM - Supply and placing of approved sand filling (150 - 300mm above pipes) (Provisional, if ordered) | m³ |  |  |  | 20 |  | 1100 |  | 0 | 0 | 0 | 0 | 1100 | 1100
| 1 | WDC | Item | S | 55 | 1 | 20 | 1 | 1100 | 0 |  | 0 | 0 | 0 | 1100 | 1100 | 95
| Line No 134 Item No 9700 | Manhole House Connection Branches
67 | Line No 135 Item No 9700.3 | PRESSURE SEWER SYSTEM - Manhole House Connection Branches - 100mm dia. house connection extension to lot 23 (from existing manhole) | m |  |  |  | 6 |  | 1500 |  | 12 | 0 | 0 | 0 | 1500 | 1500
| 1 | WDC | Item | S | 250 | 1 | 6 | 1 | 1500 | 3000 | 12 | 0 | 0 | 0 | 1500 | 1500 | 95
| Line No 136 Item No 9720 | Manholes complete in place
68 | Line No 137 Item No 9720.1 | PRESSURE SEWER SYSTEM -Manholes complete in place - Depth Range 0.5-1.5m inclusive (1050 internal diameter) - Including connection for poly pressure main and internal epoxy coating of manhole | Each |  |  |  | 1 |  | 4400 |  | 3 | 0 | 0 | 0 | 4400 | 4400
| 1 | WDC | Item | S | 4400 | 1 | 1 | 1 | 4400 | 118800 | 27 | 0 | 0 | 0 | 4400 | 4400 | 95
| Line No 138 Item No 9740 | Supply MDPE Pipe, Series 1, PN16, PE 80B complying with AS/NZS 4130
69 | Line No 139 Item No 9740.1 | PRESSURE SEWER SYSTEM - Supply MDPE Pipe, Series 1, PN16, PE 80B complying with AS/NZS 4130 - 50mm ODPE | m |  |  |  | 133 |  | 1197 |  | 0 | 0 | 0 | 0 | 1197 | 1197
| 1 | WDC | Item | S | 9 | 1 | 133 | 1 | 1197 | 0 |  | 0 | 0 | 0 | 1197 | 1197 | 95
70 | Line No 140 Item No 9740.2 | PRESSURE SEWER SYSTEM - Supply MDPE Pipe, Series 1, PN16, PE 80B complying with AS/NZS 4130 - 63mm ODPE | m |  |  |  | 237 |  | 2251.5 |  | 0 | 0 | 0 | 0 | 2251.5 | 2251.5
| 1 | WDC | Item | S | 9.5 | 1 | 237 | 1 | 2251.5 | 0 |  | 0 | 0 | 0 | 2251.5 | 2251.5 | 95
| Line No 141 Item No 9741 | Excavate, lay, bed, joint and backfill MDPE Pipe, Series 1, PN16, PE 80B pressure pipe main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835). Including supply & installation of enveloper conduit at road crossing locations.
71 | Line No 142 Item No 9741.1 | PRESSURE SEWER SYSTEM - Excavate, lay, bed, joint and backfill MDPE Pipe, Series 1, PN16, PE 80B pressure pipe main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835). Including supply & installation of enveloper conduit at road crossing locations. - 50mm ODPE | m |  |  |  | 133 |  | 7315 |  | 4 | 0 | 0 | 0 | 7315 | 7315
| 1 | WDC | Item | S | 55 | 1 | 133 | 1 | 7315 | 1645.875 | 29.925 | 0 | 0 | 0 | 7315 | 7315 | 95
72 | Line No 143 Item No 9741.2 | PRESSURE SEWER SYSTEM - Excavate, lay, bed, joint and backfill MDPE Pipe, Series 1, PN16, PE 80B pressure pipe main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835). Including supply & installation of enveloper conduit at road crossing locations. - 63mm ODPE | m |  |  |  | 237 |  | 13983 |  | 4 | 0 | 0 | 0 | 13983 | 13983
| 1 | WDC | Item | S | 59 | 1 | 237 | 1 | 13983 | 2097.45 | 35.55 | 0 | 0 | 0 | 13983 | 13983 | 95
73 | Line No 144 Item No 9742.1 | PRESSURE SEWER SYSTEM - Supply and installation of Aquatec Boundary Connection pits | Each |  |  |  | 22 |  | 19800 |  | 5 | 0 | 0 | 0 | 19800 | 19800
| 1 | WDC | Item | S | 900 | 1 | 22 | 1 | 19800 | 39600 | 44 | 0 | 0 | 0 | 19800 | 19800 | 95
74 | Line No 145 Item No 9742.2 | PRESSURE SEWER SYSTEM - Supply and installation of Aquatec flushing point | Each |  |  |  | 1 |  | 1780 |  | 0 | 0 | 0 | 0 | 1780 | 1780
| 1 | WDC | Item | S | 1780 | 1 | 1 | 1 | 1780 | 0 |  | 0 | 0 | 0 | 1780 | 1780 | 95
75 | Line No 146 Item No 9742.3 | PRESSURE SEWER SYSTEM - Supply and installation of Aquatec isolation valves | Each |  |  |  | 2 |  | 3700 |  | 0 | 0 | 0 | 0 | 3700 | 3700
| 1 | WDC | Item | S | 1850 | 1 | 2 | 1 | 3700 | 0 |  | 0 | 0 | 0 | 3700 | 3700 | 95
76 | Line No 147 Item No 9745.2 | PRESSURE SEWER SYSTEM - Dewatering of trench extra to 9610 - 9615 (Provisional, if ordered) | m |  |  |  | 370 |  | 5550 |  | 0 | 0 | 0 | 0 | 5550 | 5550
| 1 | WDC | Item | S | 15 | 1 | 370 | 1 | 5550 | 0 |  | 0 | 0 | 0 | 5550 | 5550 | 95
77 | Line No 148 Item No 9745.3 | PRESSURE SEWER SYSTEM - Supply and placing of metal ballast bedding below bottom of pipe, supply and placing of geotextile, including additional excavation below pipe barrel to maximum 400mm below pipe barrel (Provisional, if ordered) | m³ |  |  |  | 5 |  | 500 |  | 0 | 0 | 0 | 0 | 500 | 500
| 1 | WDC | Item | S | 100 | 1 | 5 | 1 | 500 | 0 |  | 0 | 0 | 0 | 500 | 500 | 95
78 | Line No 149 Item No 9750.1 | PRESSURE SEWER SYSTEM - Demolish existing sewer manhole and connect to existing 225 diameter sewer main, incl. liaison with Council and plugging of downstream manhole | Lump |  |  |  | 1 |  | 1500 |  | 1 | 0 | 0 | 0 | 1500 | 1500
| 1 | WDC | Item | S | 1500 | 1 | 1 | 1 | 1500 | 9 | 9 | 0 | 0 | 0 | 1500 | 1500 | 95
79 | Line No 150 Item No 9751.1 | PRESSURE SEWER SYSTEM - Construct vent pole and foundation as per WRC Std Dwg S0020 - incl. all materials and connection to receiving manhole | Lump |  |  |  | 1 |  | 2500 |  | 1 | 0 | 0 | 0 | 2500 | 2500
| 1 | WDC | Item | S | 2500 | 1 | 1 | 1 | 2500 | 9 | 9 | 0 | 0 | 0 | 2500 | 2500 | 95
| Line No 153 Item No Item | ANCILLARY WORKS
80 | Line No 155 Item No 9100.1 | ANCILLARY WORKS - Ergon longitudinal trenching and backfilling, including supply of all bedding and backfill sand, as directed (Provisional, if ordered) | m |  |  |  | 445 |  | 22474.87 |  | 8 | 6243.7884 | 1922.4 | 14308.6817 | 0 | 22474.87
| 1 | Purchase Material:
| 2 | Sand | tonne | M | 1 | 1 | 80.1 | 24 | 1922.4 |  |  | 0 | 1922.4 | 0 | 0 | 1922.4 | QMS
| 3 | Excavate & Install:
80.01 | 4 | Excavator - 15T | hr | P | 1 | 6.842 | 445 | 125 | 8129.9328 | 65.0395 | 65.0395 | 0 | 0 | 8129.9328 | 0 | 8129.9328 | 111
| 5 | Labour | hr | L | 2 | 6.842 | 445 | 48 | 6243.7884 | 130.0789 | 65.0395 | 6243.7884 | 0 | 0 | 0 | 6243.7884 | 111
| 6 | Bobcat | hr | P | 1 | 6.842 | 445 | 95 | 6178.7489 | 65.0395 | 65.0395 | 0 | 0 | 6178.7489 | 0 | 6178.7489 | 111
| Line No 156 Item No 9110 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered)
81 | Line No 157 Item No 9110.1 | ANCILLARY WORKS - Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 3/100mm & 1/40mm Electrical plus 2/100mm Testra | m |  |  |  | 79 |  | 2664.518 |  | 0 | 0 | 2664.518 | 0 | 0 | 2664.518
| 1 | Purchase Materials:
| 2 | 100 LD uPVC Electrical | m | M | 1 | 1 | 363.4 | 4.32 | 1569.888 |  |  | 0 | 1569.888 | 0 | 0 | 1569.888 | ETC
| 3 | Draw Rope - Conduits | m | M | 1 | 1 | 395 | 0.11 | 43.45 |  |  | 0 | 43.45 | 0 | 0 | 43.45 | ETM
| 4 | Warning Tape | each | M | 1 | 1 | 1 | 70 | 70 |  |  | 0 | 70 | 0 | 0 | 70 | ETM
| 5 | Hard Cover - Electrical | m | M | 1 | 1 | 363.4 | 2.7 | 981.18 |  |  | 0 | 981.18 | 0 | 0 | 981.18 | ETM
82 | Line No 158 Item No 9110.2 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 2/100mm plus 1/100mm Testra | m |  |  |  | 16 |  | 466.304 |  | 0 | 0 | 466.304 | 0 | 0 | 466.304
| 1 | Purchase Materials:
| 2 | 100 LD uPVC Electrical | m | M | 1 | 1 | 55.2 | 4.32 | 238.464 |  |  | 0 | 238.464 | 0 | 0 | 238.464 | ETC
| 3 | Draw Rope - Conduits | m | M | 1 | 1 | 80 | 0.11 | 8.8 |  |  | 0 | 8.8 | 0 | 0 | 8.8 | ETM
| 4 | Warning Tape | each | M | 1 | 1 | 1 | 70 | 70 |  |  | 0 | 70 | 0 | 0 | 70 | ETM
| 5 | Hard Cover - Electrical | m | M | 1 | 1 | 55.2 | 2.7 | 149.04 |  |  | 0 | 149.04 | 0 | 0 | 149.04 | ETM
83 | Line No 159 Item No 9110.3 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 1/100mm Electrical plus 1/100mm Telstra | m |  |  |  | 300 |  | 5078.8 |  | 0 | 0 | 5078.8 | 0 | 0 | 5078.8
| 1 | Purchase Materials:
| 2 | 100 LD uPVC Electrical | m | M | 1 | 1 | 690 | 4.32 | 2980.8 |  |  | 0 | 2980.8 | 0 | 0 | 2980.8 | ETC
| 3 | Draw Rope - Conduits | m | M | 1 | 1 | 1500 | 0.11 | 165 |  |  | 0 | 165 | 0 | 0 | 165 | ETM
| 4 | Warning Tape | each | M | 1 | 1 | 1 | 70 | 70 |  |  | 0 | 70 | 0 | 0 | 70 | ETM
| 5 | Hard Cover - Electrical | m | M | 1 | 1 | 690 | 2.7 | 1863 |  |  | 0 | 1863 | 0 | 0 | 1863 | ETM
84 | Line No 160 Item No 9110.4 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 1x40 Telstra | m |  |  |  | 35 |  | 371.805 |  | 0 | 0 | 371.805 | 0 | 0 | 371.805
| 1 | Purchase Materials:
| 2 | 100 LD uPVC Electrical | m | M | 1 | 1 | 40.25 | 4.32 | 173.88 |  |  | 0 | 173.88 | 0 | 0 | 173.88 | ETC
| 3 | Draw Rope - Conduits | m | M | 1 | 1 | 175 | 0.11 | 19.25 |  |  | 0 | 19.25 | 0 | 0 | 19.25 | ETM
| 4 | Warning Tape | each | M | 1 | 1 | 1 | 70 | 70 |  |  | 0 | 70 | 0 | 0 | 70 | ETM
| 5 | Hard Cover - Electrical | m | M | 1 | 1 | 40.25 | 2.7 | 108.675 |  |  | 0 | 108.675 | 0 | 0 | 108.675 | ETM
85 | Line No 161 Item No | Installation of Electrical Pits (Direction Changes) Type 5 | No. |  |  |  | 11 |  | 10450 |  | 0 | 0 | 10450 | 0 | 0 | 10450
| 1 | Electrical Pit - Type 5 | each | M | 1 | 1 | 11 | 950 | 10450 |  |  | 0 | 10450 | 0 | 0 | 10450 | ETP
86 | Line No 162 Item No | Supply & Install Internal Electrical cabling including cabling to a common point external to the sub-division to a central metering location, 'green boys' and lot connections. (ELECTRICAL METERS PROVIDED BY FUTURE LOT OWNERS) | Item |  |  |  | 1 |  | 42965 |  | 6 | 0 | 0 | 0 | 42965 | 42965
| 1 | Electrical Sub-Contract | Item | S | 42965 | 1 | 1 | 1 | 42965 | 54 | 54 | 0 | 0 | 0 | 42965 | 42965 | 113
87 | Line No 163 Item No | Supply & Install 'The Cove' sub-board including connection to Ergon POS outside development as per DWG E25 | Item |  |  |  | 1 |  | 21740 |  | 2 | 0 | 0 | 0 | 21740 | 21740
| 1 | Electrical Sub-Contract | Item | S | 21740 | 1 | 1 | 1 | 21740 | 18 | 18 | 0 | 0 | 0 | 21740 | 21740 | 113
88 | Line No 164 Item No | Supply & Install MARINA MSB as per DWG E25 | Item |  |  |  | 1 |  | 18085 |  | 2 | 0 | 0 | 0 | 18085 | 18085
| 1 | Electrical Sub-Contract | Item | S | 18085 | 1 | 1 | 1 | 18085 | 18 | 18 | 0 | 0 | 0 | 18085 | 18085 | 113
89 | Line No 165 Item No | Supply & Install MARINA Sub-Main from 'The Cove' MSB to MARINA DB | Item |  |  |  | 1 |  | 7650 |  | 2 | 0 | 0 | 0 | 7650 | 7650
| 1 | Electrical Sub-Contract | Item | S | 7650 | 1 | 1 | 1 | 7650 | 18 | 18 | 0 | 0 | 0 | 7650 | 7650 | 113
| Line No 166 Item No | Electrical trenching & Installation
| Line No 167 Item No 9120 | Ergon/Telstra road crossings in place including trenching, backfilling and supply and installation of Ergon PVC Conduits including draw cord, end caps, polymeric cable protection cover (where required), caution orange tape and installation of Telstra PVC conduits with draw cords and end caps (Provisional, if ordered)
90 | Line No 168 Item No 9120.2 | Electrical trenching & Installation - 2/100mm & 1/40 Electricity plus 1/100mm | m |  |  |  | 15 |  | 562.63 |  | 0 | 0 | 562.63 | 0 | 0 | 562.63
| 1 | Purchase Materials:
| 2 | 100 LD uPVC Electrical | m | M | 1 | 1 | 69 | 4.32 | 298.08 |  |  | 0 | 298.08 | 0 | 0 | 298.08 | ETC
| 3 | Draw Rope - Conduits | m | M | 1 | 1 | 75 | 0.11 | 8.25 |  |  | 0 | 8.25 | 0 | 0 | 8.25 | ETM
| 4 | Warning Tape | each | M | 1 | 1 | 1 | 70 | 70 |  |  | 0 | 70 | 0 | 0 | 70 | ETM
| 5 | Hard Cover - Electrical | m | M | 1 | 1 | 69 | 2.7 | 186.3 |  |  | 0 | 186.3 | 0 | 0 | 186.3 | ETM
91 | Line No 169 Item No 9125.1 | Electrical trenching & Installation - Telecommunications pits | m |  |  |  | 12 |  | 13500 |  | 0 | 0 | 13500 | 0 | 0 | 13500
| 1 | Electrical Pit - Precast | each | M | 1 | 1 | 36 | 375 | 13500 |  |  | 0 | 13500 | 0 | 0 | 13500 | ETP
92 | Line No 170 Item No 9130.1 | Supply, installation and backfill of conduit bends at pillar location, including all 80mm dia, 1200mm rad bends, end caps, 40mm dia service conduits including bends to property boundary, end caps, timber stake, polymeric cable protection cover and caution orange tape (Dwg 5164 Sh 3, 4, 5 & 6) | No |  |  |  | 12 |  | 4500 |  | 0 | 0 | 4500 | 0 | 0 | 4500
| 1 | Electrical Pit - Precast | each | M | 1 | 1 | 12 | 375 | 4500 |  |  | 0 | 4500 | 0 | 0 | 4500 | ETP
92.5 | Line No 171 Item No | Supply & Install Gas Main 63mm OD PE including Tees, joiners and construction of individual Prtoperty Feeds. (GAS METERS NOT INCLUDED - BY FUTURE OWNERS) | m |  |  |  | 445 |  | 32350 |  | 6 | 0 | 0 | 0 | 32350 | 32350
| 1 | WDC | Item | S | 32350 | 1 | 1 | 1 | 32350 | 1619521.875 | 50.0625 | 0 | 0 | 0 | 32350 | 32350 | 103
| Line No 172 Item No | Connection to Origin Gas Main (PSUM) | PS |  |  |  | 1
A provisional sum of 2,500 has been allocated to this item.
93 | Line No 173 Item No 9150.2 | Footings to streetlight poles including anchor cage, to DMR std drawing nos 1380, 1381, 1382, 1429. Footing 600mm diameter 2300mm deep. | No |  |  |  | 10 |  | 30766.2654 |  | 6 | 1871.6809 | 14607.5 | 2837.0845 | 11450 | 30766.2654
| 1 | Purchase Materials:
| 2 | Rag Bolt | each | M | 1 | 1 | 10 | 264 | 2640 |  |  | 0 | 2640 | 0 | 0 | 2640 | ETM
| 3 | N32 | m³ | M | 1 | 1 | 10 | 198 | 1980 |  |  | 0 | 1980 | 0 | 0 | 1980 | C32
| 4 | Install Footings:
93.01 | 5 | Excavator - 15T | hr | P | 1 | 1.053 | 10 | 125 | 1187.0845 | 9.4967 | 9.4967 | 0 | 0 | 1187.0845 | 0 | 1187.0845 | 111
| 6 | Labour | hr | L | 2 | 1.053 | 10 | 48 | 911.6809 | 18.9934 | 9.4967 | 911.6809 | 0 | 0 | 0 | 911.6809 | 111
| 7 | Purchase Materials:
| 8 | Light Pole - 8.5m | each | M | 1 | 1 | 10 | 382 | 3820 |  |  | 0 | 3820 | 0 | 0 | 3820 | ETM
| 9 | Light Pole Outreach (3M) | each | M | 1 | 1 | 10 | 134 | 1340 |  |  | 0 | 1340 | 0 | 0 | 1340 | ETM
| 10 | Luminaires | each | M | 1 | 1 | 10 | 414 | 4140 |  |  | 0 | 4140 | 0 | 0 | 4140 | ETM
| 11 | Electrical Bends | each | M | 1 | 1 | 27.5 | 25 | 687.5 |  |  | 0 | 687.5 | 0 | 0 | 687.5 | ETC
| 12 | Stand Poles:
| 13 | Franna Crane | hr | P | 1 | 1 | 10 | 165 | 1650 | 10 | 10 | 0 | 0 | 1650 | 0 | 1650 | 111
| 14 | Electrician | hr | S | 1 | 1 | 10 | 95 | 950 | 10 | 10 | 0 | 0 | 0 | 950 | 950 | 111
| 15 | Labour | hr | L | 2 | 1 | 10 | 48 | 960 | 20 | 10 | 960 | 0 | 0 | 0 | 960 | 111
| 16 | Pull Cables:
| 17 | Electrical Sub-Contract | Item | S | 1 | 1 | 10500 | 1 | 10500 | 30 | 30 | 0 | 0 | 0 | 10500 | 10500 | 113
94 | Line No 174 Item No 9180.2 | Excavate for padmount substation to allow Electrical Services Provider to install electrical cables and equipment, and reinstate surfaces after installation | No |  |  |  | 22 |  | 8250 |  | 0 | 0 | 8250 | 0 | 0 | 8250
| 1 | Electrical Pit - Precast | each | M | 1 | 1 | 22 | 375 | 8250 |  |  | 0 | 8250 | 0 | 0 | 8250 | 111
| Line No 179 Item No | SOFTSCAPING
95 | Line No 180 Item No | SOFTSCAPING - PLANTS WHITSUNDAY - SOFTSCAPING COMPLETE AS PER QUOTE MLS13-222 (Rev 2) | LS |  |  |  | 1 |  | 189402.18 |  | 15 | 0 | 0 | 0 | 189402.18 | 189402.18
| 1 | Landscaper | Item | S | 189402.18 | 1 | 1 | 1 | 189402.18 | 135 | 135 | 0 | 0 | 0 | 189402.18 | 189402.18 | 121
96 | Line No 181 Item No | SOFTSCAPING - Works Not Included in PWS Quote MLS13-222 (RPZ, Road Crossings, Conduits & GPO for Irrigation Controller) | LS |  |  |  | 1 |  | 7105 |  | 4 | 0 | 0 | 0 | 7105 | 7105
| 1 | WDC | Item | S | 2500 | 1 | 1 | 1 | 2500 | 2500 | 1 | 0 | 0 | 0 | 2500 | 2500 | 103
| 2 | WDC | Item | S | 65 | 1 | 45 | 1 | 2925 | 2925 | 45 | 0 | 0 | 0 | 2925 | 2925 | 103
| 3 | WDC | Item | S | 65 | 1 | 20 | 1 | 1300 | 1300 | 20 | 0 | 0 | 0 | 1300 | 1300 | 103
| 4 | Electrician | hr | S | 4 | 1 | 1 | 95 | 380 | 4 | 1 | 0 | 0 | 0 | 380 | 380 | 113
| Line No 182 Item No | SOFTSCAPING - The Cove - Landscaping Repairs | PS |  |  |  | 1
A provisional sum of 15,000 has been allocated to this item.
| Line No 185 Item No | HARDSCAPING WORKS
97 | Line No 186 Item No | HARDSCAPING WORKS - PLANTS WHITSUNDAY COMPLETE - Paver edging in lieu of Concrete Edge Strip as per Quotation MLS13-240 (2) | LS |  |  |  | 1 |  | 10227.27 |  | 5 | 0 | 0 | 0 | 10227.27 | 10227.27
| 1 | Landscaper | Item | S | 10227.27 | 1 | 1 | 1 | 10227.27 | 460227.15 | 45 | 0 | 0 | 0 | 10227.27 | 10227.27 | 121
98 | Line No 187 Item No | HARDSCAPING WORKS - PLANTS WHITSUNDAY - GRAVEL TO OUTDOOR AREAS ( COMPLETE) | LS |  |  |  | 1 |  | 22088.41 |  | 5 | 0 | 0 | 0 | 22088.41 | 22088.41
| 1 | Landscaper | Item | S | 22088.41 | 1 | 1 | 1 | 22088.41 | 993978.45 | 45 | 0 | 0 | 0 | 22088.41 | 22088.41 | 121
99 | Line No 190 Item No | HARDSCAPING WORKS - Outdoor Viewing Areas (Complete) | each |  |  |  | 3 |  | 24000 |  | 5 | 0 | 0 | 0 | 24000 | 24000
| 1 | Landscaper | Item | S | 24000 | 1 | 1 | 1 | 24000 | 1080000 | 45 | 0 | 0 | 0 | 24000 | 24000 | 123
100 | Line No 191 Item No | HARDSCAPING WORKS - PLANTS WHITSUNDAY TO COMPLETE IN FULL - Allotment Separation Fences (Removable Centre Post) REDUCED IN HEIGHT TO 1400MM | LS |  |  |  | 1 |  | 80346.6 |  | 10 | 0 | 0 | 0 | 80346.6 | 80346.6
| 1 | Landscaper | Item | S | 80346.6 | 1 | 1 | 1 | 80346.6 | 7231194 | 90 | 0 | 0 | 0 | 80346.6 | 80346.6 | 121
101 | Line No 192 Item No | HARDSCAPING WORKS - PLANTS WHITSUNDAY COMPLETE - Supply & Install Totems as Detailed (6 No.) | LS |  |  |  | 1 |  | 9436.36 |  | 1 | 0 | 0 | 0 | 9436.36 | 9436.36
| 1 | Landscaper | Item | S | 9436.36 | 1 | 1 | 1 | 9436.36 | 84927.24 | 9 | 0 | 0 | 0 | 9436.36 | 9436.36 | 121
102 | Line No 193 Item No | HARDSCAPING WORKS - Supply and Install Timber Viewing Deck as Detailed | item |  |  |  | 1 |  | 23000 |  | 5 | 0 | 0 | 0 | 23000 | 23000
| 1 | Landscaper | Item | S | 23000 | 1 | 1 | 1 | 23000 | 1035000 | 45 | 0 | 0 | 0 | 23000 | 23000 | 123
103 | Line No 194 Item No | HARDSCAPING WORKS - PLANTS WHITSUNDAY COMPLETE - Supply & Install Timber Seat (To match existing) | item |  |  |  | 2 |  | 2545.45 |  | 2 | 0 | 0 | 0 | 2545.45 | 2545.45
| 1 | Landscaper | Item | S | 2545.45 | 1 | 1 | 1 | 2545.45 | 45818.1 | 18 | 0 | 0 | 0 | 2545.45 | 2545.45 | 121
| Line No 195 Item No | HARDSCAPING WORKS - Supply & Install all Capping, Facing and Stone Treatments to Entry Statements (Detailes TBC) | PS |  |  |  | 1
A provisional sum of 25,000 has been allocated to this item.
104 | Line No 196 Item No | HARDSCAPING WORKS - Supply & Instal Stainless Steel 'The Cove' & Port of Airlie logo's as shown on entry walls | item |  |  |  | 1 |  | 6000 |  | 20 | 0 | 0 | 0 | 6000 | 6000
| 1 | Grapic Designer | item | S | 6000 | 1 | 1 | 1 | 6000 | 1080000 | 180 | 0 | 0 | 0 | 6000 | 6000 | 123
105 | Line No 197 Item No | HARDSCAPING WORKS - Core Filled Block Wall - W1 (1500mm High) | m2 |  |  |  | 45 |  | 17890 |  | 2 | 0 | 1600 | 0 | 16290 | 17890
| 1 | Footings:
| 2 | Concrete Sub-contract | m² | S | 1 | 1 | 7.2 | 1200 | 8640 | 7.2 | 7.2 | 0 | 0 | 0 | 8640 | 8640 | 123
| 3 | Block Wall
| 4 | Masonary Wall | m² | S | 1 | 1 | 45 | 170 | 7650 | 9 | 9 | 0 | 0 | 0 | 7650 | 7650 | 123
| 5 | N16 | m | M | 1 | 1 | 1 | 1600 | 1600 |  |  | 0 | 1600 | 0 | 0 | 1600 | 123
106 | Line No 198 Item No | HARDSCAPING WORKS - Core Filled Block Wall - W2 (Entry Wall with Rake) | m2 |  |  |  | 18 |  | 7028.0845 |  | 2 | 0 | 800 | 0 | 6228.0845 | 7028.0845
| 1 | Footings:
| 2 | Concrete Sub-contract | m² | S | 1 | 1 | 2.6401 | 1200 | 3168.0845 | 2.6401 | 2.6401 | 0 | 0 | 0 | 3168.0845 | 3168.0845 | 123
| 3 | Block Wall
| 4 | Masonary Wall | m² | S | 1 | 1 | 18 | 170 | 3060 | 9 | 9 | 0 | 0 | 0 | 3060 | 3060 | 123
| 5 | N16 | m | M | 1 | 1 | 0.5 | 1600 | 800 |  |  | 0 | 800 | 0 | 0 | 800 | 123
107 | Line No 199 Item No | HARDSCAPING WORKS - PLANTS WHITSUNDAY SUPERVISION / VEHICLES & ADMIN FEE | LS |  |  |  | 1 |  | 4142.85 |  | 0 | 0 | 0 | 0 | 4142.85 | 4142.85
| 1 | Landscaper | Item | S | 4142.85 | 1 | 1 | 1 | 4142.85 | 0 |  | 0 | 0 | 0 | 4142.85 | 4142.85 | 121
| Line No 201 Item No | FENCING / GATES / EQUIPMENT
108 | Line No 202 Item No | FENCING / GATES / EQUIPMENT - Supply and Install Pedestrian and Vehicular Gate and associated Security Key Pad | Item |  |  |  | 1 |  | 21670 |  | 30 | 0 | 0 | 0 | 21670 | 21670
| 1 | Automatic Gates | item | S | 1 | 1 | 1 | 20530 | 20530 | 270 | 270 | 0 | 0 | 0 | 20530 | 20530 | 131
| 2 | Electrician | hr | S | 12 | 1 | 1 | 95 | 1140 | 108 | 9 | 0 | 0 | 0 | 1140 | 1140 | 131
109 | Line No 203 Item No | FENCING / GATES / EQUIPMENT - PLANTS WHITSUNDAY COMPLETE - Supply & install boundary fence to Lot 23. | LS |  |  |  | 1 |  | 2704.55 |  | 1 | 0 | 0 | 0 | 2704.55 | 2704.55
| 1 | Landscaper | Item | S | 2704.55 | 1 | 1 | 1 | 2704.55 | 24340.95 | 9 | 0 | 0 | 0 | 2704.55 | 2704.55 | 121
110 | Line No 204 Item No | FENCING / GATES / EQUIPMENT - Supply and Install communal letterbox structure within W2 wall - aluminium fronted with range hood and rear opening | Item |  |  |  | 1 |  | 6515 |  | 40 | 0 | 6515 | 0 | 0 | 6515
| 1 | Letter Box | item | M | 1 | 1 | 1 | 6515 | 6515 |  | 360 | 0 | 6515 | 0 | 0 | 6515 | 123
Variatons
[5 empty] | Direct Cost Reate | Direct Cost | CC | Sell Rate
111 | WDC01 | Variation - Additional watermain, 50mm water meter & RPZ - installed at the Cove subdivision as directed by the Superintendent | Item |  |  |  | 1 |  | 11420 |  | 1 | 0 | 0 | 0 | 11420 | 11420
| 1 | WDC | Item | S | 11420 | 1 | 1 | 1 | 11420 | 102780 | 9 | 0 | 0 | 0 | 11420 | 11420 | 103
112 | PV01 | Variation - Installation of geotextile Mirafi in Stormwater trench where depths exceed 1.2m into marine sedimentation as directed by the Superintendent | m² |  |  | 3285 | 480 | 7.7 | 3284.9896 |  | 4 | 2654.9896 | 630 | 0 | 0 | 3284.9896
| 1 | A24 | Item | M | 1 | 1 | 600 | 1.05 | 630 |  |  | 0 | 630 | 0 | 0 | 630 | 222
| 1 | Labour | Item | L | 2 | 21.695 | 600 | 48 | 2654.9896 | 55.3123 | 27.6561 | 2654.9896 | 0 | 0 | 0 | 2654.9896 | 222
113 | PV02 | Variation - Unsuitable Subgrade replacement - Remove existing material 300 deep & replace with CBR 15 as directed by Superintendent | m² |  |  |  | 1492 |  | 30170.0486 |  | 1 | 88.0877 | 28444.98 | 1636.9809 | 0 | 30170.0486
Excavate Material
113.01 | 1 | Excavator - 25T | hr | P | 1 | 106.78 | 447.6 | 125 | 523.9745 | 4.1918 | 4.1918 | 0 | 0 | 523.9745 | 0 | 523.9745 | 53
| 2 | Tipper | hr | P | 2 | 106.78 | 447.6 | 95 | 796.4413 | 8.3836 | 4.1918 | 0 | 0 | 796.4413 | 0 | 796.4413 | 53
| 1 | Purchase Materials:
| 2 | CBR80 | tonne | M | 1 | 1 | 917.58 | 31 | 28444.98 |  |  | 0 | 28444.98 | 0 | 0 | 28444.98 | QM2.5
| 4 | Installation:
113.02 | 5 | Grader | hr | P | 1 | 1000 | 917.58 | 135 | 123.8733 | 0.91758 | 0.91758 | 0 | 0 | 123.8733 | 0 | 123.8733 | 62
| 6 | Water Cart - Hire | hr | P | 1 | 1000 | 917.58 | 100 | 91.758 | 0.91758 | 0.91758 | 0 | 0 | 91.758 | 0 | 91.758 | 62
| 7 | SD Roller - Wet (No Op) | hr | P | 1 | 1000 | 917.58 | 55 | 50.4669 | 0.91758 | 0.91758 | 0 | 0 | 50.4669 | 0 | 50.4669 | 62
| 8 | MW Roller | hr | P | 1 | 1000 | 917.58 | 55 | 50.4669 | 0.91758 | 0.91758 | 0 | 0 | 50.4669 | 0 | 50.4669 | 62
| 9 | Labour | hr | L | 2 | 1000 | 917.58 | 48 | 88.0877 | 1.8352 | 0.91758 | 88.0877 | 0 | 0 | 0 | 88.0877 | 62
114 | PV03 | Variation - Easement at Revetment wall - Relocate & replace existing revetment wall rocks, install geotextile & backfill with general fill to areas as indicated on drawing 13003 21 & 22A | Item |  | 9500 | 9500 | 27.14 | 9500 | 9499 |  | 4 | 0 | 0 | 0 | 9499 | 9499
| 17 | Place & Finish Walls:
| 18 | Rock Wall Builder < 1400 | m² | S | 1 | 1 | 27.14 | 350 | 9499 | 32.568 | 32.568 | 0 | 0 | 0 | 9499 | 9499 | 132
115 | PV04 | Variation - Privacy Screen to boundary of Lot 1 & Lot 23 - Provide 11 natural stone columns and 11 steel panels to 1400mm high fence. Stonework nib wall to easement at Lot 23. Salmon coloured footpath to boundary at Entrance & along Lot 23. | Item |  | 0 | 0 | 1 | 124941.42 | 93885.95 |  | 21 | 172.8 | 3087.65 | 171 | 90454.5 | 93885.95
| 17 | Place & Finish Walls:
| 18 | Rock Wall Builder < 1400 | m² | S | 1 | 1 | 157.15 | 350 | 55002.5 | 188.58 | 188.58 | 0 | 0 | 0 | 55002.5 | 55002.5 | 132
Posts & Powder-coated Fence
| 1 | Landscaper | Item | S | 35420 | 1 | 1 | 1 | 35420 | 35420 | 1 | 0 | 0 | 0 | 35420 | 35420 | 123
Footpath
| 1 | Purchase Materials:
| 2 | N32 | m³ | M | 1 | 1 | 9.9 | 198 | 1960.2 |  |  | 0 | 1960.2 | 0 | 0 | 1960.2 | C25
| 3 | SL82 | m² | M | 1 | 1 | 108 | 6.5 | 702 |  |  | 0 | 702 | 0 | 0 | 702 | RSM
| 4 | Sand | tonne | M | 1 | 1 | 9.9 | 24 | 237.6 |  |  | 0 | 237.6 | 0 | 0 | 237.6 | QMS
| 5 | Black Plastic | m² | M | 1 | 1 | 108 | 1.25 | 135 |  |  | 0 | 135 | 0 | 0 | 135 | RSM
| 6 | Curing Oil | litre | M | 1 | 1 | 1 | 3.35 | 3.35 |  |  | 0 | 3.35 | 0 | 0 | 3.35 | RSM
| 7 | Bar Chairs - 40mm | Item | M | 1 | 1 | 5 | 9.9 | 49.5 |  |  | 0 | 49.5 | 0 | 0 | 49.5 | RSM
| 8 | Prep & Install:
20.01 | 9 | Bobcat | hr | P | 1 | 50 | 90 | 95 | 171 | 1.8 | 1.8 | 0 | 0 | 171 | 0 | 171 | 73
| 10 | Labour | hr | L | 2 | 50 | 90 | 48 | 172.8 | 3.6 | 1.8 | 172.8 | 0 | 0 | 0 | 172.8 | 73
| 11 | Place & Finish
| 12 | Concrete Subbie | m² | S | 1 | 1 | 1 | 32 | 32 | 1 | 1 | 0 | 0 | 0 | 32 | 32 | 73
116 | GAS01 | Line Item 171 - Supply & Install Gas - Variation to adjust claimed contract value of $48,571.75 to agreed value of $15,000 | Item |  |  |  | -1 | -33571.75 | -33571.75 |  | 0 | 0 | 0 | 0 | -33571.75 | -33571.75
| 1 | WDC | Item | S | 33571.75 | 1 | -1 | 1 | -33571.75 | -33571.75 | -1 | 0 | 0 | 0 | -33571.75 | -33571.75 | 103
117 | PSUM | PROVISIONAL SUM ITEM - Supply & Install capping, facing & stone treatments to Entry Statements | Item |  |  |  | 71.43 |  | 25000.5 |  | 10 | 0 | 0 | 0 | 25000.5 | 25000.5
| 17 | Place & Finish Walls:
| 18 | Rock Wall Builder < 1400 | m² | S | 1 | 1 | 71.43 | 350 | 25000.5 | 85.716 | 85.716 | 0 | 0 | 0 | 25000.5 | 25000.5 | 132
118 | PV05 | Variation - Telstra Pit, supply & install Type 8 pit as directed by Superintendent | Item |  |  |  | 1 | 1689.1 | 950 |  | 0 | 0 | 950 | 0 | 0 | 950
| 1 | Electrical Pit - Type 5 | each | M | 1 | 1 | 1 | 950 | 950 |  |  | 0 | 950 | 0 | 0 | 950 | ETP
| Line No. | Comment | Unit |  | No | Production | Quantity | Rate |  |  |  | Labour | Material | Plant | Subcontract | Total
204 | Line No OH 1 Item No | Project Supervision |  |  |  |  | 1 |  | 66320 |  | 16 | 66320 | 0 | 0 | 0 | 66320
| 1 | Project Supervisor | week | L | 1 | 1 | 16 | 4145 | 66320 | 16 | 16 | 66320 | 0 | 0 | 0 | 66320 | 902
205 | Line No OH 2 Item No | Project Management |  |  |  |  | 1 |  | 31200 |  | 6 | 31200 | 0 | 0 | 0 | 31200
| 1 | Project Manager | week | L | 1 | 1 | 6 | 5200 | 31200 | 6 | 6 | 31200 | 0 | 0 | 0 | 31200 | 901
206 | Line No OH 3 Item No | Project Engineering |  |  |  |  | 1 |  | 30000 |  | 8 | 30000 | 0 | 0 | 0 | 30000
| 1 | Project Engineer | week | L | 1 | 1 | 8 | 3750 | 30000 | 8 | 8 | 30000 | 0 | 0 | 0 | 30000 | 901
207 | Line No OH 4 Item No | Site Facilitiues |  |  |  |  | 1 |  | 12800 |  | 16 | 0 | 0 | 12800 | 0 | 12800
| 1 | Crib Facilities | week | P | 1 | 1 | 16 | 800 | 12800 | 16 | 16 | 0 | 0 | 12800 | 0 | 12800 | 903
208 | Line No OH 5 Item No | Small Tools |  |  |  |  | 1 |  | 5000 |  | 0 | 0 | 5000 | 0 | 0 | 5000
| 1 | Small Tools | Item | M | 5000 | 1 | 1 | 1 | 5000 |  |  | 0 | 5000 | 0 | 0 | 5000 | 905
209 | Line No OH 6 Item No | Retention Costs |  |  |  |  | 1 |  | 11700 |  | 11700 | 0 | 0 | 0 | 11700 | 11700
| 1 | Retention Costs | Item | S | 1 | 1 | 11700 | 1 | 11700 | 11700 | 11700 | 0 | 0 | 0 | 11700 | 11700 | 904
210 | Line No OH 7 Item No | Contingency (Hidden Budget) - Not in Budget |  |  |  |  | 1 |  | 232675 |  | 600 | 0 | 0 | 232675 | 0 | 232675
| 1 | Grader | hr | P | 1 | 1 | 300 | 135 | 40500 | 300 | 300 | 0 | 0 | 40500 | 0 | 40500
| 2 | Excavator - 15T | hr | P | 1 | 1 | 200 | 125 | 25000 | 200 | 200 | 0 | 0 | 25000 | 0 | 25000
| 3 | Tipper | hr | P | 1 | 1 | 525 | 95 | 49875 | 525 | 525 | 0 | 0 | 49875 | 0 | 49875
| 4 | Water Cart - Hire | hr | P | 1 | 1 | 600 | 100 | 60000 | 600 | 600 | 0 | 0 | 60000 | 0 | 60000
| 5 | Bobcat | hr | P | 1 | 1 | 300 | 95 | 28500 | 300 | 300 | 0 | 0 | 28500 | 0 | 28500
| 6 | Labour | hr | P | 1 | 1 | 600 | 48 | 28800 | 600 | 600 | 0 | 0 | 28800 | 0 | 28800

## Resources
| Resource Name | Description | Type | Unit | Currency | Base Rate | Qty
LABOUR RESOURCES | Labour | Labour | L | hr | AUD | 48
| Project Administrator |  | L | hr | AUD | 48
| Project Engineer | Project Engineer - Weekly Rate | L | week | AUD | 3750
| Project Manager | Weekly Rate - Project Manager | L | week | AUD | 5200
| Project Supervisor | Project Supervisor | L | week | AUD | 4145
MATERIAL RESOURCES | 100 LD uPVC Electrical |  | M | m | AUD | 4.32
| 150 Black Max SN8 |  | M | m | AUD | 55
| 375 RCP |  | M | m | AUD | 96.09
| 450 RCP FJ CL2 |  | M | m | AUD | 119.83
| 50 HD uPVC Electrical |  | M | m | AUD | 3
| 525 RCP FJ CL2 |  | M | m | AUD | 140.9
| 600 RCP RRJ CL2 |  | M | m | AUD | 182.58
| A24 | A24 - Bidum | M | m² | AUD | 1.05
| Abel Flex |  | M | m | AUD | 1.1
| Bar Chairs - 125mm | Bag of 100 | M | Item | AUD | 24.5
| Bar Chairs - 40mm | Bag 100 | M | Item | AUD | 9.9
| Bent Steel |  | M | item | AUD | 2200
| Black Plastic |  | M | m² | AUD | 1.25
| CBR80 | CBR80 Road Base - Delivered | M | tonne | AUD | 31
| Curing Oil |  | M | litre | AUD | 3.35
| Dowel Sleeves |  | M | each | AUD | 1.4
| Dowels |  | M | each | AUD | 8
| Drainage Agg | Drainage Aggregate | M | tonne | AUD | 42.5
| Draw Rope - Conduits |  | M | m | AUD | 0.11
| Electrical Bends |  | M | each | AUD | 25
| Electrical Pit - Precast |  | M | each | AUD | 375
| Electrical Pit - Type 5 |  | M | each | AUD | 950
| Flood Flap |  | M | item | AUD | 2500
| GPT | Gross Pollutant Trap - HG18 | M | Item | AUD | 26170
| Hard Cover - Electrical |  | M | m | AUD | 2.7
| Letter Box |  | M | item | AUD | 6515
| Light Pole - 8.5m |  | M | each | AUD | 382
| Light Pole Outreach (3M) |  | M | each | AUD | 134
| Luminaires | 150W HPS | M | each | AUD | 414
| N16 |  | M | m | AUD | 1600
| N32 | N32 Concrete | M | m³ | AUD | 198
| N40 |  | M | m³ | AUD | 198
| Pugmill |  | M | tonne | AUD | 4
| Rag Bolt |  | M | each | AUD | 264
| S32 - Exposed Aggregate |  | M | m³ | AUD | 312
| S32 - Kerb Mix | S32 - Kerb Mix | M | m³ | AUD | 202
| SL82 | SL82 Reinforcing Mesh | M | m² | AUD | 6.5
| Sand | Bedding Sand | M | tonne | AUD | 24
| Small Tools |  | M | Item | AUD | 1
| Sub Soil Drain |  | M | m | AUD | 3.3
| Sub Soil Flush Fittings |  | M | each | AUD | 65
| Warning Tape | 500m roll | M | each | AUD | 70
PLANT RESOURCES | Bobcat | Bobcat - Wet Hire | P | hr | AUD | 95
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 800
| Excavator - 15T | 15T Excavator - Wet Hire | P | hr | AUD | 125
| Excavator - 25T | 25T Excavator - Wet Hire | P | hr | AUD | 125
| Franna Crane |  | P | hr | AUD | 165
| Grader | Grader - Wet Hire | P | hr | AUD | 135
| MW Roller | MW Roller (Wet No Op) | P | hr | AUD | 55
| PF Roller Wet - No OP |  | P | hr | AUD | 58
| Plate Compactor | Plate Compactor - Dry Hire | P | hr | AUD | 10
| SD Roller - Wet (No Op) | SD Roller Wet Hire - No Operator | P | hr | AUD | 55
| Tipper | Tipper (Wet Hire) | P | hr | AUD | 95
| Trench Roller |  | P | hr | AUD | 35
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 100
SUB-CONTRACT RESOURCES | Automatic Gates |  | S | item | AUD | 20530
| CAR | CAR Insurance | S | Item | AUD | 1
| Cartage - Rock |  | S | Item | AUD | 1
| Concrete Cylinders | Cylinders - Set of Three | S | each | AUD | 225
| Concrete Sub-contract | CUM Rate | S | m² | AUD | 1200
| Concrete Subbie | Concrete Pavement - Includes Pump Hire | S | m² | AUD | 32
| Concrete Subbie (Exposed) |  | S | m² | AUD | 65
| Concretor - Footings |  | S | m | AUD | 95
| Concretor - Stairs |  | S | each | AUD | 5760
| DG10 | Asphalt | S | tonne | AUD | 445
| Electrical Sub-Contract |  | S | Item | AUD | 1
| Electrician | Electrician - Hourly Rate | S | hr | AUD | 95
| Field Density (subgrade) |  | S | each | AUD | 172
| GPT Installation |  | S | item | AUD | 6500
| Grapic Designer |  | S | item | AUD | 1
| Kerb Subbie |  | S | m | AUD | 35
| Landscaper |  | S | Item | AUD | 1
| Masonary Wall |  | S | m² | AUD | 170
| Primer Seal - SP1 |  | S | m² | AUD | 17.5
| Reinforced Concrete - CUM |  | S | m³ | AUD | 950
| Retention Costs |  | S | Item | AUD | 1
| Rock Wall Builder < 1400 | Rock Wall Builder including materials for walls less than 1400 high. | S | m² | AUD | 350
| Service Locator |  | S | hr | AUD | 135
| Survey |  | S | Item | AUD | 1
| WDC | Whitsunday Drainage Contractors | S | Item | AUD | 1

## Model Inputs
WBS | DESCRIPTION | MODEL INPUT | TYPE | UOM
5 | Site establishment and disestablishment | 1 | Q | Lump
6 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 375mm diameter with saltwater cover | 63.4 | Q | m
6.01 | Excavator - 15T | 5 | P | hr
7 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 450mm diameter with saltwater cover | 26.8 | Q | m
7.01 | Excavator - 15T | 5 | P | hr
8 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 525mm diameter with saltwater cover | 70.7 | Q | m
8.01 | Excavator - 15T | 5 | P | hr
9 | Supply and installation of concrete pipe culvert components, Class 2,RRJ, 600mm diameter with saltwater cover | 31.7 | Q | m
9.01 | Excavator - 15T | 5 | P | hr
10 | Supply and installation of BlackMAX stormwater pipe, Class SN8, 150 mm diameter | 315 | Q | m
10.01 | Excavator - 15T | 5 | P | hr
11 | Supply and install 600mm flood flap | 1 | Q | each
11.01 | Labour | 0.33333 | P | hr
11.5 | End structures to culverts, reinforced concrete | 1 | Q | m3
12 | Aprons to culverts, reinforced concrete | 1 | Q | m3
13 | Concrete kerb and channel, barrier (B2) | 66 | Q | m
13.01 | Grader | 45 | P | hr
14 | Type 1 main roads flush kerb (300x200) | 377 | Q | m
14.01 | Grader | 45 | P | hr
15 | 3450x1500 ecosol RSF 500 GPT with class B lid | 1 | Q | each
16 | 600x600 RKO pit with riser 600x600 V-Grate & Concrete Surround | 8 | Q | each
17 | Concrete gullies, Drainway 0TP/X maxflow grate, standard | 1 | Q | each
18 | Concrete manhole with 600dia access lid (major) | 1 | Q | each
19 | Subsoil drains, Type C, 100 mm diameter including outlets and flush points | 390 | Q | m
19.01 | Excavator - 15T | 7.2222 | P | hr
20 | Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 1.2m wide | 188 | Q | m2
20.01 | Bobcat | 50 | P | hr
21 | Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 2.0m wide | 38.1 | Q | m2
21.01 | Bobcat | 50 | P | hr
22 | Hand-placed concrete paving, 170mm thick, N32/20 with SL82 mesh central with exposed aggregate finish (incl. joints as detailed) | 240 | Q | m2
22.01 | Bobcat | 50 | P | hr
23 | Natural local stone mass gravity wall. 500mm thick, vertical face including footing (1m x 400mm thick) and rear drainage | 677 | Q | m2
23.01 | Excavator - 15T | 7.222 | P | hr
23.02 | Bobcat | 10 | P | hr
23.03 | Bobcat | 15 | P | hr
24 | Road excavation, all materials to reprofile the subgrade level | 380 | Q | m3
24.01 | Grader | 150 | P | hr
25 | Allotment excavation to Revised RL (3.9 - 3.7) | 1000 | Q | m3
25.01 | Excavator - 25T | 62 | P | hr
26 | Re-trim allotments to revised FL | 9000 | Q | m2
26.01 | Grader | 350 | P | hr
27 | Base, unbound pavement, Type 2, Subtype 2.1 | 125 | Q | m3
27.01 | Grader | 44.4444 | P | hr
27.02 | Grader | 150 | P | hr
28 | Subbase, unbound pavement, Type 2, Subtype 2.3 | 190 | Q | m3
28.01 | Grader | 44.444 | P | hr
28.02 | Grader | 170 | P | hr
29 | Subbase, unbound pavement, Type 2, Subtype 2.3 under 170mm Concrete | 36 | Q | m3
29.01 | Grader | 33.333 | P | hr
29.02 | Grader | 50 | P | hr
30 | Sprayed bituminous surfacing, including supply of binder, including supply of additives, including supply and spreading of precoated cover aggregates. 7mm Primerseal, MC5 1.0L/m2, 175m2/m3 | 955 | Q | m2
31 | AC10 Type 2 mix | 80 | Q | tonne
32 | Stair Risers and treads (Hardwood & Stainless - Provisional) | 1 | Q | Item
33 | Survey Set Out | 1 | Q | Lump
34 | Preparation of "As constructed" drawings for submission | 1 | Q | Lump
35 | Locate and protect services - general | 1 | Q | Lump
36 | 100mm dia | 253 | Q | m
37 | 100mm dia | 6 | Q | Each
38 | 100mm x 22½o | 2 | Q | Each
39 | 100mm x 45o | 3 | Q | Each
40 | 100mm x 90o | 2 | Q | Each
41 | 100 x 100mm (FL-FLxFL) | 3 | Q | Each
42 | 100x80? | 2 | Q | Each
43 | Supply spring hydrant incl. F.B.E./Rilsan coating | 2 | Q | Each
44 | Supply hydrant risers 80?x300mm (FL-FL) (Provisional, if ordered) | 2 | Q | Each
45 | Supply hydrant cover boxes | 2 | Q | Each
46 | Install cover boxes to hydrants incl. supply of margin sets & bedding bricks & markers | 2 | Q | Each
47 | 100? | 7 | Q | Each
48 | 150mm dia | 2 | Q | Each
49 | 32mm single (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 7 | Q | Each
50 | 32mm single under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 2 | Q | Each
51 | 32mm dual (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 4 | Q | Each
52 | 32mm dual under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 3 | Q | Each
53 | 100mm dia | 253 | Q | m
54 | Supply & Installation of 100mm diameter water meter with an 80mm bypass line as per detail A of U13481.001-122(B) | 1 | Q | item
55 | Dewatering of trench extra to Items 9521 - 9524 (Provisional, if ordered) | 253 | Q | m
56 | Supply and placing of approved sand filling 150 - 300mm above top of pipe (Type 1 construction) (Provisional, if ordered) | 25 | Q | m³
57 | Supply and Install Fire Booster (Provisional, if ordered) MARINA ITEM | 1 | Q | Each
58 | Concrete Grade N20 in place for thrust blocks | 5 | Q | m³
59 | Flushing and chlorination of mains including supply of chlorine | 1 | Q | Lump
60 | Testing of water mains including supply of pressurising equipment, gauges and fittings | 1 | Q | Lump
61 | Connection to existing Council main, 100mm dia (incl. Council fees) | 1 | Q | Lump
62 | 225mm dia. | 5.3 | Q | m
63 | Depth Range 0.5-1.5m inclusive | 5.3 | Q | m
64 | 225mm dia. | 5.3 | Q | m
65 | Concrete N20 in place for pipe bedding, surrounds, stops, blocks, cover slab incl. steel reinforcement where specified incl. supply of all materials (Provisional, if ordered) | 2 | Q | m³
66 | Supply and placing of approved sand filling (150 - 300mm above pipes) (Provisional, if ordered) | 20 | Q | m³
67 | 100mm dia. house connection extension to lot 23 (from existing manhole) | 6 | Q | m
68 | Depth Range 0.5-1.5m inclusive (1050 internal diameter) - Including connection for poly pressure main and internal epoxy coating of manhole | 1 | Q | Each
69 | 50mm ODPE | 133 | Q | m
70 | 63mm ODPE | 237 | Q | m
71 | 50mm ODPE | 133 | Q | m
72 | 63mm ODPE | 237 | Q | m
73 | Supply and installation of Aquatec Boundary Connection pits | 22 | Q | Each
74 | Supply and installation of Aquatec flushing point | 1 | Q | Each
75 | Supply and installation of Aquatec isolation valves | 2 | Q | Each
76 | Dewatering of trench extra to 9610 - 9615 (Provisional, if ordered) | 370 | Q | m
77 | Supply and placing of metal ballast bedding below bottom of pipe, supply and placing of geotextile, including additional excavation below pipe barrel to maximum 400mm below pipe barrel (Provisional, if ordered) | 5 | Q | m³
78 | Demolish existing sewer manhole and connect to existing 225 diameter sewer main, incl. liaison with Council and plugging of downstream manhole | 1 | Q | Lump
79 | Construct vent pole and foundation as per WRC Std Dwg S0020 - incl. all materials and connection to receiving manhole | 1 | Q | Lump
80 | Ergon longitudinal trenching and backfilling, including supply of all bedding and backfill sand, as directed (Provisional, if ordered) | 445 | Q | m
80.01 | Excavator - 15T | 6.842 | P | hr
81 | 3/100mm & 1/40mm Electrical plus 2/100mm Testra | 79 | Q | m
82 | 2/100mm plus 1/100mm Testra | 16 | Q | m
83 | 1/100mm Electrical plus 1/100mm Telstra | 300 | Q | m
84 | 1x40 Telstra | 35 | Q | m
85 | Installation of Electrical Pits (Direction Changes) Type 5 | 11 | Q | No.
86 | Supply & Install Internal Electrical cabling including cabling to a common point external to the sub-division to a central metering location, 'green boys' and lot connections. (ELECTRICAL METERS PROVIDED BY FUTURE LOT OWNERS) | 1 | Q | Item
87 | Supply & Install 'The Cove' sub-board including connection to Ergon POS outside development as per DWG E25 | 1 | Q | Item
88 | Supply & Install MARINA MSB as per DWG E25 | 1 | Q | Item
89 | Supply & Install MARINA Sub-Main from 'The Cove' MSB to MARINA DB | 1 | Q | Item
90 | 2/100mm & 1/40 Electricity plus 1/100mm | 15 | Q | m
91 | Telecommunications pits | 12 | Q | m
92 | Supply, installation and backfill of conduit bends at pillar location, including all 80mm dia, 1200mm rad bends, end caps, 40mm dia service conduits including bends to property boundary, end caps, timber stake, polymeric cable protection cover and caution orange tape (Dwg 5164 Sh 3, 4, 5 & 6) | 12 | Q | No
92.5 | Supply & Install Gas Main 63mm OD PE including Tees, joiners and construction of individual Prtoperty Feeds. (GAS METERS NOT INCLUDED - BY FUTURE OWNERS) | 445 | Q | m
93 | Footings to streetlight poles including anchor cage, to DMR std drawing nos 1380, 1381, 1382, 1429. Footing 600mm diameter 2300mm deep. | 10 | Q | No
93.01 | Excavator - 15T | 1.053 | P | hr
94 | Excavate for padmount substation to allow Electrical Services Provider to install electrical cables and equipment, and reinstate surfaces after installation | 22 | Q | No
95 | PLANTS WHITSUNDAY - SOFTSCAPING COMPLETE AS PER QUOTE MLS13-222 (Rev 2) | 1 | Q | LS
96 | Works Not Included in PWS Quote MLS13-222 (RPZ, Road Crossings, Conduits & GPO for Irrigation Controller) | 1 | Q | LS
97 | PLANTS WHITSUNDAY COMPLETE - Paver edging in lieu of Concrete Edge Strip as per Quotation MLS13-240 (2) | 1 | Q | LS
98 | PLANTS WHITSUNDAY - GRAVEL TO OUTDOOR AREAS ( COMPLETE) | 1 | Q | LS
99 | Outdoor Viewing Areas (Complete) | 3 | Q | each
100 | PLANTS WHITSUNDAY TO COMPLETE IN FULL - Allotment Separation Fences (Removable Centre Post) REDUCED IN HEIGHT TO 1400MM | 1 | Q | LS
101 | PLANTS WHITSUNDAY COMPLETE - Supply & Install Totems as Detailed (6 No.) | 1 | Q | LS
102 | Supply and Install Timber Viewing Deck as Detailed | 1 | Q | item
103 | PLANTS WHITSUNDAY COMPLETE - Supply & Install Timber Seat (To match existing) | 2 | Q | item
104 | Supply & Instal Stainless Steel 'The Cove' & Port of Airlie logo's as shown on entry walls | 1 | Q | item
105 | Core Filled Block Wall - W1 (1500mm High) | 45 | Q | m2
106 | Core Filled Block Wall - W2 (Entry Wall with Rake) | 18 | Q | m2
107 | PLANTS WHITSUNDAY SUPERVISION / VEHICLES & ADMIN FEE | 1 | Q | LS
108 | Supply and Install Pedestrian and Vehicular Gate and associated Security Key Pad | 1 | Q | Item
109 | PLANTS WHITSUNDAY COMPLETE - Supply & install boundary fence to Lot 23. | 1 | Q | LS
110 | Supply and Install communal letterbox structure within W2 wall - aluminium fronted with range hood and rear opening | 1 | Q | Item
111 | Variation - Additional watermain, 50mm water meter & RPZ - installed at the Cove subdivision as directed by the Superintendent | 1 | Q | Item
112 | Variation - Installation of geotextile Mirafi in Stormwater trench where depths exceed 1.2m into marine sedimentation as directed by the Superintendent | 480 | Q | m²
113 | Variation - Unsuitable Subgrade replacement - Remove existing material 300 deep & replace with CBR 15 as directed by Superintendent | 1492 | Q | m²
113.01 | Excavator - 25T | 106.78 | P | hr
113.02 | Grader | 1000 | P | hr
114 | Variation - Easement at Revetment wall - Relocate & replace existing revetment wall rocks, install geotextile & backfill with general fill to areas as indicated on drawing 13003 21 & 22A | 27.14 | Q | Item
115 | Variation - Privacy Screen to boundary of Lot 1 & Lot 23 - Provide 11 natural stone columns and 11 steel panels to 1400mm high fence. Stonework nib wall to easement at Lot 23. Salmon coloured footpath to boundary at Entrance & along Lot 23. | 1 | Q | Item
116 | Line Item 171 - Supply & Install Gas - Variation to adjust claimed contract value of $48,571.75 to agreed value of $15,000 | -1 | Q | Item
117 | PROVISIONAL SUM ITEM - Supply & Install capping, facing & stone treatments to Entry Statements | 71.43 | Q | Item
118 | Variation - Telstra Pit, supply & install Type 8 pit as directed by Superintendent | 1 | Q | Item
204 | Project Supervision | 1 | Q | 0
205 | Project Management | 1 | Q | 0
206 | Project Engineering | 1 | Q | 0
207 | Site Facilitiues | 1 | Q | 0
208 | Small Tools | 1 | Q | 0
209 | Retention Costs | 1 | Q | 0
210 | Contingency (Hidden Budget) | 1 | Q | 0

## Non-Work Calendar
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | 2013-01-26 | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Working Hours | 9
Start Date | 2014-04-01

## Program Links
WBS | Task | Duration | Budget | WBS Predecessors | WBS Successors | Budget | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01
TO ENSURE LINKS ARE VALID CUT AND PASTE BELOW INTO THIRD ROW OF MS PROJECT AS PER YELLOW CELL IN PICTURE TO RIGHT
| CONTRACT AWARD |  |  |  | 5
| PRACTICAL COMPLETION |  |  | 34,96,114
5 | ROADWORKS AND DRAINAGE Site establishment and disestablishment | 5 | 12000 | 3 | 24,35,33 |  | 75% | 75% | 75% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | 100% | 100%
6 | Drainage, Retaining Structures & Protective TreatmentsSupply of Precast Concrete Pipe Culverts in accordance with AS 4058 - Exposure Class B1, and Installation of Culverts to MRS03Supply and installation of concrete pipe culvert components, Class 2, RRJ, 375mm diameter with saltwater cover | 2 | 9401.586 | 25,35 | 7 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 450mm diameter with saltwater cover | 1 | 4610.404 | 6 | 8 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 525mm diameter with saltwater cover | 2 | 13652.17 | 7 | 9 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | Supply and installation of concrete pipe culvert components, Class 2,RRJ, 600mm diameter with saltwater cover | 1 | 7442.526 | 8 | 10 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Supply of Stormwater Drainage Pipe Culverts in accordance with AS/NZS 5065, and installation of Culverts to MRS03 - Supply of Stormwater Drainage Pipe Culverts in accordance with AS/NZS 5065, and installation of Culverts to MRS03 - Supply and installation of BlackMAX stormwater pipe, Class SN8, 150 mm diameter | 7 | 33768 | 9 | 16,11 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Supply and Installation of Drainage Components - Supply and install 600mm flood flap | 1 | 2788 | 10 | 12 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | Concrete in Culverts and End Structures, MRS03 - Aprons to culverts, reinforced concrete | 1 | 950 | 11 | 26 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | Pavement Drainage, MRS03 Concrete kerb and channel, barrier (B2) | 1 | 3396.8 | 28 | 17,14 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | Pavement Drainage, MRS03 Type 1 main roads flush kerb (300x200) | 1 | 19808.2547 | 13 | 27 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | Pavement Drainage, MRS03 3450x1500 ecosol RSF 500 GPT with class B lid | 1 | 32670 | 18 | 29,19 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | Pavement Drainage, MRS03 600x600 RKO pit with riser 600x600 V-Grate & Concrete Surround | 16 | 27200 | 10 | 18,36 |  |  | 87.5% | 87.5% | 87.5% | 87.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
17 | Pavement Drainage, MRS03 - Concrete gullies, Drainway 0TP/X maxflow grate, standard | 1 | 3950 | 13 | 27 |  |  |  |  | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | Pavement Drainage, MRS03 - Concrete manhole with 600dia access lid (major) | 3 | 3950 | 16 | 15 |  |  | 80% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | Subsurface Drainage MRS03 - Subsoil drains, Type C, 100 mm diameter including outlets and flush points | 6 | 15382.5425 | 15 | 29 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | Protective Treatments, MRS03 - Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 1.2m wide | 4 | 13898.4741 | 31 | 26,21 | [7 empty] | 47.87% | 79.79% | 100% | 100% | 100% | 100%
21 | Protective Treatments, MRS03 - Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 2.0m wide | 1 | 2816.5272 | 20 | 26 | [8 empty] | 100% | 100% | 100% | 100% | 100%
22 | Protective Treatments, MRS03 - Hand-placed concrete paving, 170mm thick, N32/20 with SL82 mesh central with exposed aggregate finish (incl. joints as detailed) | 5 | 34443.1896 | 28 | 27 | [8 empty] | 89.58% | 100% | 100% | 100% | 100%
23 | Retaining Walls, MRS03 - Natural local stone mass gravity wall. 500mm thick, vertical face including footing (1m x 400mm thick) and rear drainage | 91 | 456355.226 | 25 | 26FF,117,105,114 |  |  | 21.42% | 56.87% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
24 | Earthworks - Road excavation, all materials to reprofile the subgrade level | 1 | 3690.2222 | 5 | 25112 |  |  |  | 20% | 72.63% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | Earthworks - Allotment excavation to Revised RL (3.9 - 3.7) | 2 | 10548.3871 | 24 | 23,6,80 |  |  |  | 20% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | Earthworks, Embankment, MRS04 - Re-trim allotments to revised FL | 3 | 9925.7143 | 23FF,20,21,12,93,94,92 | 95 |  |  |  | 20% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | Unbound Pavements, MRS05 - Base, unbound pavement, Type 2, Subtype 2.1 | 1 | 16887.8611 | 22,17,14 | 30 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
28 | Unbound Pavements, MRS05 - Subbase, unbound pavement, Type 2, Subtype 2.3 | 2 | 23360.7837 | 29 | 13,22 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
29 | Unbound Pavements, MRS05 - Subbase, unbound pavement, Type 2, Subtype 2.3 under 170mm Concrete | 1 | 6019.8834 | 15,19,71,112,113 | 28 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
30 | Sprayed Bituminous Surfacing (Excluding Emulsion), MRS11 - Sprayed bituminous surfacing, including supply of binder, including supply of additives, including supply and spreading of precoated cover aggregates. 7mm Primerseal, MC5 1.0L/m2, 175m2/m3 | 1 | 17548.125 | 27 | 31 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
31 | Asphalt Surfacing, Brisbane City Council Asphalt Specification S310 - Asphalt Surfacing, Brisbane City Council Asphalt Specification S310 - AC10 Type 2 mix | 1 | 39160 | 30 | 93,20,32,97 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
32 | Roadside Structures, MRS16A - Stair Risers and treads (Hardwood & Stainless - Provisional) | 13 | 84579.6 | 31 | 99 |  |  |  | 4% | 4% | 4% | 80% | 100% | 100% | 100% | 100% | 100% | 100%
33 | Survey Set Out | 0 | 15945 | 5 | 34 |  | 25% | 50% | 70% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
34 | Preparation of "As constructed" drawings for submission | 5 | 7390 | 103,104,109,108,115,117,33 | 4 |  |  |  |  | 60% | 65% | 80% | 100% | 100% | 100% | 100% | 100% | 100%
35 | Locate and protect services - general | 2 | 1998 | 5 | 6 |  | 10% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
36 | WATER PRESSURE MAINS - Water Reticulation - Supply OPVC pressure pipe, RRJ, (C.I.O.D. compatible) PN 16 100mm dia | 4 | 3795 | 16 | 37FF,49 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
37 | WATER PRESSURE MAINS Supply sluice valves, C.I. to AS 2544, PN 16, counterclockwise to close c/w spindle cap incl. F.B.E./Rilsan coating, incl 316 S/S Flange insertion set (FL-FL) 100mm dia | 0 | 8100 | 36FF | 38FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
38 | WATER PRESSURE MAINS - Supply bends, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681 (SOC-SOC) 100mm x 22½o | 0 | 240 | 37FF | 39FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
39 | WATER PRESSURE MAINS - 100mm x 45o | 0 | 360 | 38FF | 40FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
40 | WATER PRESSURE MAINS - 100mm x 90o | 0 | 280 | 39FF | 41FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
41 | WATER PRESSURE MAINS - Supply tees, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set for flange ends - 100 x 100mm (FL-FLxFL) | 0 | 840 | 40FF | 42FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
42 | WATER PRESSURE MAINS -Supply hydrant tee, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set (SOC-SOCxFL) - 100x80? | 0 | 560 | 41FF | 43FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
43 | WATER PRESSURE MAINS -Supply spring hydrant incl. F.B.E./Rilsan coating | 0 | 600 | 42FF | 44FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
44 | WATER PRESSURE MAINS - Supply hydrant risers 80?x300mm (FL-FL) (Provisional, if ordered) | 0 | 260 | 43FF | 45FF | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
45 | WATER PRESSURE MAINS - Supply hydrant cover boxes | 0 | 200 | 44FF | 46FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
46 | WATER PRESSURE MAINS - Install cover boxes to hydrants incl. supply of margin sets & bedding bricks & markers | 0 | 1040 | 45FF | 47FF | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
47 | WATER PRESSURE MAINS - Supply connectors (FL-SOC) DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set - 100? | 0 | 700 | 46FF | 48FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
48 | WATER PRESSURE MAINS - Supply gibault joints 150mm dia | 0 | 500 | 47FF | 62 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
49 | WATER PRESSURE MAINS - House Connection Services (Refer MRC Std Dwg A3-00840) including supply and installation of 100 mm tapping band, main cock and poly pipe to property boundary - 32mm single (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 3 | 2800 | 36 | 50 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
50 | WATER PRESSURE MAINS - 32mm single under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 2 | 4000 | 49 | 51 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
51 | WATER PRESSURE MAINS - 32mm dual (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 1 | 1920 | 50 | 52 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
52 | WATER PRESSURE MAINS - 32mm dual under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | 3 | 6240 | 51 | 53 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
53 | WATER PRESSURE MAINS - Excavate, lay, bed, joint and backfill OPVC pressure pipe, RRJ main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835) - 100mm dia | 5 | 20240 | 52 | 54,55FF,56FF,58FF,57,111FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
54 | WATER PRESSURE MAINS - Supply & Installation of 100mm diameter water meter with an 80mm bypass line as per detail A of U13481.001-122(B) | 1 | 9600 | 53 | 62 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
55 | WATER PRESSURE MAINS - Dewatering of trench extra to Items 9521 - 9524 (Provisional, if ordered) | 0 | 3795 | 53FF | 62
56 | WATER PRESSURE MAINS - Supply and placing of approved sand filling 150 - 300mm above top of pipe (Type 1 construction) (Provisional, if ordered) | 0 | 1375 | 53FF | 62 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
57 | WATER PRESSURE MAINS - Supply and Install Fire Booster (Provisional, if ordered) MARINA ITEM | 1 | 17266.88 | 53 | 59 | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
58 | WATER PRESSURE MAINS - Concrete Grade N20 in place for thrust blocks | 0 | 1750 | 53FF | 62 | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
59 | WATER PRESSURE MAINS - Flushing and chlorination of mains including supply of chlorine | 3 | 1000 | 57 | 60 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
60 | WATER PRESSURE MAINS - Testing of water mains including supply of pressurising equipment, gauges and fittings | 1 | 1500 | 59 | 61 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
61 | WATER PRESSURE MAINS - Connection to existing Council main, 100mm dia (incl. Council fees) | 1 | 2000 | 60 | 62 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
62 | PRESSURE SEWER SYSTEM - Supply and Delivery of uPVC sewer pipe, Class 16, complying with AS 1260, suitable for socket joints - 225mm dia. | 1 | 201.4 | 61,111,58,56,55,54,48 | 63 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
63 | PRESSURE SEWER SYSTEM - Trench excavation in soil for 225mm dia. sewers, including excavation for manholes, jump ups, slope drops, vertical drops, backfilling, disposal of spoil and restoration. Depth Range 0.5-1.5m inclusive | 1 | 265 | 62 | 64 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
64 | PRESSURE SEWER SYSTEM - Lay, bed and joint sewer pipe including main and specials, supply and place sand bedding to 150mm above top of pipe (Type 1 construction, WRC Std drawing D-0030) and testing of finished pipeline, including CCTV Survey and Report. - 225mm dia. | 1 | 1325 | 63 | 65FF,66FF,67,72 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
65 | PRESSURE SEWER SYSTEM - Concrete N20 in place for pipe bedding, surrounds, stops, blocks, cover slab incl. steel reinforcement where specified incl. supply of all materials (Provisional, if ordered) | 0 | 1000 | 64FF | 80 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
66 | PRESSURE SEWER SYSTEM - Supply and placing of approved sand filling (150 - 300mm above pipes) (Provisional, if ordered) | 0 | 1100 | 64FF | 80 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
67 | PRESSURE SEWER SYSTEM - Manhole House Connection Branches - 100mm dia. house connection extension to lot 23 (from existing manhole) | 12 | 1500 | 64 | 69FF,70FF,73 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
68 | PRESSURE SEWER SYSTEM -Manholes complete in place - Depth Range 0.5-1.5m inclusive (1050 internal diameter) - Including connection for poly pressure main and internal epoxy coating of manhole | 3 | 4400 | 72 | 73,79 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
69 | PRESSURE SEWER SYSTEM - Supply MDPE Pipe, Series 1, PN16, PE 80B complying with AS/NZS 4130 - 50mm ODPE | 0 | 1197 | 67FF | 80 |  |  | 37.59% | 37.59% | 37.59% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
70 | PRESSURE SEWER SYSTEM - Supply MDPE Pipe, Series 1, PN16, PE 80B complying with AS/NZS 4130 - 63mm ODPE | 0 | 2251.5 | 67FF | 80 |  |  | 42.19% | 42.19% | 42.19% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
71 | PRESSURE SEWER SYSTEM - Excavate, lay, bed, joint and backfill MDPE Pipe, Series 1, PN16, PE 80B pressure pipe main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835). Including supply & installation of enveloper conduit at road crossing locations. - 50mm ODPE | 4 | 7315 | 72 | 73,29 |  |  | 37.59% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
72 | PRESSURE SEWER SYSTEM - Excavate, lay, bed, joint and backfill MDPE Pipe, Series 1, PN16, PE 80B pressure pipe main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835). Including supply & installation of enveloper conduit at road crossing locations. - 63mm ODPE | 4 | 13983 | 64 | 68,71,76FF,77FF |  |  | 42.19% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
73 | PRESSURE SEWER SYSTEM - Supply and installation of Aquatec Boundary Connection pits | 5 | 19800 | 67,68,71 | 74FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
74 | PRESSURE SEWER SYSTEM - Supply and installation of Aquatec flushing point | 0 | 1780 | 73FF | 75FF |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
75 | PRESSURE SEWER SYSTEM - Supply and installation of Aquatec isolation valves | 0 | 3700 | 74FF | 78 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
76 | PRESSURE SEWER SYSTEM - Dewatering of trench extra to 9610 - 9615 (Provisional, if ordered) | 0 | 5550 | 72FF | 80
77 | PRESSURE SEWER SYSTEM - Supply and placing of metal ballast bedding below bottom of pipe, supply and placing of geotextile, including additional excavation below pipe barrel to maximum 400mm below pipe barrel (Provisional, if ordered) | 0 | 500 | 72FF | 80
78 | PRESSURE SEWER SYSTEM - Demolish existing sewer manhole and connect to existing 225 diameter sewer main, incl. liaison with Council and plugging of downstream manhole | 1 | 1500 | 75 | 80 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
79 | PRESSURE SEWER SYSTEM - Construct vent pole and foundation as per WRC Std Dwg S0020 - incl. all materials and connection to receiving manhole | 1 | 2500 | 68 | 80 |  |  | 80% | 80% | 80% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100%
80 | ANCILLARY WORKS - Ergon longitudinal trenching and backfilling, including supply of all bedding and backfill sand, as directed (Provisional, if ordered) | 8 | 22474.87 | 25,79,78,77,76,70,69,66,65 | 81FF,86 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
81 | ANCILLARY WORKS - Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 3/100mm & 1/40mm Electrical plus 2/100mm Testra | 0 | 2664.518 | 80FF | 82FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
82 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 2/100mm plus 1/100mm Testra | 0 | 466.304 | 81FF | 83FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
83 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 1/100mm Electrical plus 1/100mm Telstra | 0 | 5078.8 | 82FF | 84FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
84 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered) - 1x40 Telstra | 0 | 371.805 | 83FF | 85FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
85 | Installation of Electrical Pits (Direction Changes) Type 5 | 0 | 10450 | 84FF | 87 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
86 | Supply & Install Internal Electrical cabling including cabling to a common point external to the sub-division to a central metering location, 'green boys' and lot connections. (ELECTRICAL METERS PROVIDED BY FUTURE LOT OWNERS) | 6 | 42965 | 80 | 87 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
87 | Supply & Install 'The Cove' sub-board including connection to Ergon POS outside development as per DWG E25 | 2 | 21740 | 86,85 | 88 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
88 | Supply & Install MARINA MSB as per DWG E25 | 2 | 18085 | 87 | 89 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
89 | Supply & Install MARINA Sub-Main from 'The Cove' MSB to MARINA DB | 2 | 7650 | 88 | 90FF,94 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
90 | Electrical trenching & Installation - 2/100mm & 1/40 Electricity plus 1/100mm | 0 | 562.63 | 89FF | 91FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
91 | Electrical trenching & Installation - Telecommunications pits | 0 | 13500 | 90FF | 92FF,118FF | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
92 | Supply, installation and backfill of conduit bends at pillar location, including all 80mm dia, 1200mm rad bends, end caps, 40mm dia service conduits including bends to property boundary, end caps, timber stake, polymeric cable protection cover and caution orange tape (Dwg 5164 Sh 3, 4, 5 & 6) | 0 | 4500 | 91FF | 26 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
93 | Footings to streetlight poles including anchor cage, to DMR std drawing nos 1380, 1381, 1382, 1429. Footing 600mm diameter 2300mm deep. | 6 | 30766.2654 | 31 | 26 | [6 empty] | 50% | 100% | 100% | 100% | 100% | 100% | 100%
94 | Excavate for padmount substation to allow Electrical Services Provider to install electrical cables and equipment, and reinstate surfaces after installation | 0 | 8250 | 89 | 26 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
95 | SOFTSCAPING - PLANTS WHITSUNDAY - SOFTSCAPING COMPLETE AS PER QUOTE MLS13-222 (Rev 2) | 15 | 189402.18 | 26101104 | 96 |  |  |  | 4% | 4% | 4% | 4% | 4% | 80% | 95% | 100% | 100% | 100%
96 | SOFTSCAPING - Works Not Included in PWS Quote MLS13-222 (RPZ, Road Crossings, Conduits & GPO for Irrigation Controller) | 4 | 7105 | 95 | 4 | [6 empty] | 25% | 100% | 100% | 100% | 100% | 100% | 100%
97 | HARDSCAPING WORKS - PLANTS WHITSUNDAY COMPLETE - Paver edging in lieu of Concrete Edge Strip as per Quotation MLS13-240 (2) | 5 | 10227.27 | 31 | 98 |  |  |  | 4% | 4% | 4% | 4% | 4% | 60% | 80% | 100% | 100% | 100%
98 | HARDSCAPING WORKS - PLANTS WHITSUNDAY - GRAVEL TO OUTDOOR AREAS ( COMPLETE) | 5 | 22088.41 | 97 | 99 |  |  |  | 4% | 4% | 4% | 4% | 4% | 60% | 75% | 100% | 100% | 100%
99 | HARDSCAPING WORKS - Outdoor Viewing Areas (Complete) | 5 | 24000 | 98,32 | 100 | [8 empty] | 50% | 100% | 100% | 100% | 100%
100 | HARDSCAPING WORKS - PLANTS WHITSUNDAY TO COMPLETE IN FULL - Allotment Separation Fences (Removable Centre Post) REDUCED IN HEIGHT TO 1400MM | 10 | 80346.6 | 99 | 101 |  |  |  | 4% | 4% | 4% | 4% | 4% | 80% | 85% | 100% | 100% | 100%
101 | HARDSCAPING WORKS - PLANTS WHITSUNDAY COMPLETE - Supply & Install Totems as Detailed (6 No.) | 1 | 9436.36 | 100 | 102,95 | [9 empty] | 50% | 100% | 100% | 100%
102 | HARDSCAPING WORKS - Supply and Install Timber Viewing Deck as Detailed | 5 | 23000 | 101 | 103 | [5 empty] | 25% | 75% | 75% | 80% | 80% | 100% | 100% | 100%
103 | HARDSCAPING WORKS - PLANTS WHITSUNDAY COMPLETE - Supply & Install Timber Seat (To match existing) | 2 | 2545.45 | 102 | 34 | [11 empty] | 100% | 100%
104 | HARDSCAPING WORKS - Supply & Instal Stainless Steel 'The Cove' & Port of Airlie logo's as shown on entry walls | 20 | 6000 | 117,110FF | 34,95 | [9 empty] | 100% | 100% | 100% | 100%
105 | HARDSCAPING WORKS - Core Filled Block Wall - W1 (1500mm High) | 2 | 17890 | 23 | 106 | [7 empty] | 11.11% | 100% | 100% | 100% | 100% | 100%
106 | HARDSCAPING WORKS - Core Filled Block Wall - W2 (Entry Wall with Rake) | 2 | 7028.0845 | 105 | 117 | [7 empty] | 16.67% | 100% | 100% | 100% | 100% | 100%
107 | HARDSCAPING WORKS - PLANTS WHITSUNDAY SUPERVISION / VEHICLES & ADMIN FEE | 0 | 4142.85 | [7 empty] | 4% | 4% | 4% | 60% | 100% | 100% | 100% | 100%
108 | FENCING / GATES / EQUIPMENT - Supply and Install Pedestrian and Vehicular Gate and associated Security Key Pad | 30 | 21670 | 117 | 109,34 | [10 empty] | 80% | 100% | 100%
109 | FENCING / GATES / EQUIPMENT - PLANTS WHITSUNDAY COMPLETE - Supply & install boundary fence to Lot 23. | 1 | 2704.55 | 108 | 34 | [10 empty] | 100% | 100% | 100%
110 | FENCING / GATES / EQUIPMENT - Supply and Install communal letterbox structure within W2 wall - aluminium fronted with range hood and rear opening | 40 | 6515 | 117 | 104FF | [9 empty] | 100% | 100% | 100% | 100%
111 | Variation - Additional watermain, 50mm water meter & RPZ - installed at the Cove subdivision as directed by the Superintendent | 1 | 11420 | 53FF | 62 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
112 | Variation - Installation of geotextile Mirafi in Stormwater trench where depths exceed 1.2m into marine sedimentation as directed by the Superintendent | 4 | 3284.9896 | 24 | 29113 | [5 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
113 | Variation - Unsuitable Subgrade replacement - Remove existing material 300 deep & replace with CBR 15 as directed by Superintendent | 1 | 30170.0486 | 112 | 29 | [6 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
114 | Variation - Easement at Revetment wall - Relocate & replace existing revetment wall rocks, install geotextile & backfill with general fill to areas as indicated on drawing 13003 21 & 22A | 4 | 9499 | 23 | 4 | [7 empty] | 100% | 100% | 100% | 100% | 100% | 100%
115 | Variation - Privacy Screen to boundary of Lot 1 & Lot 23 - Provide 11 natural stone columns and 11 steel panels to 1400mm high fence. Stonework nib wall to easement at Lot 23. Salmon coloured footpath to boundary at Entrance & along Lot 23. | 21 | 93885.95 | 117 | 34 | [10 empty] | 8% | 20% | 100%
116 | Line Item 171 - Supply & Install Gas - Variation to adjust claimed contract value of $48,571.75 to agreed value of $15,000 | 0 | -33571.75 | [8 empty] | 100% | 100% | 100% | 100% | 100% | 100% | 100%
117 | PROVISIONAL SUM ITEM - Supply & Install capping, facing & stone treatments to Entry Statements | 10 | 25000.5 | 23106 | 104,110,108,115,34 | [8 empty] | 100% | 100% | 100% | 100% | 100%
118 | Variation - Telstra Pit, supply & install Type 8 pit as directed by Superintendent | 0 | 950 | 91FF | [13 empty] | 100%

## Budget & Revenue
Portfolio WBS | Item No | Description | Unit | Tender Budget | Tender Quantity | Budget Rate | Contract Sell Rate | Contract Sell Total | 2014-04-01 | %C - Apr 14 | 2014-05-01 | %C - May 14 | 2014-06-01 | %C - Jun 14 | 2014-07-01 | %C - Jul 14 | 2014-08-01 | %C - Aug 14 | 2014-09-01 | %C - Sep 14 | 2014-10-01 | %C - Oct 14 | 2014-11-01 | %C - Nov 14 | 2014-12-01 | %C - Dec 14 | 2015-01-01 | %C - Jan 15 | 2015-02-01 | %C - Feb 15 | 2015-03-01 | %C - Mar 15 | Revenue Apr 14 | Revenue May 14 | Revuenue Jun 14 | Revenue Jul 14 | Revenue Aug 14 | Revenue Sep 14 | Revenue Oct 14 | Revenue Nov 14 | Revenue Dec 14 | Revenue Jan 15 | Revenue Feb 15 | Revenue Mar 15
Contract Items
PROJECT SUMMARY - THE COVE
|  | ROADWORKS & DRAINAGE | [5 empty] | 1372784.35
|  | WATER PRESSURE MAINS | [5 empty] | 122215.13
|  | PRESSURE SEWER SYSTEM | [5 empty] | 95815.83
|  | ANCILLARY WORKS | [5 empty] | 309326.07
|  | SUB-TOTAL LANDSCAPING & HARDSCAPING | [5 empty] | 502600.18
|  | TOTAL GST EXCLUSIVE | [5 empty] | 2402741.56
| Item | ROADWORKS AND DRAINAGE
| 1000 | Establishment, Traffic and Environment
| 1100 | Contractor's Site Facilities, MRS28
5 | 1101.1 | Site establishment and disestablishment | Lump | 12000 | 1 | 15976.35 | 18017.1 | 18017.1 | 0.75 | 75% | 0.75 | 75% | 0.75 | 75% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 13512.825 | 13512.825 | 13512.825 | 14413.68 | 14413.68 | 14413.68 | 14413.68 | 14413.68 | 14413.68 | 14413.68 | 18017.1 | 18017.1
| 1200 | Provision for Traffic, MRS02
| 1211.1 | Preparation & Implimentation of TMP | Lump |  | 1
| 1310 | Environmental Management, MRS51
| 1311.1 | Preparation of the Environmental Management Plan (Construction) | Lump |  | 1
| 1312.1 | Implementation and monitoring of the Environmental Management Plan (Construction) | Lump |  | 1
| 1313.1 | Erosion and sediment control management plan | Lump |  | 1
| 1315.1 | Water quality monitoring | Lump |  | 1
| 1316.1 | Control of erosion and sedimentation | Lump |  | 1
| 2000 | Drainage, Retaining Structures & Protective Treatments
| 2120 | Supply of Precast Concrete Pipe Culverts in accordance with AS 4058 - Exposure Class B1, and Installation of Culverts to MRS03
6 | 2121.2 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 375mm diameter with saltwater cover | m | 9401.586 | 63.4 | 197.4302 | 222.65 | 14116.01 |  |  | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 63.4 | 100% | 0 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01 | 14116.01
7 | 2121.4 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 450mm diameter with saltwater cover | m | 4610.404 | 26.8 | 229.0341 | 258.29 | 6922.17 |  |  | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 26.8 | 100% | 0 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17 | 6922.17
8 | 2121.6 | Supply and installation of concrete pipe culvert components, Class 2, RRJ, 525mm diameter with saltwater cover | m | 13652.17 | 70.7 | 257.0893 | 289.93 | 20498.05 |  |  | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 70.7 | 100% | 0 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05 | 20498.05
9 | 2121.8 | Supply and installation of concrete pipe culvert components, Class 2,RRJ, 600mm diameter with saltwater cover | m | 7442.526 | 31.7 | 312.5743 | 352.5 | 11174.25 |  |  | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 31.7 | 100% | 0 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25 | 11174.25
| 2190 | Supply of Stormwater Drainage Pipe Culverts in accordance with AS/NZS 5065, and installation of Culverts to MRS03
10 | 2191.1 | Supply and installation of BlackMAX stormwater pipe, Class SN8, 150 mm diameter | m | 33768 | 315 | 142.7202 | 160.95 | 50699.25 | [10 empty] | 315 | 100% | 315 | 100% | 315 | 100% | 315 | 100% | 315 | 100% | 315 | 100% | 315 | 100% | 0 | 0 | 0 | 0 | 0 | 50699.25 | 50699.25 | 50699.25 | 50699.25 | 50699.25 | 50699.25 | 50699.25
| 2260 | Supply and Installation of Drainage Components
11 | 2261.1 | Supply and install 600mm flood flap | each | 2788 | 1 | 3711.8798 | 4186.02 | 4186.02 | [6 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 4186.02 | 4186.02 | 4186.02 | 4186.02 | 4186.02 | 4186.02 | 4186.02 | 4186.02 | 4186.02
| 2300 | Concrete in Culverts and End Structures, MRS03
11.5 | 2308 | End structures to culverts, reinforced concrete | m3 | 950 | 1 | 1264.792 | 1426.35 | 1426.35 | [6 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35
12 | 2313 | Aprons to culverts, reinforced concrete | m3 | 950 | 1 | 1264.792 | 1426.35 | 1426.35 | [6 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35 | 1426.35
| 2400 | Pavement Drainage, MRS03
13 | 2404.1 | Concrete kerb and channel, barrier (B2) | m | 3396.8 | 66 | 68.5186 | 77.27 | 5099.82 | [10 empty] | 66 | 100% | 66 | 100% | 66 | 100% | 66 | 100% | 66 | 100% | 66 | 100% | 66 | 100% | 0 | 0 | 0 | 0 | 0 | 5099.82 | 5099.82 | 5099.82 | 5099.82 | 5099.82 | 5099.82 | 5099.82
14 | 2404.3 | Type 1 main roads flush kerb (300x200) | m | 19808.2547 | 377 | 69.9545 | 78.89 | 29741.53 | [10 empty] | 377 | 100% | 377 | 100% | 377 | 100% | 377 | 100% | 377 | 100% | 377 | 100% | 377 | 100% | 0 | 0 | 0 | 0 | 0 | 29741.53 | 29741.53 | 29741.53 | 29741.53 | 29741.53 | 29741.53 | 29741.53
15 | 2413.1 | 3450x1500 ecosol RSF 500 GPT with class B lid | each | 32670 | 1 | 43495.617 | 49051.56 | 49051.56 |  |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56 | 49051.56
16 | 2413.2 | 600x600 RKO pit with riser 600x600 V-Grate & Concrete Surround | each | 27200 | 8 | 4526.6292 | 5104.84 | 40838.72 |  |  | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 7 | 87.5% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 8 | 100% | 0 | 35733.88 | 35733.88 | 35733.88 | 35733.88 | 40838.72 | 40838.72 | 40838.72 | 40838.72 | 40838.72 | 40838.72 | 40838.72
17 | 2413.4 | Concrete gullies, Drainway 0TP/X maxflow grate, standard | each | 3950 | 1 | 5258.883 | 5930.63 | 5930.63 | [6 empty] | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 4744.504 | 4744.504 | 5930.63 | 5930.63 | 5930.63 | 5930.63 | 5930.63 | 5930.63 | 5930.63
18 | 2141.2 | Concrete manhole with 600dia access lid (major) | each | 3950 | 1 | 5258.883 | 5930.63 | 5930.63 |  |  | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 4744.504 | 4744.504 | 4744.504 | 4744.504 | 5930.63 | 5930.63 | 5930.63 | 5930.63 | 5930.63 | 5930.63 | 5930.63
| 2500 | Subsurface Drainage MRS03
19 | 2501.1 | Subsoil drains, Type C, 100 mm diameter including outlets and flush points | m | 15382.5425 | 390 | 52.1751 | 58.84 | 22947.6 | [10 empty] | 390 | 100% | 390 | 100% | 390 | 100% | 390 | 100% | 390 | 100% | 390 | 100% | 390 | 100% | 0 | 0 | 0 | 0 | 0 | 22947.6 | 22947.6 | 22947.6 | 22947.6 | 22947.6 | 22947.6 | 22947.6
| 2600 | Protective Treatments, MRS03
20 | 2631.1 | Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 1.2m wide | m2 | 13898.4741 | 188 | 98.4268 | 111 | 20868 | [12 empty] | 90 | 47.87% | 150 | 79.79% | 188 | 100% | 188 | 100% | 188 | 100% | 188 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9990 | 16650 | 20868 | 20868 | 20868 | 20868
21 | 2631.2 | Hand-placed concrete paving, 100mm thick, N25/20 with SL62 mesh central to footpaths 2.0m wide | m2 | 2816.5272 | 38.1 | 98.4191 | 110.99 | 4228.72 | [14 empty] | 38.1 | 100% | 38.1 | 100% | 38.1 | 100% | 38.1 | 100% | 38.1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4228.72 | 4228.72 | 4228.72 | 4228.72 | 4228.72
22 | 2631.5 | Hand-placed concrete paving, 170mm thick, N32/20 with SL82 mesh central with exposed aggregate finish (incl. joints as detailed) | m2 | 34443.1896 | 240 | 191.0734 | 215.48 | 51715.2 | [14 empty] | 215 | 89.58% | 240 | 100% | 240 | 100% | 240 | 100% | 240 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46328.2 | 51715.2 | 51715.2 | 51715.2 | 51715.2
| 2700 | Retaining Walls, MRS03
23 | 2712 | Natural local stone mass gravity wall. 500mm thick, vertical face including footing (1m x 400mm thick) and rear drainage | m2 | 456355.226 | 677 | 777.5524 | 830.5 | 562248.5 |  |  | 145 | 21.42% | 385 | 56.87% | 677 | 100% | 677 | 100% | 677 | 100% | 677 | 100% | 677 | 100% | 677 | 100% | 677 | 100% | 677 | 100% | 677 | 100% | 0 | 120422.5 | 319742.5 | 562248.5 | 562248.5 | 562248.5 | 562248.5 | 562248.5 | 562248.5 | 562248.5 | 562248.5 | 562248.5
| 3000 | Earthworks
| 3100 | Earthworks, Preparation, MRS04
| 3101.1 | Clearing and grubbing | Lump |  | 1
| 3200 | Earthworks, Excavation, MRS04
24 | 3201 | Road excavation, all materials to reprofile the subgrade level | m3 | 3690.2222 | 380 | 12.9287 | 14.58 | 5540.4 |  |  |  |  | 76 | 20% | 276 | 72.63% | 380 | 100% | 380 | 100% | 380 | 100% | 380 | 100% | 380 | 100% | 380 | 100% | 380 | 100% | 380 | 100% | 0 | 0 | 1108.08 | 4024.08 | 5540.4 | 5540.4 | 5540.4 | 5540.4 | 5540.4 | 5540.4 | 5540.4 | 5540.4
25 | 3201.2 | Allotment excavation to Revised RL (3.9 - 3.7) | m3 | 10548.3871 | 1000 | 14.0453 | 15.84 | 15840 |  |  |  |  | 200 | 20% | 750 | 75% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 1000 | 100% | 0 | 0 | 3168 | 11880 | 15840 | 15840 | 15840 | 15840 | 15840 | 15840 | 15840 | 15840
| 3300 | Earthworks, Embankment, MRS04
26 | 3301.2 | Re-trim allotments to revised FL | m2 | 9925.7143 | 9000 | 1.471 | 1.66 | 14940 |  |  |  |  | 1800 | 20% | 6000 | 66.67% | 9000 | 100% | 9000 | 100% | 9000 | 100% | 9000 | 100% | 9000 | 100% | 9000 | 100% | 9000 | 100% | 9000 | 100% | 0 | 0 | 2988 | 9960 | 14940 | 14940 | 14940 | 14940 | 14940 | 14940 | 14940 | 14940
| 4100 | Unbound Pavements, MRS05
27 | 4103.1 | Base, unbound pavement, Type 2, Subtype 2.1 | m3 | 16887.8611 | 125 | 179.873 | 202.85 | 25356.25 | [10 empty] | 125 | 100% | 125 | 100% | 125 | 100% | 125 | 100% | 125 | 100% | 125 | 100% | 125 | 100% | 0 | 0 | 0 | 0 | 0 | 25356.25 | 25356.25 | 25356.25 | 25356.25 | 25356.25 | 25356.25 | 25356.25
28 | 4104.2 | Subbase, unbound pavement, Type 2, Subtype 2.3 | m3 | 23360.7837 | 190 | 177.852 | 200.57 | 38108.3 | [10 empty] | 190 | 100% | 190 | 100% | 190 | 100% | 190 | 100% | 190 | 100% | 190 | 100% | 190 | 100% | 0 | 0 | 0 | 0 | 0 | 38108.3 | 38108.3 | 38108.3 | 38108.3 | 38108.3 | 38108.3 | 38108.3
29 | 4104.4 | Subbase, unbound pavement, Type 2, Subtype 2.3 under 170mm Concrete | m3 | 6019.8834 | 36 | 231.1524 | 260.68 | 9384.48 | [10 empty] | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 36 | 100% | 0 | 0 | 0 | 0 | 0 | 9384.48 | 9384.48 | 9384.48 | 9384.48 | 9384.48 | 9384.48 | 9384.48
| 5100 | Sprayed Bituminous Surfacing (Excluding Emulsion), MRS11
30 | 5141.1 | Sprayed bituminous surfacing, including supply of binder, including supply of additives, including supply and spreading of precoated cover aggregates. 7mm Primerseal, MC5 1.0L/m2, 175m2/m3 | m2 | 17548.125 | 955 | 24.4647 | 27.59 | 26348.45 | [12 empty] | 955 | 100% | 955 | 100% | 955 | 100% | 955 | 100% | 955 | 100% | 955 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 26348.45 | 26348.45 | 26348.45 | 26348.45 | 26348.45 | 26348.45
| 5600 | Asphalt Surfacing, Brisbane City Council Asphalt Specification S310
31 | 5602.1 | AC10 Type 2 mix | tonne | 39160 | 80 | 651.7036 | 734.95 | 58796 | [12 empty] | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 80 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 58796 | 58796 | 58796 | 58796 | 58796 | 58796
| 6140 | Roadside Structures, MRS16A
| 6161.1 | Ballistrade guardrail (NOT INCLUDED. BY OWNERS)
32 | 6161.3 | Stair Risers and treads (Hardwood & Stainless - Provisional) | Item | 84579.6 | 1 | 112606.111 | 126989.93 | 126989.93 |  |  |  |  | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 5079.5972 | 5079.5972 | 5079.5972 | 101591.944 | 126989.93 | 126989.93 | 126989.93 | 126989.93 | 126989.93 | 126989.93
| 9000 | Miscellaneous Works
32.5 | 9001 | Compliance testing | Lump | 57531 | 1 | 76594.615 | 86378.48 | 86378.48 |  |  | 0.2 | 20% | 0.4 | 40% | 0.65 | 65% | 0.7 | 70% | 0.85 | 85% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 17275.696 | 34551.392 | 56146.012 | 60464.936 | 73421.708 | 86378.48 | 86378.48 | 86378.48 | 86378.48 | 86378.48 | 86378.48
33 | 9002 | Survey Set Out | Lump | 15945 | 1 | 21228.574 | 23940.22 | 23940.22 | 0.25 | 25% | 0.5 | 50% | 0.7 | 70% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 5985.055 | 11970.11 | 16758.154 | 19152.176 | 21546.198 | 22743.209 | 23940.22 | 23940.22 | 23940.22 | 23940.22 | 23940.22 | 23940.22
34 | 9002 | Preparation of "As constructed" drawings for submission | Lump | 7390 | 1 | 9838.768 | 11095.53 | 11095.53 | [6 empty] | 0.6 | 60% | 0.65 | 65% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% |  |  |  | 6657.318 | 7212.0945 | 8876.424 | 11095.53 | 11095.53 | 11095.53 | 11095.53 | 11095.53 | 11095.53
35 | 9051 | Locate and protect services - general | Lump | 1998 | 1 | 2660.064 | 2999.85 | 2999.85 | 0.1 | 10% | 0.25 | 25% | 0.5 | 50% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 299.985 | 749.9625 | 1499.925 | 2249.8875 | 2999.85 | 2999.85 | 2999.85 | 2999.85 | 2999.85 | 2999.85 | 2999.85 | 2999.85
| Item | WATER PRESSURE MAINS
| 9300 | Water Reticulation
| 9304 | Supply OPVC pressure pipe, RRJ, (C.I.O.D. compatible) PN 16
36 | 9304.1 | 100mm dia | m | 3795 | 253 | 19.9695 | 22.52 | 5697.56 |  |  |  |  | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 0 | 0 | 5697.56 | 5697.56 | 5697.56 | 5697.56 | 5697.56 | 5697.56 | 5697.56 | 5697.56 | 5697.56 | 5697.56
| 9311 | Supply sluice valves, C.I. to AS 2544, PN 16, counterclockwise to close c/w spindle cap incl. F.B.E./Rilsan coating, incl 316 S/S Flange insertion set (FL-FL)
37 | 9311.1 | 100mm dia | Each | 8100 | 6 | 1797.3368 | 2026.92 | 12161.52 |  |  |  |  | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 0 | 0 | 12161.52 | 12161.52 | 12161.52 | 12161.52 | 12161.52 | 12161.52 | 12161.52 | 12161.52 | 12161.52 | 12161.52
| 9320 | Supply bends, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681 (SOC-SOC)
38 | 9320.2 | 100mm x 22½o | Each | 240 | 2 | 159.763 | 180.17 | 360.34 |  |  |  |  | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 360.34 | 360.34 | 360.34 | 360.34 | 360.34 | 360.34 | 360.34 | 360.34 | 360.34 | 360.34
39 | 9320.3 | 100mm x 45o | Each | 360 | 3 | 159.763 | 180.17 | 540.51 |  |  |  |  | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 540.51 | 540.51 | 540.51 | 540.51 | 540.51 | 540.51 | 540.51 | 540.51 | 540.51 | 540.51
40 | 9320.4 | 100mm x 90o | Each | 280 | 2 | 186.391 | 210.2 | 420.4 |  |  |  |  | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 420.4 | 420.4 | 420.4 | 420.4 | 420.4 | 420.4 | 420.4 | 420.4 | 420.4 | 420.4
| 9340 | Supply tees, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set for flange ends
41 | 9343.1 | 100 x 100mm (FL-FLxFL) | Each | 840 | 3 | 372.782 | 420.4 | 1261.2 |  |  |  |  | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 1261.2 | 1261.2 | 1261.2 | 1261.2 | 1261.2 | 1261.2 | 1261.2 | 1261.2 | 1261.2 | 1261.2
| 9360 | Supply hydrant tee, DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set (SOC-SOCxFL)
42 | 9360.1 | 100x80? | Each | 560 | 2 | 372.782 | 420.4 | 840.8 |  |  |  |  | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 840.8 | 840.8 | 840.8 | 840.8 | 840.8 | 840.8 | 840.8 | 840.8 | 840.8 | 840.8
43 | 9361.1 | Supply spring hydrant incl. F.B.E./Rilsan coating | Each | 600 | 2 | 399.4105 | 450.43 | 900.86 |  |  |  |  | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 900.86 | 900.86 | 900.86 | 900.86 | 900.86 | 900.86 | 900.86 | 900.86 | 900.86 | 900.86
44 | 9362.2 | Supply hydrant risers 80?x300mm (FL-FL) (Provisional, if ordered) | Each | 260 | 2 | 173.0805 | 195.19 | 390.38 | [12 empty] | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 390.38 | 390.38 | 390.38 | 390.38 | 390.38 | 390.38
45 | 9363.1 | Supply hydrant cover boxes | Each | 200 | 2 | 133.1345 | 150.14 | 300.28 |  |  |  |  | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 300.28 | 300.28 | 300.28 | 300.28 | 300.28 | 300.28 | 300.28 | 300.28 | 300.28 | 300.28
46 | 9364.1 | Install cover boxes to hydrants incl. supply of margin sets & bedding bricks & markers | Each | 1040 | 2 | 692.308 | 780.74 | 1561.48 | [12 empty] | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1561.48 | 1561.48 | 1561.48 | 1561.48 | 1561.48 | 1561.48
| 9391 | Supply connectors (FL-SOC) DICL to AS 2280, RRJ, Class K12, bitumen coated with polyethylene sleeving to AS 3680 and 3681, incl 316 S/S Flange insertion set
47 | 9391.1 | 100? | Each | 700 | 7 | 133.1346 | 150.14 | 1050.98 | [10 empty] | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 0 | 0 | 0 | 0 | 0 | 1050.98 | 1050.98 | 1050.98 | 1050.98 | 1050.98 | 1050.98 | 1050.98
| 9400 | Supply gibault joints
48 | 9401.2 | 150mm dia | Each | 500 | 2 | 332.843 | 375.36 | 750.72 | [10 empty] | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 750.72 | 750.72 | 750.72 | 750.72 | 750.72 | 750.72 | 750.72
| 9470 | House Connection Services (Refer MRC Std Dwg A3-00840) including supply and installation of 100 mm tapping band, main cock and poly pipe to property boundary
49 | 9470.1 | 32mm single (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each | 2800 | 7 | 532.545 | 600.57 | 4203.99 | [10 empty] | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 7 | 100% | 0 | 0 | 0 | 0 | 0 | 4203.99 | 4203.99 | 4203.99 | 4203.99 | 4203.99 | 4203.99 | 4203.99
50 | 9470.2 | 32mm single under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each | 4000 | 2 | 2662.725 | 3002.85 | 6005.7 | [10 empty] | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 6005.7 | 6005.7 | 6005.7 | 6005.7 | 6005.7 | 6005.7 | 6005.7
51 | 9470.3 | 32mm dual (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each | 1920 | 4 | 639.0512 | 720.68 | 2882.72 | [10 empty] | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 4 | 100% | 0 | 0 | 0 | 0 | 0 | 2882.72 | 2882.72 | 2882.72 | 2882.72 | 2882.72 | 2882.72 | 2882.72
52 | 9470.4 | 32mm dual under road including enveloper conduit (WATER METERS NOT INCLUDED - BY FUTURE OWNERS) | Each | 6240 | 3 | 2769.2313 | 3122.96 | 9368.88 | [10 empty] | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 0 | 9368.88 | 9368.88 | 9368.88 | 9368.88 | 9368.88 | 9368.88 | 9368.88
| 9523 | Excavate, lay, bed, joint and backfill OPVC pressure pipe, RRJ main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835)
53 | 9523.1 | 100mm dia | m | 20240 | 253 | 106.5064 | 120.11 | 30387.83 |  |  |  |  | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 253 | 100% | 0 | 0 | 30387.83 | 30387.83 | 30387.83 | 30387.83 | 30387.83 | 30387.83 | 30387.83 | 30387.83 | 30387.83 | 30387.83
54 |  | Supply & Installation of 100mm diameter water meter with an 80mm bypass line as per detail A of U13481.001-122(B) | item | 9600 | 1 | 12781.08 | 14413.68 | 14413.68 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 14413.68 | 14413.68 | 14413.68 | 14413.68 | 14413.68 | 14413.68
| 9525 | Extra Over Items
55 | 9526 | Dewatering of trench extra to Items 9521 - 9524 (Provisional, if ordered) | m | 3795
56 | 9527.1 | Supply and placing of approved sand filling 150 - 300mm above top of pipe (Type 1 construction) (Provisional, if ordered) | m³ | 1375 | 25 | 73.226 | 82.58 | 2064.5 | [12 empty] | 25 | 100% | 25 | 100% | 25 | 100% | 25 | 100% | 25 | 100% | 25 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2064.5 | 2064.5 | 2064.5 | 2064.5 | 2064.5 | 2064.5
57 | 9529.1 | Supply and Install Fire Booster (Provisional, if ordered) MARINA ITEM | Each | 17266.88 | 1 | 17266.88 | 17266.88 | 17266.88 | [8 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 17266.88 | 17266.88 | 17266.88 | 17266.88 | 17266.88 | 17266.88 | 17266.88 | 17266.88
58 | 9531.2 | Concrete Grade N20 in place for thrust blocks | m³ | 1750 | 5 | 465.9778 | 525.5 | 2627.5 | [8 empty] | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 5 | 100% | 0 | 0 | 0 | 0 | 2627.5 | 2627.5 | 2627.5 | 2627.5 | 2627.5 | 2627.5 | 2627.5 | 2627.5
59 | 9596 | Flushing and chlorination of mains including supply of chlorine | Lump | 1000 | 1 | 1331.366 | 1501.43 | 1501.43 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1501.43 | 1501.43 | 1501.43 | 1501.43 | 1501.43 | 1501.43
60 | 9597 | Testing of water mains including supply of pressurising equipment, gauges and fittings | Lump | 1500 | 1 | 1997.045 | 2252.14 | 2252.14 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14
61 | 9598.1 | Connection to existing Council main, 100mm dia (incl. Council fees) | Lump | 2000 | 1 | 2662.725 | 3002.85 | 3002.85 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 3002.85 | 3002.85 | 3002.85 | 3002.85 | 3002.85 | 3002.85
| Item | PRESSURE SEWER SYSTEM
| 9600 | Sewers and Manholes, MCC 7
| 9601 | Supply and Delivery of uPVC sewer pipe, Class 16, complying with AS 1260, suitable for socket joints
62 | 9601.2 | 225mm dia. | m | 201.4 | 5.3 | 50.5896 | 57.05 | 302.37 |  |  | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 0 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37 | 302.37
| 9615 | Trench excavation in soil for 225mm dia. sewers, including excavation for manholes, jump ups, slope drops, vertical drops, backfilling, disposal of spoil and restoration.
63 | 9615.1 | Depth Range 0.5-1.5m inclusive | m | 265 | 5.3 | 66.5672 | 75.07 | 397.87 |  |  | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 0 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87 | 397.87
| 9620 | Lay, bed and joint sewer pipe including main and specials, supply and place sand bedding to 150mm above top of pipe (Type 1 construction, WRC Std drawing D-0030) and testing of finished pipeline, including CCTV Survey and Report.
64 | 9620.2 | 225mm dia. | m | 1325 | 5.3 | 332.8434 | 375.36 | 1989.41 |  |  | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 5.3 | 100% | 0 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41 | 1989.41
65 | 9640.1 | Concrete N20 in place for pipe bedding, surrounds, stops, blocks, cover slab incl. steel reinforcement where specified incl. supply of all materials (Provisional, if ordered) | m³ | 1000 | 2 | 665.6795 | 750.71 | 1501.42 | [12 empty] | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1501.42 | 1501.42 | 1501.42 | 1501.42 | 1501.42 | 1501.42
66 | 9650.1 | Supply and placing of approved sand filling (150 - 300mm above pipes) (Provisional, if ordered) | m³ | 1100 | 20 | 73.226 | 82.58 | 1651.6 | [12 empty] | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 20 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1651.6 | 1651.6 | 1651.6 | 1651.6 | 1651.6 | 1651.6
| 9700 | Manhole House Connection Branches
67 | 9700.3 | 100mm dia. house connection extension to lot 23 (from existing manhole) | m | 1500 | 6 | 332.8432 | 375.36 | 2252.16 | [12 empty] | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 6 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2252.16 | 2252.16 | 2252.16 | 2252.16 | 2252.16 | 2252.16
| 9720 | Manholes complete in place
68 | 9720.1 | Depth Range 0.5-1.5m inclusive (1050 internal diameter) - Including connection for poly pressure main and internal epoxy coating of manhole | Each | 4400 | 1 | 5857.995 | 6606.27 | 6606.27 | [10 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 6606.27 | 6606.27 | 6606.27 | 6606.27 | 6606.27 | 6606.27 | 6606.27
| 9740 | Supply MDPE Pipe, Series 1, PN16, PE 80B complying with AS/NZS 4130
69 | 9740.1 | 50mm ODPE | m | 1197 | 133 | 11.9804 | 13.51 | 1796.83 |  |  | 50 | 37.59% | 50 | 37.59% | 50 | 37.59% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 0 | 675.5 | 675.5 | 675.5 | 1796.83 | 1796.83 | 1796.83 | 1796.83 | 1796.83 | 1796.83 | 1796.83 | 1796.83
70 | 9740.2 | 63mm ODPE | m | 2251.5 | 237 | 12.6456 | 14.26 | 3379.62 |  |  | 100 | 42.19% | 100 | 42.19% | 100 | 42.19% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 0 | 1426 | 1426 | 1426 | 3379.62 | 3379.62 | 3379.62 | 3379.62 | 3379.62 | 3379.62 | 3379.62 | 3379.62
| 9741 | Excavate, lay, bed, joint and backfill MDPE Pipe, Series 1, PN16, PE 80B pressure pipe main and specials, including supply and installation of sand bedding to 150mm above top of pipe, installation of thrust blocks and disposal of spoil. (Type 1 construction, MRC Std Dwg A3-00835). Including supply & installation of enveloper conduit at road crossing locations.
71 | 9741.1 | 50mm ODPE | m | 7315 | 133 | 73.226 | 82.58 | 10983.14 |  |  | 50 | 37.59% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 133 | 100% | 0 | 4129 | 10983.14 | 10983.14 | 10983.14 | 10983.14 | 10983.14 | 10983.14 | 10983.14 | 10983.14 | 10983.14 | 10983.14
72 | 9741.2 | 63mm ODPE | m | 13983 | 237 | 78.5477 | 88.58 | 20993.46 |  |  | 100 | 42.19% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 237 | 100% | 0 | 8858 | 20993.46 | 20993.46 | 20993.46 | 20993.46 | 20993.46 | 20993.46 | 20993.46 | 20993.46 | 20993.46 | 20993.46
73 | 9742.1 | Supply and installation of Aquatec Boundary Connection pits | Each | 19800 | 22 | 1198.2246 | 1351.28 | 29728.16 |  |  |  |  | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 0 | 0 | 29728.16 | 29728.16 | 29728.16 | 29728.16 | 29728.16 | 29728.16 | 29728.16 | 29728.16 | 29728.16 | 29728.16
74 | 9742.2 | Supply and installation of Aquatec flushing point | Each | 1780 | 1 | 2369.828 | 2672.54 | 2672.54 |  |  |  |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 2672.54 | 2672.54 | 2672.54 | 2672.54 | 2672.54 | 2672.54 | 2672.54 | 2672.54 | 2672.54 | 2672.54
75 | 9742.3 | Supply and installation of Aquatec isolation valves | Each | 3700 | 2 | 2463.023 | 2777.64 | 5555.28 |  |  |  |  | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 2 | 100% | 0 | 0 | 5555.28 | 5555.28 | 5555.28 | 5555.28 | 5555.28 | 5555.28 | 5555.28 | 5555.28 | 5555.28 | 5555.28
76 | 9745.2 | Dewatering of trench extra to 9610 - 9615 (Provisional, if ordered) | m | 5550
77 | 9745.3 | Supply and placing of metal ballast bedding below bottom of pipe, supply and placing of geotextile, including additional excavation below pipe barrel to maximum 400mm below pipe barrel (Provisional, if ordered) | m³ | 500
78 | 9750.1 | Demolish existing sewer manhole and connect to existing 225 diameter sewer main, incl. liaison with Council and plugging of downstream manhole | Lump | 1500 | 1 | 1997.045 | 2252.14 | 2252.14 |  |  | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14 | 2252.14
79 | 9751.1 | Construct vent pole and foundation as per WRC Std Dwg S0020 - incl. all materials and connection to receiving manhole | Lump | 2500 | 1 | 3328.405 | 3753.56 | 3753.56 |  |  | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 3002.848 | 3002.848 | 3002.848 | 3002.848 | 3002.848 | 3002.848 | 3753.56 | 3753.56 | 3753.56 | 3753.56 | 3753.56
| Item | ANCILLARY WORKS
| 9100 | Ancillary Works
80 | 9100.1 | Ergon longitudinal trenching and backfilling, including supply of all bedding and backfill sand, as directed (Provisional, if ordered) | m | 22474.87 | 445 | 67.2407 | 75.83 | 33744.35 | [10 empty] | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 0 | 0 | 0 | 0 | 0 | 33744.35 | 33744.35 | 33744.35 | 33744.35 | 33744.35 | 33744.35 | 33744.35
| 9110 | Supply and installation of Ergon conduits including draw cord, end caps, polymeric cable protection cover (where required) and caution orange tape as directed (Provisional, if ordered)
81 | 9110.1 | 3/100mm & 1/40mm Electrical plus 2/100mm Testra | m | 2664.518 | 79 | 44.9042 | 50.64 | 4000.56 | [10 empty] | 79 | 100% | 79 | 100% | 79 | 100% | 79 | 100% | 79 | 100% | 79 | 100% | 79 | 100% | 0 | 0 | 0 | 0 | 0 | 4000.56 | 4000.56 | 4000.56 | 4000.56 | 4000.56 | 4000.56 | 4000.56
82 | 9110.2 | 2/100mm plus 1/100mm Testra | m | 466.304 | 16 | 38.8029 | 43.76 | 700.16 | [10 empty] | 16 | 100% | 16 | 100% | 16 | 100% | 16 | 100% | 16 | 100% | 16 | 100% | 16 | 100% | 0 | 0 | 0 | 0 | 0 | 700.16 | 700.16 | 700.16 | 700.16 | 700.16 | 700.16 | 700.16
83 | 9110.3 | 1/100mm Electrical plus 1/100mm Telstra | m | 5078.8 | 300 | 22.5403 | 25.42 | 7626 | [10 empty] | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 300 | 100% | 0 | 0 | 0 | 0 | 0 | 7626 | 7626 | 7626 | 7626 | 7626 | 7626 | 7626
84 | 9110.4 | 1x40 Telstra | m | 371.805 | 35 | 14.1433 | 15.95 | 558.25 | [10 empty] | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 35 | 100% | 0 | 0 | 0 | 0 | 0 | 558.25 | 558.25 | 558.25 | 558.25 | 558.25 | 558.25 | 558.25
85 |  | Installation of Electrical Pits (Direction Changes) Type 5 | No. | 10450 | 11 | 1264.7919 | 1426.35 | 15689.85 | [10 empty] | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 11 | 100% | 0 | 0 | 0 | 0 | 0 | 15689.85 | 15689.85 | 15689.85 | 15689.85 | 15689.85 | 15689.85 | 15689.85
86 |  | Supply & Install Internal Electrical cabling including cabling to a common point external to the sub-division to a central metering location, 'green boys' and lot connections. (ELECTRICAL METERS PROVIDED BY FUTURE LOT OWNERS) | Item | 42965 | 1 | 57201.993 | 64508.73 | 64508.73 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 64508.73 | 64508.73 | 64508.73 | 64508.73 | 64508.73 | 64508.73
87 |  | Supply & Install 'The Cove' sub-board including connection to Ergon POS outside development as per DWG E25 | Item | 21740 | 1 | 21740 | 21740 | 21740 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 21740 | 21740 | 21740 | 21740 | 21740 | 21740
88 |  | Supply & Install MARINA MSB as per DWG E25 | Item | 18085 | 1 | 18085 | 18085 | 18085 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 18085 | 18085 | 18085 | 18085 | 18085 | 18085
89 |  | Supply & Install MARINA Sub-Main from 'The Cove' MSB to MARINA DB | Item | 7650 | 1 | 7650 | 7650 | 7650 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 7650 | 7650 | 7650 | 7650 | 7650
Electrical trenching & Installation
| 9120 | Ergon/Telstra road crossings in place including trenching, backfilling and supply and installation of Ergon PVC Conduits including draw cord, end caps, polymeric cable protection cover (where required), caution orange tape and installation of Telstra PVC conduits with draw cords and end caps (Provisional, if ordered)
90 | 9120.2 | 2/100mm & 1/40 Electricity plus 1/100mm | m | 562.63 | 15 | 49.94 | 56.32 | 844.8 | [10 empty] | 15 | 100% | 15 | 100% | 15 | 100% | 15 | 100% | 15 | 100% | 15 | 100% | 15 | 100% | 0 | 0 | 0 | 0 | 0 | 844.8 | 844.8 | 844.8 | 844.8 | 844.8 | 844.8 | 844.8
91 | 9125.1 | Telecommunications pits | m | 13500 | 12 | 1497.7807 | 1689.1 | 20269.2 | [10 empty] | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 0 | 0 | 0 | 0 | 0 | 20269.2 | 20269.2 | 20269.2 | 20269.2 | 20269.2 | 20269.2 | 20269.2
92 | 9130.1 | Supply, installation and backfill of conduit bends at pillar location, including all 80mm dia, 1200mm rad bends, end caps, 40mm dia service conduits including bends to property boundary, end caps, timber stake, polymeric cable protection cover and caution orange tape (Dwg 5164 Sh 3, 4, 5 & 6) | No | 4500 | 12 | 499.2581 | 563.03 | 6756.36 | [10 empty] | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 12 | 100% | 0 | 0 | 0 | 0 | 0 | 6756.36 | 6756.36 | 6756.36 | 6756.36 | 6756.36 | 6756.36 | 6756.36
92.5 |  | Supply & Install Gas Main 63mm OD PE including Tees, joiners and construction of individual Prtoperty Feeds. (GAS METERS NOT INCLUDED - BY FUTURE OWNERS) | m | 32350 | 445 | 96.7865 | 109.15 | 48571.75 | [10 empty] | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 445 | 100% | 0 | 0 | 0 | 0 | 0 | 48571.75 | 48571.75 | 48571.75 | 48571.75 | 48571.75 | 48571.75 | 48571.75
|  | Connection to Origin Gas Main (PSUM) | PS |  | 1
93 | 9150.2 | Footings to streetlight poles including anchor cage, to DMR std drawing nos 1380, 1381, 1382, 1429. Footing 600mm diameter 2300mm deep. | No | 30766.2654 | 10 | 4096.2089 | 4619.44 | 46194.4 | [10 empty] | 5 | 50% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 10 | 100% | 0 | 0 | 0 | 0 | 0 | 23097.2 | 46194.4 | 46194.4 | 46194.4 | 46194.4 | 46194.4 | 46194.4
94 | 9180.2 | Excavate for padmount substation to allow Electrical Services Provider to install electrical cables and equipment, and reinstate surfaces after installation | No | 8250 | 22 | 499.258 | 563.03 | 12386.66 | [12 empty] | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 22 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 12386.66 | 12386.66 | 12386.66 | 12386.66 | 12386.66 | 12386.66
LANDSCAPING & HARDSCAPING
SOFTSCAPING
95 |  | PLANTS WHITSUNDAY - SOFTSCAPING COMPLETE AS PER QUOTE MLS13-222 (Rev 2) | LS | 189402.18 | 1 | 189402.18 | 189402.18 | 189402.18 |  |  |  |  | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.8 | 80% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 7576.0872 | 7576.0872 | 7576.0872 | 7576.0872 | 7576.0872 | 151521.744 | 179932.071 | 189402.18 | 189402.18 | 189402.18
96 |  | Works Not Included in PWS Quote MLS13-222 (RPZ, Road Crossings, Conduits & GPO for Irrigation Controller) | LS | 7105 | 1 | 9459.334 | 10667.63 | 10667.63 | [10 empty] | 0.25 | 25% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 2666.9075 | 10667.63 | 10667.63 | 10667.63 | 10667.63 | 10667.63 | 10667.63
|  | The Cove - Landscaping Repairs | LS |  | 1 |  | 15000 | 15000 | [10 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
HARDSCAPING WORKS
97 |  | PLANTS WHITSUNDAY COMPLETE - Paver edging in lieu of Concrete Edge Strip as per Quotation MLS13-240 (2) | LS | 10227.27 | 1 | 10227.27 | 10227.27 | 10227.27 |  |  |  |  | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.6 | 60% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 409.0908 | 409.0908 | 409.0908 | 409.0908 | 409.0908 | 6136.362 | 8181.816 | 10227.27 | 10227.27 | 10227.27
98 |  | PLANTS WHITSUNDAY - GRAVEL TO OUTDOOR AREAS ( COMPLETE) | LS | 22088.41 | 1 | 22088.41 | 22088.41 | 22088.41 |  |  |  |  | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.6 | 60% | 0.75 | 75% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 883.5364 | 883.5364 | 883.5364 | 883.5364 | 883.5364 | 13253.046 | 16566.3075 | 22088.41 | 22088.41 | 22088.41
Outdoor Area type A (Complete) (DELETED FROM SCOPE)
Outdoor Area Type B (Complete) (DELETED FROM SCOPE)
99 |  | Outdoor Viewing Areas (Complete) | each | 24000 | 3 | 10650.9 | 12011.4 | 36034.2 | [14 empty] | 1.5 | 50% | 3 | 100% | 3 | 100% | 3 | 100% | 3 | 100% | [7 empty] | 18017.1 | 36034.2 | 36034.2 | 36034.2 | 36034.2
100 |  | PLANTS WHITSUNDAY TO COMPLETE IN FULL - Allotment Separation Fences (Removable Centre Post) REDUCED IN HEIGHT TO 1400MM | LS | 80346.6 | 1 | 80346.6 | 80346.6 | 80346.6 |  |  |  |  | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.8 | 80% | 0.85 | 85% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 3213.864 | 3213.864 | 3213.864 | 3213.864 | 3213.864 | 64277.28 | 68294.61 | 80346.6 | 80346.6 | 80346.6
101 |  | PLANTS WHITSUNDAY COMPLETE - Supply & Install Totems as Detailed (6 No.) | LS | 9436.36 | 1 | 9436.36 | 9436.36 | 9436.36 | [16 empty] | 0.5 | 50% | 1 | 100% | 1 | 100% | 1 | 100% | [8 empty] | 4718.18 | 9436.36 | 9436.36 | 9436.36
102 |  | Supply and Install Timber Viewing Deck as Detailed | item | 23000 | 1 | 30621.341 | 34532.78 | 34532.78 | [8 empty] | 0.25 | 25% | 0.75 | 75% | 0.75 | 75% | 0.8 | 80% | 0.8 | 80% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 8633.195 | 25899.585 | 25899.585 | 27626.224 | 27626.224 | 34532.78 | 34532.78 | 34532.78
103 |  | PLANTS WHITSUNDAY COMPLETE - Supply & Install Timber Seat (To match existing) | item | 2545.45 | 2 | 1272.7285 | 1272.73 | 2545.46 | [20 empty] | 2 | 100% | 2 | 100% | [10 empty] | 2545.46 | 2545.46
|  | Supply & Install all Capping, Facing and Stone Treatments to Entry Statements (Detailes TBC) | PS |  | 1
104 |  | Supply & Instal Stainless Steel 'The Cove' & Port of Airlie logo's as shown on entry walls | item | 6000 | 1 | 7988.175 | 9008.55 | 9008.55 | [16 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9008.55 | 9008.55 | 9008.55 | 9008.55
105 |  | Core Filled Block Wall - W1 (1500mm High) | m2 | 17890 | 45 | 529.2907 | 596.9 | 26860.5 | [12 empty] | 5 | 11.11% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 45 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 2984.5 | 26860.5 | 26860.5 | 26860.5 | 26860.5 | 26860.5
106 |  | Core Filled Block Wall - W2 (Entry Wall with Rake) | m2 | 7028.0845 | 18 | 519.8211 | 586.22 | 10551.96 | [12 empty] | 3 | 16.67% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 18 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1758.66 | 10551.96 | 10551.96 | 10551.96 | 10551.96 | 10551.96
107 |  | PLANTS WHITSUNDAY SUPERVISION / VEHICLES & ADMIN FEE | LS | 4142.85 | 1 | 4142.85 | 4142.85 | 4142.85 | [8 empty] | 0.04 | 4% | 0.04 | 4% | 0.04 | 4% | 0.6 | 60% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 165.714 | 165.714 | 165.714 | 2485.71 | 4142.85 | 4142.85 | 4142.85 | 4142.85
FENCING / GATES / EQUIPMENT
108 |  | Supply and Install Pedestrian and Vehicular Gate and associated Security Key Pad | Item | 21670 | 1 | 28850.626 | 32535.88 | 32535.88 | [18 empty] | 0.8 | 80% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26028.704 | 32535.88 | 32535.88
109 |  | PLANTS WHITSUNDAY COMPLETE - Supply & install boundary fence to Lot 23. | LS | 2704.55 | 1 | 2704.55 | 2704.55 | 2704.55 | [18 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2704.55 | 2704.55 | 2704.55
110 |  | Supply and Install communal letterbox structure within W2 wall - aluminium fronted with range hood and rear opening | Item | 6515 | 1 | 6515 | 6515 | 6515 | [16 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6515 | 6515 | 6515 | 6515
Variations
111 | WDC01 | Variation - Additional watermain, 50mm water meter & RPZ - installed at the Cove subdivision as directed by the Superintendent | Item | 11420 | 1 | 11241.5625 | 12847.5 | 12847.5 | [10 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 12847.5 | 12847.5 | 12847.5 | 12847.5 | 12847.5 | 12847.5 | 12847.5
112 | PV01 | Variation - Installation of geotextile Mirafi in Stormwater trench where depths exceed 1.2m into marine sedimentation as directed by the Superintendent | m² | 3284.9896 | 480 | 6.7375 | 7.7 | 3696 | [8 empty] | 480 | 100% | 480 | 100% | 480 | 100% | 480 | 100% | 480 | 100% | 480 | 100% | 480 | 100% | 480 | 100% | 0 | 0 | 0 | 0 | 3696 | 3696 | 3696 | 3696 | 3696 | 3696 | 3696 | 3696
| PWHIT01 | Landscaping - Replace tall hedging plants along path with dense low ground covers - Provide strip of plants and irrigation along base of retaining wall - Hand placed rocks in lieu of brick edging along top of revetment wall - Powder coated steel fence posts and midrail replaced with hardwood timber - Variation as per Gavin Baxter email dated 1st July 2014 | Item |  | 1 | 0
113 | PV02 | Variation - Unsuitable Subgrade replacement - Remove existing material 300 deep & replace with CBR 15 as directed by Superintendent | m² | 30170.0486 | 1492 | 40.53 | 46.32 | 69109.44 | [10 empty] | 1492 | 100% | 1492 | 100% | 1492 | 100% | 1492 | 100% | 1492 | 100% | 1492 | 100% | 1492 | 100% | 0 | 0 | 0 | 0 | 0 | 69109.44 | 69109.44 | 69109.44 | 69109.44 | 69109.44 | 69109.44 | 69109.44
114 | PV03 | Variation - Easement at Revetment wall - Relocate & replace existing revetment wall rocks, install geotextile & backfill with general fill to areas as indicated on drawing 13003 21 & 22A | Item | 9499 | 1 | 8312.5 | 9500 | 9500 | [12 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 9500 | 9500 | 9500 | 9500 | 9500
115 | PV04 | Variation - Privacy Screen to boundary of Lot 1 & Lot 23 - Provide 11 natural stone columns and 11 steel panels to 1400mm high fence. Stonework nib wall to easement at Lot 23. Salmon coloured footpath to boundary at Entrance & along Lot 23. | Item | 93885.95 | 1 | 109323.7425 | 124941.42 | 124941.42 | [18 empty] | 0.08 | 8% | 0.2 | 20% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9995.3136 | 24988.284 | 124941.42
116 | GAS01 | Line Item 171 - Supply & Install Gas - Variation to adjust claimed contract value of $48,571.75 to agreed value of $15,000 | Item | -33571.75 | 1 | -33571.75 | -33571.75 | -33571.75 | [10 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | -33571.75 | -33571.75 | -33571.75 | -33571.75 | -33571.75 | -33571.75 | -33571.75
117 | PSUM | PROVISIONAL SUM ITEM - Supply & Install capping, facing & stone treatments to Entry Statements | Item | 25000.5 | 1 | 21875 | 25000 | 25000 | [14 empty] | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 25000 | 25000 | 25000
118 | PV05 | Variation - Telstra Pit, supply & install Type 8 pit as directed by Superintendent | Item | 950 | 1 | 1477.9625 | 1689.1 | 1689.1 | [22 empty] | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1689.1
|  | Total, all contract items and variations |  | 1951463.7421 |  |  |  | 2615953.27 | [24 empty] | 19797.865 | 329204.6555 | 685581.4936 | 990767.4951 | 1044705.7391 | 1621896.7479 | 1959105.1854 | 2319911.706 | 2407219.0485 | 2486662.0076 | 2514311.034 | 2615953.27

## Portfolio WBS
Portfolio WBS | Description | Quantity | UOM | BAC | BAC Rate | Final Qty (AQ) | Final Cost (AC) | Final Rate | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 100 | hrs | 15945 | 312.6471 | 51 | 8207.5 | 160.9314 | 10 | 1594.5 | 4.5 | 697.5 | 1406.9118 | 45 | 7175.25 | 0 | 4707.5 | 0 | 60 | 9567 | 29.5 | 4707.5 | 9223.0882 | 80 | 12756 | 45 | 7152.5 | 14069.1176 | 95 | 15147.75 | 48.5 | 7752.5 | 15163.3824 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945 | 100 | 15945 | 51 | 8207.5 | 15945
12 | Survey - As Constructed | 46 | item | 7390 | 53.9416 | 137 | 21901 | 159.8613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1606.5217 | 0 | 0 | 0 | 20 | 3213.0435 | 4.5 | 725 | 242.7372 | 20 | 3213.0435 | 14 | 2207.5 | 755.1825 | 30 | 4819.5652 | 51 | 8180 | 2751.0219 | 46 | 7390 | 73 | 11657.5 | 3937.7372 | 46 | 7390 | 103 | 16551 | 5555.9854 | 46 | 7390 | 103 | 16551 | 5555.9854 | 46 | 7390 | 125 | 19943.5 | 6742.7007 | 46 | 7390 | 137 | 21901 | 7390 | 46 | 7390 | 137 | 21901 | 7390 | 46 | 7390 | 137 | 21901 | 7390
13 | QA Testing | 1 | item | 28731 | 28731 | 1 | 9470.38 | 9470.38 | 0 | 0 | 0 | 0 | 0 | 0.1 | 2873.1 | 0.1 | 2239.93 | 2873.1 | 0.2 | 5746.2 | 0.1 | 2239.93 | 2873.1 | 0.3 | 8619.3 | 0.1 | 2365.36 | 2873.1 | 0.6 | 17238.6 | 0.35 | 3685.15 | 10055.85 | 0.75 | 21548.25 | 0.5 | 5306.89 | 14365.5 | 0.9 | 25857.9 | 0.65 | 6595.4 | 18675.15 | 1 | 28731 | 0.85 | 8332.36 | 24421.35 | 1 | 28731 | 0.95 | 9344.95 | 27294.45 | 1 | 28731 | 0.95 | 9470.38 | 27294.45 | 1 | 28731 | 0.95 | 9470.38 | 27294.45 | 1 | 28731 | 1 | 9470.38 | 28731 | 1 | 28731 | 1 | 9470.38 | 28731 | 1 | 28731 | 1 | 9470.38 | 28731
15 | Service Locations | 1 | item | 1998 | 0 | 0 | 0 | 0 | 1 | 1998 | 0 | 0 | 0 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 0 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 1 | 0 | 1998 | 1 | 1998 | 0 | 0 | 1998 | 1 | 1998 | 0 | 0 | 1998 | 1 | 1998 | 0 | 0 | 1998
41 | Demolition works | 0 | item | 0 | 0 | 1 | 1682.9 | 1682.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1682.9 | 0 | 0 | 0 | 1 | 1682.9 | 0 | 0 | 0 | 1 | 1682.9 | 0 | 0 | 0 | 1 | 1682.9 | 0 | 0 | 0 | 1 | 1682.9 | 0 | 0 | 0 | 1 | 1682.9 | 0 | 0 | 0 | 1 | 1682.9 | 0
52 | Stockpile to Fill | 677 | cum | 10200.1333 | 15.0667 | 677 | 14016.515 | 20.7039 | 0 | 0 | 0 | 0 | 0 | 200 | 3013.3333 | 0 | 0 | 0 | 677 | 10200.1333 | 150 | 3376.775 | 2260 | 677 | 10200.1333 | 480 | 9955.04 | 7232 | 677 | 10200.1333 | 677 | 13641.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333 | 677 | 10200.1333 | 677 | 14016.515 | 10200.1333
53 | Cut to Spoil | 0 | cum | 1320.4158 | 26.4083 | 50 | 11469.48 | 229.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 4498.07 | 1056.3326 | 0 | 1320.4158 | 40 | 10658.615 | 1056.3326 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158 | 0 | 1320.4158 | 50 | 11469.48 | 1320.4158
54 | Cut to Stockpile | 1000 | cum | 10548.3871 | 4.2194 | 2500 | 36701.55 | 14.6806 | 0 | 0 | 0 | 0 | 0 | 350 | 3691.9355 | 0 | 0 | 0 | 1000 | 10548.3871 | 0 | 355.99 | 0 | 1000 | 10548.3871 | 50 | 1040.93 | 210.9677 | 1000 | 10548.3871 | 1200 | 15035.49 | 5063.2258 | 1000 | 10548.3871 | 1400 | 20480.44 | 5907.0968 | 1000 | 10548.3871 | 2400 | 35521.275 | 10126.4516 | 1000 | 10548.3871 | 2400 | 35806.275 | 10126.4516 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871 | 1000 | 10548.3871 | 2500 | 36701.55 | 10548.3871
57 | Cut to Fill | 0 | cum | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 220 | 0
59 | Trim unpaved areas - footpaths, batters, drains etc | 9000 | sqm | 9925.7143 | 1.1029 | 9000 | 10847.275 | 1.2053 | 0 | 0 | 0 | 0 | 0 | 2000 | 2205.7143 | 0 | 0 | 0 | 4000 | 4411.4286 | 2300 | 2803.89 | 2536.5714 | 6000 | 6617.1429 | 4500 | 5617.475 | 4962.8571 | 6000 | 6617.1429 | 4500 | 5725.525 | 4962.8571 | 60000 | 66171.4286 | 6900 | 8833.575 | 7609.7143 | 9000 | 9925.7143 | 8900 | 10563.595 | 9815.4286 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143 | 9000 | 9925.7143 | 9000 | 10847.275 | 9925.7143
61 | Subgrade Preparation | 380 | sqm | 3690.2222 | 3.8641 | 955 | 12355.115 | 12.9373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236.21 | 0 | 380 | 3690.2222 | 0 | 236.21 | 0 | 380 | 3690.2222 | 450 | 8828.555 | 1738.8482 | 380 | 3690.2222 | 750 | 9390.995 | 2898.0803 | 380 | 3690.2222 | 850 | 10544.735 | 3284.491 | 380 | 3690.2222 | 850 | 10873.895 | 3284.491 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222 | 380 | 3690.2222 | 955 | 12355.115 | 3690.2222
62 | Place & Compact Gravel | 842.4 | tonne | 9049.1915 | 5.1621 | 1753 | 23084.9625 | 13.1688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 842.4 | 9049.1915 | 0 | 550 | 0 | 842.4 | 9049.1915 | 0 | 1126.075 | 0 | 842.4 | 9049.1915 | 1753 | 22163.3925 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915 | 842.4 | 9049.1915 | 1753 | 23084.9625 | 9049.1915
63 | Trim All Layers | 2339 | sqm | 8139.9895 | 2.4712 | 3294 | 21526.71 | 6.5351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 2339 | 8139.9895 | 0 | 120 | 0 | 2339 | 8139.9895 | 0 | 1685.67 | 0 | 2339 | 8139.9895 | 2100 | 14302.925 | 5189.4287 | 2339 | 8139.9895 | 3000 | 19887.195 | 7413.4695 | 2339 | 8139.9895 | 3200 | 21032.97 | 7907.7008 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895 | 2339 | 8139.9895 | 3294 | 21526.71 | 8139.9895
64 | Sweep & Prime / Primer seal or Seal | 955 | sqm | 17548.125 | 18.375 | 955 | 6539.39 | 6.8475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 955 | 17548.125 | 0 | 0 | 0 | 955 | 17548.125 | 0 | 0 | 0 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125 | 955 | 17548.125 | 955 | 6539.39 | 17548.125
65 | Asphalt | 88 | tonne | 39160 | 454.2923 | 86.2 | 34904.46 | 404.9241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88 | 39160 | 0 | 0 | 0 | 88 | 39160 | 0 | 0 | 0 | 88 | 39160 | 86.2 | 34298.94 | 39160 | 88 | 39160 | 86.2 | 34465.66 | 39160 | 88 | 39160 | 86.2 | 34465.66 | 39160 | 88 | 39160 | 86.2 | 34904.46 | 39160 | 88 | 39160 | 86.2 | 34904.46 | 39160 | 88 | 39160 | 86.2 | 34904.46 | 39160 | 88 | 39160 | 86.2 | 34904.46 | 39160 | 88 | 39160 | 86.2 | 34904.46 | 39160
71 | Place Kerb & Channel / Inverts | 443 | m | 16834 | 38 | 443 | 14639.324 | 33.0459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 443 | 16834 | 0 | 78.11 | 0 | 443 | 16834 | 0 | 78.11 | 0 | 443 | 16834 | 443 | 14132.814 | 16834 | 443 | 16834 | 443 | 14255.699 | 16834 | 443 | 16834 | 443 | 14450.204 | 16834 | 443 | 16834 | 443 | 14450.204 | 16834 | 443 | 16834 | 443 | 14639.324 | 16834 | 443 | 16834 | 443 | 14639.324 | 16834 | 443 | 16834 | 443 | 14639.324 | 16834 | 443 | 16834 | 443 | 14639.324 | 16834 | 443 | 16834 | 443 | 14639.324 | 16834
72 | Form & Pour Headwalls | 1 | cum | 1900 | 1900 | 1 | 532.5 | 532.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900 | 1 | 1900 | 1 | 532.5 | 1900
73 | Form & Place Footpath | 466.1 | sqm | 24991.502 | 44.9407 | 556.1 | 38225.2775 | 68.7381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 10723.6653 | 0 | 0 | 0 | 466.1 | 24991.502 | 135 | 9330.355 | 6066.9893 | 466.1 | 24991.502 | 380 | 26282.4175 | 17077.4515 | 466.1 | 24991.502 | 540 | 37199.7975 | 24267.9573 | 466.1 | 24991.502 | 540 | 37199.7975 | 24267.9573 | 466.1 | 24991.502 | 540 | 37199.7975 | 24267.9573 | 466.1 | 24991.502 | 556.1 | 38225.2775 | 24991.502 | 466.1 | 24991.502 | 556.1 | 38225.2775 | 24991.502 | 466.1 | 24991.502 | 556.1 | 38225.2775 | 24991.502
81 | > 450 | 405.2 | m | 18720.24 | 46.2 | 405.2 | 16600.83 | 40.9695 | 200 | 9240 | 0 | 0 | 0 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24 | 405.2 | 18720.24 | 405.2 | 16600.83 | 18720.24
82 | 525 > 750 | 102.4 | m | 4730.88 | 46.2 | 102.4 | 10332.59 | 100.9042 | 0 | 0 | 0 | 0 | 0 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 102.4 | 4730.88 | 95 | 9895.95 | 4389 | 102.4 | 4730.88 | 102.4 | 10005.11 | 4730.88 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88 | 102.4 | 4730.88 | 102.4 | 10332.59 | 4730.88
85 | Install SW Pits & Chambers | 1 | each | 35388 | 35388 | 1 | 6064.855 | 6064.855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 35388 | 0 | 0 | 0 | 1 | 35388 | 0 | 0 | 0 | 1 | 35388 | 0 | 97.3 | 0 | 1 | 35388 | 0 | 914.245 | 35388 | 1 | 35388 | 0.8 | 4894 | 35388 | 1 | 35388 | 1 | 6064.855 | 35388 | 1 | 35388 | 0 | 6064.855 | 0 | 1 | 35388 | 0 | 6064.855 | 0 | 1 | 35388 | 0 | 6064.855 | 0 | 1 | 35388 | 1 | 6064.855 | 35388 | 1 | 35388 | 1 | 6064.855 | 35388 | 1 | 35388 | 1 | 6064.855 | 35388
86 | SW Sub-contractors | 11 | each | 6500 | 590.9091 | 11 | 22752.36 | 2068.3964 | 2 | 1181.8182 | 0 | 0 | 0 | 6 | 3545.4545 | 2 | 5635.2 | 1181.8182 | 11 | 6500 | 3 | 8090.2 | 1772.7273 | 11 | 6500 | 3 | 8090.2 | 1772.7273 | 11 | 6500 | 3 | 8090.2 | 1772.7273 | 11 | 6500 | 10.5 | 22643.2 | 6204.5455 | 11 | 6500 | 10.5 | 22643.2 | 6204.5455 | 11 | 6500 | 10.5 | 22643.2 | 6204.5455 | 11 | 6500 | 11 | 22752.36 | 6500 | 11 | 6500 | 11 | 22752.36 | 6500 | 11 | 6500 | 11 | 22752.36 | 6500 | 11 | 6500 | 11 | 22752.36 | 6500 | 11 | 6500 | 11 | 22752.36 | 6500 | 11 | 6500 | 11 | 22752.36 | 6500
87 | Supply & Place Subsoil Drainage | 1017 | m | 40568.4377 | 39.8903 | 1017 | 17562.98 | 17.2694 | 0 | 0 | 0 | 0 | 0 | 300 | 11967.0908 | 0 | 658 | 0 | 1017 | 40568.4377 | 265 | 4562.595 | 10570.9302 | 1017 | 40568.4377 | 350 | 6164.32 | 13961.6059 | 1017 | 40568.4377 | 350 | 6440.79 | 13961.6059 | 1017 | 40568.4377 | 900 | 16574.48 | 35901.2723 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377 | 1017 | 40568.4377 | 1017 | 17562.98 | 40568.4377
95 | Sewer Sub-contractors | 16 | item | 69867.9 | 4366.7437 | 16 | 85835.88 | 5364.7425 | 8 | 34933.95 | 0 | 0 | 0 | 16 | 69867.9 | 9.5 | 52026.8 | 20533.698 | 16 | 69867.9 | 15 | 79383 | 44843.0693 | 16 | 69867.9 | 15 | 79383 | 49363.2783 | 16 | 69867.9 | 15 | 79987.58 | 49600.9155 | 16 | 69867.9 | 15 | 79987.58 | 50080.4291 | 16 | 69867.9 | 15 | 82587.58 | 62689.847 | 16 | 69867.9 | 15 | 82587.58 | 62689.847 | 16 | 69867.9 | 16 | 85835.88 | 69867.9 | 16 | 69867.9 | 16 | 85835.88 | 69867.9 | 16 | 69867.9 | 16 | 85835.88 | 69867.9 | 16 | 69867.9 | 16 | 85835.88 | 69867.9 | 16 | 69867.9 | 16 | 85835.88 | 69867.9 | 16 | 69867.9 | 16 | 85835.88 | 69867.9
103 | Water Sub-contractor | 27 | item | 107885.13 | 3995.7456 | 27 | 93624.379 | 3467.5696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213.6 | 31706.702 | 12 | 47948.9467 | 10 | 34703.604 | 69243.5347 | 27 | 107885.13 | 13 | 46203.604 | 76223.3257 | 27 | 107885.13 | 13 | 46203.604 | 76590.2685 | 27 | 107885.13 | 13 | 47423.549 | 77330.6999 | 27 | 107885.13 | 22 | 76903.549 | 96801.282 | 27 | 107885.13 | 22 | 76903.549 | 96801.282 | 27 | 107885.13 | 27 | 93624.379 | 107885.13 | 27 | 107885.13 | 27 | 93624.379 | 107885.13 | 27 | 107885.13 | 27 | 93624.379 | 107885.13 | 27 | 107885.13 | 27 | 93624.379 | 107885.13 | 27 | 107885.13 | 27 | 93624.379 | 107885.13 | 27 | 107885.13 | 27 | 93624.379 | 107885.13
111 | Install Conduits / pits / rag bolts | 456 | m | 34461.2355 | 75.5729 | 456 | 57698.3105 | 126.5314 | 0 | 0 | 0 | 0 | 0 | 200 | 15114.577 | 135 | 17380 | 10202.3394 | 200 | 15114.577 | 135 | 17380 | 10202.3394 | 456 | 34461.2355 | 135 | 17380 | 10202.3394 | 456 | 34461.2355 | 135 | 17380 | 10202.3394 | 456 | 34461.2355 | 365 | 46098.8175 | 27584.103 | 456 | 34461.2355 | 425 | 54113.9705 | 32118.476 | 456 | 34461.2355 | 430 | 54579.5805 | 32496.3405 | 456 | 34461.2355 | 435 | 55155.6105 | 32874.2049 | 456 | 34461.2355 | 435 | 55155.6105 | 32874.2049 | 456 | 34461.2355 | 435 | 55155.6105 | 32874.2049 | 456 | 34461.2355 | 456 | 56606.7105 | 34461.2355 | 456 | 34461.2355 | 456 | 56606.7105 | 34461.2355 | 456 | 34461.2355 | 456 | 57698.3105 | 34461.2355
113 | Electrical Sub-contract works | 6 | item | 101320 | 16886.6667 | 6 | 91724.16 | 15287.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 86632.52 | 14353.6667 | 6 | 101320 | 0.85 | 86632.52 | 14353.6667 | 6 | 101320 | 1 | 91396.68 | 16886.6667 | 6 | 101320 | 1 | 91396.68 | 16886.6667 | 6 | 101320 | 1 | 91396.68 | 16886.6667 | 6 | 101320 | 6 | 91396.68 | 101320 | 6 | 101320 | 6 | 91396.68 | 101320 | 6 | 101320 | 6 | 91724.16 | 101320
121 | Landscaping Sub-contractors | 1 | item | 405473.27 | 405473.27 | 1 | 343303.69 | 343303.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 40547.327 | 0.028751 | 9657.1439 | 11657.5875 | 0.2 | 81094.654 | 0.028751 | 9657.1439 | 11657.5875 | 0.2 | 81094.654 | 0.028751 | 9657.1439 | 11657.5875 | 0.25 | 101368.3175 | 0.064312 | 21602.0339 | 26076.8198 | 0.75 | 304104.9525 | 0.21642 | 72693.1618 | 87751.2966 | 1 | 405473.27 | 0.76569 | 257190.633 | 310466.7752 | 1 | 405473.27 | 0.90125 | 302723.3795 | 365431.4712 | 1 | 405473.27 | 0.971 | 326154.5772 | 393716.3598 | 1 | 405473.27 | 1 | 326154.5772 | 405473.27 | 1 | 405473.27 | 1 | 343303.69 | 405473.27 | 1 | 405473.27 | 1 | 343303.69 | 405473.27 | 1 | 405473.27 | 1 | 343303.69 | 405473.27
123 | Supply & Installation of Street Furniture | 1 | item | 119853.0845 | 119853.0845 | 1 | 109537.7 | 109537.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.017132 | 2895.45 | 2053.2658 | 0 | 0 | 0.30678 | 51850 | 36768.6653 | 0.35 | 41948.5796 | 0.3302 | 55808.35 | 39575.671 | 1 | 119853.0845 | 0.36422 | 61558.35 | 43653.199 | 1 | 119853.0845 | 0.47269 | 79890.29 | 56653.0248 | 1 | 119853.0845 | 0.50852 | 85945.7 | 60947.1298 | 1 | 119853.0845 | 0.54915 | 92812.7 | 65816.7619 | 1 | 119853.0845 | 1 | 92812.7 | 119853.0845 | 1 | 119853.0845 | 1 | 109537.7 | 119853.0845 | 1 | 119853.0845 | 1 | 109537.7 | 119853.0845
131 | Fencing Sub-contractors | 1 | item | 21670 | 21670 | 1 | 18080.5 | 18080.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194.6 | 0 | 0 | 0 | 0 | 303.76 | 0 | 0 | 0 | 0 | 303.76 | 0 | 1 | 21670 | 0 | 731.66 | 0 | 1 | 21670 | 0.1 | 1355.5 | 2167 | 1 | 21670 | 0.1 | 1355.5 | 2167 | 1 | 21670 | 1 | 18080.5 | 21670 | 1 | 21670 | 1 | 18080.5 | 21670 | 1 | 21670 | 1 | 18080.5 | 21670 | 1 | 21670 | 1 | 18080.5 | 21670
132 | Retaining Walls sub-contractors | 677 | sqm | 349020.0103 | 432.4907 | 807 | 322580.1561 | 399.7276 | 0 | 0 | 0 | 0 | 0 | 150 | 77330.8738 | 100 | 42453.6871 | 43249.0719 | 325 | 167550.2265 | 325 | 122163.2821 | 140559.4837 | 500 | 257769.5792 | 620 | 243242.2971 | 268144.2458 | 677 | 349020.0103 | 675 | 265477.6521 | 291931.2354 | 677 | 349020.0103 | 675 | 266128.9271 | 291931.2354 | 677 | 349020.0103 | 675 | 266128.9271 | 291931.2354 | 677 | 349020.0103 | 738 | 292216.0861 | 319178.1507 | 677 | 349020.0103 | 743 | 294585.2661 | 321340.6043 | 677 | 349020.0103 | 745 | 294803.5861 | 322205.5857 | 677 | 349020.0103 | 745 | 295560.0661 | 322205.5857 | 677 | 349020.0103 | 807 | 322580.1561 | 349020.0103 | 677 | 349020.0103 | 807 | 322580.1561 | 349020.0103 | 677 | 349020.0103 | 807 | 322580.1561 | 349020.0103
135 | Form & Pour Retaining Wall Footings | 577 | m | 54137.2054 | 93.8253 | 577 | 62335.54 | 108.0339 | 50 | 4691.2656 | 20 | 2434.035 | 1876.5063 | 300 | 28147.5938 | 250 | 27212.315 | 23456.3282 | 500 | 46912.6563 | 380 | 41215.715 | 35653.6188 | 577 | 54137.2054 | 445 | 49041.35 | 41752.2641 | 577 | 54137.2054 | 480 | 52921.38 | 45036.1501 | 577 | 54137.2054 | 480 | 53326.22 | 45036.1501 | 577 | 54137.2054 | 535 | 59107.16 | 50196.5423 | 577 | 54137.2054 | 535 | 59461.06 | 50196.5423 | 577 | 54137.2054 | 535 | 59461.06 | 50196.5423 | 577 | 54137.2054 | 577 | 62335.54 | 54137.2054 | 577 | 54137.2054 | 577 | 62335.54 | 54137.2054 | 577 | 54137.2054 | 577 | 62335.54 | 54137.2054 | 577 | 54137.2054 | 577 | 62335.54 | 54137.2054 | 577 | 54137.2054 | 577 | 62335.54 | 54137.2054
151 | Supply & Place Silt fences & protective devices | 0 | m | 0 | 0 | 100 | 3567.895 | 35.679 | 0 | 0 | 0 | 106.12 | 0 | 0 | 0 | 50 | 1714.585 | 0 | 0 | 0 | 0.6 | 1973.925 | 0 | 0 | 0 | 0.6 | 1973.925 | 0 | 0 | 0 | 0.75 | 2721.905 | 0 | 0 | 0 | 0.75 | 2721.905 | 0 | 0 | 0 | 0.75 | 2721.905 | 0 | 0 | 0 | 0.75 | 2721.905 | 0 | 0 | 0 | 0.75 | 2721.905 | 0 | 0 | 0 | 1 | 3567.895 | 0 | 0 | 0 | 1 | 3567.895 | 0 | 0 | 0 | 100 | 3567.895 | 0 | 0 | 0 | 100 | 3567.895 | 0 | 0 | 0 | 100 | 3567.895 | 0
152 | Supply & Install safety devices | 0 | item | 0 | 0 | 1 | 875 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0 | 0 | 0 | 1 | 875 | 0
222 | Supply & Place Geo-fabric | 2600 | sqm | 5804.9529 | 0 | 0 | 76.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2232.6742 | 0 | 76.9 | 0 | 2600 | 5804.9529 | 0 | 76.9 | 0 | 2600 | 5804.9529 | 0 | 76.9 | 0 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529 | 2600 | 5804.9529 | 0 | 76.9 | 5804.9529
901 | Project Management | 14 | week | 61200 | 9540.7661 | 6.4146 | 28040.875 | 4371.4286 | 2 | 8742.8571 | 0.25 | 1245.875 | 2385.1915 | 4 | 17485.7143 | 0.75 | 3775.875 | 7155.5745 | 6 | 26228.5714 | 1.3 | 6811.875 | 12402.9959 | 8 | 34971.4286 | 1.5 | 7892.875 | 14311.1491 | 10 | 43714.2857 | 1.8 | 9732.875 | 17173.3789 | 12 | 52457.1429 | 2.7 | 14171.875 | 25760.0684 | 13 | 56828.5714 | 3.1 | 16563.875 | 29576.3748 | 14 | 61200 | 4.4 | 23325.875 | 41979.3707 | 14 | 61200 | 5 | 26338.875 | 47703.8303 | 14 | 61200 | 5.1 | 26568.875 | 48657.9069 | 14 | 61200 | 5.2 | 27212.875 | 49611.9835 | 14 | 61200 | 6.4146 | 27971.875 | 61200 | 14 | 61200 | 6.3988 | 27971.875 | 61200 | 14 | 61200 | 6.3988 | 28040.875 | 61200
902 | Project Supervision | 16 | week | 66320 | 2459.0343 | 26.9699 | 111790.39 | 4145 | 2 | 8290 | 0.2 | 789.8 | 491.8069 | 4 | 16580 | 2.2 | 9080.68 | 5409.8754 | 6 | 24870 | 3.7 | 15596.23 | 9098.4268 | 8 | 33160 | 5 | 20920.63 | 12295.1713 | 10 | 41450 | 7.1 | 29528.41 | 17459.1433 | 12 | 49740 | 11.5 | 47853.22 | 28278.8941 | 14 | 58030 | 15.8 | 65823.07 | 38852.7415 | 16 | 66320 | 20 | 83304.85 | 49180.6854 | 16 | 66320 | 23 | 95684.08 | 56557.7882 | 16 | 66320 | 25.5 | 105844.81 | 62705.3739 | 16 | 66320 | 26 | 107841.46 | 63934.891 | 16 | 66320 | 26.9699 | 109483.15 | 66320 | 16 | 66320 | 26.4133 | 109483.15 | 66320 | 16 | 66320 | 26.4133 | 111790.39 | 66320
903 | Project Facilities | 16 | week | 12800 | 835.7526 | 15.3155 | 12252.43 | 800 | 2 | 1600 | 3.4 | 3027.55 | 2841.5588 | 4 | 3200 | 3.4 | 3050.08 | 2841.5588 | 6 | 4800 | 4.8 | 4334.58 | 4011.6124 | 8 | 6400 | 5.2 | 4658.46 | 4345.9134 | 10 | 8000 | 6.6 | 5894.21 | 5515.967 | 12 | 9600 | 7.1 | 6364.21 | 5933.8433 | 14 | 11200 | 9.2 | 8193.22 | 7688.9237 | 16 | 12800 | 11.4 | 10188.99 | 9527.5794 | 16 | 12800 | 12.9 | 11540.66 | 10781.2083 | 16 | 12800 | 13.4 | 11979.7 | 11199.0846 | 16 | 12800 | 13.4 | 11979.7 | 11199.0846 | 16 | 12800 | 15.3155 | 11979.7 | 12800 | 16 | 12800 | 14.9746 | 12252.43 | 12800 | 16 | 12800 | 14.9746 | 12252.43 | 12800
904 | Project Insurance, Fees & Levies | 1 | item | 23700 | 23700 | 1 | 9907.84 | 9907.84 | 0.75 | 17775 | 0.8 | 8405.25 | 18960 | 0.8 | 18960 | 0.85 | 8649.57 | 20145 | 0.85 | 20145 | 0.85 | 8699.97 | 20145 | 0.9 | 21330 | 0.85 | 8699.97 | 20145 | 0.95 | 22515 | 0.9 | 8836 | 21330 | 1 | 23700 | 0.95 | 9497.2 | 22515 | 1 | 23700 | 0.95 | 9712.97 | 22515 | 1 | 23700 | 0.95 | 9749.63 | 22515 | 1 | 23700 | 1 | 9907.84 | 23700 | 1 | 23700 | 1 | 9907.84 | 23700 | 1 | 23700 | 1 | 9907.84 | 23700 | 1 | 23700 | 1 | 9907.84 | 23700 | 1 | 23700 | 1 | 9907.84 | 23700 | 1 | 23700 | 1 | 9907.84 | 23700
905 | Small Tools | 1 | item | 5000 | 5000 | 1 | 3960.37 | 3960.37 | 0 | 0 | 0 | 0 | 0 | 0.2 | 1000 | 0.6 | 3039.66 | 3000 | 0.4 | 2000 | 0.66 | 3277.71 | 3300 | 0.6 | 3000 | 0.65554 | 3277.71 | 3277.71 | 0.8 | 4000 | 0.65 | 3285.73 | 3250 | 1 | 5000 | 0.7 | 3397.46 | 3500 | 1 | 5000 | 0.7 | 3408.78 | 3500 | 1 | 5000 | 0.7 | 3408.78 | 3500 | 1 | 5000 | 0.8 | 3960.37 | 4000 | 1 | 5000 | 0.8 | 3960.37 | 4000 | 1 | 5000 | 1 | 3960.37 | 5000 | 1 | 5000 | 1 | 3960.37 | 5000 | 1 | 5000 | 1 | 3960.37 | 5000 | 1 | 5000 | 1 | 3960.37 | 5000
906 | Miscellaneous Items - Project Contingency | 1 | item | 0 | 0 | 1 | 24005.0022 | 24005.0022 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 1800 | 0 | 0.5 | 0 | 0 | 1800 | 0 | 0.6 | 0 | 0 | 1800 | 0 | 0.75 | 0 | 0 | 1800 | 0 | 0.9 | 0 | 0 | 3779.535 | 0 | 1 | 0 | 0 | 8850.655 | 0 | 1 | 0 | 0 | 9703.155 | 0 | 1 | 0 | 0 | 13061.915 | 0 | 1 | 0 | 0 | 17165.1686 | 0 | 1 | 0 | 1 | 19871.0114 | 0 | 1 | 0 | 1 | 22192.6162 | 0 | 1 | 0 | 1 | 24005.0022 | 0
910 | De-Establishment & Cleanup | 0 | item | 0 | 0 | 1 | 8179.135 | 8179.135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252.175 | 0 | 0 | 0 | 0 | 252.175 | 0 | 0 | 0 | 0 | 3501.09 | 0 | 0 | 0 | 0 | 5430.585 | 0 | 0 | 0 | 0 | 5430.585 | 0 | 0 | 0 | 0 | 6330.005 | 0 | 0 | 0 | 0 | 6330.005 | 0 | 0 | 0 | 1 | 7301.655 | 0 | 0 | 0 | 1 | 8179.135 | 0 | 0 | 0 | 1 | 8179.135 | 0
913 | Wet Weather (Labour) | 0 | hrs | 0 | 0 | 97 | 5482.79 | 56.5236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1529.975 | 0 | 0 | 0 | 64 | 3103.6 | 0 | 0 | 0 | 64 | 3103.6 | 0 | 0 | 0 | 64 | 3103.6 | 0 | 0 | 0 | 72 | 3463.6 | 0 | 0 | 0 | 72 | 3463.6 | 0 | 0 | 0 | 72 | 3463.6 | 0 | 0 | 0 | 72 | 3463.6 | 0 | 0 | 0 | 97 | 5482.79 | 0 | 0 | 0 | 97 | 5482.79 | 0 | 0 | 0 | 97 | 5482.79 | 0 | 0 | 0 | 97 | 5482.79 | 0 | 0 | 0 | 97 | 5482.79 | 0
914 | Training | 0 | hrs | 0 | 0 | 4.5 | 207.5 | 46.1111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0 | 0 | 0 | 4.5 | 207.5 | 0
916 | Site Administration | 600 | hrs | 28800 | 34.023 | 846.4873 | 40631.39 | 48 | 50 | 2400 | 9 | 448.56 | 306.2066 | 150 | 7200 | 95.3 | 4575.71 | 3242.3877 | 250 | 12000 | 162 | 7779.71 | 5511.7189 | 350 | 16800 | 206.1 | 9894.35 | 7012.1313 | 450 | 21600 | 289.7 | 13910.03 | 9856.4504 | 500 | 24000 | 453.5 | 21770.51 | 15429.4106 | 550 | 26400 | 611 | 29331.95 | 20788.0262 | 600 | 28800 | 728.5 | 34970.99 | 24785.7236 | 600 | 28800 | 758.3 | 36402.11 | 25799.6076 | 600 | 28800 | 838.9 | 40268.27 | 28541.8579 | 600 | 28800 | 846.4 | 40631.39 | 28797.0301 | 600 | 28800 | 846.4873 | 40631.39 | 28800 | 600 | 28800 | 846.4873 | 40631.39 | 28800 | 600 | 28800 | 846.4873 | 40631.39 | 28800
C20 | 20 MPa Concrete | 235 | cum | 46527.5946 | 278.0366 | 167.3434 | 33134 | 198 | 0 | 0 | 0 | 0 | 0 | 52 | 10295.4677 | 85 | 16770.6 | 23633.1085 | 113 | 22372.8434 | 97 | 19219.8 | 26969.5473 | 170 | 33658.2599 | 160 | 31487 | 44485.8513 | 235 | 46527.5946 | 163 | 32342 | 45319.961 | 235 | 46527.5946 | 163 | 32342 | 45319.961 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946 | 235 | 46527.5946 | 167.3434 | 33134 | 46527.5946
C25 | 25 Mpa | 24.871 | cum | 6884.6088 | 40.5711 | 169.6925 | 33596 | 197.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2768.127 | 12 | 19068.2 | 486.8529 | 24.871 | 6884.6088 | 12 | 22522.4 | 486.8529 | 24.871 | 6884.6088 | 12 | 23822 | 486.8529 | 24.871 | 6884.6088 | 13.4 | 24125.2 | 543.6524 | 24.871 | 6884.6088 | 37.5 | 28928 | 1521.4152 | 24.871 | 6884.6088 | 55.5 | 32468.8 | 2251.6945 | 24.871 | 6884.6088 | 61.26 | 33596 | 2485.3839 | 24.871 | 6884.6088 | 61.26 | 33596 | 2485.3839 | 24.871 | 6884.6088 | 61.26 | 33596 | 2485.3839 | 24.871 | 6884.6088 | 169.6925 | 33596 | 6884.6088 | 24.871 | 6884.6088 | 169.6925 | 33596 | 6884.6088 | 24.871 | 6884.6088 | 169.6925 | 33596 | 6884.6088
C32 | 32 Mpa | 11 | cum | 1980 | 313.5962 | 6.3139 | 1359.2 | 215.2727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 351.4 | 501.754 | 11 | 1980 | 1.6 | 351.4 | 501.754 | 11 | 1980 | 6.31 | 1359.2 | 1978.7922 | 11 | 1980 | 6.31 | 1359.2 | 1978.7922 | 11 | 1980 | 6.31 | 1359.2 | 1978.7922 | 11 | 1980 | 6.31 | 1359.2 | 1978.7922 | 11 | 1980 | 6.31 | 1359.2 | 1978.7922 | 11 | 1980 | 6.3139 | 1359.2 | 1980 | 11 | 1980 | 6.3139 | 1359.2 | 1980 | 11 | 1980 | 6.3139 | 1359.2 | 1980
CKM | Kerb Mix | 31.544 | cum | 6371.0547 | 242.3227 | 26.2916 | 5311 | 202.0036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.544 | 6371.0547 | 0 | 0 | 0 | 31.544 | 6371.0547 | 0 | 0 | 0 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547 | 31.544 | 6371.0547 | 26.2916 | 5311 | 6371.0547
E32 | Exposed Aggregate Concrete | 44.88 | cum | 14001.4959 | 313.4087 | 44.6749 | 13939 | 312.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.88 | 14001.4959 | 0 | 0 | 0 | 44.88 | 14001.4959 | 0 | 0 | 0 | 44.88 | 14001.4959 | 29.9 | 9323 | 9370.9204 | 44.88 | 14001.4959 | 44.67 | 13939 | 13999.967 | 44.88 | 14001.4959 | 44.67 | 13939 | 13999.967 | 44.88 | 14001.4959 | 44.67 | 13939 | 13999.967 | 44.88 | 14001.4959 | 44.6749 | 13939 | 14001.4959 | 44.88 | 14001.4959 | 44.6749 | 13939 | 14001.4959 | 44.88 | 14001.4959 | 44.6749 | 13939 | 14001.4959
ETC | Conduits | 1170 | m | 6278.5876 | 5.3663 | 1170 | 8596.694 | 7.3476 | 0 | 0 | 0 | 0 | 0 | 1000 | 5366.3142 | 900 | 6187.74 | 4829.6828 | 1000 | 5366.3142 | 900 | 6187.74 | 4829.6828 | 1170 | 6278.5876 | 900 | 6187.74 | 4829.6828 | 1170 | 6278.5876 | 900 | 6187.74 | 4829.6828 | 1170 | 6278.5876 | 900 | 6989.59 | 4829.6828 | 1170 | 6278.5876 | 1170 | 8507.09 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8507.09 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8552.194 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8552.194 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8552.194 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8552.194 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8596.694 | 6278.5876 | 1170 | 6278.5876 | 1170 | 8596.694 | 6278.5876
ETM | Miscellaneous (rope, glue, plugs etc) | 6 | item | 15822.945 | 2637.1575 | 6 | 12952.31 | 2158.7183 | 0 | 0 | 0 | 0 | 0 | 6 | 15822.945 | 0 | 174.68 | 0 | 6 | 15822.945 | 3 | 7480.68 | 7911.4725 | 6 | 15822.945 | 3 | 7480.68 | 7911.4725 | 6 | 15822.945 | 3 | 7480.68 | 7911.4725 | 6 | 15822.945 | 3 | 7570 | 7911.4725 | 6 | 15822.945 | 6 | 12798.36 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945 | 6 | 15822.945 | 6 | 12952.31 | 15822.945
ETP | Pits & Lids | 23 | each | 29400 | 1278.2609 | 23 | 1580 | 68.6957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1580 | 0 | 0 | 0 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400 | 23 | 29400 | 23 | 1580 | 29400
QM2.1 | 2.1 | 300 | tonne | 10500 | 35.522 | 295.5914 | 10345.698 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 10500 | 0 | 0 | 0 | 300 | 10500 | 0 | 0 | 0 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500 | 300 | 10500 | 295.5914 | 10345.698 | 10500
QM2.3 | 2.3 | 542.4 | tonne | 18984 | 42.4061 | 447.6711 | 15668.488 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.4 | 18984 | 0 | 0 | 0 | 542.4 | 18984 | 0 | 0 | 0 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984 | 542.4 | 18984 | 447.6711 | 15668.488 | 18984
QM2.5 | 2.5 | 0 | tonne | 28444.98 | 31.2136 | 911.3 | 14580.8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98 | 911.3 | 28444.98 | 911.3 | 14580.8 | 28444.98
QMR | Supply & Deliver Rock - Retaining Walls | 800 | tonne | 42835.8689 | 40.5821 | 1055.5372 | 46148.0854 | 43.72 | 0 | 0 | 0 | 0 | 0 | 177 | 9477.436 | 48 | 2131.18 | 1947.9387 | 390 | 20882.4861 | 695 | 30507.62 | 28204.529 | 600 | 32126.9017 | 995 | 43587.5848 | 40379.1458 | 800 | 42835.8689 | 1010 | 44268.4948 | 40987.8767 | 800 | 42835.8689 | 1010 | 44268.4948 | 40987.8767 | 800 | 42835.8689 | 1010 | 44268.4948 | 40987.8767 | 800 | 42835.8689 | 1055.5372 | 46189.1848 | 42835.8689 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689 | 800 | 42835.8689 | 1055.5372 | 46148.0854 | 42835.8689
QMS | Sand | 687.161 | tonne | 6947.8917 | 10.8741 | 638.9373 | 22283.1785 | 34.8754 | 0 | 0 | 0 | 0 | 0 | 200 | 2022.202 | 125 | 4314.14 | 1359.2672 | 400 | 4044.404 | 180 | 6263.59 | 1957.3448 | 500 | 5055.505 | 200 | 7079.65 | 2174.8276 | 600 | 6066.606 | 200 | 7079.65 | 2174.8276 | 687.161 | 6947.8917 | 560 | 19592.9867 | 6089.5172 | 687.161 | 6947.8917 | 585 | 20475.3448 | 6361.3706 | 687.161 | 6947.8917 | 610 | 21398.7134 | 6633.224 | 687.161 | 6947.8917 | 610 | 21398.7134 | 6633.224 | 687.161 | 6947.8917 | 610 | 21398.7134 | 6633.224 | 687.161 | 6947.8917 | 610 | 21990.5944 | 6633.224 | 687.161 | 6947.8917 | 638.9373 | 22283.1785 | 6947.8917 | 687.161 | 6947.8917 | 638.9373 | 22283.1785 | 6947.8917 | 687.161 | 6947.8917 | 638.9373 | 22283.1785 | 6947.8917
RSB | Straight / Bent Bar | 6.8926 | tonne | 21441 | 8576.4 | 2.5 | 7224.56 | 2889.824 | 2 | 6221.4509 | 2 | 5787.79 | 17152.8 | 2 | 6221.4509 | 2 | 5787.79 | 17152.8 | 2 | 6221.4509 | 2 | 5787.79 | 17152.8 | 2 | 6221.4509 | 2 | 5787.79 | 17152.8 | 2.5 | 7776.8136 | 2 | 5787.79 | 17152.8 | 6.893 | 21441 | 2 | 5787.79 | 17152.8 | 6.893 | 21441 | 2.3 | 6664.02 | 19725.72 | 6.893 | 21441 | 2.5 | 7107.38 | 21441 | 6.893 | 21441 | 2.5 | 7224.56 | 21441 | 6.893 | 21441 | 2.5 | 7224.56 | 21441 | 6.893 | 21441 | 2.5 | 7224.56 | 21441 | 6.893 | 21441 | 2.5 | 7224.56 | 21441 | 6.893 | 21441 | 2.5 | 7224.56 | 21441 | 6.893 | 21441 | 2.5 | 7224.56 | 21441
SWL | Grates, Frames & Lids | 10 | each | 2500 | 250 | 10 | 5034 | 503.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5034 | 2500 | 0 | 0 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500 | 10 | 2500 | 10 | 5034 | 2500
SWP | RCP | 507.6 | m | 42802.166 | 84.3226 | 507.6 | 11450.18 | 22.5575 | 0 | 0 | 0 | 0 | 0 | 400 | 33729.0512 | 400 | 8953.67 | 33729.0512 | 400 | 33729.0512 | 400 | 8953.67 | 33729.0512 | 507.6 | 42802.166 | 400 | 8953.67 | 33729.0512 | 507.6 | 42802.166 | 400 | 8953.67 | 33729.0512 | 507.6 | 42802.166 | 400 | 8953.67 | 33729.0512 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166 | 507.6 | 42802.166 | 507.6 | 11450.18 | 42802.166
SWPC | Pre-cast Pits | 2 | each | 26170 | 13085 | 2 | 29445 | 14722.5 | 0 | 0 | 0.54 | 7975 | 7065.9 | 2 | 26170 | 2 | 30945 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170 | 2 | 26170 | 2 | 29445 | 26170
Note on H26: Brett Thiele: water & sewer contractor is the same. Bill has been mis-entered as all work on one invoice. Unclear what is for what. Final bill under budget, so difficult to determine exact EAC from here. Must combine both and treat as such.
Note on H53: Brett Thiele: The costs for pits & lids have been included here also by mistake but invoice poorly recorded & impossible to correctly attribute the items to ETM / ETP. Treat as a combined CC for EAC purposes.
Note on L63: Brett Thiele: 25% deposit required for GPT's, AQ adjusted to reflect this for EV purposes as expenses made, although not claimable.
Note on M63: Brett Thiele: Deposit for GPT's, actual quote = $29445.

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | Total | Portfolio WBS | 2015-06-01
Cost Code 011
2014-04-08 | The Cove Engineering Setout | Survey |  | 1 | 697.5 | 697.5 | 11
2014-05-22 | The Cove Engineering Setout | Survey |  | 1 | 1325 | 1325 | 11
2014-05-24 | The Cove Engineering Setout | Survey |  | 1 | 2685 | 2685 | 11
2014-07-28 | The Cove Engineering Setout | Survey |  | 1 | 2445 | 2445 | 11
2014-08-18 | The Cove Engineering Setout | Survey |  | 1 | 600 | 600 | 11
2014-09-22 | The Cove Engineering Setout | Survey |  | 1 | 455 | 455 | 11
| Subtotal for 011 |  |  |  |  | 8207.5
Cost Code 012
2014-08-18 | The Cove Engineering Setout | Survey |  | 1 | 600 | 600 | 12
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 1 | 125 | 125 | 12
2014-09-22 | The Cove Engineering Setout | Survey |  | 1 | 1482.5 | 1482.5 | 12
2014-10-23 | The Cove Engineering Setout | Survey |  | 1 | 5972.5 | 5972.5 | 12
2014-11-28 | The Cove Engineering Setout | Survey |  | 1 | 3477.5 | 3477.5 | 12
2014-12-18 | The Cove Engineering Setout | Survey |  | 1 | 4893.5 | 4893.5 | 12
2015-02-27 | The Cove Engineering Setout | Survey |  | 1 | 3392.5 | 3392.5 | 12
2015-03-27 | The Cove Engineering Setout | Survey |  | 1 | 1957.5 | 1957.5 | 12
| Subtotal for 012 |  |  |  |  | 21901
Cost Code 013
2014-05-30 | Field Density | Field Density |  | 1 | 125.45 | 125.45 | 13
2014-05-30 | Field Density | Field Density |  | 1 | 2114.48 | 2114.48 | 13
2014-07-25 | Field Density | Field Density |  | 1 | 125.43 | 125.43 | 13
2014-08-28 | Field Density | Field Density |  | 1 | 125.43 | 125.43 | 13
2014-08-29 | Field Density | Field Density |  | 1 | 1194.36 | 1194.36 | 13
2014-09-26 | Field Density | Field Density |  | 1 | 1621.74 | 1621.74 | 13
2014-10-31 | Field Density | Field Density |  | 1 | 1288.51 | 1288.51 | 13
2014-11-20 | Allciv - Labour Hire Office Work QA | Labour | hr | 3.5 | 42.72 | 149.52 | 13
2014-11-28 | Field Density | Field Density |  | 1 | 1587.44 | 1587.44 | 13
2014-12-19 | Field Density | Field Density |  | 1 | 1012.59 | 1012.59 | 13
2015-01-30 | Field Density | Field Density |  | 1 | 125.43 | 125.43 | 13
| Subtotal for 013 |  |  |  |  | 9470.38
Cost Code 041
2014-11-26 | Backhoe - Wet Hire | Back Hoe | hr | 8.5 | 110 | 935 | 41
2014-11-26 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 41
2014-11-26 | Tipper (Wet Hire) | Tipper | hr | 5 | 95 | 475 | 41
| Subtotal for 041 |  |  |  |  | 1682.9
Cost Code 052
2014-06-04 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 52
2014-06-06 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 52
2014-06-23 | Hire of Labour | Labour | hr | 2.5 | 38.45 | 96.125 | 52
2014-06-23 | Allciv - Labour HIre | Labour | hr | 1 | 42.72 | 42.72 | 52
2014-06-23 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 52
2014-06-24 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 52
2014-06-30 | For Plant Hire used at The Cover Estate at POA | Sewer Subbie |  | 1 | 2715.83 | 2715.83 | 52
2014-07-07 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 52
2014-07-09 | Hire of Labour | Labour | hr | 8 | 38.45 | 307.6 | 52
2014-07-09 | Whitsunday Drainage Contractors | WDC | hr | 10 |  |  | 52
2014-07-10 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 52
2014-07-10 | Allciv - Labour HIre | Labour | hr | 1 | 42.72 | 42.72 | 52
2014-07-10 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 1 | 25.78 | 25.78 | 52
2014-07-14 | Whitsunday Drainage Contractors | WDC | hr | 5.5 |  |  | 52
2014-07-24 | Allciv - Labour Hire | Labour | hr | 7 | 35.11 | 245.77 | 52
2014-07-24 | Whitsunday Drainage Contractors | WDC | hr | 72.5 |  |  | 52
2014-07-24 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 52
2014-07-24 | Hire of Labour | Labour | hr | 7 | 38.45 | 269.15 | 52
2014-07-25 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 52
2014-07-25 | Whitsunday Drainage Contractors | WDC | hr | 7 |  |  | 52
2014-07-25 | Hire of Labour | Labour | hr | 6 | 38.45 | 230.7 | 52
2014-07-29 | Hire of Labour | Labour | hr | 6.5 | 38.45 | 249.925 | 52
2014-07-29 | Whitsunday Drainage Contractors | WDC | Item | 7.5 |  |  | 52
2014-07-29 | Tipper (Wet Hire) | Tipper | hr | 7.5 | 95 | 712.5 | 52
2014-07-29 | Allciv - Labour HIre | Labour | hr | 5.5 | 42.72 | 234.96 | 52
2014-07-30 | Whitsunday Drainage Contractors | WDC | Item | 9 |  |  | 52
2014-07-30 | Claim for machine hire used at The cove | Sewer Subbie |  | 28 | 125 | 3500 | 52
2014-08-05 | Whitsunday Drainage Contractors- excavator | WDC | Item | 5 |  |  | 52
2014-08-05 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 52
2014-08-05 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 52
2014-08-11 | Loader | Loader | hr | 2 | 145 | 290 | 52
2014-08-11 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 2 | 25.78 | 51.56 | 52
2014-08-11 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 52
2014-08-12 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 52
2014-08-12 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 52
2014-08-12 | Allciv - Labour HIre | Labour | hr | 2.5 | 35.11 | 87.775 | 52
2014-08-12 | Loader | Loader | hr | 2.5 | 145 | 362.5 | 52
2014-08-12 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 52
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 16.5 | 125 | 2062.5 | 52
2014-09-05 | Whitsunday Drainage Contractors | WDC | Item | 2 |  |  | 52
2014-09-30 | Claim for 24T Excavator at the Cove Sub-Division | Sewer Subbie |  | 3 | 125 | 375 | 52
| Subtotal for 052 |  |  |  |  | 14016.515
Cost Code 053
2014-08-20 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 53
2014-08-20 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 53
2014-08-20 | Allciv - Labour HIre | Labour | hr | 8.5 | 42.72 | 363.12 | 53
2014-08-20 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 53
2014-08-20 | Mack - Tip Truck | Mack Tipper | hr | 8.5 | 42.79 | 363.715 | 53
2014-08-20 | UD Water Cart - No Driver | UD Water Cart | hr | 7 | 21.61 | 151.27 | 53
2014-08-21 | Mack - Tip Truck | Mack Tipper | hr | 9.5 | 42.79 | 406.505 | 53
2014-08-21 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 53
2014-08-21 | Backhoe - Wet Hire | Back Hoe |  | 7 | 110 | 770 | 53
2014-08-21 | New Holland Compact Grader - No Operator | NH Grader | hr | 1.5 | 25.78 | 38.67 | 53
2014-08-21 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 53
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 8.5 | 125 | 1062.5 | 53
2014-09-01 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 53
2014-09-01 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 53
2014-09-01 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 53
2014-09-01 | UD Water Cart - No Driver | UD Water Cart | hr | 9.5 | 21.61 | 205.295 | 53
2014-09-02 | UD Water Cart - No Driver | UD Water Cart | hr | 9.5 | 21.61 | 205.295 | 53
2014-09-02 | Whitsunday Drainage Contractors | WDC | Item | 6 |  |  | 53
2014-09-02 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 53
2014-09-02 | Allciv - Labour Hire | Labour | hr | 7 | 35.11 | 245.77 | 53
2014-09-02 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 53
2014-09-30 | Claim for 24T, 8T and 14T Excavator at the Cove Sub-Division | Sewer Subbie |  | 1 | 2407.5 | 2407.5 | 53
2014-09-30 | Claim for 24T Excavator at the Cove Sub-Division | Sewer Subbie |  | 17.5 | 125 | 2187.5 | 53
2014-10-02 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 53
2014-10-02 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 53
2014-10-02 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 53
2014-10-02 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 53
| Subtotal for 053 |  |  |  |  | 11469.48
Cost Code 054
2014-06-27 | Hire of Labour | Labour | hr | 5 | 38.45 | 192.25 | 54
2014-06-27 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 54
2014-07-30 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 54
2014-07-30 | Labour Hire | Labour | hr | 9 | 39.98 | 359.82 | 54
2014-07-30 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 54
2014-08-04 | Allciv - Labour HIre | Labour | hr | 9 | 35.11 | 315.99 | 54
2014-08-04 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 54
2014-08-04 | Whitsunday Drainage Contractors | WDC | Item | 6.5 |  |  | 54
2014-08-04 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 54
2014-08-08 | Allciv-Supervisor | Supervisor | hr | 2 | 88.74 | 177.48 | 54
2014-08-08 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 54
2014-08-22 | Backhoe - Wet Hire | Back Hoe |  | 8.5 | 110 | 935 | 54
2014-08-23 | Backhoe - Wet Hire | Back Hoe |  | 6 | 110 | 660 | 54
2014-08-23 | Tipper (Wet Hire) | Tipper | hr | 6 | 95 | 570 | 54
2014-08-25 | Mack - Tip Truck | Mack Tipper | hr | 8.5 | 42.79 | 363.715 | 54
2014-08-25 | New Holland Compact Grader - No Operator | NH Grader | hr | 1.5 | 25.78 | 38.67 | 54
2014-08-25 | Backhoe - Wet Hire | Back Hoe |  | 5 | 110 | 550 | 54
2014-08-25 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 54
2014-08-25 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 54
2014-08-25 | Allciv - Labour HIre | Labour | hr | 8.5 | 42.72 | 363.12 | 54
2014-08-26 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 54
2014-08-26 | Mack - Tip Truck | Mack Tipper | hr | 9.5 | 42.79 | 406.505 | 54
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 15.5 | 125 | 1937.5 | 54
2014-08-26 | Backhoe - Wet Hire | Back Hoe |  | 9.5 | 110 | 1045 | 54
2014-08-26 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 54
2014-08-26 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 54
2014-08-26 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 54
2014-08-26 | Allciv - Labour HIre | Labour | hr | 9.5 | 35.11 | 333.545 | 54
2014-08-27 | Backhoe - Wet Hire | Back Hoe | hr | 9 | 110 | 990 | 54
2014-08-27 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 54
2014-08-28 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 54
2014-08-28 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 54
2014-08-29 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 54
2014-08-29 | Mack - Tip Truck | Mack Tipper | hr | 9 | 42.79 | 385.11 | 54
2014-08-29 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 54
2014-08-29 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 54
2014-08-29 | Backhoe - Wet Hire | Back Hoe |  | 8 | 110 | 880 | 54
2014-08-29 | Tipper (Wet Hire) | Tipper | hr | 9 | 95 | 855 | 54
2014-08-29 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 54
2014-09-01 | Mack - Tip Truck | Mack Tipper | hr | 9.5 | 42.79 | 406.505 | 54
2014-09-01 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 54
2014-09-01 | Labour Hire | Labour | hr | 9 | 39.98 | 359.82 | 54
2014-09-01 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 54
2014-09-01 | Backhoe - Wet Hire | Back Hoe | hr | 9.5 | 110 | 1045 | 54
2014-09-01 | Tipper (Wet Hire) | Tipper | hr | 9.5 | 95 | 902.5 | 54
2014-09-02 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 54
2014-09-02 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 54
2014-09-02 | Mack - Tip Truck | Mack Tipper | hr | 9.5 | 42.79 | 406.505 | 54
2014-09-02 | New Holland Compact Grader - No Operator | NH Grader | hr | 0.5 | 25.78 | 12.89 | 54
2014-09-02 | Backhoe - Wet Hire | Back Hoe | hr | 3.5 | 110 | 385 | 54
2014-09-03 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 54
2014-09-03 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 54
2014-09-04 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 54
2014-09-04 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 54
2014-09-04 | Backhoe - Wet Hire | Back Hoe | hr | 1 | 110 | 110 | 54
2014-09-04 | Mack - Tip Truck | Mack Tipper | hr | 3 | 42.79 | 128.37 | 54
2014-09-05 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 54
2014-09-05 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 54
2014-10-02 | Tipper (Wet Hire) | Tipper | hr | 9.5 | 95 | 902.5 | 54
2014-10-03 | Tipper (Wet Hire) | Tipper | hr | 6 | 95 | 570 | 54
2014-10-09 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 54
2014-10-09 | UD Water Cart - No Driver | UD Water Cart | hr | 1.5 | 21.61 | 32.415 | 54
2014-10-09 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 54
2014-10-09 | Labour Hire | Labour | hr | 5.5 | 39.98 | 219.89 | 54
2014-10-09 | Whitsunday Drainage Contractors | WDC | Item | 9.5 |  |  | 54
2014-10-09 | Tipper (Wet Hire) | Tipper | hr | 9 | 95 | 855 | 54
2014-10-09 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 54
2014-10-09 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 54
2014-10-13 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 54
2014-10-13 | 120H Grader | 120H Grader | hr | 5 | 120 | 600 | 54
2014-10-14 | Whitsunday Drainage Contractors | WDC | Item | 9.5 |  |  | 54
2014-10-14 | Backhoe - Wet Hire | Back Hoe | hr | 9.5 | 110 | 1045 | 54
2014-10-14 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 54
2014-10-14 | Tipper (Wet Hire) | Tipper | hr | 9.5 | 95 | 902.5 | 54
2014-10-14 | UD Water Cart - No Driver | UD Water Cart | hr | 9 | 21.61 | 194.49 | 54
2014-10-14 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 54
2014-10-15 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 54
2014-10-15 | UD Water Cart - No Driver | UD Water Cart | hr | 9.5 | 21.61 | 205.295 | 54
2014-10-15 | 120H Grader | 120H Grader | hr | 4 | 120 | 480 | 54
2014-10-15 | Labour Hire | Labour | hr | 10 | 39.98 | 399.8 | 54
2014-10-15 | Allciv - Leading Hand | Labour | Hr | 10 | 54.58 | 545.8 | 54
2014-10-15 | Tipper (Wet Hire) | Tipper | hr | 11 | 95 | 1045 | 54
2014-10-15 | Whitsunday Drainage Contractors | WDC | Item | 10 |  |  | 54
2014-10-16 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 54
2014-10-23 | CAT297C MTL - No Operator | CAT297 | hr | 0.5 | 46.5 | 23.25 | 54
2014-10-28 | Claim fo the hire of 14T Excavator | Sewer Subbie |  | 43.5 | 115 | 5002.5 | 54
2014-11-13 | Tipper (Wet Hire) | Tipper | hr | 3 | 95 | 285 | 54
2014-12-11 | Backhoe - Wet Hire | Back Hoe | hr | 4.75 | 110 | 522.5 | 54
2014-12-11 | Tipper (Wet Hire) | Tipper | hr | 3 | 95 | 285 | 54
2014-12-11 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 54
| Subtotal for 054 |  |  |  |  | 36701.55
Cost Code 057
2014-10-03 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 57
| Subtotal for 057 |  |  |  |  | 220
Cost Code 059
2014-06-03 | Tipper (Wet Hire) | Tipper | hr | 9.5 | 95 | 902.5 | 59
2014-06-16 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 59
2014-06-17 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 59
2014-06-17 | 120H Grader | 120H Grader | hr | 4 | 120 | 480 | 59
2014-06-17 | Backhoe - Wet Hire | Back Hoe | hr | 5.25 | 110 | 577.5 | 59
2014-06-18 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 59
2014-06-23 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 59
2014-06-23 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 59
2014-06-23 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 59
2014-07-07 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 59
2014-07-28 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 59
2014-07-28 | Water Cart Allciv - No Operator | WC - Allciv | hr | 5.5 | 42.79 | 235.345 | 59
2014-07-28 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 59
2014-07-29 | 120H Grader | 120H Grader | hr | 7.5 | 120 | 900 | 59
2014-07-29 | Water Cart Allciv - No Operator | WC - Allciv | hr | 7.5 | 42.79 | 320.925 | 59
2014-07-30 | 120H Grader | 120H Grader | hr | 5.5 | 120 | 660 | 59
2014-07-30 | Water Cart Allciv - No Operator | WC - Allciv | hr | 5.5 | 42.79 | 235.345 | 59
2014-08-01 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 59
2014-09-03 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 59
2014-09-03 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 59
2014-09-18 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 59
2014-09-18 | 120H Grader | 120H Grader | hr | 6.5 | 120 | 780 | 59
2014-09-18 | Posie Track | CAT297 | hr | 8.5 | 46.5 | 395.25 | 59
2014-09-18 | UD Water Cart - No Driver | UD Water Cart | hr | 6.5 | 21.61 | 140.465 | 59
2014-09-18 | Allciv - Labour HIre | Labour | hr | 7 | 42.72 | 299.04 | 59
2014-09-18 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 59
2014-09-18 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 59
2014-09-26 | Whitsunday Drainage Contractors | WDC | Item | 8 |  |  | 59
2014-09-26 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 59
2014-09-26 | CAT297C MTL - No Operator | CAT297 | hr | 1.5 | 46.5 | 69.75 | 59
2014-09-26 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 59
2014-09-26 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 59
2014-10-01 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 59
2014-10-01 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 59
2014-10-08 | Backhoe - Wet Hire | Back Hoe | hr | 6 | 110 | 660 | 59
2014-10-28 | Claim fo the hire of 14T Excavator | Sewer Subbie |  | 8 | 115 | 920 | 59
2014-11-07 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 59
2014-11-07 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 59
| Subtotal for 059 |  |  |  |  | 10847.275
Cost Code 061
2014-06-30 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 61
2014-06-30 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 61
2014-08-20 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 61
2014-08-21 | UD Water Cart - No Driver | UD Water Cart | hr | 3.5 | 21.61 | 75.635 | 61
2014-08-21 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 61
2014-08-22 | Tipper (Wet Hire) | Tipper | hr | 8.5 | 95 | 807.5 | 61
2014-08-25 | UD Water Cart - No Driver | UD Water Cart | hr | 8.5 | 21.61 | 183.685 | 61
2014-08-25 | Allciv - Labour HIre | Labour | hr | 5 | 35.11 | 175.55 | 61
2014-08-25 | Whitsunday Drainage Contractors | WDC | Item | 8.5 |  |  | 61
2014-08-25 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 61
2014-08-25 | Labour Hire | Labour | hr | 7.5 | 39.98 | 299.85 | 61
2014-08-26 | Whitsunday Drainage Contractors | WDC | Item | 9.5 |  |  | 61
2014-08-26 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 61
2014-08-26 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 61
2014-08-26 | 120H Grader | 120H Grader | hr | 4 | 120 | 480 | 61
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 32.5 | 125 | 4062.5 | 61
2014-08-27 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 61
2014-08-27 | Whitsunday Drainage Contractors | WDC | Item | 9.5 |  |  | 61
2014-08-27 | Allciv - Labour HIre | Labour | hr | 3 | 35.11 | 105.33 | 61
2014-08-27 | Labour Hire | Labour | hr | 4.5 | 39.98 | 179.91 | 61
2014-08-28 | Allciv - Labour HIre | Labour | hr | 3 | 35.11 | 105.33 | 61
2014-08-28 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 61
2014-08-29 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 61
2014-08-29 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 61
2014-08-29 | Whitsunday Drainage Contractors | WDC | Item | 9 |  |  | 61
2014-08-29 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 61
2014-08-29 | Water Cart Allciv - No Operator | WC - Allciv | hr | 9.5 | 42.79 | 406.505 | 61
2014-09-12 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 61
2014-09-15 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 61
2014-09-15 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 61
2014-10-21 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 61
2014-10-21 | Backhoe - Wet Hire | Back Hoe | hr | 9 | 110 | 990 | 61
2014-11-14 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 61
2014-11-26 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 61
2014-12-03 | Backhoe - Wet Hire | Back Hoe | hr | 3 | 110 | 330 | 61
2014-12-03 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 61
2014-12-04 | Backhoe - Wet Hire | Back Hoe | hr | 6 | 110 | 660 | 61
2014-12-04 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 61
| Subtotal for 061 |  |  |  |  | 12355.115
Cost Code 062
2014-06-18 | Backhoe - Wet Hire | Back Hoe | hr | 5 | 110 | 550 | 62
2014-08-19 | Labour Hire | Labour | hr | 3.5 | 39.98 | 139.93 | 62
2014-08-19 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.11 | 122.885 | 62
2014-08-19 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 62
2014-08-19 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 62
2014-09-03 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 62
2014-09-03 | Backhoe - Wet Hire | Back Hoe | hr | 9.5 | 110 | 1045 | 62
2014-09-03 | UD Water Cart - No Driver | UD Water Cart | hr | 9.5 | 21.61 | 205.295 | 62
2014-09-03 | Allciv - Leading Hand | Labour | Hr | 7.5 | 54.58 | 409.35 | 62
2014-09-03 | Allciv - Labour Hire | Labour | hr | 1.5 | 35.11 | 52.665 | 62
2014-09-03 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 62
2014-09-03 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 62
2014-09-04 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 62
2014-09-04 | Backhoe - Wet Hire | Back Hoe | hr | 8.5 | 110 | 935 | 62
2014-09-04 | Whitsunday Drainage Contractors | WDC | Item | 3.5 |  |  | 62
2014-09-04 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 62
2014-09-04 | UD Water Cart - No Driver | UD Water Cart | hr | 9.5 | 21.61 | 205.295 | 62
2014-09-04 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 62
2014-09-04 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 62
2014-09-04 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 62
2014-09-05 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 62
2014-09-05 | UD Water Cart - No Driver | UD Water Cart | hr | 9 | 21.61 | 194.49 | 62
2014-09-05 | Whitsunday Drainage Contractors | WDC | Item | 3.5 |  |  | 62
2014-09-05 | Backhoe - Wet Hire | Back Hoe | hr | 8.5 | 110 | 935 | 62
2014-09-05 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 62
2014-09-05 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 62
2014-09-05 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 62
2014-09-08 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 62
2014-09-08 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 62
2014-09-09 | Backhoe - Wet Hire | Back Hoe | hr | 8 | 110 | 880 | 62
2014-09-12 | Plate Compactor - Dry Hire 11/9/14 and Unleaded fuel | Plate Compactor |  | 1 | 83.85 | 83.85 | 62
2014-09-12 | Pad Foot Roller - Dry Hired 3*9/14 - 9/9/14 and Delivery | PF Roller |  | 1 | 1288 | 1288 | 62
2014-09-15 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 62
2014-09-16 | CAT297C MTL - No Operator | CAT297 | hr | 9.5 | 46.5 | 441.75 | 62
2014-09-16 | UD Water Cart - No Driver | UD Water Cart | hr | 6 | 21.61 | 129.66 | 62
2014-09-16 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 62
2014-09-16 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 62
2014-09-16 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 62
2014-09-16 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 62
2014-09-17 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 62
2014-09-17 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 62
2014-09-17 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 62
2014-09-17 | 120H Grader | 120H Grader | hr | 5 | 120 | 600 | 62
2014-09-17 | Allciv - Leading Hand | Labour | Hr | 8.5 | 54.58 | 463.93 | 62
2014-09-18 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 62
2014-09-18 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 62
2014-09-25 | 120H Grader | 120H Grader | hr | 9 | 120 | 1080 | 62
2014-09-25 | Allciv - Labour HIre | Labour | hr | 9.25 | 42.72 | 395.16 | 62
2014-09-25 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 62
2014-09-25 | UD Water Cart - No Driver | UD Water Cart | hr | 9.25 | 21.61 | 199.8925 | 62
2014-09-26 | 8T Double Drum Roller Hired from 12/9/14 - 17/9/14 | DD Roller |  | 1 | 1276.8 | 1276.8 | 62
2014-09-26 | 3 & 4 Double Drum Roller Hired from 18/9/14 - 18/9/14 | DD Roller |  | 1 | 1693.02 | 1693.02 | 62
2014-09-26 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.11 | 122.885 | 62
2014-09-29 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 62
2014-09-29 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 62
2014-09-29 | 120H Grader | 120H Grader | hr | 3 | 120 | 360 | 62
2014-09-30 | 8 Double Drum Roller Hired from 26/9/14 - 30/9/14 | DD Roller |  | 1 | 852.6 | 852.6 | 62
2014-10-03 | 8T Double Drum Roller Hired from 30/9/14 - 2/10/14 | DD Roller |  | 1 | 568.4 | 568.4 | 62
2014-10-10 | 3 & 4T Double Drum Roller Hired from 9/10/14 - 10/10/14 | DD Roller |  | 1 | 1 | 353.17 | 62
| Subtotal for 062 |  |  |  |  | 23084.9625
Cost Code 063
2014-06-23 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 63
2014-08-01 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 63
2014-08-01 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 63
2014-08-01 | Allciv - Labour HIre | Labour | hr | 5 | 35.11 | 175.55 | 63
2014-08-04 | 120H Grader | 120H Grader | hr | 3.5 | 120 | 420 | 63
2014-08-04 | Allciv - Labour HIre | Labour | hr | 3.5 | 42.72 | 149.52 | 63
2014-08-06 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 63
2014-08-08 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 63
2014-08-27 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 63
2014-09-03 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 63
2014-09-04 | 120H Grader | 120H Grader | hr | 4 | 120 | 480 | 63
2014-09-05 | 120H Grader | 120H Grader | hr | 5 | 120 | 600 | 63
2014-09-08 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 4 | 48 | 192 | 63
2014-09-08 | Labour Hire | Labour | hr | 7 | 39.98 | 279.86 | 63
2014-09-08 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 63
2014-09-08 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 63
2014-09-08 | 120H Grader | 120H Grader | hr | 2 | 120 | 240 | 63
2014-09-08 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 63
2014-09-15 | Labour Hire | Labour | hr | 9 | 39.98 | 359.82 | 63
2014-09-15 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 63
2014-09-15 | UD Water Cart - No Driver | UD Water Cart | hr | 9 | 21.61 | 194.49 | 63
2014-09-17 | Allciv - Labour HIre | Labour | hr | 3.5 | 42.72 | 149.52 | 63
2014-09-17 | UD Water Cart - No Driver | UD Water Cart | hr | 8.5 | 21.61 | 183.685 | 63
2014-09-17 | 120H Grader | 120H Grader | hr | 3.5 | 120 | 420 | 63
2014-09-17 | Posie Track | CAT297 | hr | 8.5 | 46.5 | 395.25 | 63
2014-09-18 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 63
2014-09-18 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 63
2014-09-18 | 120H Grader | 120H Grader | hr | 2 | 120 | 240 | 63
2014-09-19 | 120H Grader | 120H Grader | hr | 8.5 | 120 | 1020 | 63
2014-09-19 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 63
2014-09-19 | Allciv - Leading Hand | Labour | Hr | 4.5 | 54.58 | 245.61 | 63
2014-09-19 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 63
2014-09-19 | Posie Track | CAT297 | hr | 6 | 46.5 | 279 | 63
2014-09-19 | UD Water Cart - No Driver | UD Water Cart | hr | 6 | 21.61 | 129.66 | 63
2014-09-19 | Allciv - Labour HIre | Labour | hr | 7 | 42.72 | 299.04 | 63
2014-09-22 | 120H Grader | 120H Grader | hr | 7 | 120 | 840 | 63
2014-09-22 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 63
2014-09-22 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 63
2014-09-24 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 63
2014-09-26 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 63
2014-09-26 | 120H Grader | 120H Grader | hr | 5 | 120 | 600 | 63
2014-09-26 | CAT297C MTL - No Operator | CAT297 | hr | 6.5 | 46.5 | 302.25 | 63
2014-09-26 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 63
2014-09-26 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 63
2014-09-26 | Allciv - Labour HIre | Labour | hr | 8 | 42.72 | 341.76 | 63
2014-09-29 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 63
2014-09-29 | Allciv - Labour HIre | Labour | hr | 8.5 | 42.72 | 363.12 | 63
2014-09-29 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 63
2014-09-29 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 63
2014-09-29 | CAT297C MTL - No Operator | CAT297 | hr | 8.5 | 46.5 | 395.25 | 63
2014-09-30 | CAT297C MTL - No Operator | CAT297 | hr | 8.5 | 46.5 | 395.25 | 63
2014-09-30 | UD Water Cart - No Driver | UD Water Cart | hr | 8.5 | 21.61 | 183.685 | 63
2014-09-30 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 63
2014-09-30 | Allciv - Labour HIre | Labour | hr | 8.5 | 42.72 | 363.12 | 63
2014-10-01 | Allciv - Leading Hand | Labour | Hr | 7.5 | 54.58 | 409.35 | 63
2014-10-01 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 63
2014-10-01 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 63
2014-10-01 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 63
2014-10-01 | CAT297C MTL - No Operator | CAT297 | hr | 8.5 | 46.5 | 395.25 | 63
2014-10-01 | UD Water Cart - No Driver | UD Water Cart | hr | 6.5 | 21.61 | 140.465 | 63
2014-10-01 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 63
2014-10-02 | UD Water Cart - No Driver | UD Water Cart | hr | 1 | 21.61 | 21.61 | 63
2014-10-02 | Allciv - Labour HIre | Labour | hr | 1 | 42.72 | 42.72 | 63
2014-10-02 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 63
2014-10-09 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 63
2014-10-09 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 63
2014-10-09 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 63
2014-10-13 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 63
2014-10-13 | UD Water Cart - No Driver | UD Water Cart | hr | 8 | 21.61 | 172.88 | 63
2014-10-13 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 63
2014-10-13 | 120H Grader | 120H Grader | hr | 1.5 | 120 | 180 | 63
2014-10-13 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 4 | 48 | 192 | 63
2014-10-13 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 63
2014-10-13 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 4 | 25.78 | 103.12 | 63
2014-10-16 | UD Water Cart - No Driver | UD Water Cart | hr | 8 | 21.61 | 172.88 | 63
2014-10-16 | 120H Grader | 120H Grader | hr | 2 | 120 | 240 | 63
2014-10-16 | CAT311D - 12T Excavator (No Operator) | CAT297 | hr | 6 | 46.5 | 279 | 63
2014-10-16 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 63
2014-10-16 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 63
2014-10-28 | Claim fo the hire of 14T Excavator | Sewer Subbie |  | 1.5 | 115 | 172.5 | 63
2014-10-29 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 63
2014-10-29 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 63
2014-10-29 | Backhoe - Wet Hire | Back Hoe | hr | 3.25 | 110 | 357.5 | 63
2014-10-29 | Allciv - Labour Hire | Labour | hr | 5.5 | 35.11 | 193.105 | 63
2014-11-06 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 63
2014-11-06 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 63
2014-11-10 | 120H Grader | 120H Grader | hr | 2 | 120 | 240 | 63
2014-11-10 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 63
2014-11-10 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 63
2014-11-10 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 63
2014-11-14 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 63
2014-11-14 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 63
2014-11-14 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 63
2014-12-03 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 63
2014-12-03 | Backhoe - Wet Hire | Back Hoe | hr | 3 | 110 | 330 | 63
| Subtotal for 063 |  |  |  |  | 21526.71
Cost Code 064
2014-10-10 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 64
2014-10-10 | Sweep and Prime with AMC00 | Rock N Road | hr | 987 | 6.32 | 6237.84 | 64
2014-10-10 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 64
2014-10-10 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 64
2014-10-10 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 64
2014-10-10 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 64
| Subtotal for 064 |  |  |  |  | 6539.39
Cost Code 065
2014-10-14 | Supply, Cart, Lay & Compact AC 10MM Mix | Rock N Road | hr | 86.2 | 396 | 34135.2 | 65
2014-10-14 | Rock N Road Labour Hours | Rock N Road | hr | 49.2 |  |  | 65
2014-10-28 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 65
2014-11-04 | Backhoe - Wet Hire | Back Hoe | hr | 1 | 110 | 110 | 65
2014-11-04 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 65
2014-11-04 | UD Water Cart - No Driver | UD Water Cart | hr | 1 | 21.61 | 21.61 | 65
2015-01-19 | Vibrating Rammer hired Hired 19/1/15 | Vibrating |  | 1 | 79.31 | 79.31 | 65
2015-01-19 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 65
2015-01-21 | Vibrating Rammer hired Hired 21/1/15 | Vibrating |  | 1 | 86.59 | 86.59 | 65
2015-01-29 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 65
| Subtotal for 065 |  |  |  |  | 34904.46
Cost Code 071
2014-07-24 | Hessian For Curing | Hessian |  | 78.11 | 1 | 78.11 | 71
2014-09-05 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 71
2014-09-15 | 18 Brass Kerb Marker, Tie Wire | Kerb Adaptors |  | 1 | 152.8 | 152.8 | 71
2014-09-23 | Hammer Drill Medium with Drills and Petrol Generator Hierd 23/9/14 | Hammer |  | 1 | 136.01 | 136.01 | 71
2014-09-23 | 120H Grader | 120H Grader | hr | 4 | 120 | 480 | 71
2014-09-23 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 71
2014-09-23 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 71
2014-09-23 | Posie Track | CAT297 | hr | 4 | 46.5 | 186 | 71
2014-09-23 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 71
2014-09-23 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 71
2014-09-23 | Allciv - Leading Hand | Labour | Hr | 7.3 | 54.58 | 398.434 | 71
2014-09-24 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 71
2014-09-24 | CAT297C MTL - No Operator | CAT297 | hr | 5 | 46.5 | 232.5 | 71
2014-09-24 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 71
2014-09-24 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 71
2014-09-24 | 120H Grader | 120H Grader | hr | 5 | 120 | 600 | 71
2014-09-24 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 71
2014-09-26 | 348 L/M of M6 Edge Restraint and 68 L/M if ttoe 5 Kerb Only | Kerb Subbie |  | 1 | 10400 | 10400 | 71
2014-10-15 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.11 | 122.885 | 71
2014-11-05 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 71
2014-11-05 | Allciv - Labour Hire | Labour | hr | 1.5 | 35.11 | 52.665 | 71
2014-11-05 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 71
2015-01-12 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 71
2015-01-12 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 71
| Subtotal for 071 |  |  |  |  | 14639.324
Cost Code 072
2014-07-30 | Claim for Labour used in the sonstruction of 2 headwalls a the port of Airlie | Sewer Subbie |  | 1 | 532.5 | 532.5 | 72
| Subtotal for 072 |  |  |  |  | 532.5
Cost Code 073
2014-10-01 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 73
2014-10-07 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 73
2014-10-07 | UD Water Cart - No Driver | UD Water Cart | hr | 5.5 | 21.61 | 118.855 | 73
2014-10-07 | 120H Grader | 120H Grader | hr | 2 | 120 | 240 | 73
2014-10-09 | UD Water Cart - No Driver | UD Water Cart | hr | 8 | 21.61 | 172.88 | 73
2014-10-16 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 73
2014-10-28 | Claim fo the hire of 14T Excavator | Sewer Subbie |  | 8.5 | 115 | 977.5 | 73
2014-10-29 | Dalton Concrete - Labour x 3 | Dalton Concrete | hr | 21 |  |  | 73
2014-10-30 | Dalton Concrete - Labour x 3 | Dalton Concrete | hr | 16 |  |  | 73
2014-10-30 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 73
2014-10-30 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 73
2014-10-31 | UD Water Cart - No Driver | UD Water Cart | hr | 3.5 | 21.61 | 75.635 | 73
2014-10-31 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 73
2014-10-31 | Claim for item 2631.1 for 31/10/2014 |  | m2 | 140.8 | 26 | 3660.8 | 73
2014-10-31 | Claim for item for 31/10/2014 |  | item | 1 | 3240 | 3240 | 73
2014-11-01 | Dalton Concrete - Labour | Dalton Concrete | hr | 0.5 |  |  | 73
2014-11-03 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 73
2014-11-03 | UD Water Cart - No Driver | UD Water Cart | hr | 3 | 21.61 | 64.83 | 73
2014-11-10 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
2014-11-12 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 73
2014-11-13 | CAT297C MTL - No Operator | CAT297 | hr | 1 | 46.5 | 46.5 | 73
2014-11-13 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 2 | 25.78 | 51.56 | 73
2014-11-13 | Allciv - Labour Hire | Labour | hr | 1.25 | 35.11 | 43.8875 | 73
2014-11-13 | Labour Hire | Labour | hr | 1.25 | 39.98 | 49.975 | 73
2014-11-13 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 73
2014-11-14 | Backhoe - Wet Hire | Back Hoe | hr | 4 | 110 | 440 | 73
2014-11-14 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 3 | 25.78 | 77.34 | 73
2014-11-14 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 73
2014-11-24 | Ablel Flex | Small Tools |  | 1 | 56.4 | 56.4 | 73
2014-11-25 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
2014-11-26 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
2014-11-28 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 73
2014-11-29 | Diamond Blade | Small Tools |  | 1 | 285.55 | 285.55 | 73
2014-11-30 | Claim for item 2631.1 for 30/11/2014 |  | m2 | 93 | 26 | 2418 | 73
2014-11-30 | Claim for item DCC01 for 30/11/2014 |  | lm | 89 | 65 | 5785 | 73
2014-11-30 | Claim for item 2631.5 for 30/11/2014 |  | m2 | 146 | 32 | 4672 | 73
2014-11-30 | Claim for item 2631.2 for 30/11/2014 |  | m2 | 74 | 26 | 1924 | 73
2014-12-01 | Dalton Concrete - Labour | Dalton Concrete | hr | 30 |  |  | 73
2014-12-01 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 73
2014-12-02 | Dalton Concrete - Labour | Dalton Concrete | hr | 19.5 |  |  | 73
2014-12-02 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
2014-12-04 | Backhoe - Wet Hire | Back Hoe | hr | 1 | 110 | 110 | 73
2014-12-04 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
2014-12-05 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 73
2014-12-08 | Allciv - Leading Hand | Labour | Hr | 8.5 | 54.58 | 463.93 | 73
2014-12-09 | Allciv - Leading Hand | Labour | Hr | 6.5 | 54.58 | 354.77 | 73
2014-12-09 | Masking Tape x 5 and Sikaflex x 6 | Small Tools |  | 1 | 105.43 | 105.43 | 73
2014-12-10 | Allciv - Leading Hand | Labour | Hr | 5.5 | 54.58 | 300.19 | 73
2014-12-10 | Grey sikaflex sausage x 10 | Small Tools |  | 1 | 162.2 | 162.2 | 73
2014-12-11 | Dowel Galvanised x 2 | Small Tools |  | 1 | 2.47 | 2.47 | 73
2014-12-11 | Grey sikaflex sausage x 6 | Small Tools |  | 1 | 90.36 | 90.36 | 73
2014-12-11 | Backhoe - Wet Hire | Back Hoe | hr | 4 | 110 | 440 | 73
2014-12-11 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 73
2014-12-11 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 73
2014-12-12 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 73
2014-12-12 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 73
2014-12-15 | Rivert Gun, Riverts and Drill Bit | Small Tools |  | 1 | 22.1 | 22.1 | 73
2014-12-15 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 73
2014-12-15 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 73
2014-12-16 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 73
2014-12-17 | Place Concrete paths. Salmon, Exsposed and Kerb | Dalton Concrete |  | 1 | 6779.76 | 6779.76 | 73
2015-03-19 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 73
2015-03-19 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
2015-03-19 | Backhoe - Wet Hire | Back Hoe | hr | 5 | 110 | 550 | 73
2015-03-26 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 73
2015-03-26 | Backhoe - Wet Hire | Back Hoe |  | 1 | 110 | 110 | 73
2015-03-26 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 73
| Subtotal for 073 |  |  |  |  | 38225.2775
Cost Code 081
2014-05-08 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 81
2014-05-08 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 81
2014-05-14 | 26 x 375mm, 18 x 450mm, 25 x 525mm Class 2 RRJ RC Pipes | 450 RCP FJ CL2 |  | 1 | 15965 | 15965 | 81
2014-05-21 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 81
2014-05-21 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 81
2014-05-21 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 81
2014-05-21 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 81
| Subtotal for 081 |  |  |  |  | 16600.83
Cost Code 082
2014-05-08 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 82
2014-05-08 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 82
2014-05-14 | 26 x 600mm Class 2 RRJ RC Pipes | 525 RCP RRJ CL2 |  | 26 | 375 | 9750 | 82
2014-07-29 | Whitsunday Drainage Contractors | WDC | Item | 3 |  |  | 82
2014-07-30 | Whitsunday Drainage Contractors | WDC | Item | 20 |  |  | 82
2014-11-28 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 82
2014-12-02 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 82
| Subtotal for 082 |  |  |  |  | 10332.59
Cost Code 085
2014-08-14 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 85
2014-08-14 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 85
2014-09-08 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 85
2014-09-30 | Allciv - Leading Hand | Labour | Hr | 8.5 | 54.58 | 463.93 | 85
2014-09-30 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 85
2014-10-01 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 85
2014-10-02 | Backhoe - Wet Hire | Back Hoe | hr | 1.25 | 110 | 137.5 | 85
2014-10-02 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 85
2014-10-02 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 85
2014-10-02 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 85
2014-10-03 | Backhoe - Wet Hire | Back Hoe | hr | 3 | 110 | 330 | 85
2014-10-03 | Allciv - Labour HIre | Labour | hr | 8 | 42.72 | 341.76 | 85
2014-10-03 | UD Water Cart - No Driver | UD Water Cart | hr | 8 | 21.61 | 172.88 | 85
2014-10-03 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 85
2014-10-03 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 85
2014-10-07 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 85
2014-10-07 | Allciv - Leading Hand | Labour | Hr | 4.5 | 54.58 | 245.61 | 85
2014-10-08 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 85
2014-10-08 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 85
2014-10-08 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 85
2014-10-08 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 85
2014-10-09 | Plate Compactor - Dry Hire | Plate Compactor |  | 1 | 152.09 | 152.09 | 85
2014-10-15 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 85
2014-10-16 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 85
2014-11-06 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 85
2014-11-06 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 85
2014-11-06 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 85
2014-11-11 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 85
2014-11-11 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 85
2014-11-11 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 85
2014-11-18 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 85
2014-11-19 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 85
| Subtotal for 085 |  |  |  |  | 6064.855
Cost Code 086
2014-05-08 | Aggregate 20mm | Aggregate 20mm | tonne | 24.38 | 33.5 | 816.73 | 86
2014-05-08 | Aggregate 20mm | Aggregate 20mm | tonne | 24.18 | 33.5 | 810.03 | 86
2014-05-12 | Aggregate 20mm | Aggregate 20mm | tonne | 48.74 | 33.5 | 1632.79 | 86
2014-05-13 | Aggregate 20mm | Aggregate 20mm | tonne | 24.72 | 33.5 | 828.12 | 86
2014-05-22 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 86
2014-05-23 | N40 Concrete & Min Load Charge | N40 |  | 1 | 817.2 | 817.2 | 86
2014-05-29 | Aggregate 20mm | Aggregate 20mm | tonne | 25 | 25 | 625 | 86
2014-06-18 | N25 Concrete and Min Load Charge | Stabilised Sand |  | 1 | 440 | 440 | 86
2014-06-26 | Socked Ag-line Delivery | Flood Flap |  | 0.5 | 4030 | 2015 | 86
2014-09-11 | Whitsunday Drainage Contractors | WDC | Item | 38 |  |  | 86
2014-09-29 | Whitsunday Drainage Contractors | WDC | Item | 36 |  |  | 86
2014-09-30 | Whitsunday Drainage Contractors | WDC | Item | 34 |  |  | 86
2014-09-30 | Claim for installation of 150mm storm water | Sewer Subbie |  | 1 | 14553 | 14553 | 86
2014-10-01 | Whitsunday Drainage Contractors | WDC | Item | 27 |  |  | 86
2014-12-01 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 86
| Subtotal for 086 |  |  |  |  | 22752.36
Cost Code 087
2014-05-21 | 100m x 100mm Socked Ag-Line | Ag-Line Socked |  | 2 | 329 | 658 | 87
2014-06-03 | Hire of Labour | Labour | hr | 3.5 | 38.45 | 134.575 | 87
2014-06-04 | Hire of Labour | Labour | hr | 2 | 38.45 | 76.9 | 87
2014-06-06 | Hire of Labour 6.5 x O/T1 Hours & 4.5 x O/T2 Hours | Labour | hr | 1 | 651 | 651 | 87
2014-06-06 | Hire of Labour 4.5 x O/T1 Hours | Labour | hr | 1 | 234.36 | 234.36 | 87
2014-06-06 | Hire of Labour | Labour | hr | 2.5 | 38.45 | 96.125 | 87
2014-06-06 | Hire of Labour 6.5 x O/T1 Hours & 4.5 x O/T2 Hours | Labour | hr | 1 | 668.36 | 668.36 | 87
2014-06-23 | Hire of Labour | Labour | hr | 2 | 38.45 | 76.9 | 87
2014-06-23 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 87
2014-06-23 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 87
2014-06-24 | Hire of Labour | Labour | hr | 6.5 | 38.45 | 249.925 | 87
2014-06-24 | Socked Ag-line Delivery | Sub Soil Drain |  | 0.5 | 3141 | 1570.5 | 87
2014-07-07 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 87
2014-07-07 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 87
2014-07-10 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 2 | 25.78 | 51.56 | 87
2014-07-10 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 87
2014-07-10 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 87
2014-07-10 | Hire of Labour | Labour | hr | 2.5 | 38.45 | 96.125 | 87
2014-07-24 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 87
2014-07-30 | Claim for machine hire used at The cove | Sewer Subbie |  | 7.5 | 125 | 937.5 | 87
2014-08-12 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 87
2014-08-12 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 87
2014-09-08 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 87
2014-09-08 | Allciv - Labour HIre | Labour | hr | 1 | 42.72 | 42.72 | 87
2014-09-08 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 87
2014-09-08 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 87
2014-09-09 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 87
2014-09-09 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 87
2014-09-09 | UD Water Cart - No Driver | UD Water Cart | hr | 8 | 21.61 | 172.88 | 87
2014-09-09 | 6 x DWV PVC Junction | PVC Juntion Pipe |  | 6 | 7.52 | 45.11 | 87
2014-09-09 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 8 | 48 | 384 | 87
2014-09-09 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 87
2014-09-09 | Allciv - Labour HIre | Labour | hr | 8 | 42.72 | 341.76 | 87
2014-09-10 | Labour Hire | Labour | hr | 4.5 | 39.98 | 179.91 | 87
2014-09-10 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 87
2014-09-10 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 87
2014-09-10 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 87
2014-09-10 | Backhoe - Wet Hire | Back Hoe | hr | 9.5 | 110 | 1045 | 87
2014-09-10 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 5 | 48 | 240 | 87
2014-09-10 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 87
2014-09-11 | Backhoe - Wet Hire | Back Hoe | hr | 7 | 110 | 770 | 87
2014-09-11 | Allciv - Labour HIre | Labour | hr | 7 | 42.72 | 299.04 | 87
2014-09-11 | UD Water Cart - No Driver | UD Water Cart | hr | 9.5 | 21.61 | 205.295 | 87
2014-09-11 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 9.5 | 48 | 456 | 87
2014-09-11 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 87
2014-09-11 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 87
2014-09-11 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 87
2014-09-12 | UD Water Cart - No Driver | UD Water Cart | hr | 5.5 | 21.61 | 118.855 | 87
2014-09-12 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 6.5 | 48 | 312 | 87
2014-09-12 | Backhoe - Wet Hire | Back Hoe | hr | 5.5 | 110 | 605 | 87
2014-09-12 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 87
2014-09-12 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 87
2014-09-12 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 87
2014-09-12 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 87
2014-09-15 | Backhoe - Wet Hire | Back Hoe | hr | 2.5 | 110 | 275 | 87
2014-10-08 | 3 x 100m x 100mm Socked Ag-Line | Ag-Line Socked |  | 3 | 329.5 | 988.5 | 87
| Subtotal for 087 |  |  |  |  | 17562.98
Cost Code 095
2014-05-30 | Claim for varior works compleded at the Cove sewers and Manholes | Sewer Subbie |  | 1 | 26013.4 | 26013.4 | 95
2014-05-31 | Claim for item 9740.1 for 31/05/2014 |  | m | 133 | 9 | 1197 | 95
2014-05-31 | Claim for item 9741.2 for 31/05/2014 |  | m | 177.75 | 59 | 10487.25 | 95
2014-05-31 | Claim for item 9750.1 for 31/05/2014 |  | Lump | 1 | 1500 | 1500 | 95
2014-05-31 | Claim for item 9740.2 for 31/05/2014 |  | m | 237 | 9.5 | 2251.5 | 95
2014-05-31 | Claim for item 9741.1 for 31/05/2014 |  | m | 99.75 | 55 | 5486.25 | 95
2014-05-31 | Claim for item 9620.2 for 31/05/2014 |  | m | 5.3 | 250 | 1325 | 95
2014-05-31 | Claim for item 9615.1 for 31/05/2014 |  | m | 5.3 | 50 | 265 | 95
2014-05-31 | Claim for item 9601.2 for 31/05/2014 |  | m | 5.3 | 38 | 201.4 | 95
2014-05-31 | Claim for item 9720.1 for 31/05/2014 |  | Each | 0.75 | 4400 | 3300 | 95
2014-06-30 | Claim for item 9742.3 for 30/06/2014 |  | Each | 1 | 1850 | 1850 | 95
2014-06-30 | Claim for item 9742.1 for 30/06/2014 |  | Each | 22 | 900 | 19800 | 95
2014-06-30 | Claim for item 9741.2 for 30/06/2014 |  | m | 35.55 | 59 | 2097.45 | 95
2014-06-30 | Claim for item 9741.1 for 30/06/2014 |  | m | 33.25 | 55 | 1828.75 | 95
2014-06-30 | Claim for item 9742.2 for 30/06/2014 |  | Each | 1 | 1780 | 1780 | 95
2014-08-01 | Backhoe - Wet Hire | Back Hoe |  | 5 | 110 | 550 | 95
2014-08-12 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 95
2014-10-02 | Whitsunday Drainage Contractors | WDC | Item | 27 |  |  | 95
2014-10-31 | Claim for item 9700.3 for 31/10/2014 |  | m | 6 | 250 | 1500 | 95
2014-10-31 | Claim for item 9720.1 for 31/10/2014 |  | Each | 0.25 | 4400 | 1100 | 95
2014-12-31 | Claim for item 9741.2 for 31/12/2014 |  | m | 23.7 | 59 | 1398.3 | 95
2014-12-31 | Claim for item 9742.3 for 31/12/2014 |  | Each | 1 | 1850 | 1850 | 95
| Subtotal for 095 |  |  |  |  | 85835.88
Cost Code 103
2014-05-13 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 103
2014-06-24 | Float 14T excavator to P038 for water | Float |  | 1 | 405 | 405 | 103
2014-06-30 | Claim for item 9320.4 for 30/06/2014 |  | Each | 0.7778 | 180 | 140.004 | 103
2014-06-30 | Claim for item 9523.1 for 30/06/2014 |  | m | 253 | 80 | 20240 | 103
2014-06-30 | Claim for item 9343.1 for 30/06/2014 |  | Each | 3 | 280 | 840 | 103
2014-06-30 | Claim for item 9363.1 for 30/06/2014 |  | Each | 2 | 100 | 200 | 103
2014-06-30 | Claim for item 9391.1 for 30/06/2014 |  | Each | 6 | 100 | 600 | 103
2014-06-30 | Claim for item 9361.1 for 30/06/2014 |  | Each | 2 | 300 | 600 | 103
2014-06-30 | Claim for item 9360.1 for 30/06/2014 |  | Each | 2 | 280 | 560 | 103
2014-06-30 | Claim for item 9320.3 for 30/06/2014 |  | Each | 1 | 120 | 120 | 103
2014-06-30 | Claim for item 9320.2 for 30/06/2014 |  | Each | 2 | 120 | 240 | 103
2014-06-30 | Claim for item 9304.1 for 30/06/2014 |  | m | 253 | 15 | 3795 | 103
2014-06-30 | Claim for item 9311.1 for 30/06/2014 |  | Each | 5 | 1350 | 6750 | 103
2014-07-31 | Claim for item 9529.1 for 31/07/2014 |  | Each | 1 | 11500 | 11500 | 103
2014-08-01 | Whitsunday Drainage Contractors(2) | WDC | Item | 5 |  |  | 103
2014-08-04 | Whitsunday Drainage Contractors(2) | WDC | Item | 5 |  |  | 103
2014-09-01 | Whitsunday Drainage Contractors | WDC | Item | 30 |  |  | 103
2014-09-02 | Whitsunday Drainage Contractors | WDC | Item | 22.5 |  |  | 103
2014-09-10 | UD Water Cart - No Driver | UD Water Cart | hr | 5.5 | 21.61 | 118.855 | 103
2014-09-10 | Whitsunday Drainage Contractors | WDC | Item | 9.5 |  |  | 103
2014-09-10 | 9 x Stormwater Pipe, 14 PVC Bends Dwv Slab Repair Pipe to Socket, Push on Cap, Threades Couplings, Solvent Cement, Priming Fluid | PVC Stormwater |  | 1 | 1014.65 | 1014.65 | 103
2014-09-19 | Whitsunday Drainage Contractors | WDC | Item | 36 |  |  | 103
2014-09-22 | Whitsunday Drainage Contractors | WDC | Item | 28.5 |  |  | 103
2014-09-24 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 103
2014-10-03 | Whitsunday Drainage Contractors | WDC | Item | 24 |  |  | 103
2014-10-07 | Whitsunday Drainage Contractors | WDC | Item | 24 |  |  | 103
2014-10-08 | Whitsunday Drainage Contractors | WDC | Item | 30 |  |  | 103
2014-10-09 | Whitsunday Drainage Contractors | WDC | Item | 32 |  |  | 103
2014-10-27 | Whitsunday Drainage Contractors | WDC | Item | 8 |  |  | 103
2014-10-28 | Claim for the supply & installaiton of a 100mm bypass. | Sewer Subbie |  | 1 | 9600 | 9600 | 103
2014-10-28 | Claim for the various work undertaken at he Cove . Testing of 50mm water meter and RPZ Valve | Sewer Subbie |  | 1 | 7580 | 7580 | 103
2014-10-28 | Claim for the supply & installaiton of a 50mm RPZ valve onto the 63mm irrigation line at the Cove | Sewer Subbie |  | 1 | 2400 | 2400 | 103
2014-10-31 | Claim for item 9362.2 for 31/10/2014 |  | Each | 2 | 130 | 260 | 103
2014-10-31 | Claim for item 9051 for 31/10/2014 |  | Lump | 1 | 2000 | 2000 | 103
2014-10-31 | Claim for item 9596 for 31/10/2014 |  | Lump | 1 | 1000 | 1000 | 103
2014-10-31 | Claim for item 9364.1 for 31/10/2014 |  | Each | 2 | 520 | 1040 | 103
2014-10-31 | Claim for item 9470.5 for 31/10/2014 |  | Item | 1 | 1500 | 1500 | 103
2014-10-31 | Claim for item 9391.1 for 31/10/2014 |  | Each | 1 | 100 | 100 | 103
2014-10-31 | Claim for item 9401.2 for 31/10/2014 |  | Each | 2 | 250 | 500 | 103
2014-10-31 | Claim for item 9598.1 for 31/10/2014 |  | Lump | 1 | 2000 | 2000 | 103
2014-10-31 | Claim for item 9597 for 31/10/2014 |  | Lump | 1 | 1500 | 1500 | 103
2014-12-05 | Plasson Pushfit Coupler | Small Tools |  | 1 | 10.83 | 10.83 | 103
2014-12-31 | Claim for item 9470.3 for 31/12/2014 |  | Each | 4 | 480 | 1920 | 103
2014-12-31 | Claim for item 9470.2 for 31/12/2014 |  | Each | 2 | 2000 | 4000 | 103
2014-12-31 | Claim for item 9470.4 for 31/12/2014 |  | Each | 3 | 2080 | 6240 | 103
2014-12-31 | Claim for item 9531.2 for 31/12/2014 |  | m³ | 5 | 350 | 1750 | 103
2014-12-31 | Claim for item 9470.3 for 31/12/2014 |  | Each | 7 | 400 | 2800 | 103
| Subtotal for 103 |  |  |  |  | 93624.379
Cost Code 111
2014-05-22 | 12 x Cable Pit 700 x 810mm and 12 x Cement concrete pit lid | HDPE Cable Pit |  | 11 | 1580 | 17380 | 111
2014-09-15 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 111
2014-09-15 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 111
2014-09-15 | Whitsunday Drainage Contractors | WDC | Item | 57 |  |  | 111
2014-09-15 | Rope Blue x Yellow 6mm | Electrical Conduit |  | 2 | 38.74 | 77.48 | 111
2014-09-16 | UD Water Cart - No Driver | UD Water Cart | hr | 3.5 | 21.61 | 75.635 | 111
2014-09-16 | Whitsunday Drainage Contractors | WDC | Item | 57 |  |  | 111
2014-09-18 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 111
2014-09-18 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 111
2014-09-19 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 111
2014-09-19 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 111
2014-09-19 | Labour Hire | Labour | hr | 4.5 | 39.98 | 179.91 | 111
2014-09-19 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 111
2014-09-19 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 111
2014-09-19 | UD Water Cart - No Driver | UD Water Cart | hr | 2.5 | 21.61 | 54.025 | 111
2014-09-22 | Labour Hire | Labour | hr | 9 | 39.98 | 359.82 | 111
2014-09-22 | Posie Track | CAT297 | hr | 9 | 46.5 | 418.5 | 111
2014-09-22 | Allciv - Labour Hire | Labour | hr | 9 | 35.11 | 315.99 | 111
2014-09-22 | Allciv - Labour HIre | Labour | hr | 9 | 42.72 | 384.48 | 111
2014-09-22 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 111
2014-09-22 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 111
2014-09-23 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 111
2014-09-23 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 111
2014-09-23 | Whitsunday Drainage Contractors | WDC | Item | 24 |  |  | 111
2014-09-23 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 111
2014-09-23 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 111
2014-09-23 | Posie Track | CAT297 | hr | 5.5 | 46.5 | 255.75 | 111
2014-09-24 | Labour Hire | Labour | hr | 2.5 | 39.98 | 99.95 | 111
2014-09-24 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 111
2014-09-24 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 111
2014-09-24 | CAT297C MTL - No Operator | CAT297 | hr | 3.5 | 46.5 | 162.75 | 111
2014-09-24 | Whitsunday Drainage Contractors | WDC | Item | 30 |  |  | 111
2014-09-24 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 111
2014-09-25 | CAT297C MTL - No Operator | CAT297 | hr | 2 | 46.5 | 93 | 111
2014-09-25 | Allciv - Labour Hire | Labour | hr | 1.25 | 35.11 | 43.8875 | 111
2014-09-25 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 111
2014-09-25 | Whitsunday Drainage Contractors | WDC | Item | 28.5 |  |  | 111
2014-09-26 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 111
2014-09-29 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 111
2014-09-30 | Electrical Breaker and Points Hired 29/9/14 - 30/9/14 | Electric Breaker |  | 1 | 327.8 | 327.8 | 111
2014-09-30 | Claim for the installation of Electrical & Telstra Conduits at the Cove Sub-Division | Sewer Subbie |  | 1 | 22472.5 | 22472.5 | 111
2014-10-01 | 3 x 20mm x 90 Deg x 305mm Vinidex P/No | Small Tools |  | 3 | 3.236 | 9.708 | 111
2014-10-03 | Backhoe - Wet Hire | Back Hoe | hr | 3 | 110 | 330 | 111
2014-10-07 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 111
2014-10-07 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 111
2014-10-07 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 111
2014-10-07 | Backhoe - Wet Hire | Back Hoe | hr | 7.75 | 110 | 852.5 | 111
2014-10-07 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 111
2014-10-07 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 111
2014-10-08 | UD Water Cart - No Driver | UD Water Cart | hr | 5.5 | 21.61 | 118.855 | 111
2014-10-08 | Labour Hire | Labour | hr | 4.5 | 39.98 | 179.91 | 111
2014-10-08 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 111
2014-10-08 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 111
2014-10-09 | Backhoe - Wet Hire | Back Hoe | hr | 4 | 110 | 440 | 111
2014-10-09 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 111
2014-10-09 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 111
2014-10-09 | Allciv - Labour Hire | Labour | hr | 1.5 | 35.11 | 52.665 | 111
2014-10-09 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 111
2014-10-09 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 111
2014-10-13 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 111
2014-10-13 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 4 | 25.78 | 103.12 | 111
2014-10-16 | Allciv - Labour Hire | Labour | hr | 1.5 | 35.11 | 52.665 | 111
2014-10-20 | Backhoe - Wet Hire | Back Hoe | hr | 9.5 | 110 | 1045 | 111
2014-10-20 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 111
2014-10-20 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 111
2014-10-20 | 25 x PVC sweep bend 40mm 90 degree orange | Small Tools |  | 1 | 156.61 | 156.61 | 111
2014-10-21 | PVC Telstra Pip | Pvc Rigid Conduit |  | 1 | 18.46 | 18.46 | 111
2014-10-21 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 111
2014-10-23 | Labour Hire | Labour | hr | 3.5 | 39.98 | 139.93 | 111
2014-10-29 | Backhoe - Wet Hire | Back Hoe | hr | 4 | 110 | 440 | 111
2014-10-29 | Labour Hire | Labour | hr | 5.5 | 39.98 | 219.89 | 111
2014-10-29 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 111
2014-10-29 | Allciv - Leading Hand | Labour | Hr | 6.5 | 54.58 | 354.77 | 111
2014-10-29 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 111
2014-11-14 | Allciv - Leading Hand | Labour | Hr | 4.5 | 54.58 | 245.61 | 111
2014-11-14 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 111
2014-12-03 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 111
2014-12-03 | Backhoe - Wet Hire | Back Hoe | hr | 3.5 | 110 | 385 | 111
2015-03-26 | Backhoe - Wet Hire | Back Hoe |  | 7 | 110 | 770 | 111
2015-03-26 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 111
2015-03-26 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 111
2015-05-05 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 111
2015-05-06 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 111
2015-05-07 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 111
| Subtotal for 111 |  |  |  |  | 57698.3105
Cost Code 113
2014-10-17 | Electrical-Sub Contractor | Reef Electical | hr | 10 |  |  | 113
2014-10-20 | Electrical-Sub Contractor | Reef Electical | hr | 11 |  |  | 113
2014-10-22 | Electrical-Sub Contractor | Reef Electical | hr | 16 |  |  | 113
2014-10-22 | UD Water Cart - No Driver | UD Water Cart | hr | 3 | 21.61 | 64.83 | 113
2014-10-23 | Allciv - Leading Hand | Labour | Hr | 7.5 | 54.58 | 409.35 | 113
2014-10-23 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 113
2014-10-23 | Electrical-Sub Contractor | Reef Electical | hr | 8.5 |  |  | 113
2014-10-23 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 113
2014-10-23 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 113
2014-10-24 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 113
2014-10-24 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 113
2014-10-24 | Labour Hire | Labour | hr | 2.5 | 39.98 | 99.95 | 113
2014-10-27 | Electrical-Sub Contractor | Reef Electical | hr | 19 |  |  | 113
2014-10-28 | Electrical-Sub Contractor | Reef Electical | hr | 19 |  |  | 113
2014-10-28 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 113
2014-10-28 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 113
2014-10-28 | CAT297C MTL - No Operator | CAT297 | hr | 1.5 | 46.5 | 69.75 | 113
2014-10-29 | Labour Hire | Labour | hr | 2.5 | 39.98 | 99.95 | 113
2014-10-29 | Electrical-Sub Contractor | Reef Electical | hr | 19 |  |  | 113
2014-10-30 | Electrical-Sub Contractor | Reef Electical | hr | 38 |  |  | 113
2014-10-31 | Claim for item for 31/10/2014 |  | Item | 1 | 42965 | 42965 | 113
2014-10-31 | Claim for item for 31/10/2014 |  | Item | 1 | 19325 | 19325 | 113
2014-10-31 | Claim for item for 31/10/2014 |  | Item | 1 | 16075 | 16075 | 113
2014-10-31 | Claim for item for 31/10/2014 |  | Item | 1 | 6800 | 6800 | 113
2014-10-31 | Claim for item for 31/10/2014 |  | LS |  | 3440 |  | 113
2014-11-03 | Electrical-Sub Contractor | Reef Electical | hr | 2.25 |  |  | 113
2014-12-05 | Electrical-Sub Contractor | Reef Electical | hr | 18.5 |  |  | 113
2014-12-08 | Electrical-Sub Contractor | Reef Electical | hr | 5.5 |  |  | 113
2014-12-09 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 113
2014-12-19 | Electrical-Sub Contractor | Reef Electical | hr | 1 | 4655 | 4655 | 113
2015-05-15 | Electrical-Sub Contractor | Reef Electical | hr | 6 |  |  | 113
2015-05-15 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 113
| Subtotal for 113 |  |  |  |  | 91724.16
Cost Code 121
2014-06-05 | Hire of Labour | Labour | hr | 5 | 38.45 | 192.25 | 121
2014-06-30 | Claim for item for 30/06/2014 |  | LS | 0.0373 | 3820.46 | 142.5032 | 121
2014-06-30 | Claim for item for 30/06/2014 |  | LS | 0.052 | 22088.41 | 1148.5973 | 121
2014-06-30 | Claim for item for 30/06/2014 |  | LS | 0.038 | 80346.6 | 3053.1708 | 121
2014-06-30 | Claim for item for 30/06/2014 |  | LS | 0.0377 | 10227.27 | 385.5681 | 121
2014-06-30 | Claim for item for 30/06/2014 |  | LS | 0.025 | 189402.18 | 4735.0545 | 121
2014-09-11 | Backhoe - Wet Hire | Back Hoe | hr | 2.5 | 110 | 275 | 121
2014-09-11 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 121
2014-09-11 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 121
2014-09-30 | Landscape the area opposite the bus stop & Irrigate & Partially re-turf right side of the road leading to the Cove | Landscaper |  | 1 | 11426.64 | 11426.64 | 121
2014-10-08 | Backhoe - Wet Hire Northern easement sea wall top up | Back Hoe | hr | 3.5 | 110 | 385 | 121
2014-10-09 | Backhoe - Wet Hire | Back Hoe | hr | 3.5 | 110 | 385 | 121
2014-10-22 | Plants Whitsunday X 2 | Plants Whitsunday | hr | 14 |  |  | 121
2014-10-23 | Plants Whitsunday X 2 | Plants Whitsunday | hr | 28 |  |  | 121
2014-10-27 | Install of 3 x Street trees adjacent to bus stop. | Landscaper |  | 1 | 573.11 | 573.11 | 121
2014-10-28 | Plants Whitsunday X 2 | Plants Whitsunday | hr | 18 |  |  | 121
2014-10-30 |  | Plants Whitsunday | hr | 16 |  |  | 121
2014-10-31 | Claim for item for 31/10/2014 |  | LS | 0.3 | 10227.27 | 3068.181 | 121
2014-10-31 | Claim for item for 31/10/2014 |  | LS | 0.0425 | 189402.18 | 8049.5926 | 121
2014-10-31 |  | Plants Whitsunday | hr | 63 |  |  | 121
2014-10-31 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 121
2014-10-31 | Claim for item for 31/10/2014 |  | LS | 0.3155 | 3820.46 | 1205.3551 | 121
2014-10-31 | Claim for item for 31/10/2014 |  | LS | 0.462 | 80346.6 | 37120.1292 | 121
2014-10-31 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 121
2014-11-01 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 121
2014-11-01 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 121
2014-11-01 |  | Plants Whitsunday | hr | 2 |  |  | 121
2014-11-03 |  | Plants Whitsunday | hr | 63 |  |  | 121
2014-11-03 | UD Water Cart - No Driver | UD Water Cart | hr | 2.5 | 21.61 | 54.025 | 121
2014-11-04 |  | Plants Whitsunday | hr | 64.05 |  |  | 121
2014-11-04 | UD Water Cart - No Driver | UD Water Cart | hr | 6 | 21.61 | 129.66 | 121
2014-11-04 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 121
2014-11-06 | Water Cart Allciv - No Operator | WC - Allciv | hr | 1 | 42.79 | 42.79 | 121
2014-11-07 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 121
2014-11-07 | Water Cart Allciv - No Operator | WC - Allciv | hr | 1 | 42.79 | 42.79 | 121
2014-11-10 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 121
2014-11-10 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 121
2014-11-10 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 121
2014-11-13 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 121
2014-11-13 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 2.5 | 25.78 | 64.45 | 121
2014-11-17 | Allciv - Leading Hand | Labour | Hr | 8.5 | 54.58 | 463.93 | 121
2014-11-17 | Water Cart Allciv - No Operator | WC - Allciv | hr | 2 | 42.79 | 85.58 | 121
2014-11-18 | Water Cart Allciv - No Operator | WC - Allciv | hr | 2 | 42.79 | 85.58 | 121
2014-11-18 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 121
2014-11-19 | Water Cart Allciv - No Operator | WC - Allciv | hr | 2 | 42.79 | 85.58 | 121
2014-11-19 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 121
2014-11-20 |  | Plants Whitsunday | hr | 81 |  |  | 121
2014-11-20 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 121
2014-11-20 | Water Cart Allciv - No Operator | WC - Allciv | hr | 6 | 42.79 | 256.74 | 121
2014-11-21 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 121
2014-11-21 | Water Cart Allciv - No Operator | WC - Allciv | hr | 6 | 42.79 | 256.74 | 121
2014-11-21 |  | Plants Whitsunday | hr | 56 |  |  | 121
2014-11-25 |  | Plants Whitsunday | hr | 81 |  |  | 121
2014-11-25 | Allciv - Leading Hand | Labour | Hr | 9 | 54.58 | 491.22 | 121
2014-11-25 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 121
2014-11-25 | Water Cart Allciv - No Operator | WC - Allciv | hr | 9 | 42.79 | 385.11 | 121
2014-11-26 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 121
2014-11-26 |  | Plants Whitsunday | hr | 81 |  |  | 121
2014-11-27 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 121
2014-11-27 |  | Plants Whitsunday | hr | 81 |  |  | 121
2014-11-27 | Allciv - Leading Hand | Labour | Hr | 10 | 54.58 | 545.8 | 121
2014-11-28 | Water Cart Allciv - No Operator | WC - Allciv | hr | 4 | 42.79 | 171.16 | 121
2014-11-28 |  | Plants Whitsunday | hr | 80 |  |  | 121
2014-11-28 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 121
2014-11-30 | Claim for item for 30/11/2014 |  | LS | 0.2472 | 3820.46 | 944.4177 | 121
2014-11-30 | Claim for item for 30/11/2014 |  | LS | 0.3 | 80346.6 | 24103.98 | 121
2014-11-30 | Claim for item for 30/11/2014 |  | LS | 0.7325 | 189402.18 | 138737.0969 | 121
2014-11-30 | Claim for item for 30/11/2014 |  | LS | 0.2623 | 10227.27 | 2682.6129 | 121
2014-11-30 | Claim for item for 30/11/2014 |  | LS | 0.548 | 22088.41 | 12104.4487 | 121
2014-12-01 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 121
2014-12-01 |  | Plants Whitsunday | hr | 25 |  |  | 121
2014-12-01 | Water Cart Allciv - No Operator | WC - Allciv | hr | 4 | 42.79 | 171.16 | 121
2014-12-02 |  | Plants Whitsunday | hr | 54 |  |  | 121
2014-12-02 | Progress Claim Three $178,572.54 paid, however doubles up from S/C management in accrual, therefore zero out here. | Plants Whitsunday |  |  | 178572.54 |  | 121
2014-12-03 |  | Plants Whitsunday | hr | 54 |  |  | 121
2014-12-04 |  | Plants Whitsunday | hr | 84.5 |  |  | 121
2014-12-04 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 121
2014-12-04 | Backhoe - Wet Hire | Back Hoe | hr | 2.5 | 110 | 275 | 121
2014-12-05 |  | Plants Whitsunday | hr | 25.35 |  |  | 121
2014-12-05 | Water Cart Allciv - No Operator | WC - Allciv | hr | 2.5 | 42.79 | 106.975 | 121
2014-12-05 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 121
2014-12-08 |  | Plants Whitsunday | hr | 16 |  |  | 121
2014-12-09 |  | Plants Whitsunday | hr | 2 |  |  | 121
2014-12-10 |  | Plants Whitsunday | hr | 41 |  |  | 121
2014-12-10 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 121
2014-12-11 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 121
2014-12-11 |  | Plants Whitsunday | hr | 68 |  |  | 121
2014-12-11 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 121
2014-12-12 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 121
2014-12-12 |  | Plants Whitsunday | hr | 6 |  |  | 121
2014-12-15 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 121
2014-12-15 |  | Plants Whitsunday | hr | 27 |  |  | 121
2014-12-16 |  | Plants Whitsunday | hr | 27 |  |  | 121
2014-12-16 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 121
2014-12-17 |  | Plants Whitsunday | hr | 27 |  |  | 121
2014-12-17 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 121
2014-12-18 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 121
2014-12-18 |  | Plants Whitsunday | hr | 45 |  |  | 121
2014-12-19 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 121
2014-12-19 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 121
2014-12-19 | Progress Claim Three $43,077.64 paid, but doubles up in accrual from S/C management, therefore zero out here. | Plants Whitsunday |  |  | 43077.64 |  | 121
2014-12-19 |  | Plants Whitsunday | hr | 22 |  |  | 121
2014-12-31 | Claim for item for 31/12/2014 |  | LS | 0.15 | 22088.41 | 3313.2615 | 121
2014-12-31 | Claim for item for 31/12/2014 |  | LS | 0.2 | 10227.27 | 2045.454 | 121
2014-12-31 | Claim for item for 31/12/2014 |  | LS | 0.5 | 9436.36 | 4718.18 | 121
2014-12-31 | Claim for item for 31/12/2014 |  | LS | 0.05 | 80346.6 | 4017.33 | 121
2014-12-31 | Claim for item for 31/12/2014 |  | LS | 0.15 | 3820.46 | 573.069 | 121
2014-12-31 | Claim for item for 31/12/2014 |  | LS | 0.15 | 189402.18 | 28410.327 | 121
2015-01-12 |  | Plants Whitsunday | hr | 57 |  |  | 121
2015-01-12 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 121
2015-01-12 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 121
2015-01-13 |  | Plants Whitsunday | hr | 57 |  |  | 121
2015-01-14 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 121
2015-01-14 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 121
2015-01-28 |  | Plants Whitsunday | hr | 17 |  |  | 121
2015-01-29 |  | Plants Whitsunday | hr | 9 |  |  | 121
2015-01-30 |  | Plants Whitsunday | hr | 14 |  |  | 121
2015-01-31 | Claim for item for 31/01/2015 |  | LS | 0.03 | 189402.18 | 5682.0654 | 121
2015-01-31 | Claim for item for 31/01/2015 |  | LS | 0.25 | 22088.41 | 5522.1025 | 121
2015-01-31 | Claim for item for 31/01/2015 |  | LS | 0.5 | 9436.36 | 4718.18 | 121
2015-01-31 | Claim for item for 31/01/2015 |  | LS | 0.05 | 80346.6 | 4017.33 | 121
2015-01-31 | Claim for item for 31/01/2015 |  | LS | 0.23 | 3820.46 | 878.7058 | 121
2015-01-31 | Claim for item for 31/01/2015 |  | LS | 0.2 | 10227.27 | 2045.454 | 121
2015-02-12 |  | Plants Whitsunday | hr | 22 |  |  | 121
2015-03-31 | Claim for item for 31/03/2015 |  | LS | 0.02 | 189402.18 | 3788.0436 | 121
2015-03-31 | Claim for item for 31/03/2015 |  | LS | 1 | 2704.55 | 2704.55 | 121
2015-03-31 | Claim for item for 31/03/2015 |  | item | 2 | 1272.725 | 2545.45 | 121
2015-03-31 | Claim for item for 31/03/2015 |  | LS | 0.02 | 3820.46 | 76.4092 | 121
2015-03-31 | Claim for item for 31/03/2015 |  | LS | 0.1 | 80346.6 | 8034.66 | 121
| Subtotal for 121 |  |  |  |  | 343303.69
Cost Code 123
2014-08-01 | Supply sample stairs as per quote includes crane hire & materials to extend | Stairs |  | 1 | 2895.45 | 2895.45 | 123
2014-09-30 | Labour and materials supplied to construct 18 Sets of HWD stairs | Stairs |  | 1 | 48954.55 | 48954.55 | 123
2014-10-02 | 10% Deposit on Supply and install 7.5 Mts stainless steel hand railing | Steel Fixing |  | 1 | 940 | 940 | 123
2014-10-10 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 123
2014-10-10 | Labour Hire | Labour | hr | 7 | 39.98 | 279.86 | 123
2014-10-10 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 123
2014-10-10 | Allciv - Labour Hire | Labour | hr | 7 | 35.11 | 245.77 | 123
2014-10-10 | CAT311D - 12T Excavator (No Operator) | CAT311 | hr | 7 | 48 | 336 | 123
2014-10-10 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 123
2014-10-28 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 123
2014-10-28 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 123
2014-10-28 | Claim fo the hire of 14T Excavator | Sewer Subbie |  | 8 | 115 | 920 | 123
2014-10-28 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 123
2014-11-20 | 21 - 30 Multi of 25 - 1850 x 900 x 510 Multibank with sliding flange. Includes stainless steel front & Freight | Multibank |  | 1 | 5750 | 5750 | 123
2014-12-09 | Green Homes Whitsunday - Labour | Green Homes Whitsunday | hr | 17 |  |  | 123
2014-12-10 | Green Homes Whitsunday - Labour | Green Homes Whitsunday | hr | 2.5 |  |  | 123
2014-12-11 | Labour & materials - viewing deck | Green Homes Whitsunday | hr | 1 | 3986.36 | 3986.36 | 123
2014-12-15 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 123
2014-12-18 | Supply & install handrailing for viewing deck | Steel Fixing |  | 1 | 4700 | 4700 | 123
2014-12-18 | Fabricate & install 2 gates incl 52 x rc's | Steel Fixing |  | 1 | 8200 | 8200 | 123
2014-12-18 | Supply 2 steel lintels | Steel Fixing |  | 1 | 1254.55 | 1254.55 | 123
2015-01-09 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 123
2015-01-12 | Silvo Polish and Aquadhere Exterior | Small Tools |  | 1 | 24.89 | 24.89 | 123
2015-01-13 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 123
2015-01-13 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 123
2015-01-14 | Stainless Steel works for Viewing Platform | Steel Fixing |  | 1 | 3760 | 3760 | 123
2015-01-14 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 123
2015-01-14 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 123
2015-01-21 | Lettering to wall at The Cove | Small Signs |  | 1 | 1594 | 1594 | 123
2015-02-26 | Progress Claim for manufacture of both gates. | Steel Fixing |  | 1 | 6867 | 6867 | 123
2015-04-09 | Supply and install 65 Mts fencing panels | Steel Fixing |  | 1 | 16725 | 16725 | 123
| Subtotal for 123 |  |  |  |  | 109537.7
Cost Code 131
2014-08-07 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 131
2014-08-07 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 131
2014-09-02 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 131
2014-10-27 | Plants Whitsunday X 2 | Plants Whitsunday | hr | 16 |  |  | 131
2014-10-31 | Claim for item for 31/10/2014 |  | Item |  | 1050 |  | 131
2014-11-11 | 103 x Knovk outs, 9 x Corner Knock outs and 8 x Halves | Knock Outs |  | 1 | 352.9 | 352.9 | 131
2014-11-12 | 1 Tonne bags of Brickies Loam | Small Tools |  | 1 | 75 | 75 | 131
2014-12-12 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 131
2014-12-15 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 131
2014-12-15 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 131
2014-12-16 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 131
2014-12-16 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 131
2014-12-17 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 131
2014-12-18 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 131
2014-12-19 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 131
2015-02-27 | Supply and install 65 Mts fencing panels | Steel Fixing |  | 1 | 16725 | 16725 | 131
| Subtotal for 131 |  |  |  |  | 18080.5
Cost Code 132
2014-05-08 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 132
2014-05-08 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3.085 | 42.79 | 132.0071 | 132
2014-05-12 |  | Cement - GP Bulk |  | 1 | 712.91 | 712.91 | 132
2014-05-13 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-05-14 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-05-15 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-05-20 | Petrol Water Blaster Hired 20/5/14 - 20/5/14 | Water Blaster |  | 1 | 106.69 | 106.69 | 132
2014-05-21 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-05-21 | Cement GP 20Kg Bag | Cement - GP Bulk |  | 1 | 712.91 | 712.91 | 132
2014-05-22 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-05-23 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 8.5 | 25.78 | 219.13 | 132
2014-05-26 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-05-26 | Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 712.91 | 712.91 | 132
2014-05-27 | New Holland Compact Grader - No Operator | NH Grader | hr | 1 | 25.78 | 25.78 | 132
2014-05-27 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 10 | 25.78 | 257.8 | 132
2014-05-28 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-05-30 | Hire of Excavator | Sewer Subbie |  | 1 | 1092.5 | 1092.5 | 132
2014-05-31 | Claim for item 2712 for 31/05/2014 |  | m2 | 133.5 | 275 | 36712.5 | 132
2014-06-02 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-06-03 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-06-03 | Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 1332.98 | 1332.98 | 132
2014-06-04 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-06-06 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-06-17 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 5 | 25.78 | 128.9 | 132
2014-06-18 | Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 1332.98 | 1332.98 | 132
2014-06-18 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 10 | 25.78 | 257.8 | 132
2014-06-19 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 10 | 25.78 | 257.8 | 132
2014-06-23 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.25 | 25.78 | 238.465 | 132
2014-06-23 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 1292.95 | 1292.95 | 132
2014-06-24 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-06-26 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 686.95 | 686.95 | 132
2014-06-26 | Ivecko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-06-27 | Iveko Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-06-30 | Claim for item SAC01 for 30/06/2014 |  | lm | 292 | 16 | 4672 | 132
2014-06-30 | Claim for item 2712 for 30/06/2014 |  | m2 | 236.04 | 275 | 64911 | 132
2014-06-30 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-06-30 | For Plant Hire used at The Cover Estate at POA | Sewer Subbie |  | 1 | 2715.83 | 2715.83 | 132
2014-07-01 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 132
2014-07-01 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 1332.98 | 1332.98 | 132
2014-07-01 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-07-01 | UD Water Cart - No Driver | UD Water Cart | hr | 4.5 | 21.61 | 97.245 | 132
2014-07-02 | Delivery of Conduit for weepholes at rear of stone wall | Small Tools |  | 1 | 22.73 | 22.73 | 132
2014-07-03 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 132
2014-07-03 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 5 | 25.78 | 128.9 | 132
2014-07-04 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-07-05 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 4 | 25.78 | 103.12 | 132
2014-07-07 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-07-08 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-07-08 | Rock Mason | Rock Mason |  | 66.5 |  |  | 132
2014-07-08 | Foamjoint Expansion | Small Tools |  | 1 | 142.82 | 142.82 | 132
2014-07-09 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 810 | 810 | 132
2014-07-09 | Rock Mason (5) | Rock Mason |  | 42.5 |  |  | 132
2014-07-09 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 8.5 | 25.78 | 219.13 | 132
2014-07-10 | Rock Mason | Rock Mason |  | 56 |  |  | 132
2014-07-11 | Rock Mason (7) | Rock Mason |  | 52.5 |  |  | 132
2014-07-11 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 7.5 | 25.78 | 193.35 | 132
2014-07-12 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 4.5 | 25.78 | 116.01 | 132
2014-07-12 | Water Cart Allciv - No Operator | WC - Allciv | hr | 4.5 | 42.79 | 192.555 | 132
2014-07-12 | Rock Mason (2) | Rock Mason |  | 9 |  |  | 132
2014-07-14 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 8 | 25.78 | 206.24 | 132
2014-07-14 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 132
2014-07-14 | Water Cart Allciv - No Operator | WC - Allciv | hr | 4.5 | 42.79 | 192.555 | 132
2014-07-14 | Rock Mason (2) | Rock Mason |  | 24 |  |  | 132
2014-07-14 | Water Cart Allciv - No Operator | WC - Allciv | hr | 4.5 | 42.79 | 192.555 | 132
2014-07-14 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 522.98 | 522.98 | 132
2014-07-16 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-07-16 | Water Cart Allciv - No Operator | WC - Allciv | hr | 4.5 | 42.79 | 192.555 | 132
2014-07-16 | Allciv - Labour HIre | Labour | hr | 4.5 | 42.72 | 192.24 | 132
2014-07-16 | Water Cart Allciv - No Operator | WC - Allciv | hr | 2 | 42.79 | 85.58 | 132
2014-07-16 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 686.95 | 686.95 | 132
2014-07-17 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-07-17 | Whitsunday Drainage Contractors | WDC | Item | 4 |  |  | 132
2014-07-21 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 132
2014-07-21 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 646.04 | 646.04 | 132
2014-07-21 | Whitsunday Drainage Contractors | WDC | hr | 2 |  |  | 132
2014-07-21 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 132
2014-07-21 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-07-22 | UD Water Cart - No Driver | UD Water Cart | hr | 1 | 21.61 | 21.61 | 132
2014-07-22 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-07-22 | Whitsunday Drainage Contractors | WDC | Item | 2 |  |  | 132
2014-07-22 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 1332.98 | 1332.98 | 132
2014-07-22 | Rock MasonX 7 | Rock Mason |  | 66.5 |  |  | 132
2014-07-22 | Allciv - Labour HIre | Labour | hr | 1 | 42.72 | 42.72 | 132
2014-07-23 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 1332.98 | 1332.98 | 132
2014-07-23 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-07-23 | Allciv - Labour HIre | Labour | hr | 1 | 42.72 | 42.72 | 132
2014-07-23 | Whitsunday Drainage Contractors | WDC | Item | 1 |  |  | 132
2014-07-23 | Rock MasonX 7 | Rock Mason |  | 76 |  |  | 132
2014-07-23 | Whitsunday Drainage Contractors | WDC | hr | 2.5 |  |  | 132
2014-07-24 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 132
2014-07-24 | Whitsunday Drainage Contractors | WDC | hr | 2.5 |  |  | 132
2014-07-24 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 132
2014-07-24 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 132
2014-07-24 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9.5 | 25.78 | 244.91 | 132
2014-07-24 | Hire of Labour | Labour | hr | 1 | 38.45 | 38.45 | 132
2014-07-24 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 132
2014-07-24 | Water Cart Allciv - No Operator | WC - Allciv | hr | 1 | 42.79 | 42.79 | 132
2014-07-24 | Rock Mason x 8 | Rock Mason |  | 80 |  |  | 132
2014-07-25 | Water Cart Allciv - No Operator | WC - Allciv | hr | 1 | 42.79 | 42.79 | 132
2014-07-25 | Rock Mason x 8 | Rock Mason |  | 60 |  |  | 132
2014-07-25 | Whitsunday Drainage Contractors | WDC | hr | 5.5 |  |  | 132
2014-07-25 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 8 | 25.78 | 206.24 | 132
2014-07-26 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 132
2014-07-26 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 8 | 25.78 | 206.24 | 132
2014-07-26 | Rock Mason x 4 | Rock Mason |  | 14 |  |  | 132
2014-07-26 | Water Cart Allciv - No Operator | WC - Allciv | hr | 1 | 42.79 | 42.79 | 132
2014-07-28 | New Holland Compact Grader - No Operator | NH Grader | hr | 10 | 25.78 | 257.8 | 132
2014-07-28 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 10 | 25.78 | 257.8 | 132
2014-07-28 | Rock Mason x 4 | Rock Mason |  | 14 |  |  | 132
2014-07-28 | Whitsunday Drainage Contractors | WDC | Item | 5.5 |  |  | 132
2014-07-28 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 132
2014-07-28 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 132
2014-07-28 | Hire of Labour | Labour | hr | 8 | 38.45 | 307.6 | 132
2014-07-29 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 7.5 | 25.78 | 193.35 | 132
2014-07-29 | New Holland Compact Grader - No Operator | NH Grader | hr | 7.5 | 25.78 | 193.35 | 132
2014-07-29 | Rock Mason x 4 | Rock Mason |  | 28 |  |  | 132
2014-07-29 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 132
2014-07-29 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 132
2014-07-29 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 132
2014-07-30 | Rock Mason x 4 | Rock Mason |  | 20 |  |  | 132
2014-07-30 | New Holland Compact Grader - No Operator | NH Grader | hr | 5.5 | 25.78 | 141.79 | 132
2014-07-30 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 5.5 | 25.78 | 141.79 | 132
2014-07-30 | Claim for machine hire used at The cove | Sewer Subbie |  | 13.5 | 115 | 1552.5 | 132
2014-07-30 | Claim for machine hire used at The cove | Sewer Subbie |  | 14.5 | 125 | 1812.5 | 132
2014-07-31 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 132
2014-07-31 | Hire of Labour | Labour | hr | 8.5 | 38.45 | 326.825 | 132
2014-07-31 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 132
2014-07-31 | Claim for item 2712 for 31/07/2014 |  | m2 | 367.645 | 275 | 101102.375 | 132
2014-07-31 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 132
2014-07-31 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 132
2014-08-01 | Allciv - Labour HIre | Labour | hr | 2.5 | 42.72 | 106.8 | 132
2014-08-01 | Whitsunday Drainage Contractors - Excavator | WDC | Item | 8 |  |  | 132
2014-08-01 | Hire of Labour O/T1 Week Ending 3/8/14 | Labour | hr | 9 | 52.08 | 468.72 | 132
2014-08-01 | Hire of Labour | Labour | hr | 8 | 38.45 | 307.6 | 132
2014-08-01 | Rock Mason | Rock Mason |  | 22 |  |  | 132
2014-08-04 | Whitsunday Drainage Contractors | WDC | Item | 1 |  |  | 132
2014-08-04 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 132
2014-08-04 | Rock Mason | Rock Mason |  | 22 |  |  | 132
2014-08-05 | Rock Mason | Rock Mason | hr | 21 |  |  | 132
2014-08-05 | Allciv - Labour HIre | Labour | hr | 2 | 35.11 | 70.22 | 132
2014-08-05 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 7 | 25.78 | 180.46 | 132
2014-08-06 | Rock Mason | Rock Mason | hr | 25.5 |  |  | 132
2014-08-06 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 8.5 | 25.78 | 219.13 | 132
2014-08-07 | Rock Mason | Rock Mason | hr | 4 |  |  | 132
2014-08-07 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 4 | 25.78 | 103.12 | 132
2014-08-07 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 132
2014-08-08 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 9 | 25.78 | 232.02 | 132
2014-08-08 | UD Water Cart - No Driver | UD Water Cart | hr | 1.5 | 21.61 | 32.415 | 132
2014-08-08 | Rock Mason | Rock Mason | hr | 4 |  |  | 132
2014-08-08 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 132
2014-08-08 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 132
2014-08-08 | Allciv - Labour HIre | Labour | hr | 2.5 | 35.11 | 87.775 | 132
2014-08-08 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 132
2014-08-11 | Loader | Loader | hr | 2 | 145 | 290 | 132
2014-08-11 | UD Water Cart - No Driver | UD Water Cart | hr | 7.5 | 21.61 | 162.075 | 132
2014-08-11 | Pallet Cement GP 20Kg Bag and Delivery | Cement - GP Bulk |  | 1 | 686.95 | 686.95 | 132
2014-08-11 | Rock Mason | Rock Mason | hr | 22.5 |  |  | 132
2014-08-11 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 132
2014-08-11 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 132
2014-08-11 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 132
2014-08-11 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 132
2014-08-12 | Rock Mason | Rock Mason | hr | 25.5 |  |  | 132
2014-08-12 | UD Water Cart - No Driver | UD Water Cart | hr | 8.5 | 21.61 | 183.685 | 132
2014-08-13 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 132
2014-08-13 | Rock Mason | Rock Mason | hr | 16.5 |  |  | 132
2014-08-13 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 132
2014-08-13 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 132
2014-08-14 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 132
2014-08-14 | UD Water Cart - No Driver | UD Water Cart | hr | 6.5 | 21.61 | 140.465 | 132
2014-08-14 | Rock Mason | Rock Mason | hr | 13 |  |  | 132
2014-08-14 | Allciv - Labour HIre | Labour | hr | 2.5 | 35.11 | 87.775 | 132
2014-08-14 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 132
2014-08-14 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 132
2014-08-14 | Labour Hire | Labour | hr | 7 | 39.98 | 279.86 | 132
2014-08-18 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 132
2014-08-18 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 132
2014-08-21 | UD Water Cart - No Driver | UD Water Cart | hr | 6 | 21.61 | 129.66 | 132
2014-08-25 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 132
2014-08-26 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 132
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 24 | 125 | 3000 | 132
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 3 | 115 | 345 | 132
2014-08-26 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 132
2014-08-26 | Rock Mason | Stone Mason |  | 6.5 |  |  | 132
2014-08-26 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 132
2014-08-26 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 132
2014-08-27 | CAT297 Stabiliser - No operator | CAT297 Stabiliser | hr | 3 | 66.07 | 198.21 | 132
2014-08-27 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 132
2014-08-28 | Allciv - Labour Hire | Labour | hr | 4.5 | 35.11 | 157.995 | 132
2014-08-28 | Water Cart Allciv - No Operator | WC - Allciv | hr | 8.5 | 42.79 | 363.715 | 132
2014-08-28 | Rock Mason | Stone Mason |  | 22.35 |  |  | 132
2014-08-29 | Rock Mason | Stone Mason |  | 25.5 |  |  | 132
2014-08-31 | Construction of Stone Work for viewing platform 29.1 Square M | Rock Mason |  | 1 | 7275 | 7275 | 132
2014-08-31 | Remainder of cost for forming up wall | Rock Mason |  | 1 | 4247.27 | 4247.27 | 132
2014-09-02 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 132
2014-09-02 | Whitsunday Drainage Contractors | WDC | Item | 2.5 |  |  | 132
2014-09-02 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 132
2014-09-02 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 132
2014-09-03 | Whitsunday Drainage Contractors | WDC | Item | 1.5 |  |  | 132
2014-09-04 | Side Boundary retaining wall and Front stone wall | Stone Mason |  | 4 |  |  | 132
2014-09-30 | Claim for 24T Excavator at the Cove Sub-Division | Sewer Subbie |  | 2.5 | 125 | 312.5 | 132
2014-11-01 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 132
2014-11-01 | Water Cart Allciv - No Operator | WC - Allciv | hr | 1 | 42.79 | 42.79 | 132
2014-11-11 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 132
2014-11-11 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 132
2014-11-12 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 132
2014-11-13 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 132
2014-11-14 | Allciv - Leading Hand | Labour | Hr | 0.05 | 54.58 | 2.729 | 132
2014-11-24 | Stone Entrance, Stone Pedestrian, Stone Letterbox recess | Rock Mason |  | 1 | 22959.2 | 22959.2 | 132
2014-11-25 | 15L Polymer Render | Paint |  | 1 | 269.73 | 269.73 | 132
2014-11-25 | Dingo Cement 20Kg & Delivery | Small Tools |  | 1 | 477.27 | 477.27 | 132
2014-11-27 | 86 x 20Kg Bags of Cement and Delivery | Small Tools |  | 1 | 770.69 | 770.69 | 132
2014-11-30 | Claim for item for 30/11/2014 |  | hr | 18 | 65 | 1170 | 132
2014-12-01 | Stone letterbox header | Rock Mason |  | 1 | 670.45 | 670.45 | 132
2014-12-01 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 132
2014-12-02 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 132
2014-12-02 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 132
2014-12-03 | 3 x Foamjoint Expansion | Small Tools |  | 1 | 154.09 | 154.09 | 132
2014-12-04 | 15L Polymer Render | Paint |  | 1 | 89.98 | 89.98 | 132
2014-12-16 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 132
2014-12-16 | Allciv - Labour Hire | Labour | hr | 7 | 35.11 | 245.77 | 132
2014-12-17 | Skim Coat Blocks | Retaining Walls |  | 1 | 180 | 180 | 132
2014-12-17 | Solagard15lt | Paint |  | 1 | 180.86 | 180.86 | 132
2014-12-17 | Skim Coat Blocks as required at Port of Airlie Labour and Materials | Small Tools |  | 1 | 180 | 180 | 132
2014-12-18 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 132
2015-01-09 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 132
2015-02-02 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 132
2015-02-02 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 132
2015-03-13 | Stone Pillars and Stone Walls | Rock Mason |  | 1 | 27020.09 | 27020.09 | 132
| Subtotal for 132 |  |  |  |  | 322580.1561
Cost Code 135
2014-04-28 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 135
2014-04-28 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 135
2014-04-29 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-04-30 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.11 | 122.885 | 135
2014-04-30 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 135
2014-04-30 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-04-30 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-04-30 | Pad Foot Roller - Dry Hired 29/4/14 - 30/4/14 | PF Roller |  | 1 | 689 | 689 | 135
2014-05-01 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 135
2014-05-01 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-05-01 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 135
2014-05-01 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 135
2014-05-07 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-05-07 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 135
2014-05-07 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 135
2014-05-07 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 135
2014-05-08 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 135
2014-05-08 | Labour Hire | Labour | hr | 7.5 | 39.98 | 299.85 | 135
2014-05-08 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 135
2014-05-08 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 135
2014-05-08 | Allciv - Leading Hand | Labour | Hr | 8.5 | 54.58 | 463.93 | 135
2014-05-08 | Pad Foot Roller - Dry hired from 30/4/14 - 7/5/14 | PF Roller |  | 1 | 1602.5 | 1602.5 | 135
2014-05-09 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 135
2014-05-09 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 135
2014-05-09 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 135
2014-05-10 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 135
2014-05-10 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 135
2014-05-10 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 135
2014-05-10 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 135
2014-05-12 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-05-12 | Allciv - Labour HIre | Labour | hr | 7 | 42.72 | 299.04 | 135
2014-05-13 | Allciv - Leading Hand | Labour | Hr | 8.5 | 54.58 | 463.93 | 135
2014-05-13 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-05-13 | Allciv - Labour HIre | Labour | hr | 7 | 42.72 | 299.04 | 135
2014-05-14 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 135
2014-05-14 | Allciv - Labour HIre | Labour | hr | 8 | 42.72 | 341.76 | 135
2014-05-14 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 135
2014-05-15 | Vibrating Rammer hired 5/5/14 - 15/5/14 | Vibrating |  | 1 | 551.84 | 551.84 | 135
2014-05-15 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 135
2014-05-16 | Allciv - Leading Hand | Labour | Hr | 7.5 | 54.58 | 409.35 | 135
2014-05-19 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 135
2014-05-19 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 135
2014-05-19 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 135
2014-05-20 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 135
2014-05-20 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 135
2014-05-20 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 135
2014-05-21 | Labour Hire | Labour | hr | 5.5 | 39.98 | 219.89 | 135
2014-05-21 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 135
2014-05-21 | Hire of Labour Week Ending 18/5/14 | Labour |  | 9.5 | 38.45 | 365.275 | 135
2014-05-21 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 135
2014-05-21 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 135
2014-05-22 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-05-22 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-05-22 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 135
2014-05-23 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 135
2014-05-23 | New Holland Compact Grader - No Operator | NH Grader | hr | 3 | 25.78 | 77.34 | 135
2014-05-23 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 135
2014-05-23 | Allciv - Labour HIre | Labour | hr | 9 | 42.72 | 384.48 | 135
2014-05-24 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 135
2014-05-24 | Hire of Labour 16 Hrs Hourly, 3 OT and4 DT | Labour | hr | 1 | 1049.2 | 1049.2 | 135
2014-05-24 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 135
2014-05-26 | Allciv - Leading Hand | Labour | Hr | 4.5 | 54.58 | 245.61 | 135
2014-05-26 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-05-26 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 135
2014-05-26 | Allciv - Labour HIre | Labour | hr | 8 | 42.72 | 341.76 | 135
2014-05-26 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-05-27 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 135
2014-05-27 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-05-27 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-05-28 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 135
2014-05-28 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 135
2014-05-28 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 135
2014-05-30 | Hire of Excavator | Sewer Subbie |  | 1 | 5775 | 5775 | 135
2014-06-03 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 135
2014-06-05 | Backhoe - Wet Hire | Back Hoe | hr | 5.25 | 110 | 577.5 | 135
2014-06-06 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-06-16 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 135
2014-06-16 | Hire of Labour | Labour | hr | 9 | 38.45 | 346.05 | 135
2014-06-16 | Allciv - Labour Hire | Labour | hr | 9.5 | 35.11 | 333.545 | 135
2014-06-16 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-06-16 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-06-17 | Labour Hire | Labour | hr | 5.5 | 39.98 | 219.89 | 135
2014-06-17 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-06-17 | Allciv - Labour HIre | Labour | hr | 5.5 | 42.72 | 234.96 | 135
2014-06-17 | Allciv - Labour Hire | Labour | hr | 5.5 | 35.11 | 193.105 | 135
2014-06-17 | Hire of Labour | Labour | hr | 5.5 | 38.45 | 211.475 | 135
2014-06-18 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 135
2014-06-18 | Allciv - Leading Hand | Labour | Hr | 5.5 | 54.58 | 300.19 | 135
2014-06-18 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 135
2014-06-18 | 120H Grader | 120H Grader | hr | 1 | 120 | 120 | 135
2014-06-18 | Hire of Labour | Labour | hr | 8.5 | 38.45 | 326.825 | 135
2014-06-18 | Allciv - Labour HIre | Labour | hr | 9.5 | 42.72 | 405.84 | 135
2014-06-19 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 135
2014-06-19 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 135
2014-06-19 | Hire of Labour | Labour | hr | 6.5 | 38.45 | 249.925 | 135
2014-06-19 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 135
2014-06-23 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 135
2014-06-23 | Hire of Labour | Labour | hr | 3.5 | 38.45 | 134.575 | 135
2014-06-23 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.11 | 122.885 | 135
2014-06-23 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 135
2014-06-24 | Hire of Labour | Labour | hr | 3 | 38.45 | 115.35 | 135
2014-06-24 | Labour Hire | Labour | hr | 5.5 | 39.98 | 219.89 | 135
2014-06-24 | Allciv - Leading Hand | Labour | Hr | 9.5 | 54.58 | 518.51 | 135
2014-06-26 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 135
2014-06-26 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-06-26 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 135
2014-06-26 | Hire of Labour | Labour | hr | 9.5 | 38.45 | 365.275 | 135
2014-06-26 | Allciv - Labour HIre | Labour | hr | 6.5 | 42.72 | 277.68 | 135
2014-06-27 | Hire of Labour 5x O/T1 Hours &5 x O/T2 Week Ending 22/6/14 | Labour | hr | 1 | 607 | 667 | 135
2014-06-27 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 135
2014-06-27 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 135
2014-06-28 | Allciv - Labour HIre | Labour | hr | 6 | 42.72 | 256.32 | 135
2014-06-28 | Hire of Labour | Labour | hr | 6 | 38.45 | 230.7 | 135
2014-06-28 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-06-28 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 135
2014-06-30 | For Plant Hire used at The Cover Estate at POA | Sewer Subbie |  | 1 | 2715.83 | 2715.83 | 135
2014-06-30 | Allciv - Labour HIre | Labour | hr | 3 | 42.72 | 128.16 | 135
2014-06-30 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 135
2014-06-30 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 135
2014-07-01 | Labour Hire | Labour | hr | 3.5 | 39.98 | 139.93 | 135
2014-07-01 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-07-01 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 135
2014-07-03 | Allciv - Labour HIre | Labour | hr | 4 | 42.72 | 170.88 | 135
2014-07-03 | Hire of Labour | Labour | hr | 2 | 38.45 | 76.9 | 135
2014-07-03 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 135
2014-07-03 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 135
2014-07-04 | Hire of Labour | Labour | hr | 6 | 38.45 | 230.7 | 135
2014-07-04 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-07-04 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 135
2014-07-09 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 135
2014-07-09 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 135
2014-07-14 | Whitsunday Drainage Contractors | WDC | Item | 5.5 |  |  | 135
2014-07-14 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 135
2014-07-14 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 135
2014-07-16 | Hire of Labour | Labour | hr | 4 | 38.45 | 153.8 | 135
2014-07-16 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 135
2014-07-17 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 135
2014-07-17 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 135
2014-07-17 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 135
2014-07-21 | Hire of Labour | Labour | hr | 8 | 38.45 | 307.6 | 135
2014-07-21 | Whitsunday Drainage Contractors | WDC | hr | 2.5 |  |  | 135
2014-07-21 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 135
2014-07-21 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 135
2014-07-22 | Whitsunday Drainage Contractors | WDC | Item | 2.5 |  |  | 135
2014-07-23 | Whitsunday Drainage Contractors | WDC | Item | 2.5 |  |  | 135
2014-07-23 | Whitsunday Drainage Contractors | WDC | hr | 1 |  |  | 135
2014-07-23 | Allciv - Labour Hire | Labour | hr | 7 | 35.11 | 245.77 | 135
2014-07-23 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 135
2014-07-24 | Whitsunday Drainage Contractors | WDC | Item | 15 |  |  | 135
2014-07-24 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 135
2014-07-25 | Whitsunday Drainage Contractors | WDC | hr | 4 |  |  | 135
2014-07-25 | Whitsunday Drainage Contractors | WDC | Item | 15 |  |  | 135
2014-07-25 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 135
2014-07-25 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 135
2014-07-26 | Hire of Labour 3.8 O/T1 Hours & 2.25x O/T2 Week Ending 27/7/14 | Labour | hr | 1 | 353.89 | 413.89 | 135
2014-07-26 | Allciv - Leading Hand | Labour | Hr | 6.5 | 54.58 | 354.77 | 135
2014-07-26 | Whitsunday Drainage Contractors | WDC | Item | 15 |  |  | 135
2014-07-28 | Whitsunday Drainage Contractors | WDC | Item | 4 |  |  | 135
2014-07-28 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 135
2014-07-28 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 135
2014-07-28 | Hire of Labour | Labour | hr | 2 | 38.45 | 76.9 | 135
2014-07-29 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 135
2014-07-29 | Hire of Labour | Labour | hr | 3.5 | 38.45 | 134.575 | 135
2014-07-29 | Whitsunday Drainage Contractors | WDC | Item | 2 |  |  | 135
2014-07-30 | Claim for machine hire used at The cove | Sewer Subbie |  | 7 | 125 | 875 | 135
2014-07-30 | For Plant Hire used at The Cover Estate at POA | Sewer Subbie |  | 5.5 | 105 | 577.5 | 135
2014-07-30 | Allciv - Labour HIre | Labour | hr | 1.5 | 42.72 | 64.08 | 135
2014-07-30 | Hire of Labour | Labour | hr | 1.5 | 38.45 | 57.675 | 135
2014-08-04 | Whitsunday Drainage Contractors - Excavator | WDC | Item | 1.5 |  |  | 135
2014-08-04 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 135
2014-08-04 | Allciv - Labour HIre | Labour | hr | 1 | 35.11 | 35.11 | 135
2014-08-05 | Hire of Labour | Labour | hr | 8 | 38.45 | 307.6 | 135
2014-08-05 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 135
2014-08-05 | Whitsunday Drainage Contractors - Excavator | WDC | Item |  |  |  | 135
2014-08-05 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 135
2014-08-05 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 135
2014-08-05 | Allciv - Labour HIre | Labour | hr | 1 | 35.11 | 35.11 | 135
2014-08-05 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 135
2014-08-05 | Allciv - Labour HIre | Labour | hr | 5 | 42.72 | 213.6 | 135
2014-08-06 | Hire of Labour | Labour | hr | 3 | 38.45 | 115.35 | 135
2014-08-06 | UD Water Cart - No Driver | UD Water Cart | hr | 5 | 21.61 | 108.05 | 135
2014-08-07 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 135
2014-08-07 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 135
2014-08-08 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 135
2014-08-11 | Loader | Loader | hr | 2 | 145 | 290 | 135
2014-08-11 | Allciv - Leading Hand | Labour | Hr | 0.5 | 54.58 | 27.29 | 135
2014-08-11 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 135
2014-08-11 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 2 | 25.78 | 51.56 | 135
2014-08-11 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 135
2014-08-20 | Whitsunday Drainage Contractors - Excavator | WDC | Item | 8.5 |  |  | 135
2014-08-21 | Whitsunday Drainage Contractors - Excavator | WDC | Item | 9.5 |  |  | 135
2014-08-22 | Whitsunday Drainage Contractors - Excavator | WDC | Item | 8.5 |  |  | 135
2014-08-23 | Whitsunday Drainage Contractors - Excavator | WDC | Item | 6 |  |  | 135
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 9 | 125 | 1125 | 135
2014-08-28 | Labour Hire | Labour | hr | 4.5 | 39.98 | 179.91 | 135
2014-08-28 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 135
2014-09-08 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 135
2014-09-08 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 135
2014-09-15 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 135
2014-09-15 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 135
2014-10-20 | Mini Excavator Hire & Auger | Excavator - 5T | hr | 2.5 | 115 | 287.5 | 135
2014-10-20 | 5T Excavator Hire | Excavator - 5T | hr | 3.5 | 100 | 350 | 135
2014-10-20 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 135
2014-10-21 | 5T Excavator Hire & Auger | Excavator - 5T | hr | 2 | 115 | 230 | 135
2014-10-21 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 135
2014-10-21 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 135
2014-10-21 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 135
2014-10-21 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 135
2014-10-22 | UD Water Cart - No Driver | UD Water Cart | hr | 3.5 | 21.61 | 75.635 | 135
2014-10-22 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 135
2014-10-22 | Allciv - Leading Hand | Labour | Hr | 6.5 | 54.58 | 354.77 | 135
2014-10-22 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 135
2014-10-23 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 135
2014-10-23 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 135
2014-10-24 | Allciv - Labour Hire | Labour | hr | 4 | 35.11 | 140.44 | 135
2014-10-24 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 135
2014-10-24 | Labour Hire | Labour | hr | 4 | 39.98 | 159.92 | 135
2014-10-30 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 135
2014-10-30 | Allciv - Labour Hire | Labour | hr | 7.5 | 35.11 | 263.325 | 135
2014-10-30 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 135
2014-10-30 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 135
2014-10-31 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 135
2014-10-31 | 5T Excavator Hire | Excavator - 5T | hr | 8.5 | 105 | 892.5 | 135
2014-10-31 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 135
2014-11-01 | Rock Mason | Rock Mason |  | 22.5 |  |  | 135
2014-11-03 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 135
2014-11-11 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 135
2014-11-11 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 135
2014-11-11 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 135
2015-01-12 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 135
2015-01-12 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 135
2015-01-14 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 135
2015-01-14 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 135
2015-01-16 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 135
2015-01-16 | Labour Hire | Labour | hr | 5 | 39.98 | 199.9 | 135
2015-01-19 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 135
2015-01-19 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 135
2015-01-22 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 135
2015-01-22 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 135
2015-01-22 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 135
2015-02-18 | Rock Mason | Rock Mason |  | 8 |  |  | 135
| Subtotal for 135 |  |  |  |  | 62335.54
Cost Code 151
2014-03-28 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 151
2014-03-28 | Allciv - Plant Operator | Labour | Hr | 1 | 51.54 | 51.54 | 151
2014-05-05 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 151
2014-05-15 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 151
2014-05-15 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 151
2014-05-15 | Allciv - Labour Hire | Labour | hr | 1.5 | 35.11 | 52.665 | 151
2014-05-16 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 151
2014-05-19 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 151
2014-05-19 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 151
2014-05-20 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 151
2014-05-20 | Allciv - Leading Hand | Labour | Hr | 5 | 54.58 | 272.9 | 151
2014-05-20 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 151
2014-06-11 | Allciv - Labour Hire | Labour | hr | 2 | 35.11 | 70.22 | 151
2014-06-11 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 151
2014-06-11 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 151
2014-08-13 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 151
2014-08-13 | Allciv - Leading Hand | Labour | Hr | 5.5 | 54.58 | 300.19 | 151
2014-08-13 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 151
2014-08-26 | Claim for the Supply of a 24Tonne Excavator. | Sewer Subbie |  | 2.5 | 105 | 262.5 | 151
2015-01-05 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 151
2015-01-06 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 151
2015-01-08 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 151
| Subtotal for 151 |  |  |  |  | 3567.895
Cost Code 152
2014-07-30 | Claim for machine hire used at The cove | Sewer Subbie |  | 7 | 125 | 875 | 152
| Subtotal for 152 |  |  |  |  | 875
Cost Code 222
2014-06-03 | Hire of Labour | Labour | hr | 2 | 38.45 | 76.9 | 222
| Subtotal for 222 |  |  |  |  | 76.9
Cost Code 901
2014-03-02 | - Tech Officer Week Ending 2/3 | Technical Officer |  | 2 | 46 |  | 901
2014-03-09 | - Tech Officer Week Ending 9/3 | Technical Officer |  | 4 | 46 |  | 901
2014-03-16 | Hourly Rate - Project Manager Week Ending 16/3/14 | Project Manager |  | 2 | 106.25 | 212.5 | 901
2014-03-16 | - Tech Officer Week Ending 16/3 | Technical Officer |  | 2 | 46 |  | 901
2014-03-23 | Hourly Rate - Project Manager Week Ending 23/3/14 | Project Manager |  | 1.5 | 106.25 | 159.375 | 901
2014-03-30 | - Tech Officer 30/4/14 | Technical Officer |  |  | 46 |  | 901
2014-04-06 | - Tech Officer 6/4/14 | Technical Officer |  | 5.5 | 46 | 253 | 901
2014-04-13 | - Tech Officer 13/4/14 | Technical Officer |  | 6.5 | 46 | 299 | 901
2014-04-20 | - Tech Officer 20/4/14 | Technical Officer |  | 7 | 46 | 322 | 901
2014-05-11 | - Tech Officer 11/5/14 | Technical Officer |  | 16.5 | 46 | 759 | 901
2014-05-18 | - Tech Officer 18/5/14 | Technical Officer |  | 25.5 | 46 | 1173 | 901
2014-05-25 | - Tech Officer | Technical Officer |  | 13 | 46 | 598 | 901
2014-06-01 | - Tech Officer | Technical Officer |  | 8 | 46 | 368 | 901
2014-06-15 | - Tech Officer Fortnight Ending 15/6/14 | Technical Officer |  | 31 | 46 | 1426 | 901
2014-06-29 | - Tech Officer Fortnight Ending 29/6/14 | Technical Officer |  | 27 | 46 | 1242 | 901
2014-07-13 | - Tech Officer Fortnight Ending 13/7/14 | Technical Officer |  | 23.5 | 46 | 1081 | 901
2014-08-10 | - Tech Officer Fortnight Ending 10/8/14 | Technical Officer |  | 21.5 | 46 | 989 | 901
2014-08-24 | - Tech Officer Fortnight Ending 24/8/14 | Technical Officer |  | 18.5 | 46 | 851 | 901
2014-09-07 | - Tech Officer Fortnight Ending 7/9/14 | Technical Officer |  | 45 | 46 | 2070 | 901
2014-09-21 | - Tech Officer Fortnight Ending 21/9/14 | Technical Officer |  | 51.5 | 46 | 2369 | 901
2014-10-19 | - Tech Officer Fortnight Ending 19/10/14 | Technical Officer |  | 52 | 46 | 2392 | 901
2014-11-02 | - Tech Officer Fortnight Ending 2/11/14 | Technical Officer |  | 51 | 46 | 2346 | 901
2014-11-16 | - Tech Officer Fortnight Ending 16/11/14 | Technical Officer |  | 37 | 46 | 1702 | 901
2014-11-30 | - Tech Officer Fortnight Ending 30/11/14 | Technical Officer |  | 59 | 46 | 2714 | 901
2014-12-14 | - Tech Officer Fortnight Ending 14/11/14 | Technical Officer |  | 58.5 | 46 | 2691 | 901
2014-12-28 | - Tech Officer Fortnight Ending 28/12/14 | Technical Officer |  | 7 | 46 | 322 | 901
2015-01-11 | - Tech Officer Fortnight Ending 11/1/15 | Technical Officer |  | 4 | 46 | 184 | 901
2015-01-25 | - Tech Officer Fortnight Ending 25/1/15 | Technical Officer |  | 1 | 46 | 46 | 901
2015-02-01 | - Tech Officer Fortnight Ending 25/1/15 | Technical Officer |  | 4 | 46 | 184 | 901
2015-02-08 | - Tech Officer Fortnight Ending 8/2/15 | Technical Officer |  | 4 | 46 | 184 | 901
2015-02-22 | - Tech Officer Fortnight Ending 22/2/15 | Technical Officer |  | 6 | 46 | 276 | 901
2015-03-08 | - Tech Officer Fortnight Ending 8/3/15 | Technical Officer |  | 9.5 | 46 | 437 | 901
2015-03-22 | - Tech Officer Fortnight Ending 22/3/15 | Technical Officer |  | 7 | 46 | 322 | 901
2015-05-03 | - Tech Officer Fortnight Ending 3/5/15 | Technical Officer |  | 1.5 | 46 | 69 | 901
| Subtotal for 901 |  |  |  |  | 28040.875
Cost Code 902
2014-03-28 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-04-28 | Allciv-Supervisor | Supervisor | hr | 2 | 71.8 | 143.6 | 902
2014-04-29 | Allciv-Supervisor | Supervisor | hr | 2 | 71.8 | 143.6 | 902
2014-04-30 | Allciv-Supervisor | Supervisor | hr | 2 | 71.8 | 143.6 | 902
2014-05-01 | Allciv-Supervisor | Supervisor | hr | 6.5 | 71.8 | 466.7 | 902
2014-05-02 | Allciv-Supervisor | Supervisor | hr | 2 | 71.8 | 143.6 | 902
2014-05-07 | Allciv-Supervisor | Supervisor | hr | 8.5 | 71.8 | 610.3 | 902
2014-05-08 | Allciv-Supervisor | Supervisor | hr | 8.5 | 71.8 | 610.3 | 902
2014-05-09 | Allciv-Supervisor | Supervisor | hr | 4.5 | 71.8 | 323.1 | 902
2014-05-10 | Allciv-Supervisor | Supervisor | hr | 2 | 71.8 | 143.6 | 902
2014-05-12 | Allciv-Supervisor | Supervisor | hr | 6 | 71.8 | 430.8 | 902
2014-05-13 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-14 | Allciv-Supervisor | Supervisor | hr | 8 | 71.8 | 574.4 | 902
2014-05-15 | Allciv-Supervisor | Supervisor | hr | 2 | 88.74 | 177.48 | 902
2014-05-16 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-19 | Allciv-Supervisor | Supervisor | hr | 4 | 71.8 | 287.2 | 902
2014-05-20 | Allciv-Supervisor | Supervisor | hr | 9 | 71.8 | 646.2 | 902
2014-05-21 | Allciv-Supervisor | Supervisor | hr | 8.5 | 71.8 | 610.3 | 902
2014-05-22 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-23 | Allciv-Supervisor | Supervisor | hr | 4.5 | 71.8 | 323.1 | 902
2014-05-24 | Allciv-Supervisor | Supervisor | hr | 3 | 71.8 | 215.4 | 902
2014-05-26 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-27 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-28 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-29 | Allciv-Supervisor | Supervisor | hr | 5 | 71.8 | 359 | 902
2014-05-30 | Allciv-Supervisor | Supervisor | hr | 3 | 71.8 | 215.4 | 902
2014-06-02 | Allciv-Supervisor | Supervisor | hr | 4.5 | 71.8 | 323.1 | 902
2014-06-03 | Allciv-Supervisor | Supervisor | hr | 4.5 | 71.8 | 323.1 | 902
2014-06-04 | Allciv-Supervisor | Supervisor | hr | 4.5 | 71.8 | 323.1 | 902
2014-06-06 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 902
2014-06-11 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2014-06-16 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-06-17 | Allciv-Supervisor | Supervisor | hr | 5.5 | 88.74 | 488.07 | 902
2014-06-18 | Allciv-Supervisor | Supervisor | hr | 5.5 | 88.74 | 488.07 | 902
2014-06-19 | Allciv-Supervisor | Supervisor | hr | 5.5 | 88.74 | 488.07 | 902
2014-06-23 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 902
2014-06-24 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 902
2014-06-26 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 902
2014-06-27 | Allciv-Supervisor | Supervisor | hr | 2.5 | 88.74 | 221.85 | 902
2014-06-28 | Allciv-Supervisor | Supervisor | hr | 3 | 88.74 | 266.22 | 902
2014-06-30 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-07-01 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 902
2014-07-02 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-07-03 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-07-04 | Allciv-Supervisor | Supervisor | hr | 1 | 88.74 | 88.74 | 902
2014-07-07 | Allciv-Supervisor | Supervisor | hr | 1 | 88.74 | 88.74 | 902
2014-07-08 | Allciv-Supervisor | Supervisor | hr | 1 | 88.74 | 88.74 | 902
2014-07-09 | Allciv-Supervisor | Supervisor | hr | 1 | 88.74 | 88.74 | 902
2014-07-10 | Allciv-Supervisor | Supervisor | hr | 2 | 88.74 | 177.48 | 902
2014-07-11 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-12 | Allciv-Supervisor | Supervisor | hr | 2.5 | 88.74 | 221.85 | 902
2014-07-14 | Allciv-Supervisor | Supervisor | hr | 2 | 88.74 | 177.48 | 902
2014-07-16 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-17 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-21 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-22 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-23 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-24 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-25 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2014-07-26 | Allciv-Supervisor | Supervisor | hr | 3 | 88.74 | 266.22 | 902
2014-07-28 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-07-29 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-07-30 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-07-31 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-08-01 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-08-04 | Allciv-Supervisor | Supervisor | hr | 5 | 88.74 | 443.7 | 902
2014-08-05 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 902
2014-08-06 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2014-08-07 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2014-08-11 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2014-08-12 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2014-08-13 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2014-08-14 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2014-08-19 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2014-08-20 | Allciv-Supervisor | Supervisor | hr | 6.5 | 88.74 | 576.81 | 902
2014-08-21 | Allciv-Supervisor | Supervisor | hr | 7 | 88.74 | 621.18 | 902
2014-08-25 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-08-26 | Allciv-Supervisor | Supervisor | hr | 6.5 | 88.74 | 576.81 | 902
2014-08-27 | Allciv-Supervisor | Supervisor | hr | 6.5 | 88.74 | 576.81 | 902
2014-08-28 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2014-08-29 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-09-01 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-02 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-03 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-04 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-05 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-08 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-09-09 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-09-10 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-11 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-12 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2014-09-15 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-09-16 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-17 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-09-18 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-09-19 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-09-22 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-09-23 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-09-24 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-09-25 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-09-26 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-09-29 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-09-30 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-10-01 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-10-02 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-10-03 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-10-07 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-10-08 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-10-09 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-10-10 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-10-13 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-10-14 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-10-15 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-10-16 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2014-10-17 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-10-20 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-10-21 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-10-22 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-10-23 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-10-24 | Allciv-Supervisor | Supervisor | hr | 7 | 88.74 | 621.18 | 902
2014-10-27 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-10-28 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-10-29 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-10-30 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-10-31 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-11-01 | Allciv-Supervisor | Supervisor | hr | 7 | 88.74 | 621.18 | 902
2014-11-03 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-11-04 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-11-05 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-11-06 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-11-07 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-11-10 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-11-11 | Allciv-Supervisor | Supervisor | hr | 11 | 88.74 | 976.14 | 902
2014-11-12 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-11-13 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-11-14 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-11-17 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-11-18 | Allciv-Supervisor | Supervisor | hr | 10.5 | 88.74 | 931.77 | 902
2014-11-19 | Allciv-Supervisor | Supervisor | hr | 10.25 | 88.74 | 909.585 | 902
2014-11-20 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-11-21 | Allciv-Supervisor | Supervisor | hr | 8.5 | 88.74 | 754.29 | 902
2014-11-25 | Allciv-Supervisor | Supervisor | hr | 11 | 88.74 | 976.14 | 902
2014-11-26 | Allciv-Supervisor | Supervisor | hr | 11 | 88.74 | 976.14 | 902
2014-11-27 | Allciv-Supervisor | Supervisor | hr | 10.25 | 88.74 | 909.585 | 902
2014-11-28 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-12-01 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-02 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-03 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-04 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-05 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-08 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-12-09 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-12-10 | Allciv-Supervisor | Supervisor | hr | 11.5 | 88.74 | 1020.51 | 902
2014-12-11 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-12 | Allciv-Supervisor | Supervisor | hr | 7.5 | 88.74 | 665.55 | 902
2014-12-15 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2014-12-16 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2014-12-17 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2014-12-18 | Allciv-Supervisor | Supervisor | hr | 10 | 88.74 | 887.4 | 902
2014-12-19 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2015-01-05 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-01-06 | Allciv-Supervisor | Supervisor | hr | 3.5 | 88.74 | 310.59 | 902
2015-01-07 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2015-01-08 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-01-09 | Allciv-Supervisor | Supervisor | hr | 6.5 | 88.74 | 576.81 | 902
2015-01-12 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2015-01-13 | Allciv-Supervisor | Supervisor | hr | 9.5 | 88.74 | 843.03 | 902
2015-01-14 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2015-01-16 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2015-01-19 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2015-01-20 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-01-23 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2015-01-27 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-01-28 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-01-29 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-01-30 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2015-02-02 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-02-12 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2015-02-13 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
2015-02-26 | Allciv-Supervisor | Supervisor | hr | 2.5 | 88.74 | 221.85 | 902
2015-03-05 | Allciv-Supervisor | Supervisor | hr | 1.5 | 88.74 | 133.11 | 902
2015-03-19 | Allciv-Supervisor | Supervisor | hr | 9 | 88.74 | 798.66 | 902
2015-03-26 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-05-05 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 902
2015-05-06 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-05-07 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 902
2015-05-15 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 902
| Subtotal for 902 |  |  |  |  | 111790.39
Cost Code 903
2014-02-28 | Portable Building Hired 31/1/2014 - 28/2/2014 | Portable Build |  | 1 | 237.58 | 237.58 | 903
2014-02-28 | Portable Building Hired 31/1/14 - 28/2/14 | Portable Build |  | 1 | 196 | 196 | 903
2014-02-28 | Temp Fencing Hired 17/2/14 - 28/2/14 | Temporary Fencing |  | 1 | 2057.43 | 2057.43 | 903
2014-04-30 | Hire of Water Cooler April | Water Cooler Rent |  | 1 | 19.8 | 19.8 | 903
2014-04-30 | Portable Building Hired 31/3/14 - 30/4/14 | Crib Facilities |  | 1 | 516.74 | 516.74 | 903
2014-05-03 | Hire of Water Cooler April | Water Cooler Rent |  | 1 | 19.8 | 19.8 | 903
2014-05-16 | Pine OCleen | Small Tools |  | 1 | 2.73 | 2.73 | 903
2014-06-04 | Black and Gold Milk and Paper Cups | Small Tools |  | 1 | 15.71 | 15.71 | 903
2014-06-23 | Disposal of Waste | Waste Disposal |  | 1 | 566.44 | 566.44 | 903
2014-06-28 | Disposal of Waste | Waste Disposal |  | 1 | 268.35 | 268.35 | 903
2014-06-30 | Portable Building hired 30/4/14 - 31/05/14 | Portable Build |  | 1 | 434 | 434 | 903
2014-07-02 | Black and Gold Milk and Paper Cups | Small Tools |  | 1 | 23.42 | 23.42 | 903
2014-07-14 | 50 x Party Ice | Party Ice |  | 50 | 2 | 100 | 903
2014-07-14 | 20 x Party Ice | Party Ice |  | 20 | 2 | 40 | 903
2014-07-15 | Transport Posi tractor from Jubillee Pocket to POA | Float |  | 1 | 130 | 130 | 903
2014-07-25 | Black, Cyan, Yellow and Magenta Cartridges | Office Supplies |  | 1 | 30.46 | 30.46 | 903
2014-08-05 | Milk x 4, and Coffee | Small Tools |  | 1 | 23.2 | 23.2 | 903
2014-08-05 | Paper Cups | Small Tools |  | 1 | 8.46 | 8.46 | 903
2014-08-21 | 30 x Party Ice | Party Ice |  | 30 | 2 | 60 | 903
2014-08-31 | Temporary Fencing 17/8/14 - 31/08/14 | Temporary Fencing |  | 1 | 710.09 | 710.09 | 903
2014-08-31 | Portable Building hired 31/7/14 - 31/8/14 | Portable Build |  | 1 | 434 | 434 | 903
2014-09-09 | 25 x Party Ice | Party Ice |  | 25 | 2 | 50 | 903
2014-09-30 | Portable Building hired 31/8/14 - 30/9/14 | Portable Build |  | 1 | 420 | 420 | 903
2014-10-14 | Float excavator to Site | Float |  | 1.5 | 135 | 202.5 | 903
2014-10-17 | Disposal of Waste | Waste Disposal |  | 1 | 566.44 | 566.44 | 903
2014-10-30 | Float Excavator to site | Excavator - 5T | hr | 1 | 100 | 100 | 903
2014-10-31 | Portable Building Hired 30/9/14 - 31/10/14 | Portable Build |  | 1 | 526.07 | 526.07 | 903
2014-10-31 | Portable Building Hired 30/9/14 - 31/10/14 | Crib Facilities |  | 1 | 434 | 434 | 903
2014-11-05 | 30 x Party Ice | Party Ice |  | 30 | 2 | 60 | 903
2014-11-19 | Portable Building Hired 31/10/14 - 18/11/14 | Portable Build |  | 1 | 310.04 | 310.04 | 903
2014-11-20 | Milk | Small Tools |  | 1 | 2.6 | 2.6 | 903
2014-11-24 | Disposal of Waste | Waste Disposal |  | 1 | 1132.73 | 1132.73 | 903
2014-11-26 | 10 x Party Ice | Party Ice |  | 10 | 2 | 20 | 903
2014-11-30 | Portable Building Hired 31/10/14 - 30/11/2014 | Portable Build |  | 1 | 470.4 | 470.4 | 903
2014-12-10 | 10 x Party Ice | Party Ice |  | 10 | 2 | 20 | 903
2014-12-31 | Temporary Fencing 1/12/2014 - 31/12/2014 | Temporary Fencing |  | 1 | 897.67 | 897.67 | 903
2014-12-31 | Portable Building Hired 01/12/14 - 31/12/2014 | Portable Build |  | 1 | 434 | 434 | 903
2015-01-31 | Portable Building Hired 30/1/14 - 29/01/2014 | Portable Build |  | 1 | 439.04 | 439.04 | 903
2015-04-09 | Transport of 2 x Containers for POA to Proserpine Shed | Float |  | 1 | 272.73 | 272.73 | 903
| Subtotal for 903 |  |  |  |  | 12252.43
Cost Code 904
2014-02-28 | Damage Waiver | Insurance |  | 1 | 28.51 | 28.51 | 904
2014-02-28 | Damage Waiver on Portable Build | Insurance |  | 1 | 23.52 | 23.52 | 904
2014-02-28 | Damage Waiver on Temp Fencing | Insurance |  | 1 | 243.25 | 243.25 | 904
2014-03-14 | Construction Risk | Insurance |  | 1 | 7976.88 | 7976.88 | 904
2014-04-30 | Damage Waiver on Portable Build | Insurance |  | 1 | 61.09 | 61.09 | 904
2014-04-30 | Damage Waiver on PF Roller | Insurance |  | 1 | 72 | 72 | 904
2014-05-08 | Damage Waiver on Padfoot Roller | Insurance |  | 1 | 180 | 180 | 904
2014-05-15 | Damage Waiver | Insurance |  | 1 | 64.32 | 64.32 | 904
2014-06-30 | Damage Waiver on Portable Build | Insurance |  | 1 | 50.4 | 50.4 | 904
2014-08-31 | Damage Waiver on Portable Build | Insurance |  | 1 | 52.08 | 52.08 | 904
2014-08-31 | Damage Waiver to Temporary Fencing | Insurance |  | 1 | 83.95 | 83.95 | 904
2014-09-12 | Damage Waiver on Padfoot Roller | Insurance |  | 1 | 144 | 144 | 904
2014-09-23 | Damage Waiver on Hammer Hired 23/9/14 | Insurance |  | 1 | 16.08 | 16.08 | 904
2014-09-26 | Damage Waiver | Insurance |  | 1 | 200.16 | 200.16 | 904
2014-09-26 | Damage Waiver on 8T D/D Roller | Insurance |  | 1 | 100.8 | 100.8 | 904
2014-09-26 | Damage Waiver on 8T D/D Roller | Insurance |  | 1 | 134.4 | 134.4 | 904
2014-09-30 | Damage Waiver on Electric Breaker | Insurance |  | 1 | 15.36 | 15.36 | 904
2014-09-30 | Damage Waiver on Portable Build | Insurance |  | 1 | 50.4 | 50.4 | 904
2014-10-03 | Damage Waiver on 8T Double Drum Roller | Insurance |  | 1 | 67.2 | 67.2 | 904
2014-10-03 | Damage Waiver on 3 - 4T Double Drum Roller | Insurance |  | 1 | 33.36 | 33.36 | 904
2014-10-31 | Damage Waiver on Portable Build Hired 30/9/14 - 31/10/14 | Insurance |  | 1 | 52.08 | 52.08 | 904
2014-10-31 | Damage Waiver on Portable Build Hired 30/9/14 - 31/10/14 | Insurance |  | 1 | 63.13 | 63.13 | 904
2014-11-19 | Damage Waiver on Portable Build Hired 31/10/14 - 18/11/14 | Insurance |  | 1 | 36.66 | 36.66 | 904
2014-12-31 | Damage Waiver to Temporary Fencing 1/12/2014 - 31/12/2014 | Insurance |  | 1 | 106.13 | 106.13 | 904
2014-12-31 | Damage Waiver on Portable Build Hired 1/12/14 - 31/12/14 | Insurance |  | 1 | 52.08 | 52.08 | 904
| Subtotal for 904 |  |  |  |  | 9907.84
Cost Code 905
2014-05-16 | Coles Wipes and Air Freshener | Small Tools |  | 1 | 7.73 | 7.73 | 905
2014-05-22 | Pincers Carpenter | Small Tools |  | 1 | -13.05 | -13.05 | 905
2014-05-22 | Star Posts, Star Post Caps Round, Barber Pole Mesh, T-Top Base 8Kg, Stiltmasta Sand Bag Filler. | Small Tools |  | 1 | 2998.25 | 2998.25 | 905
2014-05-23 | Handsaw Jack and Cable Ties | Small Tools |  | 1 | 46.73 | 46.73 | 905
2014-06-06 | Spray & Mark X 10 Wire tie belt pack Storage box | Small Tools |  | 1 | 137.5 | 137.5 | 905
2014-06-30 | PVC Pipe | Small Tools |  | 1 | 100.55 | 100.55 | 905
2014-08-11 | 1 x PVC Pipe | Small Tools |  | 1 | 8.02 | 8.02 | 905
2014-09-01 | Nozzles | Small Tools |  | 1 | 1.94 | 1.94 | 905
2014-09-01 | Grey sikaflex sausage | Small Tools |  | 1 | 64.88 | 64.88 | 905
2014-09-02 | 1 Bag of T-Shirt Rags | Small Tools |  | 1 | 22 | 22 | 905
2014-09-05 | sand bags | Small Tools |  | 1 | 22.91 | 22.91 | 905
2014-10-21 | Tie Wire | Small Tools |  | 1 | 11.32 | 11.32 | 905
2014-12-09 | Labour to repair/Replace pump assy on PTX 301 | Labour |  | 1 | 419.09 | 419.09 | 905
2014-12-12 | Roll viscreen | Small Tools |  |  | 95.86 |  | 905
2014-12-12 | 3 x Power Fast Pro | Small Tools |  | 1 | 132.5 | 132.5 | 905
| Subtotal for 905 |  |  |  |  | 3960.37
Cost Code 906
2014-06-11 | Disposal of Concrete at Warren Transport Yard | Waste Disposal |  | 1 | 900 | 900 | 906
2014-06-24 | Disposal of Concrete at Warren Transport Yard | Waste Disposal |  | 3 | 300 | 900 | 906
2014-10-30 | 5T Excavator Hire | Excavator - 5T | hr | 9 | 105 | 945 | 906
2014-10-31 | CAT297C MTL - No Operator | CAT297 | hr | 6 | 46.5 | 279 | 906
2014-10-31 | Allciv - Leading Hand | Labour | Hr | 2 | 54.58 | 109.16 | 906
2014-10-31 | Allciv - Labour Hire | Labour | hr | 7.5 | 35.11 | 263.325 | 906
2014-10-31 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 906
2014-10-31 | Labour Hire | Labour | hr | 8.5 | 39.98 | 339.83 | 906
2014-11-03 | Allciv - Leading Hand | Labour | Hr | 9 | 54.58 | 491.22 | 906
2014-11-03 | Mini Excavator Hire | Excavator - 5T | hr | 7.5 | 105 | 787.5 | 906
2014-11-03 | CAT297C MTL - No Operator | CAT297 | hr | 9 | 46.5 | 418.5 | 906
2014-11-03 | UD Water Cart - No Driver | UD Water Cart | hr | 3.5 | 21.61 | 75.635 | 906
2014-11-03 | Allciv - Labour Hire | Labour | hr | 9 | 35.11 | 315.99 | 906
2014-11-03 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 906
2014-11-04 | CAT297C MTL - No Operator | CAT297 | hr | 9.5 | 46.5 | 441.75 | 906
2014-11-04 | Backhoe - Wet Hire | Back Hoe | hr | 8.5 | 110 | 935 | 906
2014-11-04 | UD Water Cart - No Driver | UD Water Cart | hr | 2 | 21.61 | 43.22 | 906
2014-11-04 | Labour Hire | Labour | hr | 9.5 | 39.98 | 379.81 | 906
2014-11-04 | Allciv - Labour Hire | Labour | hr | 8.5 | 35.11 | 298.435 | 906
2014-11-04 | Allciv - Leading Hand | Labour | Hr | 7.5 | 54.58 | 409.35 | 906
2014-11-06 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 906
2014-11-06 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 906
2014-12-20 | Backhoe - Wet Hire | Back Hoe | hr | 7.75 | 110 | 852.5 | 906
2015-01-14 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 906
2015-01-14 | Labour Hire | Labour | hr | 1.5 | 39.98 | 59.97 | 906
2015-01-16 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 906
2015-01-16 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 906
2015-01-20 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 906
2015-01-22 | N25 Concrete 14.6M3 & Min Charge | N25 |  | 14.6 | 171 | 2496.6 | 906
2015-02-16 | Allciv-Supervisor | Supervisor | hr | 8 | 88.74 | 709.92 | 906
2015-02-16 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 906
2015-02-17 | 5 x Power Fast Pro Chemset cartridges | Small Tools |  | 1 | 200.75 | 200.75 | 906
2015-02-17 | Allciv-Supervisor | Supervisor | hr | 6 | 88.74 | 532.44 | 906
2015-02-17 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 906
2015-02-18 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 906
2015-02-18 | Allciv-Supervisor | Supervisor | hr | 6.5 | 88.74 | 576.81 | 906
2015-02-18 | 30 x Cement GP 20Kg Bag | Cement - GP Bulk |  | 1 | 240 | 240 | 906
2015-02-18 | Gabion Rock RW Footing to Fences Variation | Rock |  | 12.28 | 50.12 | 615.4736 | 906
2015-02-19 | Hire of Mini Loader Post hole Digger Hired | Loader |  | 1 | 215.65 | 215.65 | 906
2015-02-26 | Allciv - Leading Hand | Labour | Hr | 2.5 | 54.58 | 136.45 | 906
2015-03-03 | 10 x Cement GP 20Kg Bag | Cement - GP Bulk |  | 1 | 80 | 80 | 906
2015-03-04 | 30 x Cement GP 20Kg Bag | Cement - GP Bulk |  | 1 | 240 | 240 | 906
2015-03-04 | 30 x Cement GP 20Kg Bag | Cement - GP Bulk |  | 1 | 84.17 | 84.17 | 906
2015-03-04 | 30 x Cement GP 20Kg Bag & Hessian Bags | Cement - GP Bulk |  | 1 | 285.35 | 285.35 | 906
2015-03-05 | Gabion Rock RW Footing to Fences Variation | Rock |  | 12.94 | 50.12 | 648.5528 | 906
2015-03-05 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 906
2015-03-09 | 20 x Cement GP 20Kg Bag | Cement - GP Bulk |  | 1 | 240 | 240 | 906
2015-03-17 | Telstra Bush Pit | Telstra Bush Pits |  | 6 | 2.65 | 15.9 | 906
2015-03-18 | Type 8 - Plastic Pit Drg Communication & Freight Charges | Electrical Pit - Type 8 |  | 1 | 440 | 440 | 906
2015-03-18 | Type 6/8 Cement Lid 2pt CLA-Com | Elec Pit/Lid - Type 8 |  | 1 | 60 | 60 | 906
2015-03-19 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 906
2015-03-27 | Heat and Bend Reo Bars. | Steel Fixing |  | 1 | 310 | 310 | 906
2015-04-02 | N25 Concrete 7.20M3 & Min Charge Sika Salmon | N25 |  | 7.2 | 236.334 | 1701.6048 | 906
2015-04-10 | Supply only 1 x light pole to replace pole WDC damaged. | Steel Fixing |  | 1 | 620 | 620 | 906
2015-05-05 | Pvc Seeep bend 40mm 90 degree orange x 2 | PVC Juntion Pipe |  | 2 | 6.892 | 13.784 | 906
2015-05-07 | N25 Concrete 0.6M3 & Min Charge | N25 |  | 0.6 | 397.67 | 238.602 | 906
2015-05-11 | Set Place and finish of Coloured concrete path of entrance to the Cove Estate | Dalton Concrete |  | 1 | 1560 | 1560 | 906
| Subtotal for 906 |  |  |  |  | 24005.0022
Cost Code 910
2014-08-18 | Labour Hire | Labour | hr | 2.5 | 39.98 | 99.95 | 910
2014-08-18 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 2.5 | 25.78 | 64.45 | 910
2014-08-18 | Allciv - Labour Hire | Labour | hr | 2.5 | 35.11 | 87.775 | 910
2014-10-15 | Backhoe - Wet Hire Removal of Concrete | Back Hoe | hr | 10 | 110 | 1100 | 910
2014-10-16 | Labour Hire | Labour | hr | 2 | 39.98 | 79.96 | 910
2014-10-16 | CAT311D - 12T Excavator (No Operator) | CAT297 | hr | 2 | 46.5 | 93 | 910
2014-10-17 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 910
2014-10-17 | UD Water Cart - No Driver | UD Water Cart | hr | 3 | 21.61 | 64.83 | 910
2014-10-17 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 910
2014-10-20 | UD Water Cart - No Driver | UD Water Cart | hr | 4 | 21.61 | 86.44 | 910
2014-10-27 | CAT297C MTL - No Operator | CAT297 | hr | 2 | 46.5 | 93 | 910
2014-10-27 | Iveco Ute - 744 SDX | Ivecko - 744 SDX | hr | 8 | 25.78 | 206.24 | 910
2014-10-27 | Labour Hire | Labour | hr | 8 | 39.98 | 319.84 | 910
2014-10-27 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 910
2014-10-27 | Allciv - Labour Hire | Labour | hr | 8 | 35.11 | 280.88 | 910
2014-11-05 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 910
2014-11-05 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 910
2014-11-05 | Allciv - Leading Hand | Labour | Hr | 7.5 | 54.58 | 409.35 | 910
2014-11-06 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 910
2014-11-06 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 910
2014-11-07 | Allciv - Labour Hire | Labour | hr | 3 | 35.11 | 105.33 | 910
2014-11-07 | Water Cart Allciv - No Operator | WC - Allciv | hr | 3 | 42.79 | 128.37 | 910
2014-11-07 | Labour Hire | Labour | hr | 3 | 39.98 | 119.94 | 910
2014-11-07 | Allciv - Leading Hand | Labour | Hr | 3 | 54.58 | 163.74 | 910
2014-11-18 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 910
2014-11-19 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 910
2015-01-23 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 910
2015-01-27 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 910
2015-01-28 | Allciv - Leading Hand | Labour | Hr | 8 | 54.58 | 436.64 | 910
2015-01-28 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 910
2015-01-29 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 910
2015-01-29 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 910
2015-03-05 | Allciv - Leading Hand | Labour | Hr | 1.5 | 54.58 | 81.87 | 910
2015-03-19 | Mac & Tag Trailer | Tipper |  | 7 | 35 | 245 | 910
2015-03-19 | Backhoe - Wet Hire | Back Hoe | hr | 2 | 110 | 220 | 910
2015-03-19 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 910
2015-03-19 | Allciv - Leading Hand | Labour | Hr | 7 | 54.58 | 382.06 | 910
2015-04-09 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 910
2015-04-09 | Backhoe - Wet Hire | Back Hoe |  | 5 | 110 | 550 | 910
| Subtotal for 910 |  |  |  |  | 8179.135
Cost Code 913
2014-05-15 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 913
2014-05-15 | Allciv-Supervisor | Supervisor | hr | 6 | 71.8 | 430.8 | 913
2014-05-15 | Labour Hire | Labour | hr | 6.5 | 39.98 | 259.87 | 913
2014-05-15 | Allciv - Labour Hire | Labour | hr | 6.5 | 35.11 | 228.215 | 913
2014-05-15 | Allciv - Leading Hand | Labour | Hr | 6.5 | 54.58 | 354.77 | 913
2014-06-11 | Allciv - Leading Hand | Labour | Hr | 6 | 54.58 | 327.48 | 913
2014-06-11 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 913
2014-06-11 | Allciv - Labour Hire | Labour | hr | 6 | 35.11 | 210.66 | 913
2014-06-11 | Labour Hire | Labour | hr | 6 | 39.98 | 239.88 | 913
2014-06-13 | Allciv - Leading Hand | Labour | Hr | 3.5 | 54.58 | 191.03 | 913
2014-06-13 | Allciv - Labour Hire | Labour | hr | 3.5 | 35.11 | 122.885 | 913
2014-06-13 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 913
2014-06-13 | Labour Hire | Labour | hr | 3.5 | 39.98 | 139.93 | 913
2014-09-19 | Posir Track | CAT297 | hr | 2.5 | 48 | 120 | 913
2014-09-22 | 120H Grader | 120H Grader | hr | 2 | 120 | 240 | 913
2015-01-06 | Allciv-Supervisor | Supervisor | hr | 4.5 | 88.74 | 399.33 | 913
2015-01-06 | Allciv - Leading Hand | Labour | Hr | 4.5 | 54.58 | 245.61 | 913
2015-01-06 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 913
2015-01-07 | Allciv - Leading Hand | Labour | Hr | 4 | 54.58 | 218.32 | 913
2015-01-07 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 913
2015-01-07 | Allciv-Supervisor | Supervisor | hr | 4 | 88.74 | 354.96 | 913
2015-01-23 | Allciv - Leading Hand | Labour | Hr | 4.5 | 54.58 | 245.61 | 913
2015-01-23 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 913
| Subtotal for 913 |  |  |  |  | 5482.79
Cost Code 914
2014-08-14 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 914
2014-08-14 | Allciv - Labour HIre | Labour | hr | 1 | 35.11 | 35.11 | 914
2014-08-14 | Allciv - Leading Hand | Labour | Hr | 1 | 54.58 | 54.58 | 914
2014-08-14 | Allciv - Labour Hire | Labour | hr | 1 | 35.11 | 35.11 | 914
2014-08-14 | Labour Hire | Labour | hr | 1 | 39.98 | 39.98 | 914
| Subtotal for 914 |  |  |  |  | 207.5
Cost Code 916
2014-03-28 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-04-30 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-05-01 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-05-02 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-05-07 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-05-08 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 916
2014-05-10 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-05-12 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-05-14 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-05-15 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-05-16 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-05-19 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-05-20 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-05-22 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-05-23 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-05-26 | Allciv - Labour Hire | Labour | hr | 5 | 35.11 | 175.55 | 916
2014-05-27 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-05-28 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-05-29 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-05-30 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 916
2014-06-02 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-06-03 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-06-04 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-06-06 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 916
2014-06-11 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-06-13 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-06-16 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-06-17 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 916
2014-06-18 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 916
2014-06-19 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 916
2014-06-23 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-06-24 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-06-25 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-06-26 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-06-27 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-06-30 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-07-01 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-07-02 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-07-03 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-07-04 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-07-07 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-07-08 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-07-09 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 916
2014-07-10 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-07-11 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-07-14 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-07-16 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
2014-07-17 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
2014-07-21 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
2014-07-22 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 916
2014-07-23 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
2014-07-24 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
2014-07-25 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-08-04 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 916
2014-08-05 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-08-06 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-08-07 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-08-08 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
2014-08-11 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-08-12 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-08-13 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-08-14 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-08-19 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-08-20 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2014-08-21 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 916
2014-08-25 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-08-26 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-08-27 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-08-28 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2014-08-29 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-01 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-02 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-02 | Allciv - Labour HIre | Labour | hr | 2 | 42.72 | 85.44 | 916
2014-09-03 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-04 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-05 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-09-08 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-09-09 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-09-10 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-09-11 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-12 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-09-15 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 916
2014-09-16 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-17 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-18 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-19 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-22 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-09-23 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-09-24 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-25 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-09-26 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-09-29 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-30 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-10-01 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-10-02 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-10-03 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-07 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-10-08 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-10-09 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-10-10 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-13 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-14 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-10-16 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-17 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2014-10-20 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-10-21 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-10-22 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-10-23 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-10-24 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2014-10-27 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-28 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-29 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-30 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-10-31 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-11-03 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-11-04 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-11-05 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-06 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-07 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-11-10 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-11 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 916
2014-11-12 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-13 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-14 | Allciv - Labour Hire | Labour | hr | 7.5 | 42.72 | 320.4 | 916
2014-11-17 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-18 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-11-19 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2014-11-20 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 916
2014-11-21 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 916
2014-11-25 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-11-26 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-27 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-11-28 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-12-01 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-12-02 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-12-03 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-12-04 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-12-05 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2015-01-05 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-06 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 916
2015-01-07 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 916
2015-01-08 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-09 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2015-01-13 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-14 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-16 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2015-01-16 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2015-01-19 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-20 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-22 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2015-01-23 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2015-01-27 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-28 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2015-01-29 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 916
2015-01-30 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2015-02-02 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 916
2015-02-13 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 916
2015-02-18 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 916
| Subtotal for 916 |  |  |  |  | 40631.39
Cost Code C20
2014-05-11 | N25 Concrete | N25 |  | 5.6 | 171 | 957.6 | C20
2014-05-11 | N25 Concrete | N25 |  | 1 | 2745.6 | 2745.6 | C20
2014-05-13 | N25 Concrete | N25 |  | 5 | 171 | 855 | C20
2014-05-15 | N25 Concrete | N25 |  | 5.6 | 171 | 957.6 | C20
2014-05-16 | N25 Concrete | N25 |  | 1 | 1451.2 | 1451.2 | C20
2014-05-16 | N25 Concrete | N25 |  | 5.4 | 171 | 923.4 | C20
2014-05-21 | N25 Concrete | N25 |  | 5 | 170 | 850 | C20
2014-05-21 | N20 Concrete and waiting time | N20 |  | 1 | 905 | 905 | C20
2014-05-22 | N25 Concrete and Min Load Charge | N25 |  | 1 | 1424 | 1424 | C20
2014-05-26 | N20 Concrete | N20 |  | 1 | 1267 | 1267 | C20
2014-05-27 | N20 Concrete | N20 |  | 1 | 1744.2 | 1744.2 | C20
2014-05-28 | N20 Concrete | N20 |  | 1 | 2112 | 2112 | C20
2014-05-31 | N20 Concrete | N20 |  | 1 | 578 | 578 | C20
2014-06-02 | N25 Concrete and Min Load Charge | N25 |  | 1 | 602.4 | 602.4 | C20
2014-06-17 | N25 Concrete and Min Load Charge | N25 |  | 10.8 | 171 | 1846.8 | C20
2014-07-03 | N25 Concrete and Min Load Charge 14.20 M3 | N20 |  | 1 | 2499.2 | 2499.2 | C20
2014-07-04 | N25 Concrete and Min Load Charge 8.4 M3 | N20 |  | 1 | 1457.4 | 1457.4 | C20
2014-07-15 | N25 Concrete | N25 |  | 5.2 | 171 | 889.2 | C20
2014-07-16 | N25 Concrete | N25 |  | 5.4 | 171 | 923.4 | C20
2014-07-17 | N25 Concrete | N25 |  | 10.2 | 171 | 1744.2 | C20
2014-07-24 | N25 Concrete | N25 |  | 1 | 1778.4 | 1778.4 | C20
2014-07-29 | N25 Concrete 12.80m3 | N25 |  | 1 | 2188.8 | 2188.8 | C20
2014-07-29 | N25 Concrete 4.6m3 | N25 |  | 1 | 786.6 | 786.6 | C20
2014-08-05 | N25 Concrete 5.00M3 | N25 |  | 5 | 171 | 855 | C20
2014-10-09 | N25 Concrete 2.40M3 Min load charge | N25 |  | 1 | 792 | 792 | C20
| Subtotal for C20 |  |  |  |  | 33134
Cost Code C25
2014-06-06 | N25 Concrete | N25 |  | 1 | 923.4 | 923.4 | C25
2014-06-08 | N25 Concrete and Min Load Charge | N25 |  | 1 | 656.8 | 656.8 | C25
2014-06-18 | N25 Concrete and Min Load Charge | N25 |  | 1 | 855 | 855 | C25
2014-06-19 | N25 Concrete and Min Load Charge | N25 |  | 1 | 2492.4 | 2492.4 | C25
2014-06-23 | N25 Concrete and Min Load Charge | N25 |  | 7 | 1267 | 8869 | C25
2014-06-26 | N25 Concrete Min Load Charge Waiting time charge | N25 |  | 1 | 2918 | 2918 | C25
2014-06-26 | N25 Concrete and Min Load Charge | N25 |  | 1 | 575.2 | 575.2 | C25
2014-06-30 | N25 Concrete and Min Load Charge | N25 |  | 1 | 1778.4 | 1778.4 | C25
2014-07-09 | N20 Concrete 10 M3 | N20 |  | 1 | 1710 | 1710 | C25
2014-07-17 | 10.2 M3 N25 Concrete | N25 |  | 10.2 | 171 | 1744.2 | C25
2014-08-05 | N25 Concrete 4.6m3 | N25 |  | 2.2 | 171 | 376.2 | C25
2014-08-14 | N25 Concrete 5.40M3 | N25 |  | 5.4 | 171 | 923.4 | C25
2014-09-25 | N25 Concrete 1.2M3 Min load charge | N25 |  | 1 | 303.2 | 303.2 | C25
2014-10-16 | N25 Concrete 5.4M3 This invoice is to be credited due to slab failure. | N25 |  | 1 | 923.4 | 923.4 | C25
2014-10-16 | N25 Concrete 5.4M3 | N25 |  | 1 | 923.4 | 923.4 | C25
2014-10-26 | N25 Concrete 5.20M3 | N25 |  | 5.2 | 171 | 889.2 | C25
2014-10-31 | N25 Concrete 4M3 | N25 |  | 4 | 171 | 684 | C25
2014-10-31 | N25 Concrete 5.20M3 | N25 |  | 5.2 | 171 | 889.2 | C25
2014-10-31 | N25 Concrete 2.6M3 & Min Load Charge | N25 |  | 1 | 493.6 | 493.6 | C25
2014-11-04 | N25 Concrete 5.20M3 | N25 |  | 4 | 171 | 684 | C25
2014-11-16 | N25 Concrete 4.00M3 & 1.00M3 Coremasta | N25 |  | 1 | 967 | 967 | C25
2014-11-25 | N25 Concrete 3.80M3 & Min Charge | N25 |  | 1 | 656.8 | 656.8 | C25
2014-11-26 | N25 Concrete 4.80M3 & Min Charge | N25 |  | 4.8 | 171 | 820.8 | C25
2014-11-30 | N25 Concrete 2.00M3 & Min Charge | N25 |  | 1 | 412.2 | 412.2 | C25
2014-12-02 | N25 Concrete 2.00M3 & Min Charge | N25 |  | 1 | 412 | 412 | C25
2014-12-10 | N25 Concrete 2.60M3 & Min Charge | N25 |  | 1 | 493.6 | 493.6 | C25
2014-12-11 | N25 Concrete .60M3 & Min Charge | N25 |  | 1 | 221.6 | 221.6 | C25
2014-12-12 | N25 Concrete 2.60M3 & Min Charge | N25 |  | 4 |  |  | C25
| Subtotal for C25 |  |  |  |  | 33596
Cost Code C32
2014-08-07 | N32 Concrete | N32 |  | 1 | 351.4 | 351.4 | C32
2014-10-02 | N32 Concrete | N32 |  | 1 | 368.8 | 368.8 | C32
2014-10-05 | N32 Concrete 3.00M3 | N32 |  | 1 | 639 | 639 | C32
| Subtotal for C32 |  |  |  |  | 1359.2
Cost Code CKM
2014-09-23 | N32 Concrete | N32 |  | 1 | 5311 | 5311 | CKM
| Subtotal for CKM |  |  |  |  | 5311
Cost Code E32
2014-11-06 | Exsposed salt & pepper N32 | E32 |  | 1 | 854 | 854 | E32
2014-11-06 | Exsposed salt & pepper N32 | E32 |  | 1 | 854 | 854 | E32
2014-11-07 | Exsposed salt & pepper N32 | E32 |  | 1 | 812 | 812 | E32
2014-11-11 | Amber Pearl | E32 |  | 1 | 914 | 914 | E32
2014-11-11 | Exsposed salt & pepper N32 | E32 |  | 1 | 1540 | 1540 | E32
2014-11-12 | Exsposed salt & pepper N32 | E32 |  | 1 | 1020 | 1020 | E32
2014-11-12 | Exsposed salt & pepper N32 | E32 |  | 1 | 686 | 686 | E32
2014-11-13 | Amber Pearl | E32 |  | 4 | 250 | 1000 | E32
2014-11-25 | Amber Pearl & Min Load Charge 3.80M3 | E32 |  | 1 | 957 | 957 | E32
2014-11-30 | Exsposed salt & pepper N32 & Min Charge | E32 |  | 1 | 686 | 686 | E32
2014-12-05 | Exsposed salt & pepper N32 | E32 |  | 4 | 245 | 980 | E32
2014-12-09 | N25 Concrete 5.00M3 | E32 |  | 5 | 213 | 1065 | E32
2014-12-09 | N25 Concrete 9.40M3 | E32 |  | 1 | 2571 | 2571 | E32
| Subtotal for E32 |  |  |  |  | 13939
Cost Code ETC
2014-05-27 | PVC Telstra Pipe | PVC Telstra Pipe |  | 1 | 6187.74 | 6187.74 | ETC
2014-09-24 | PVC Telstra Pipe | PVC Telstra Pipe |  | 1 | 14.24 | 14.24 | ETC
2014-09-24 | 12 Pvc 150 x 90 Deg, 2 x Pvc 150 x 45 Deg | PVC Stormwater |  | 1 | 336.74 | 336.74 | ETC
2014-09-24 | 4 x PVC Bend & 4 DWV Bend | PVC Stormwater |  | 1 | 205.87 | 205.87 | ETC
2014-09-24 | 8 x PVC Bend | PVC Stormwater |  | 1 | -130.56 | -130.56 | ETC
2014-09-26 | 1 x PVC Bend | PVC Stormwater |  | 1 | -14.52 | -14.52 | ETC
2014-09-26 | 1 x PVC 150 x 15 Deg Bend | PVC Stormwater |  | 1 | 21.7 | 21.7 | ETC
2014-09-29 | 30Pvc 150 x 15 Deg, 5 x Pvc 150 x 90 De, 3 150 x 45, 3 x 150 x 30 | PVC Stormwater |  | 1 | 184.19 | 184.19 | ETC
2014-09-30 | 3 Pvc 150 x 15 Deg, 2 x Pvc 150 x 90 Deg & 3 x DWV Bend | PVC Stormwater |  | 1 | 184.19 | 184.19 | ETC
2014-10-01 | Bush Pit 10mm PVC Vinidex | Small Tools |  | 5 | 3.5 | 17.5 | ETC
2014-10-28 | Claim forthe supply of 150 lengths of 100mm electrical conduit used at the Cove | Sewer Subbie |  | 1 | 1500 | 1500 | ETC
2014-12-03 | Pvc Seeep bend 40mm 90 degree orange x 5 | PVC Juntion Pipe |  | 5 | 6.264 | 31.32 | ETC
2014-12-09 | Pvc Seeep bend 40mm 90 degree orange x 2 | PVC Juntion Pipe |  | 2 | 6.892 | 13.784 | ETC
2015-04-01 | 100mm Austel 90d bebd 600rn | 90 Bend - 600rn |  | 2 | 22.25 | 44.5 | ETC
| Subtotal for ETC |  |  |  |  | 8596.694
Cost Code ETM
2014-05-08 | Pinchers Capenter and Wire Tie Belt | Small Tools |  | 1 | 46.32 | 46.32 | ETM
2014-05-10 | Nippers End Cutting | Small Tools |  | 1 | 76.89 | 76.89 | ETM
2014-05-14 | Cap Safety Steel Post | Small Tools |  | 1 | 51.47 | 51.47 | ETM
2014-06-17 | 10 X Nostalgia 50mv 10 Pole estate 4.5m 10 Foundation cage | Light |  | 1 | 7306 | 7306 | ETM
2014-09-16 | Tape Duct PVC Tartan and Cable Ties | Small Tools |  | 1 | 32.77 | 32.77 | ETM
2014-09-19 | Holesaw 127mm | Small Tools |  | 1 | 56.55 | 56.55 | ETM
2014-10-13 | 10 X Nostalgia 50mv | Light |  | 1 | 5200 | 5200 | ETM
2014-10-20 | Tape Duct PVC | Small Tools |  | 1 | 28.36 | 28.36 | ETM
2014-11-05 | Foamjoint Expansion | Small Tools |  | 1 | 153.95 | 153.95 | ETM
| Subtotal for ETM |  |  |  |  | 12952.31
Cost Code ETP
2014-05-28 | 12 x Cable Pit 700 x 810mm and Cement concrete pit lid | HDPE Cable Pit |  | 1 | 1580 | 1580 | ETP
| Subtotal for ETP |  |  |  |  | 1580
Cost Code QM2.1
2014-09-25 | Roadbase 2.1 | 2.1 Roadbase |  | 335.82 | 29.7 | 9973.854 | QM2.1
2014-09-29 | Roadbase 2.1 | 2.1 Roadbase |  | 12.52 | 29.7 | 371.844 | QM2.1
| Subtotal for QM2.1 |  |  |  |  | 10345.698
Cost Code QM2.3
2014-09-16 | Roadbase 2.3 | 2.3 Roadbase |  | 490.98 | 28.7 | 14091.136 | QM2.3
2014-09-17 | Roadbase 2.3 | 2.3 Roadbase |  | 54.96 | 28.7 | 1577.352 | QM2.3
| Subtotal for QM2.3 |  |  |  |  | 15668.488
Cost Code QM2.5
2014-09-03 | Sekect/Embankment Fill | Embankment Fill | tonne | 517.56 | 16 | 8280.96 | QM2.5
2014-09-04 | Sekect/Embankment Fill | Embankment Fill | tonne | 393.74 | 16 | 6299.84 | QM2.5
| Subtotal for QM2.5 |  |  |  |  | 14580.8
Cost Code QMR
2014-05-31 | Stone Pitching Loam | Stone pitching Loam |  | 1 | 2131.18 | 2131.18 | QMR
2014-06-04 | Aggregate 20mm | Aggregate 20mm | tonne | 56.14 | 33.5 | 1880.69 | QMR
2014-06-05 | Gabion Rock | Rock |  | 1 | 4692.03 | 4692.03 | QMR
2014-06-16 | Gabion Rock | Rock |  | 1 | 5480.74 | 5480.74 | QMR
2014-06-19 | Stone Pitching Loam | Stone pitching Loam |  | 1 | 520.63 | 520.63 | QMR
2014-06-23 | Gabion Rock | Rock |  | 11 | 1395.34 | 15348.74 | QMR
2014-06-24 | Stone Pitching Loam | Stone pitching Loam |  | 1 | 453.61 | 453.61 | QMR
2014-07-02 | Docket WD-100516 | Rock |  | 1 | 5091.63 | 5091.63 | QMR
2014-07-02 | Stone Pitching Loam | Stone pitching Loam |  | 14.5212 | 35.27 | 512.1627 | QMR
2014-07-03 | Aggregate 20mm | Aggregate 20mm | tonne | 12.48 | 35.5 | 443.04 | QMR
2014-07-08 | Aggregate 20mm | Aggregate 20mm | tonne | 27.38 | 33.5 | 917.23 | QMR
2014-07-09 | Stone Pitching Loam | Stone pitching Loam |  | 15.2012 | 35.27 | 536.1463 | QMR
2014-07-14 | Stone Pitching Loam | Stone pitching Loam |  | 13.96 | 35.273 | 492.4111 | QMR
2014-07-14 | Stone Pitching Loam | Stone pitching Loam |  | 15.02 | 35.273 | 529.8005 | QMR
2014-07-15 | Aggregate 20mm | Aggregate 20mm | tonne | 81.38 | 33.5 | 2726.23 | QMR
2014-07-16 | Stone Pitching Loam | Stone pitching Loam |  | 12.48 | 23.454 | 292.7059 | QMR
2014-07-22 | Stone Pitching Loam | Stone pitching Loam |  | 14.34 | 35.273 | 505.8148 | QMR
2014-07-22 | Stone Pitching Loam | Stone pitching Loam |  | 13.7 | 35.273 | 483.2401 | QMR
2014-07-31 | Stone Pitching Loam | Stone pitching Loam |  | 15.58 | 35.273 | 549.5533 | QMR
2014-08-07 | Gabion Rock | Rock |  | 1 | 596.43 | 596.43 | QMR
2014-08-27 | Gabion Rock | Rock |  | 1 | 84.48 | 84.48 | QMR
2014-11-24 | Gabion Rock | Rock |  | 1 | 1885.69 | 1885.69 | QMR
2014-11-27 | 11 x Knovk outs, 1 x Corner Knock outs | Knock Outs |  | 1 | 35 | 35 | QMR
2014-12-08 | Credit note for Invoice 10588 Charged Caratage: Should have been Self haul Dkt 9273 | Rock |  | 23.895 | -1.72 | -41.0994 | QMR
| Subtotal for QMR |  |  |  |  | 46148.0854
Cost Code QMS
2014-05-31 | Medium Fine Sand | Sand |  | 1 | 4314.14 | 4314.14 | QMS
2014-06-17 | Stone pitching Loam | Stone pitching Loam |  | 1 | 538.26 | 538.26 | QMS
2014-06-26 | Medium Fine Sand | Medium Fine Sand |  | 1 | 287.08 | 287.08 | QMS
2014-06-26 | Medium Fine Sand | Medium Fine Sand |  | 1 | 289.9 | 289.9 | QMS
2014-06-30 | Medium Fine Sand | Medium Fine Sand |  | 1 | 521.33 | 521.33 | QMS
2014-06-30 | Medium Fine Sand | Medium Fine Sand |  | 1 | 312.88 | 312.88 | QMS
2014-07-09 | Aggregate 20mm | Aggregate 20mm | tonne | 24.36 | 33.5 | 816.06 | QMS
2014-09-02 | Medium Fine Sand | Medium Fine Sand |  | 33.1005 | 23.454 | 776.3391 | QMS
2014-09-09 | Medium Fine Sand | Medium Fine Sand |  | 28.6407 | 23.454 | 671.739 | QMS
2014-09-09 | Medium Fine Sand | Medium Fine Sand |  | 27.6805 | 23.454 | 649.2184 | QMS
2014-09-10 | Medium Fine Sand | Medium Fine Sand |  | 28.6407 | 23.454 | 671.739 | QMS
2014-09-11 | Stabilised Sand SNDCEM 9M3 | Stabilised Sand |  | 1 | 1300 | 1300 | QMS
2014-09-12 | Medium Fine Sand | Medium Fine Sand |  | 30.6407 | 23.454 | 718.647 | QMS
2014-09-12 | Medium Fine Sand | Medium Fine Sand |  | 28.2006 | 23.454 | 661.4169 | QMS
2014-09-12 | Medium Fine Sand | Medium Fine Sand |  | 28.2407 | 23.454 | 662.3574 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.2806 | 23.454 | 663.2932 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.8005 | 23.454 | 675.4869 | QMS
2014-09-17 | Pitching Stone Loam | Stone pitching Loam |  | 12.601 | 35.27 | 444.4373 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.2805 | 23.454 | 663.2908 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.9405 | 23.454 | 678.7705 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 27.4407 | 23.454 | 643.5942 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.2407 | 23.454 | 662.3574 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.4607 | 23.454 | 667.5173 | QMS
2014-09-17 | Medium Fine Sand | Medium Fine Sand |  | 28.4007 | 23.454 | 666.11 | QMS
2014-09-24 | Medium Fine Sand | Medium Fine Sand |  | 27.1605 | 23.454 | 637.0224 | QMS
2014-10-15 | Medium Fine Sand | Medium Fine Sand | tonne | 12.7006 | 23.453 | 297.8672 | QMS
2014-10-20 | Medium Fine Sand | Medium Fine Sand | tonne | 13.061 | 23.453 | 306.3196 | QMS
2014-10-24 | Medium Fine Sand | Medium Fine Sand | tonne | 11.8608 | 23.453 | 278.1713 | QMS
2014-11-17 | Stone Pitching Loam | Stone pitching Loam | tonne | 13.02 | 35.27 | 459.2154 | QMS
2014-11-26 | Stone Pitching Loam | Stone pitching Loam | tonne | 13.16 | 35.27 | 464.1532 | QMS
2015-02-16 | Stone Pitching Loam | Stone pitching Loam | tonne | 16.78 | 35.273 | 591.8809 | QMS
2015-03-09 | Stone Pitching Loam | Stone pitching Loam | tonne | 6.62 | 44.197 | 292.5841 | QMS
2015-05-07 | Medium Fine Sand | Medium Fine Sand |  | 1.14 |  |  | QMS
| Subtotal for QMS |  |  |  |  | 22283.1785
Cost Code RSB
2014-04-11 | 95 x Steel Deformed Bars,, Dowels, Mesh and Bar Chairs | Staigth / Bent Bar |  | 1 | 5787.79 | 5787.79 | RSB
2014-10-11 | 50 x Steel Round Dowels | Dowels |  | 1 | 313.59 | 313.59 | RSB
2014-10-13 | 32 x N12 Deformed Steel, 15 x Starter Bars, 5 x 12mm Dowel and 16 x 16mm Dowels | Dowels |  | 1 | 562.64 | 562.64 | RSB
2014-11-04 | 12 x 6M Deformed Steel | Deformed Steel |  | 1 | 384.91 | 384.91 | RSB
2014-11-26 | 12 x Steel Round Dowels | Dowels |  | 1 | 58.45 | 58.45 | RSB
2014-12-08 | 12 x Steel Round Dowels | Dowels |  | 1 | 117.18 | 117.18 | RSB
| Subtotal for RSB |  |  |  |  | 7224.56
Cost Code SWL
2014-05-23 | 600 x 600 H/Duty V Gates | Grate & Frame |  | 1 | 5034 | 5034 | SWL
| Subtotal for SWL |  |  |  |  | 5034
Cost Code SWP
2014-05-30 | 1 x 375mm, 450mm, 525mm, 600mm | 375 RCP RRJ CL2 |  | 1 | 8953.67 | 8953.67 | SWP
2014-10-11 | 52 Stormwater Pipe PVC Plain | PVC Stormwater |  | 1 | 2459.52 | 2459.52 | SWP
2014-10-11 | 2 x DWV Ben 150 x 30 Degree & 2 x 150 x 15 Deg | DWV Bend |  | 1 | 105.09 | 105.09 | SWP
2014-10-14 | 3 x 150 x 45 Pvc S/W Bend and 5 x 150 x 90 PVC S/W Bends | PVC Stormwater |  | 1 | 66.08 | 66.08 | SWP
2014-10-14 | Credit Note for 143789285 | DWV Bend |  | 1 | -134.18 | -134.18 | SWP
| Subtotal for SWP |  |  |  |  | 11450.18
Cost Code SWPC
2014-04-30 | 50 Deposit fro the design, manufacture and delovery of Ecosol Net Gaurd | Ecosol Net Guard |  | 1 | 7975 | 7975 | SWPC
2014-05-30 | Install Ecosol Pit and Construction of varios stormwater pits | Sewer Subbie |  | 1 | 22970 | 22970 | SWPC
2014-06-04 | Credit Note for Exosol Gaurd | Ecosol Net Guard |  | 1 | -1500 | -1500 | SWPC
| Subtotal for SWPC |  |  |  |  | 29445
| Grand Total |  |  |  |  | 2045983.9807