## Estimate
[9 empty] | 2344789.4933 |  |  | 555246.3177 | 55772.398 | 708161.0329 | 1025609.7447 | 2344789.4933
WBS | Line No. | Resorce Name | Unit | Type | No | Production | Quantity | Rate | Cost | Usage | Duration | Labour | Material | Plant | Subcontract | Total | Portfolio WBS
1 | Line No 1 Item No | HSC 14/12 REHABILITATION OF MULTIPLE ROADS AND STREETS
2 | Line No 3 Item No | ESTABLISHMENT / PRELIMINARIES
3 | Line No 5 Item No MRS28 - 1101 | Contractor's site facilities, including establishment at commencement and disestablishment at completion of the project. | Lump |  |  |  | 1 |  | 27679 |  | 5 | 5184 | 2650 | 12525 | 7320 | 27679
| 1 | Site Facilities:
| 2 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 3 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 4 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 5 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 6 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 7 | Temporary Fence | m | P | 1 | 1 | 100 | 11.25 | 1125 |  |  | 0 | 0 | 1125 | 0 | 1125 | 903
| 9 | Set Up Site Facilitues:
| 10 | CBR15 (Fill) | tonne | M | 1 | 1 | 100 | 26.5 | 2650 |  |  | 0 | 2650 | 0 | 0 | 2650 | QMR
| 11 | Labour | hr | L | 1 | 1 | 108 | 48 | 5184 | 108 |  | 5184 | 0 | 0 | 0 | 5184 | 907
| 12 | Backhoe | hr | P | 1 | 1 | 36 | 100 | 3600 | 36 |  | 0 | 0 | 3600 | 0 | 3600 | 907
| 13 | Electrician | hr | S | 1 | 1 | 6 | 95 | 570 | 6 |  | 0 | 0 | 0 | 570 | 570 | 907
| 15 | Establish Machinery:
| 16 | Float | LS | P | 1 | 1 | 1200 | 1 | 1200 |  |  | 0 | 0 | 1200 | 0 | 1200 | 907
| 17 | Float | LS | P | 1 | 1 | 1200 | 1 | 1200 |  |  | 0 | 0 | 1200 | 0 | 1200 | 907
| 18 | Float | LS | P | 1 | 1 | 1200 | 1 | 1200 |  |  | 0 | 0 | 1200 | 0 | 1200 | 907
| 19 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 20 | Float | LS | P | 1 | 1 | 600 | 1 | 600 |  |  | 0 | 0 | 600 | 0 | 600 | 907
| 22 | Retention Costs:
| 23 | Retention Costs | item | S | 1 | 1 | 6750 | 1 | 6750 |  |  | 0 | 0 | 0 | 6750 | 6750 | 904
4 | Line No 6 Item No MRS28 - 1101 | Contractor's site facilities (disestablishment and re-establishment between general localities within the Shire) (Provisional Quantity, if ordered) | Per r |  |  |  | 12 |  | 18000 |  | 2 | 18000 | 0 | 0 | 0 | 18000
| 1 | Re-establishment | each | L | 1 | 1 | 12 | 1500 | 18000 | 12 | 12 | 18000 | 0 | 0 | 0 | 18000 | 910
5 | Line No 7 Item No MRS51 - 1331 | Develop Environmental Management Plan (Construction) | Lump |  |  |  | 1 |  |  |  | 5 | 4000 | 0 | 0 | 0 | 4000
| 1 | Project Manager | week | L | 1 | 1 | 1 | 4000 | 4000 | 1 | 1 | 4000 | 0 | 0 | 0 | 4000 | 901
6 | Line No 8 Item No MRS51 - 1332 | Implement Environmental Management Plan (Construction) | Lump |  |  |  | 1 |  | 14800 |  | 6 | 4800 | 0 | 10000 | 0 | 14800
| 1 | Backhoe | hr | P | 1 | 1 | 50 | 100 | 5000 | 50 | 50 | 0 | 0 | 5000 | 0 | 5000 | 151
| 2 | Labour | hr | L | 2 | 1 | 50 | 48 | 4800 | 100 | 50 | 4800 | 0 | 0 | 0 | 4800 | 151
| 3 | Water Cart - Hire | hr | P | 1 | 1 | 50 | 100 | 5000 | 50 | 50 | 0 | 0 | 5000 | 0 | 5000 | 151
7 | Line No 9 Item No n/a | Provision of Insurances - As outlined in Condiions of Contract | Lump |  |  |  | 1 |  | 12000 |  | 1 | 0 | 0 | 0 | 12000 | 12000
| 1 | CAR | Item | S | 12000 | 1 | 1 | 1 | 12000 | 12000 | 1 | 0 | 0 | 0 | 12000 | 12000 | 904
8 | Line No 10 Item No MRS02 - 1201 | Provision for Traffic | Lump |  |  |  | 1 |  | 117220.267 |  | 99 | 112320 | 0 | 4900.267 | 0 | 117220.267
8.1 | 1 | Traffic Control Hours |  |  |  |  | 624
| 2 | Traffic Controller (Allci | item | L | 4 | 1 | 624 | 45 | 112320 | 277.3333 | 69.3333 | 112320 | 0 | 0 | 0 | 112320 | 141
| 3 | Ute - Hire | day | P | 2 | 1 | 98.0053 | 25 | 4900.267 | 196.0107 | 98.0053 | 0 | 0 | 4900.267 | 0 | 4900.267 | 141
9 | Line No 11 Item No MRS02 - 1202 | Traffic Management Plan | Lump |  |  |  | 1 |  | 4000 |  | 1 | 4000 | 0 | 0 | 0 | 4000
| 1 | Project Manager | week | L | 1 | 1 | 1 | 4000 | 4000 | 1 | 1 | 4000 | 0 | 0 | 0 | 4000 | 901
10 | Line No 12 Item No n/a | Site Safety Plan (Construction) | Lump |  |  |  | 1 |  | 4000 |  | 1 | 4000 | 0 | 0 | 0 | 4000
| 1 | Project Manager | week | L | 1 | 1 | 1 | 4000 | 4000 | 1 | 1 | 4000 | 0 | 0 | 0 | 4000 | 901
11 | Line No 13 Item No 9001S | Survey of existing road formation, delineation, road furniture and culverts prior to works, to provide locality, geometry and detail for reconstruction | m of |  |  |  | 5645 |  | 33305.5 |  | 15 | 0 | 0 | 0 | 33305.5 | 33305.5
| 1 | Survey | day | S | 1 | 1 | 5645 | 5.9 | 33305.5 | 15 | 15 | 0 | 0 | 0 | 33305.5 | 33305.5 | 11
12 | Line No 15 Item No | EARTHWORKS
13 | Line No 17 Item No MRS04 - 3208 | Special excavation, removing existing seal (contaminated material) at repair areas and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 769 |  | 8544.4444 |  | 9 | 0 | 0 | 8544.4444 | 0 | 8544.4444
| 1 | Run Tractor Through & Mix with General Fill.
13.05 | 2 | Depth to remove |  |  |  |  | 0.03
| 3 | Area = Volume / depth |  |  |  |  | 25633.3333
13.1 | 4 | WS220 | day | P | 1 | 3000 | 25633.3333 | 1000 | 8544.4444 | 8.5444 | 8.5444 | 0 | 0 | 8544.4444 | 0 | 8544.4444 | 53
14 | Line No 18 Item No MRS04 - 3208 | Special box excavation, all materials and disposal at approved HSC site for road repairs, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 | [5 empty] | 173481.0467 |  |  | 47912.63 | 0 | 125568.4167 | 0 | 173481.0467
| 1 | Depth of Excacvation (Average):
| 2 | Depth = Area from Item 17 / QTY |  |  |  |  | 0.3625
15 | 4 | Ann Street | m3 |  |  |  | 214 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 5 | Quantity |  |  |  |  | 214
15.1 | 6 | Excavator - 25T | hr | P | 1 | 23.7778 | 214 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 7 | Tipper | hr | P | 2 | 23.7778 | 214 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 8 | Labour | hr | L | 3 | 23.7778 | 214 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 9 | PF Roller | day | P | 1 | 214 | 23.7778 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 10 | CAT297 | hr | P | 1 | 214 | 23.7778 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
16 | 11 | Barberos Road | m3 |  |  |  | 195 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 12 | Quantity |  |  |  |  | 195
16.1 | 13 | Excavator - 25T | hr | P | 1 | 21.6667 | 195 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 14 | Tipper | hr | P | 2 | 21.6667 | 195 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 15 | Labour | hr | L | 3 | 21.6667 | 195 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 16 | PF Roller | day | P | 1 | 195 | 21.6667 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 17 | CAT297 | hr | P | 1 | 195 | 21.6667 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
17 | 18 | Burke Offset Road | m3 |  |  |  | 261 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 19 | Quantity |  |  |  |  | 261
17.1 | 20 | Excavator - 25T | hr | P | 1 | 29 | 261 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 21 | Tipper | hr | P | 2 | 29 | 261 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 22 | Labour | hr | L | 3 | 29 | 261 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 23 | PF Roller | day | P | 1 | 261 | 29 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 24 | CAT297 | hr | P | 1 | 261 | 29 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
18 | 25 | Fabris Road | m3 |  |  |  | 420 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 26 | Quantity |  |  |  |  | 420
18.1 | 27 | Excavator - 25T | hr | P | 1 | 46.6667 | 420 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 28 | Tipper | hr | P | 2 | 46.6667 | 420 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 29 | Labour | hr | L | 3 | 46.6667 | 420 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 30 | PF Roller | day | P | 1 | 420 | 46.6667 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 31 | CAT297 | hr | P | 1 | 420 | 46.6667 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
19 | 32 | Harvey Road | m3 |  |  |  | 40 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 33 | Quantity |  |  |  |  | 40
19.1 | 34 | Excavator - 25T | hr | P | 1 | 4.4444 | 40 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 35 | Tipper | hr | P | 2 | 4.4444 | 40 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 36 | Labour | hr | L | 3 | 4.4444 | 40 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 37 | PF Roller | day | P | 1 | 40 | 4.4444 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 38 | CAT297 | hr | P | 1 | 40 | 4.4444 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
20 | 39 | Heards Road | m3 |  |  |  | 160 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 40 | Quantity |  |  |  |  | 160
20.1 | 41 | Excavator - 25T | hr | P | 1 | 17.7778 | 160 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 42 | Tipper | hr | P | 2 | 17.7778 | 160 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 43 | Labour | hr | L | 3 | 17.7778 | 160 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 44 | PF Roller | day | P | 1 | 160 | 17.7778 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 45 | CAT297 | hr | P | 1 | 160 | 17.7778 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
21 | 46 | Mile Road | m3 |  |  |  | 6 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 47 | Quantity |  |  |  |  | 6
21.1 | 48 | Excavator - 25T | hr | P | 1 | 0.66667 | 6 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 49 | Tipper | hr | P | 2 | 0.66667 | 6 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 50 | Labour | hr | L | 3 | 0.66667 | 6 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 51 | PF Roller | day | P | 1 | 6 | 0.66667 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 52 | CAT297 | hr | P | 1 | 6 | 0.66667 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
22 | 53 | Wallaman Falls Road | m2 |  |  |  | 16140 |  | 88577.7244 |  | 19 | 23435.28 | 0 | 65142.4444 | 0 | 88577.7244
| 54 | Quantity |  |  |  |  | 16140
22.1 | 55 | Excavator - 25T | hr | P | 1 | 36 | 5858.82 | 130 | 21156.85 | 162.745 | 162.745 | 0 | 0 | 21156.85 | 0 | 21156.85 | 53
| 56 | Tipper | hr | P | 3 | 36 | 5858.82 | 90 | 43941.15 | 488.235 | 162.745 | 0 | 0 | 43941.15 | 0 | 43941.15 | 53
| 57 | Labour | hr | L | 3 | 36 | 5858.82 | 48 | 23435.28 | 488.235 | 162.745 | 23435.28 | 0 | 0 | 0 | 23435.28 | 53
| 58 | PF Roller | day | P | 1 | 324 | 36 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 59 | CAT297 | hr | P | 1 | 324 | 36 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
23 | 61 | Allingham Road | m3 |  |  |  | 264 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 62 | Quantity |  |  |  |  | 264
23.1 | 63 | Excavator - 25T | hr | P | 1 | 29.3333 | 264 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 64 | Tipper | hr | P | 2 | 29.3333 | 264 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 65 | Labour | hr | L | 3 | 29.3333 | 264 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 66 | PF Roller | day | P | 1 | 264 | 29.3333 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 67 | CAT297 | hr | P | 1 | 264 | 29.3333 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
24 | 68 | Taylors Beach Road | m2 |  |  |  | 4915 |  | 26967.7222 |  | 6 | 7126.75 | 0 | 19840.9722 | 0 | 26967.7222
| 69 | Quantity |  |  |  |  | 4915
24.1 | 70 | Excavator - 25T | hr | P | 1 | 36 | 1781.6875 | 130 | 6433.8715 | 49.4913 | 49.4913 | 0 | 0 | 6433.8715 | 0 | 6433.8715 | 53
| 71 | Tipper | hr | P | 3 | 36 | 1781.6875 | 90 | 13362.6562 | 148.474 | 49.4913 | 0 | 0 | 13362.6562 | 0 | 13362.6562 | 53
| 72 | Labour | hr | L | 3 | 36 | 1781.6875 | 48 | 7126.75 | 148.474 | 49.4913 | 7126.75 | 0 | 0 | 0 | 7126.75 | 53
| 73 | PF Roller | day | P | 1 | 324 | 36 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 74 | CAT297 | hr | P | 1 | 324 | 36 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
25 | 76 | Taraken Road | m3 |  |  |  | 19 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 77 | Quantity |  |  |  |  | 19
25.1 | 78 | Excavator - 25T | hr | P | 1 | 2.1111 | 19 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 79 | Tipper | hr | P | 2 | 2.1111 | 19 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 80 | Labour | hr | L | 3 | 2.1111 | 19 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 81 | PF Roller | day | P | 1 | 19 | 2.1111 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 82 | CAT297 | hr | P | 1 | 19 | 2.1111 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
26 | 83 | Amos St | m3 |  |  |  | 180 |  | 4130.4444 |  | 1 | 1296 | 0 | 2834.4444 | 0 | 4130.4444
| 84 | Quantity |  |  |  |  | 180
26.1 | 85 | Excavator - 25T | hr | P | 1 | 20 | 180 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 53
| 86 | Tipper | hr | P | 2 | 20 | 180 | 90 | 1620 | 18 | 9 | 0 | 0 | 1620 | 0 | 1620 | 53
| 87 | Labour | hr | L | 3 | 20 | 180 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 53
| 88 | PF Roller | day | P | 1 | 180 | 20 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 89 | CAT297 | hr | P | 1 | 180 | 20 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
27 | 90 | Lannercost Extension Road | m2 |  |  |  | 3028 |  | 16631.1556 |  | 4 | 4390.6 | 0 | 12240.5556 | 0 | 16631.1556
| 91 | Quantity |  |  |  |  | 3028
27.1 | 92 | Excavator - 25T | hr | P | 1 | 36 | 1097.65 | 130 | 3963.7361 | 30.4903 | 30.4903 | 0 | 0 | 3963.7361 | 0 | 3963.7361 | 53
| 93 | Tipper | hr | P | 3 | 36 | 1097.65 | 90 | 8232.375 | 91.4708 | 30.4903 | 0 | 0 | 8232.375 | 0 | 8232.375 | 53
| 94 | Labour | hr | L | 3 | 36 | 1097.65 | 48 | 4390.6 | 91.4708 | 30.4903 | 4390.6 | 0 | 0 | 0 | 4390.6 | 53
| 95 | PF Roller | day | P | 1 | 324 | 36 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 53
| 96 | CAT297 | hr | P | 1 | 324 | 36 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 53
28 | Line No 19 Item No MRS04 - 3208 | Special excavation all materials, for pothole repairs and disposal at approved HSC disposal site, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 9 |  | 8016 |  | 3 | 3456 | 0 | 4560 | 0 | 8016
| 1 | 4 Locations for potholes, assume 6 hours per pot hole.
28.1 | 2 | Backhoe | hr | P | 1 | 1 | 24 | 100 | 2400 | 24 | 24 | 0 | 0 | 2400 | 0 | 2400 | 53
| 3 | Tipper | hr | P | 1 | 1 | 24 | 90 | 2160 | 24 | 24 | 0 | 0 | 2160 | 0 | 2160 | 53
| 4 | Labour | hr | L | 3 | 1 | 24 | 48 | 3456 | 72 | 24 | 3456 | 0 | 0 | 0 | 3456 | 53
29 | Line No 20 Item No MRS04 - 3208 | Special excavation, all materials for culverts, inlet and outlet structures and disposal at approved HSC disposal site, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 15 |  | 14028 |  | 5 | 6048 | 0 | 7980 | 0 | 14028
| 1 | 7 Locations for culverts, assume 6 hours per pot hole.
29.1 | 2 | Backhoe | hr | P | 1 | 1 | 42 | 100 | 4200 | 42 | 42 | 0 | 0 | 4200 | 0 | 4200 | 88
| 3 | Tipper | hr | P | 1 | 1 | 42 | 90 | 3780 | 42 | 42 | 0 | 0 | 3780 | 0 | 3780 | 88
| 4 | Labour | hr | L | 3 | 1 | 42 | 48 | 6048 | 126 | 42 | 6048 | 0 | 0 | 0 | 6048 | 88
30 | Line No 21 Item No MRS04 - 3208 | Special excavation, removal of debris and silt from culvert inlets and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 18 |  | 8016 |  | 3 | 3456 | 0 | 4560 | 0 | 8016
| 1 | 4 Locations for culverts, assume 6 hours per pot hole.
30.1 | 2 | Backhoe | hr | P | 1 | 1 | 24 | 100 | 2400 | 24 | 24 | 0 | 0 | 2400 | 0 | 2400 | 88
| 3 | Tipper | hr | P | 1 | 1 | 24 | 90 | 2160 | 24 | 24 | 0 | 0 | 2160 | 0 | 2160 | 88
| 4 | Labour | hr | L | 3 | 1 | 24 | 48 | 3456 | 72 | 24 | 3456 | 0 | 0 | 0 | 3456 | 88
31 | Line No 22 Item No MRS04 - 3208 | Special excavation, removal of debris and silt from culvert barrels including hydraulic pressure blasting applied for dislodging, removal and cleaning and disposal at approved HSC site, iincluding haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 7 |  | 3106 |  | 1 | 1296 | 0 | 1810 | 0 | 3106
| 1 | 1Locations for de-silting, assume 9 hours per pot hole.
31.1 | 2 | Backhoe | hr | P | 1 | 1 | 9 | 100 | 900 | 9 | 9 | 0 | 0 | 900 | 0 | 900 | 88
| 3 | Tipper | hr | P | 1 | 1 | 9 | 90 | 810 | 9 | 9 | 0 | 0 | 810 | 0 | 810 | 88
| 4 | Labour | hr | L | 3 | 1 | 9 | 48 | 1296 | 27 | 9 | 1296 | 0 | 0 | 0 | 1296 | 88
| 5 | Water Cart - Hire | hr | P | 1 | 1 | 1 | 100 | 100 | 1 | 1 | 0 | 0 | 100 | 0 | 100 | 88
32 | Line No 23 Item No MRS04 - 3208 | Special excavation, removal of silt from table drains and reshape drains; and from road surfaces and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 101 |  | 10020 |  | 4 | 4320 | 0 | 5700 | 0 | 10020
| 1 | 5 Locations for Drain Cleaning, assume 6 hours per location.
32.1 | 2 | Backhoe | hr | P | 1 | 1 | 30 | 100 | 3000 | 30 | 30 | 0 | 0 | 3000 | 0 | 3000 | 88
| 3 | Tipper | hr | P | 1 | 1 | 30 | 90 | 2700 | 30 | 30 | 0 | 0 | 2700 | 0 | 2700 | 88
| 4 | Labour | hr | L | 3 | 1 | 30 | 48 | 4320 | 90 | 30 | 4320 | 0 | 0 | 0 | 4320 | 88
33 | Line No 24 Item No MRS04 - 3108 | Excavation and disposal of Unsuitable Material with individual excavation <= 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | m3 |  |  |  | 160 |  | 9124.4444 |  | 3 | 2880 | 0 | 6244.4444 | 0 | 9124.4444
33.1 | 1 | Excavator - 25T | hr | P | 1 | 8 | 160 | 130 | 2600 | 20 | 20 | 0 | 0 | 2600 | 0 | 2600 | 57
| 2 | Tipper | hr | P | 2 | 8 | 160 | 90 | 3600 | 40 | 20 | 0 | 0 | 3600 | 0 | 3600 | 57
| 3 | Labour | hr | L | 3 | 8 | 160 | 48 | 2880 | 60 | 20 | 2880 | 0 | 0 | 0 | 2880 | 57
| 4 | PF Roller | day | P | 1 | 72 | 8 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 57
| 5 | CAT297 | hr | P | 1 | 72 | 8 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 57
34 | Line No 25 Item No MRS04 - 3109 | Excavation and disposal of Unsuitable Material with individual excavation > 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | [6 empty] | 94060.0108 |  |  | 26528.6256 | 0 | 67531.3853 | 0 | 94060.0108
| 1 | Depth of Excacvation (Average):
| 2 | QTY / Area of seal to be removed (4259 / 25842) |  |  |  |  | 0.1648
35 | 4 | Ann Street | m3 |  |  |  | 214 |  | 4130.4406 |  | 1 | 1295.9988 | 0 | 2834.4418 | 0 | 4130.4406
| 5 | Quantity |  |  |  |  | 214
35.1 | 6 | Excavator - 25T | hr | P | 1 | 23.7778 | 214 | 130 | 1169.9989 | 9 | 9 | 0 | 0 | 1169.9989 | 0 | 1169.9989 | 57
| 7 | Tipper | hr | P | 2 | 23.7778 | 214 | 90 | 1619.9985 | 18 | 9 | 0 | 0 | 1619.9985 | 0 | 1619.9985 | 57
| 8 | Labour | hr | L | 3 | 23.7778 | 214 | 48 | 1295.9988 | 27 | 9 | 1295.9988 | 0 | 0 | 0 | 1295.9988 | 57
| 9 | PF Roller | day | P | 1 | 214.0002 | 23.7778 | 365 | 40.5555 | 0.11111 | 0.11111 | 0 | 0 | 40.5555 | 0 | 40.5555 | 57
| 10 | CAT297 | hr | P | 1 | 214.0002 | 23.7778 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 57
36 | 11 | Barberos Road | m3 |  |  |  | 195 |  | 3763.7192 |  | 1 | 1180.9335 | 0 | 2582.7857 | 0 | 3763.7192
| 12 | Quantity |  |  |  |  | 195
36.1 | 13 | Excavator - 25T | hr | P | 1 | 23.7778 | 195 | 130 | 1066.1205 | 8.2009 | 8.2009 | 0 | 0 | 1066.1205 | 0 | 1066.1205 | 57
| 14 | Tipper | hr | P | 2 | 23.7778 | 195 | 90 | 1476.1668 | 16.4019 | 8.2009 | 0 | 0 | 1476.1668 | 0 | 1476.1668 | 57
| 15 | Labour | hr | L | 3 | 23.7778 | 195 | 48 | 1180.9335 | 24.6028 | 8.2009 | 1180.9335 | 0 | 0 | 0 | 1180.9335 | 57
| 16 | PF Roller | day | P | 1 | 214.0002 | 21.6667 | 365 | 36.9548 | 0.10125 | 0.10125 | 0 | 0 | 36.9548 | 0 | 36.9548 | 57
| 17 | CAT297 | hr | P | 1 | 214.0002 | 21.6667 | 35 | 3.5436 | 0.10125 | 0.10125 | 0 | 0 | 3.5436 | 0 | 3.5436 | 57
37 | 18 | Burke Offset Road | m3 |  |  |  | 261 |  | 5037.5934 |  | 2 | 1580.634 | 0 | 3456.9594 | 0 | 5037.5934
| 19 | Quantity |  |  |  |  | 261
37.1 | 20 | Excavator - 25T | hr | P | 1 | 23.7778 | 261 | 130 | 1426.9613 | 10.9766 | 10.9766 | 0 | 0 | 1426.9613 | 0 | 1426.9613 | 57
| 21 | Tipper | hr | P | 2 | 23.7778 | 261 | 90 | 1975.7925 | 21.9533 | 10.9766 | 0 | 0 | 1975.7925 | 0 | 1975.7925 | 57
| 22 | Labour | hr | L | 3 | 23.7778 | 261 | 48 | 1580.634 | 32.9299 | 10.9766 | 1580.634 | 0 | 0 | 0 | 1580.634 | 57
| 23 | PF Roller | day | P | 1 | 214.0002 | 29 | 365 | 49.4626 | 0.13551 | 0.13551 | 0 | 0 | 49.4626 | 0 | 49.4626 | 57
| 24 | CAT297 | hr | P | 1 | 214.0002 | 29 | 35 | 4.743 | 0.13551 | 0.13551 | 0 | 0 | 4.743 | 0 | 4.743 | 57
38 | 25 | Fabris Road | m3 |  |  |  | 420 |  | 8106.4722 |  | 2 | 2543.549 | 0 | 5562.9231 | 0 | 8106.4722
| 26 | Quantity |  |  |  |  | 420
38.1 | 27 | Excavator - 25T | hr | P | 1 | 23.7778 | 420 | 130 | 2296.2595 | 17.6635 | 17.6635 | 0 | 0 | 2296.2595 | 0 | 2296.2595 | 57
| 28 | Tipper | hr | P | 2 | 23.7778 | 420 | 90 | 3179.4363 | 35.3271 | 17.6635 | 0 | 0 | 3179.4363 | 0 | 3179.4363 | 57
| 29 | Labour | hr | L | 3 | 23.7778 | 420 | 48 | 2543.549 | 52.9906 | 17.6635 | 2543.549 | 0 | 0 | 0 | 2543.549 | 57
| 30 | PF Roller | day | P | 1 | 214.0002 | 46.6667 | 365 | 79.5949 | 0.21807 | 0.21807 | 0 | 0 | 79.5949 | 0 | 79.5949 | 57
| 31 | CAT297 | hr | P | 1 | 214.0002 | 46.6667 | 35 | 7.6324 | 0.21807 | 0.21807 | 0 | 0 | 7.6324 | 0 | 7.6324 | 57
39 | 32 | Harvey Road | m3 |  |  |  | 40 |  | 772.045 |  | 1 | 242.2428 | 0 | 529.8022 | 0 | 772.045
| 33 | Quantity |  |  |  |  | 40
39.1 | 34 | Excavator - 25T | hr | P | 1 | 23.7778 | 40 | 130 | 218.6914 | 1.6822 | 1.6822 | 0 | 0 | 218.6914 | 0 | 218.6914 | 57
| 35 | Tipper | hr | P | 2 | 23.7778 | 40 | 90 | 302.8035 | 3.3645 | 1.6822 | 0 | 0 | 302.8035 | 0 | 302.8035 | 57
| 36 | Labour | hr | L | 3 | 23.7778 | 40 | 48 | 242.2428 | 5.0467 | 1.6822 | 242.2428 | 0 | 0 | 0 | 242.2428 | 57
| 37 | PF Roller | day | P | 1 | 214.0002 | 4.4444 | 365 | 7.5805 | 0.020768 | 0.020768 | 0 | 0 | 7.5805 | 0 | 7.5805 | 57
| 38 | CAT297 | hr | P | 1 | 214.0002 | 4.4444 | 35 | 0.72689 | 0.020768 | 0.020768 | 0 | 0 | 0.72689 | 0 | 0.72689 | 57
40 | 39 | Heards Road | m3 |  |  |  | 160 |  | 3088.1799 |  | 1 | 968.9711 | 0 | 2119.2088 | 0 | 3088.1799
| 40 | Quantity |  |  |  |  | 160
40.1 | 41 | Excavator - 25T | hr | P | 1 | 23.7778 | 160 | 130 | 874.7655 | 6.729 | 6.729 | 0 | 0 | 874.7655 | 0 | 874.7655 | 57
| 42 | Tipper | hr | P | 2 | 23.7778 | 160 | 90 | 1211.2138 | 13.4579 | 6.729 | 0 | 0 | 1211.2138 | 0 | 1211.2138 | 57
| 43 | Labour | hr | L | 3 | 23.7778 | 160 | 48 | 968.9711 | 20.1869 | 6.729 | 968.9711 | 0 | 0 | 0 | 968.9711 | 57
| 44 | PF Roller | day | P | 1 | 214.0002 | 17.7778 | 365 | 30.3219 | 0.083074 | 0.083074 | 0 | 0 | 30.3219 | 0 | 30.3219 | 57
| 45 | CAT297 | hr | P | 1 | 214.0002 | 17.7778 | 35 | 2.9076 | 0.083074 | 0.083074 | 0 | 0 | 2.9076 | 0 | 2.9076 | 57
41 | 46 | Mile Road | m3 |  |  |  | 6 |  | 115.8067 |  | 1 | 36.3364 | 0 | 79.4703 | 0 | 115.8067
| 47 | Quantity |  |  |  |  | 6
41.1 | 48 | Excavator - 25T | hr | P | 1 | 23.7778 | 6 | 130 | 32.8037 | 0.25234 | 0.25234 | 0 | 0 | 32.8037 | 0 | 32.8037 | 57
| 49 | Tipper | hr | P | 2 | 23.7778 | 6 | 90 | 45.4205 | 0.50467 | 0.25234 | 0 | 0 | 45.4205 | 0 | 45.4205 | 57
| 50 | Labour | hr | L | 3 | 23.7778 | 6 | 48 | 36.3364 | 0.75701 | 0.25234 | 36.3364 | 0 | 0 | 0 | 36.3364 | 57
| 51 | PF Roller | day | P | 1 | 214.0002 | 0.66667 | 365 | 1.1371 | 0.0031153 | 0.0031153 | 0 | 0 | 1.1371 | 0 | 1.1371 | 57
| 52 | CAT297 | hr | P | 1 | 214.0002 | 0.66667 | 35 | 0.10903 | 0.0031153 | 0.0031153 | 0 | 0 | 0.10903 | 0 | 0.10903 | 57
42 | 53 | Wallaman Falls Road | m3 |  |  |  | 2660 |  | 40240 |  | 9 | 10640 | 0 | 29600 | 0 | 40240
| 54 | Quantity |  |  |  |  | 16140
42.1 | 55 | Excavator - 25T | hr | P | 1 | 36 | 2660 | 130 | 9605.5556 | 73.8889 | 73.8889 | 0 | 0 | 9605.5556 | 0 | 9605.5556 | 57
| 56 | Tipper | hr | P | 3 | 36 | 2660 | 90 | 19950 | 221.6667 | 73.8889 | 0 | 0 | 19950 | 0 | 19950 | 57
| 57 | Labour | hr | L | 3 | 36 | 2660 | 48 | 10640 | 221.6667 | 73.8889 | 10640 | 0 | 0 | 0 | 10640 | 57
| 58 | PF Roller | day | P | 1 | 324 | 36 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 57
| 59 | CAT297 | hr | P | 1 | 324 | 36 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 57
43 | 61 | Allingham Road | m3 |  |  |  | 264 |  | 5095.4968 |  | 2 | 1598.8022 | 0 | 3496.6946 | 0 | 5095.4968
| 62 | Quantity |  |  |  |  | 264
43.1 | 63 | Excavator - 25T | hr | P | 1 | 23.7778 | 264 | 130 | 1443.3631 | 11.1028 | 11.1028 | 0 | 0 | 1443.3631 | 0 | 1443.3631 | 57
| 64 | Tipper | hr | P | 2 | 23.7778 | 264 | 90 | 1998.5028 | 22.2056 | 11.1028 | 0 | 0 | 1998.5028 | 0 | 1998.5028 | 57
| 65 | Labour | hr | L | 3 | 23.7778 | 264 | 48 | 1598.8022 | 33.3084 | 11.1028 | 1598.8022 | 0 | 0 | 0 | 1598.8022 | 57
| 66 | PF Roller | day | P | 1 | 214.0002 | 29.3333 | 365 | 50.0311 | 0.13707 | 0.13707 | 0 | 0 | 50.0311 | 0 | 50.0311 | 57
| 67 | CAT297 | hr | P | 1 | 214.0002 | 29.3333 | 35 | 4.7975 | 0.13707 | 0.13707 | 0 | 0 | 4.7975 | 0 | 4.7975 | 57
44 | 68 | Taylors Beach Road | m3 |  |  |  | 810 |  | 12284.4444 |  | 3 | 3240 | 0 | 9044.4444 | 0 | 12284.4444
| 69 | Quantity (m2 of road - From item ) |  |  |  |  | 4915
44.1 | 70 | Excavator - 25T | hr | P | 1 | 36 | 810 | 130 | 2925 | 22.5 | 22.5 | 0 | 0 | 2925 | 0 | 2925 | 57
| 71 | Tipper | hr | P | 3 | 36 | 810 | 90 | 6075 | 67.5 | 22.5 | 0 | 0 | 6075 | 0 | 6075 | 57
| 72 | Labour | hr | L | 3 | 36 | 810 | 48 | 3240 | 67.5 | 22.5 | 3240 | 0 | 0 | 0 | 3240 | 57
| 73 | PF Roller | day | P | 1 | 324 | 36 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 57
| 74 | CAT297 | hr | P | 1 | 324 | 36 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 57
45 | 76 | Taraken Road | m3 |  |  |  | 19 |  | 366.7214 |  | 1 | 115.0653 | 0 | 251.656 | 0 | 366.7214
| 77 | Quantity |  |  |  |  | 19
45.1 | 78 | Excavator - 25T | hr | P | 1 | 23.7778 | 19 | 130 | 103.8784 | 0.79906 | 0.79906 | 0 | 0 | 103.8784 | 0 | 103.8784 | 57
| 79 | Tipper | hr | P | 2 | 23.7778 | 19 | 90 | 143.8316 | 1.5981 | 0.79906 | 0 | 0 | 143.8316 | 0 | 143.8316 | 57
| 80 | Labour | hr | L | 3 | 23.7778 | 19 | 48 | 115.0653 | 2.3972 | 0.79906 | 115.0653 | 0 | 0 | 0 | 115.0653 | 57
| 81 | PF Roller | day | P | 1 | 214.0002 | 2.1111 | 365 | 3.6007 | 0.009865 | 0.009865 | 0 | 0 | 3.6007 | 0 | 3.6007 | 57
| 82 | CAT297 | hr | P | 1 | 214.0002 | 2.1111 | 35 | 0.34527 | 0.009865 | 0.009865 | 0 | 0 | 0.34527 | 0 | 0.34527 | 57
46 | 83 | Amos Street | m3 |  |  |  | 180 |  | 3474.2024 |  | 1 | 1090.0924 | 0 | 2384.1099 | 0 | 3474.2024
| 84 | Quantity |  |  |  |  | 180
46.1 | 85 | Excavator - 25T | hr | P | 1 | 23.7778 | 180 | 130 | 984.1112 | 7.5701 | 7.5701 | 0 | 0 | 984.1112 | 0 | 984.1112 | 57
| 86 | Tipper | hr | P | 2 | 23.7778 | 180 | 90 | 1362.6155 | 15.1402 | 7.5701 | 0 | 0 | 1362.6155 | 0 | 1362.6155 | 57
| 87 | Labour | hr | L | 3 | 23.7778 | 180 | 48 | 1090.0924 | 22.7103 | 7.5701 | 1090.0924 | 0 | 0 | 0 | 1090.0924 | 57
| 88 | PF Roller | day | P | 1 | 214.0002 | 20 | 365 | 34.1121 | 0.093458 | 0.093458 | 0 | 0 | 34.1121 | 0 | 34.1121 | 57
| 89 | CAT297 | hr | P | 1 | 214.0002 | 20 | 35 | 3.271 | 0.093458 | 0.093458 | 0 | 0 | 3.271 | 0 | 3.271 | 57
47 | 90 | Lannercost Extension Road | m3 |  |  |  | 499 |  | 7584.8889 |  | 2 | 1996 | 0 | 5588.8889 | 0 | 7584.8889
| 91 | Quantity |  |  |  |  | 3028
47.1 | 92 | Excavator - 25T | hr | P | 1 | 36 | 499 | 130 | 1801.9444 | 13.8611 | 13.8611 | 0 | 0 | 1801.9444 | 0 | 1801.9444 | 57
| 93 | Tipper | hr | P | 3 | 36 | 499 | 90 | 3742.5 | 41.5833 | 13.8611 | 0 | 0 | 3742.5 | 0 | 3742.5 | 57
| 94 | Labour | hr | L | 3 | 36 | 499 | 48 | 1996 | 41.5833 | 13.8611 | 1996 | 0 | 0 | 0 | 1996 | 57
| 95 | PF Roller | day | P | 1 | 324 | 36 | 365 | 40.5556 | 0.11111 | 0.11111 | 0 | 0 | 40.5556 | 0 | 40.5556 | 57
| 96 | CAT297 | hr | P | 1 | 324 | 36 | 35 | 3.8889 | 0.11111 | 0.11111 | 0 | 0 | 3.8889 | 0 | 3.8889 | 57
48 | Line No 26 Item No MRS04 - 3502 | PRINCIPAL SUPPLIED - Supply select backfill material for backfill to unsuitable excavations, -75 mm graded rock (Principal paid material) (Provisional Quantity, if ordered)
49 | Line No 27 Item No MRS04 - 3502 | Deliver select backfill material for backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 160 |  | 691.2 |  | 18 | 0 | 0 | 0 | 691.2 | 691.2
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 384
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 160 | 0.24 | 691.2 | 2880 | 160 | 0 | 0 | 0 | 691.2 | 691.2 | 613
50 | Line No 28 Item No MRS04 - 3502 | Backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 160 |  | 10338.9867 |  | 2 | 2949.12 | 0 | 7389.8667 | 0 | 10338.9867
50.1 | 1 | Grader | hr | P | 1 | 25 | 384 | 165 | 2534.4 | 15.36 | 15.36 | 0 | 0 | 2534.4 | 0 | 2534.4 | 57
| 2 | Water Cart - Hire | hr | P | 2 | 25 | 384 | 100 | 3072 | 30.72 | 15.36 | 0 | 0 | 3072 | 0 | 3072 | 57
| 3 | SD Roller | day | P | 1 | 225 | 384 | 365 | 622.9333 | 1.7067 | 1.7067 | 0 | 0 | 622.9333 | 0 | 622.9333 | 57
| 4 | PF Roller | day | P | 1 | 225 | 384 | 365 | 622.9333 | 1.7067 | 1.7067 | 0 | 0 | 622.9333 | 0 | 622.9333 | 57
| 5 | Labour | hr | L | 4 | 25 | 384 | 48 | 2949.12 | 61.44 | 15.36 | 2949.12 | 0 | 0 | 0 | 2949.12 | 57
| 6 | CAT297 | hr | P | 1 | 25 | 384 | 35 | 537.6 | 15.36 | 15.36 | 0 | 0 | 537.6 | 0 | 537.6 | 57
51 | Line No 29 Item No MRS04 - 3501 | PRINCIPAL SUPPLIED - Supply general fill material for repairs to formation, culverts and drains (Principal paid material) (Provisional Quantity, if ordered)
52 | Line No 30 Item No MRS04 - 3501 | Deliver general fill material, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 52 |  | 539.136 |  | 14 | 0 | 0 | 0 | 539.136 | 539.136
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 124.8
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 124.8 | 0.24 | 539.136 | 2246.4 | 124.8 | 0 | 0 | 0 | 539.136 | 539.136 | 613
53 | Line No 31 Item No MRS04 - 3501 | Fill repair to formation, inlet structure backfill and drain repairs with general fill material (Contractor installation Rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 52 |  | 6680 |  | 3 | 2880 | 0 | 3800 | 0 | 6680
| 1 | 5 Locations for Drain Cleaning, assume 4 hours per location.
53.1 | 2 | Backhoe | hr | P | 1 | 1 | 20 | 100 | 2000 | 20 | 20 | 0 | 0 | 2000 | 0 | 2000 | 88
| 3 | Tipper | hr | P | 1 | 1 | 20 | 90 | 1800 | 20 | 20 | 0 | 0 | 1800 | 0 | 1800 | 88
| 4 | Labour | hr | L | 3 | 1 | 20 | 48 | 2880 | 60 | 20 | 2880 | 0 | 0 | 0 | 2880 | 88
54 | Line No 32 Item No MRS04 - 3402 | Subgrade treatment Type A, compact existing (Provisonal Quantity, if ordered) | m2 |  |  |  | 15971 |  | 28719.4071 |  | 8 | 9199.296 | 0 | 19520.1111 | 0 | 28719.4071
54.1 | 1 | Grader | hr | P | 1 | 250 | 15971 | 165 | 10540.86 | 63.884 | 63.884 | 0 | 0 | 10540.86 | 0 | 10540.86 | 61
| 2 | PF Roller | day | P | 1 | 2250 | 15971 | 365 | 2590.8511 | 7.0982 | 7.0982 | 0 | 0 | 2590.8511 | 0 | 2590.8511 | 61
| 3 | Water Cart - Hire | hr | P | 1 | 250 | 15971 | 100 | 6388.4 | 63.884 | 63.884 | 0 | 0 | 6388.4 | 0 | 6388.4 | 61
| 4 | Labour | hr | L | 3 | 250 | 15971 | 48 | 9199.296 | 191.652 | 63.884 | 9199.296 | 0 | 0 | 0 | 9199.296 | 61
55 | Line No 33 Item No MRS04 - 3411 | PRINCIPAL SUPPLIED - Supply -75 mm graded rock material for subgrade treatment Type I (Principal paid material) (Provisional Quantity, if ordered)
56 | Line No 34 Item No MRS04 - 3411 | Deliver -75 mm graded rock material for subgrade treatment Type I, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 4259 |  | 44157.312 |  | 0 | 0 | 0 | 0 | 44157.312 | 44157.312
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 10221.6
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 10221.6 | 0.24 | 44157.312 | 0 | 0 | 0 | 0 | 0 | 44157.312 | 44157.312 | 613
57 | Line No 35 Item No MRS04 - 3411 | Subgrade in cuttings, subgrade treatment Type I, -75 mm graded rock fill (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 4259 |  | 103203.572 |  |  | 29438.0608 | 0 | 73765.5112 | 0 | 103203.572
57.01 | 4 | Ann Street | m3 |  |  | 3.736% | 159.1177 |  |  |  | 1 | 1099.8158 | 0 | 2755.9042 | 0 | 3855.72
57.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 144.9904 |  |  |  | 1 | 1002.1686 | 0 | 2511.2211 | 0 | 3513.3898
57.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 194.0641 |  |  |  | 1 | 1341.3642 | 0 | 3361.1729 | 0 | 4702.5371
57.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 312.287 |  |  |  | 2 | 2158.517 | 0 | 5408.784 | 0 | 7567.301
57.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 29.7416 |  |  |  | 1 | 205.5731 | 0 | 515.1223 | 0 | 720.6953
57.06 | 39 | Heards Road | m3 |  |  | 2.793% | 118.9665 |  |  |  | 1 | 822.2922 | 0 | 2060.4891 | 0 | 2882.7813
57.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 4.4612 |  |  |  | 1 | 30.836 | 0 | 77.2683 | 0 | 108.1043
57.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 1977.8177 |  |  |  | 8 | 13670.6078 | 0 | 34255.6319 | 0 | 47926.2398
57.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 196.2947 |  |  |  | 1 | 1356.7821 | 0 | 3399.8071 | 0 | 4756.5892
57.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 602.2678 |  |  |  | 3 | 4162.8543 | 0 | 10431.2263 | 0 | 14594.0805
57.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 14.1273 |  |  |  | 1 | 97.6472 | 0 | 244.6831 | 0 | 342.3303
57.12 | 83 | Amos Street | m3 |  |  | 3.142% | 133.8373 |  |  |  | 1 | 925.0787 | 0 | 2318.0503 | 0 | 3243.129
57.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 371.0267 |  |  |  | 2 | 2564.5238 | 0 | 6426.1505 | 0 | 8990.6743
57.2 | 1 | Grader | hr | P | 1 | 66.667 | 10221.6 | 165 | 25298.3335 | 153.3232 | 153.3232 | 0 | 0 | 25298.3335 | 0 | 25298.3335 | 61
| 2 | Water Cart - Hire | hr | P | 2 | 66.667 | 10221.6 | 100 | 30664.6467 | 306.6465 | 153.3232 | 0 | 0 | 30664.6467 | 0 | 30664.6467 | 61
| 3 | SD Roller | day | P | 1 | 600.003 | 10221.6 | 365 | 6218.1089 | 17.0359 | 17.0359 | 0 | 0 | 6218.1089 | 0 | 6218.1089 | 61
| 4 | PF Roller | day | P | 1 | 600.003 | 10221.6 | 365 | 6218.1089 | 17.0359 | 17.0359 | 0 | 0 | 6218.1089 | 0 | 6218.1089 | 61
| 5 | Labour | hr | L | 4 | 66.667 | 10221.6 | 48 | 29438.0608 | 613.2929 | 153.3232 | 29438.0608 | 0 | 0 | 0 | 29438.0608 | 61
| 6 | CAT297 | hr | P | 1 | 66.667 | 10221.6 | 35 | 5366.3132 | 153.3232 | 153.3232 | 0 | 0 | 5366.3132 | 0 | 5366.3132 | 61
58 | Line No 36 Item No MRS04 - 3304 | Supply and installation of geotextile, Strength Class D, Filtration Class IV for subgrade treatment Type I and drainage (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | m2 |  |  |  | 10648 |  | 26353.8 |  | 0 | 0 | 26353.8 | 0 | 0 | 26353.8
| 1 | A34 | m² | M | 1 | 1 | 11712.8 | 2.25 | 26353.8 |  |  | 0 | 26353.8 | 0 | 0 | 26353.8 | 222
59 | Line No 37 Item No MRS04 - 3304 | Supply and installation of geotextile, Strength Class D, Filtration Class IV at culvert pipe repair joints in 200 mm wide circumferential strips with 500 mm end overlaps (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | m2 |  |  |  | 8 |  | 19.8 |  | 0 | 0 | 19.8 | 0 | 0 | 19.8
| 1 | A34 | m² | M | 1 | 1 | 8.8 | 2.25 | 19.8 |  |  | 0 | 19.8 | 0 | 0 | 19.8 | 222
60 | Line No 38 Item No 9002PS | Extra over Items MRS04-3208.1PS to MRS04-3208.9PS, MRS04-3108PS and MRS04-3109PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | m3 * |  |  |  | 71570 |  | 49469.184 |  | 0 | 0 | 0 | 0 | 49469.184 | 49469.184
| 1 | Gravel Haulage (18 km) | km | S | 1 | 1 | 206121.6 | 0.24 | 49469.184 | 0 |  | 0 | 0 | 0 | 49469.184 | 49469.184 | 57
61 | Line No 39 Item No 9003PS | Extra over Items MRS04-3502.2PS and MRS04-3411.2PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | m3 * |  |  |  | 59212 |  | 40927.3344 |  | 0 | 0 | 0 | 0 | 40927.3344 | 40927.3344
| 1 | Gravel Haulage (18 km) | km | S | 1 | 1 | 170530.56 | 0.24 | 40927.3344 | 0 |  | 0 | 0 | 0 | 40927.3344 | 40927.3344 | 613
62 | Line No 41 Item No | DRAINAGE AND PROTECTION
63 | Line No 43 Item No MRS03 - 2101 | Removal and salvaging existing culverts for reinstallation; pipe culverts up to 600 dia, box culverts up to 600 x 600 (Provisional Quantity, if ordered) | m |  |  |  | 10 |  | 2723.4553 |  | 1 | 863.8272 | 0 | 1859.6281 | 0 | 2723.4553
63.1 | 1 | Excavator - 25T | hr | P | 1 | 1.667 | 10 | 130 | 779.844 | 5.9988 | 5.9988 | 0 | 0 | 779.844 | 0 | 779.844 | 41
| 2 | Tipper | hr | P | 2 | 1.667 | 10 | 90 | 1079.784 | 11.9976 | 5.9988 | 0 | 0 | 1079.784 | 0 | 1079.784 | 41
| 3 | Labour | hr | L | 3 | 1.667 | 10 | 48 | 863.8272 | 17.9964 | 5.9988 | 863.8272 | 0 | 0 | 0 | 863.8272 | 41
64 | Line No 44 Item No MRS03 - 2101 | Removal and disposal at approved HSC site, of culvert pipes up to 600 dia, including all haulage (Provisional Quantity, if ordered) | m |  |  |  | 24 |  | 4085.4893 |  | 1 | 1295.838 | 0 | 2789.6513 | 0 | 4085.4893
64.1 | 1 | Excavator - 25T | hr | P | 1 | 2.667 | 24 | 130 | 1169.8538 | 8.9989 | 8.9989 | 0 | 0 | 1169.8538 | 0 | 1169.8538 | 41
| 2 | Tipper | hr | P | 2 | 2.667 | 24 | 90 | 1619.7975 | 17.9978 | 8.9989 | 0 | 0 | 1619.7975 | 0 | 1619.7975 | 41
| 3 | Labour | hr | L | 3 | 2.667 | 24 | 48 | 1295.838 | 26.9966 | 8.9989 | 1295.838 | 0 | 0 | 0 | 1295.838 | 41
65 | Line No 45 Item No MRS03 - 2102 | Demolition and removal of culvert end structures and disposal at approved HSC site, including all haulage (Provisional Quantity, if ordered) | m3 |  |  |  | 2 |  | 817.2817 |  | 1 | 259.2259 | 0 | 558.0558 | 0 | 817.2817
65.1 | 1 | Excavator - 25T | hr | P | 1 | 1.111 | 2 | 130 | 234.0234 | 1.8002 | 1.8002 | 0 | 0 | 234.0234 | 0 | 234.0234 | 41
| 2 | Tipper | hr | P | 2 | 1.111 | 2 | 90 | 324.0324 | 3.6004 | 1.8002 | 0 | 0 | 324.0324 | 0 | 324.0324 | 41
| 3 | Labour | hr | L | 3 | 1.111 | 2 | 48 | 259.2259 | 5.4005 | 1.8002 | 259.2259 | 0 | 0 | 0 | 259.2259 | 41
65.5 | Line No 46 Item No MRS03 - 2221 | Installation of salvaged concrete culvert components, pipe culverts up to 600 mm dia, box culverts up to 600 x 600 (Provisional Quantity, if ordered) | m |  |  |  | 10 |  | 4086.4086 |  | 2 | 1296.1296 | 0 | 2790.279 | 0 | 4086.4086
65.6 | 1 | Excavator - 25T | hr | P | 1 | 1.111 | 10 | 130 | 1170.117 | 9.0009 | 9.0009 | 0 | 0 | 1170.117 | 0 | 1170.117 | 82
| 2 | Tipper | hr | P | 2 | 1.111 | 10 | 90 | 1620.162 | 18.0018 | 9.0009 | 0 | 0 | 1620.162 | 0 | 1620.162 | 82
| 3 | Labour | hr | L | 3 | 1.111 | 10 | 48 | 1296.1296 | 27.0027 | 9.0009 | 1296.1296 | 0 | 0 | 0 | 1296.1296 | 82
66 | Line No 47 Item No MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 2, 375 mm dia (Provisional Quantity, if ordered) | m |  |  |  | 7.2 |  | 2859.048 |  | 1 | 864 | 735.048 | 1260 | 0 | 2859.048
| 1 | Purchase Materials:
| 2 | 375 RCP | m | M | 1 | 1 | 7.2 | 96.09 | 691.848 |  |  | 0 | 691.848 | 0 | 0 | 691.848 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 1.8 | 24 | 43.2 |  |  | 0 | 43.2 | 0 | 0 | 43.2 | QMS
| 4 | Install:
66.1 | 5 | Excavator - 25T | hr | P | 1 | 0.8 | 7.2 | 130 | 1170 | 9 | 9 | 0 | 0 | 1170 | 0 | 1170 | 81
| 6 | Labour | hr | L | 2 | 0.8 | 7.2 | 48 | 864 | 18 | 9 | 864 | 0 | 0 | 0 | 864 | 81
| 7 | Plate Compactor | hr | P | 1 | 0.8 | 7.2 | 10 | 90 | 9 | 9 | 0 | 0 | 90 | 0 | 90 | 81
67 | Line No 48 Item No MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 4, 450 mm dia (Provisional Quantity, if ordered) | m |  |  |  | 6 |  | 2974.9385 |  | 1 | 863.5682 | 852 | 1259.3703 | 0 | 2974.9385
| 1 | Purchase Materials:
| 2 | 450 RCP FJ CL2 | m | M | 1 | 1 | 6 | 136 | 816 |  |  | 0 | 816 | 0 | 0 | 816 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 1.5 | 24 | 36 |  |  | 0 | 36 | 0 | 0 | 36 | QMS
| 4 | Install:
67.1 | 5 | Excavator - 25T | hr | P | 1 | 0.667 | 6 | 130 | 1169.4153 | 8.9955 | 8.9955 | 0 | 0 | 1169.4153 | 0 | 1169.4153 | 81
| 6 | Labour | hr | L | 2 | 0.667 | 6 | 48 | 863.5682 | 17.991 | 8.9955 | 863.5682 | 0 | 0 | 0 | 863.5682 | 81
| 7 | Plate Compactor | hr | P | 1 | 0.667 | 6 | 10 | 89.955 | 8.9955 | 8.9955 | 0 | 0 | 89.955 | 0 | 89.955 | 81
68 | Line No 49 Item No MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 8, 525 mm dia (Provisional Quantity, if ordered) | m |  |  |  | 6 |  | 3268.9385 |  | 1 | 863.5682 | 1146 | 1259.3703 | 0 | 3268.9385
| 1 | Purchase Materials:
| 2 | 525 RCP | m | M | 1 | 1 | 6 | 185 | 1110 |  |  | 0 | 1110 | 0 | 0 | 1110 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 1.5 | 24 | 36 |  |  | 0 | 36 | 0 | 0 | 36 | QMS
| 4 | Install:
68.1 | 5 | Excavator - 25T | hr | P | 1 | 0.667 | 6 | 130 | 1169.4153 | 8.9955 | 8.9955 | 0 | 0 | 1169.4153 | 0 | 1169.4153 | 82
| 6 | Labour | hr | L | 2 | 0.667 | 6 | 48 | 863.5682 | 17.991 | 8.9955 | 863.5682 | 0 | 0 | 0 | 863.5682 | 82
| 7 | Plate Compactor | hr | P | 1 | 0.667 | 6 | 10 | 89.955 | 8.9955 | 8.9955 | 0 | 0 | 89.955 | 0 | 89.955 | 82
69 | Line No 50 Item No MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 8, 600 mm dia (Provisional Quantity, if ordered) | m |  |  |  | 6 |  | 3568.9385 |  | 1 | 863.5682 | 1446 | 1259.3703 | 0 | 3568.9385
| 1 | Purchase Materials:
| 2 | 600 RCP | m | M | 1 | 1 | 6 | 235 | 1410 |  |  | 0 | 1410 | 0 | 0 | 1410 | SWP
| 3 | Sand | tonne | M | 1 | 1 | 1.5 | 24 | 36 |  |  | 0 | 36 | 0 | 0 | 36 | QMS
| 4 | Install:
69.1 | 5 | Excavator - 25T | hr | P | 1 | 0.667 | 6 | 130 | 1169.4153 | 8.9955 | 8.9955 | 0 | 0 | 1169.4153 | 0 | 1169.4153 | 82
| 6 | Labour | hr | L | 2 | 0.667 | 6 | 48 | 863.5682 | 17.991 | 8.9955 | 863.5682 | 0 | 0 | 0 | 863.5682 | 82
| 7 | Plate Compactor | hr | P | 1 | 0.667 | 6 | 10 | 89.955 | 8.9955 | 8.9955 | 0 | 0 | 89.955 | 0 | 89.955 | 82
70 | Line No 51 Item No MRS03 - 2308 | End structures to culverts and repairs to end structures, reinforced concrete (Provisional Quantity, if ordered) | m3 |  |  |  | 2 |  | 2200 |  | 2 | 0 | 0 | 0 | 2200 | 2200
70.1 | 1 | Concrete Sub-contract | m² | S | 1 | 1 | 2 | 1100 | 2200 | 2 | 2 | 0 | 0 | 0 | 2200 | 2200 | 72
71 | Line No 52 Item No MRS03 - 2643 | PRINCIPAL SUPPLIED - Supply rock for protection (300 mm rock) (Principal paid material) (Provisional Quantity, if ordered)
72 | Line No 53 Item No MRS03 - 2643 | Deliver rock for protection (300 mm rock) (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 6 |  | 62.208 |  | 2 | 0 | 0 | 0 | 62.208 | 62.208
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 14.4
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 14.4 | 0.24 | 62.208 | 259.2 | 14.4 | 0 | 0 | 0 | 62.208 | 62.208 | 613
73 | Line No 54 Item No MRS03 - 2643 | Rock protection (300 mm rock) (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | m3 |  |  |  | 6 |  | 1356 |  | 1 | 576 | 0 | 780 | 0 | 1356
73.1 | 1 | Excavator - 25T | hr | P | 1 | 1 | 6 | 130 | 780 | 6 | 6 | 0 | 0 | 780 | 0 | 780 | 221
| 2 | Labour | hr | L | 2 | 1 | 6 | 48 | 576 | 12 | 6 | 576 | 0 | 0 | 0 | 576 | 221
74 | Line No 55 Item No | Pothole Repairs (Asphalt)
75 | Line No 56 Item No 9004PS | Supply premix asphalt material, apply emulsion tack coat (0.3 L/m2) and patch potholes (Provisional Quantity, if ordered) | tonne |  |  |  | 20 |  | 8000 |  | 1 | 0 | 8000 | 0 | 0 | 8000
| 1 | Cold Mix Asphalt | tonne | M | 1 | 1 | 20 | 400 | 8000 |  | 1 | 0 | 8000 | 0 | 0 | 8000 | 65
76 | Line No 58 Item No | PAVEMENT
77 | Line No 60 Item No MRS05 - 4151 | PRINCIPAL SUPPLIED - Supply Subtype 2.2 Unbound Pavement material for Base course. (Provisional Quantity, if ordered) (Principal paid material)
78 | Line No 61 Item No MRS05 - 4151 | Deliver Subtype 2.2 Unbound Pavement material for Base course, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | m3 |  |  |  | 3993 |  | 41399.424 |  | 3 | 0 | 0 | 0 | 41399.424 | 41399.424
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 9583.2
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 9583.2 | 0.24 | 41399.424 | 360 | 20 | 0 | 0 | 0 | 41399.424 | 41399.424 | 613
79 | Line No 62 Item No MRS05 - 4151 | Base course, unbound pavement, Subtype 2.2 (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | m3 |  |  |  | 3993 |  | 84519.2022 |  |  | 21000.8789 | 0 | 63518.3233 | 0 | 84519.2022
79.01 | 4 | Ann Street | m3 |  |  | 3.736% | 149.1798 |  |  |  | 1 | 784.5999 | 0 | 2373.0658 | 0 | 3157.6657
79.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 135.9349 |  |  |  | 1 | 714.9391 | 0 | 2162.3731 | 0 | 2877.3122
79.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 181.9436 |  |  |  | 1 | 956.9185 | 0 | 2894.2532 | 0 | 3851.1717
79.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 292.7828 |  |  |  | 1 | 1539.8689 | 0 | 4657.419 | 0 | 6197.2879
79.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 27.8841 |  |  |  | 1 | 146.6542 | 0 | 443.5637 | 0 | 590.2179
79.06 | 39 | Heards Road | m3 |  |  | 2.793% | 111.5363 |  |  |  | 1 | 586.6167 | 0 | 1774.2548 | 0 | 2360.8716
79.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 4.1826 |  |  |  | 1 | 21.9981 | 0 | 66.5346 | 0 | 88.5327
79.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 1854.2912 |  |  |  | 6 | 9752.5031 | 0 | 29496.9867 | 0 | 39249.4898
79.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 184.0349 |  |  |  | 1 | 967.9176 | 0 | 2927.5205 | 0 | 3895.4381
79.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 564.6526 |  |  |  | 2 | 2969.7472 | 0 | 8982.1651 | 0 | 11951.9123
79.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 13.2449 |  |  |  | 1 | 69.6607 | 0 | 210.6928 | 0 | 280.3535
79.12 | 83 | Amos Street | m3 |  |  | 3.142% | 125.4784 |  |  |  | 1 | 659.9438 | 0 | 1996.0367 | 0 | 2655.9805
79.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 347.8539 |  |  |  | 2 | 1829.5109 | 0 | 5533.4573 | 0 | 7362.9682
79.2 | 1 | Grader | hr | P | 1 | 88.889 | 9583.2 | 165 | 17788.7928 | 107.8109 | 107.8109 | 0 | 0 | 17788.7928 | 0 | 17788.7928 | 62
| 2 | Water Cart - Hire | hr | P | 2 | 88.889 | 9583.2 | 100 | 21562.173 | 215.6217 | 107.8109 | 0 | 0 | 21562.173 | 0 | 21562.173 | 62
| 3 | SD Roller | day | P | 1 | 800.001 | 9583.2 | 365 | 4372.3295 | 11.979 | 11.979 | 0 | 0 | 4372.3295 | 0 | 4372.3295 | 62
| 4 | MW Roller - Day | day | P | 1 | 800.001 | 9583.2 | 365 | 4372.3295 | 11.979 | 11.979 | 0 | 0 | 4372.3295 | 0 | 4372.3295 | 62
| 5 | Labour | hr | L | 3 | 88.889 | 9583.2 | 48 | 15524.7646 | 323.4326 | 107.8109 | 15524.7646 | 0 | 0 | 0 | 15524.7646 | 62
79.3 | 6 | Intermediate Trim: QTY based on depth |  |  |  |  | 0.3
79.4 | 7 | Grader | hr | P | 1 | 350 | 13310 | 165 | 6274.7143 | 38.0286 | 38.0286 | 0 | 0 | 6274.7143 | 0 | 6274.7143 | 63
| 8 | Water Cart - Hire | hr | P | 2 | 350 | 13310 | 100 | 7605.7143 | 76.0571 | 38.0286 | 0 | 0 | 7605.7143 | 0 | 7605.7143 | 63
| 9 | MW Roller - Day | day | P | 1 | 3150 | 13310 | 365 | 1542.2698 | 4.2254 | 4.2254 | 0 | 0 | 1542.2698 | 0 | 1542.2698 | 63
| 10 | Labour | hr | L | 3 | 350 | 13310 | 48 | 5476.1143 | 114.0857 | 38.0286 | 5476.1143 | 0 | 0 | 0 | 5476.1143 | 63
80 | Line No 63 Item No MRS05 - 4153 | PRINCIPAL SUPPLIED - Supply Subtype 2.3 Unbound Pavement material for Subbase course. (Provisional quantity, if ordered) (Principal paid material)
81 | Line No 64 Item No MRS05 - 4153 | Deliver Subtype 2.3 Unbound Pavement material for Subbase course, including haulage up to 18 km. (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | m3 |  |  |  | 3993 |  |  |  | 3 | 0 | 0 | 0 | 41399.424 | 41399.424
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 9583.2
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 9583.2 | 0.24 | 41399.424 | 360 | 20 | 0 | 0 | 0 | 41399.424 | 41399.424 | 613
82 | Line No 65 Item No MRS05 - 4153 | Subbase course, unbound pavement, Subtype 2.3. (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | m3 |  |  |  | 3993 |  | 84519.2022 |  |  | 21000.8789 | 0 | 63518.3233 | 0 | 84519.2022
82.01 | 4 | Ann Street | m3 |  |  | 3.736% | 149.1798 |  |  |  | 1 | 784.5999 | 0 | 2373.0658 | 0 | 3157.6657
82.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 135.9349 |  |  |  | 1 | 714.9391 | 0 | 2162.3731 | 0 | 2877.3122
82.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 181.9436 |  |  |  | 1 | 956.9185 | 0 | 2894.2532 | 0 | 3851.1717
82.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 292.7828 |  |  |  | 1 | 1539.8689 | 0 | 4657.419 | 0 | 6197.2879
82.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 27.8841 |  |  |  | 1 | 146.6542 | 0 | 443.5637 | 0 | 590.2179
82.06 | 39 | Heards Road | m3 |  |  | 2.793% | 111.5363 |  |  |  | 1 | 586.6167 | 0 | 1774.2548 | 0 | 2360.8716
82.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 4.1826 |  |  |  | 1 | 21.9981 | 0 | 66.5346 | 0 | 88.5327
82.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 1854.2912 |  |  |  | 6 | 9752.5031 | 0 | 29496.9867 | 0 | 39249.4898
82.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 184.0349 |  |  |  | 1 | 967.9176 | 0 | 2927.5205 | 0 | 3895.4381
82.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 564.6526 |  |  |  | 2 | 2969.7472 | 0 | 8982.1651 | 0 | 11951.9123
82.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 13.2449 |  |  |  | 1 | 69.6607 | 0 | 210.6928 | 0 | 280.3535
82.12 | 83 | Amos Street | m3 |  |  | 3.142% | 125.4784 |  |  |  | 1 | 659.9438 | 0 | 1996.0367 | 0 | 2655.9805
82.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 347.8539 |  |  |  | 2 | 1829.5109 | 0 | 5533.4573 | 0 | 7362.9682
82.2 | 1 | Grader | hr | P | 1 | 88.889 | 9583.2 | 165 | 17788.7928 | 107.8109 | 107.8109 | 0 | 0 | 17788.7928 | 0 | 17788.7928 | 62
| 2 | Water Cart - Hire | hr | P | 2 | 88.889 | 9583.2 | 100 | 21562.173 | 215.6217 | 107.8109 | 0 | 0 | 21562.173 | 0 | 21562.173 | 62
| 3 | SD Roller | day | P | 1 | 800.001 | 9583.2 | 365 | 4372.3295 | 11.979 | 11.979 | 0 | 0 | 4372.3295 | 0 | 4372.3295 | 62
| 4 | MW Roller - Day | day | P | 1 | 800.001 | 9583.2 | 365 | 4372.3295 | 11.979 | 11.979 | 0 | 0 | 4372.3295 | 0 | 4372.3295 | 62
| 5 | Labour | hr | L | 3 | 88.889 | 9583.2 | 48 | 15524.7646 | 323.4326 | 107.8109 | 15524.7646 | 0 | 0 | 0 | 15524.7646 | 62
82.3 | 6 | Intermediate Trim: QTY based on depth |  |  |  |  | 0.3
82.4 | 7 | Grader | hr | P | 1 | 350 | 13310 | 165 | 6274.7143 | 38.0286 | 38.0286 | 0 | 0 | 6274.7143 | 0 | 6274.7143 | 63
| 8 | Water Cart - Hire | hr | P | 2 | 350 | 13310 | 100 | 7605.7143 | 76.0571 | 38.0286 | 0 | 0 | 7605.7143 | 0 | 7605.7143 | 63
| 9 | MW Roller - Day | day | P | 1 | 3150 | 13310 | 365 | 1542.2698 | 4.2254 | 4.2254 | 0 | 0 | 1542.2698 | 0 | 1542.2698 | 63
| 10 | Labour | hr | L | 3 | 350 | 13310 | 48 | 5476.1143 | 114.0857 | 38.0286 | 5476.1143 | 0 | 0 | 0 | 5476.1143 | 63
83 | Line No 66 Item No 9005.1PS | PRINCIPAL SUPPLIED - Supply unbound pavement, Wearing Course Type gravel for shoulders (Principal paid material) (Provisional quantity, if ordered)
84 | Line No 67 Item No 9005.2PS | Deliver unbound pavement, Wearing Course Type gravel for shoulders, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | m3 |  |  |  | 2152 |  |  |  | 2 | 0 | 0 | 0 | 22311.936 | 22311.936
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 5164.8
| 2 | Haul Distance |  |  | 18
| 3 | Gravel Haulage (18 km) | km | S | 18 | 1 | 5164.8 | 0.24 | 22311.936 | 306 | 17 | 0 | 0 | 0 | 22311.936 | 22311.936 | 613
85 | Line No 68 Item No 9005.3PS | Unbound pavement, Wearing Course Type gravel for shoulders (Provisional quantity, if ordered) (Contractor installation rate) (Principal paid material) | m3 |  |  |  | 2152 |  | 68243.4033 |  |  | 17058.5408 | 0 | 51184.8625 | 0 | 68243.4033
85.01 | 4 | Ann Street | m3 |  |  | 3.736% | 149.1798 |  |  |  | 1 | 637.3128 | 0 | 1912.2836 | 0 | 2549.5964
85.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 135.9349 |  |  |  | 1 | 580.729 | 0 | 1742.5014 | 0 | 2323.2304
85.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 181.9436 |  |  |  | 1 | 777.2834 | 0 | 2332.2711 | 0 | 3109.5545
85.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 292.7828 |  |  |  | 1 | 1250.8008 | 0 | 3753.08 | 0 | 5003.8808
85.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 27.8841 |  |  |  | 1 | 119.1239 | 0 | 357.4362 | 0 | 476.5601
85.06 | 39 | Heards Road | m3 |  |  | 2.793% | 111.5363 |  |  |  | 1 | 476.4956 | 0 | 1429.7448 | 0 | 1906.2403
85.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 4.1826 |  |  |  | 1 | 17.8686 | 0 | 53.6154 | 0 | 71.484
85.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 1854.2912 |  |  |  | 4 | 7921.7386 | 0 | 23769.5067 | 0 | 31691.2453
85.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 184.0349 |  |  |  | 1 | 786.2177 | 0 | 2359.0789 | 0 | 3145.2965
85.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 564.6526 |  |  |  | 2 | 2412.2587 | 0 | 7238.0829 | 0 | 9650.3416
85.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 13.2449 |  |  |  | 1 | 56.5838 | 0 | 169.7822 | 0 | 226.366
85.12 | 83 | Amos Street | m3 |  |  | 3.142% | 125.4784 |  |  |  | 1 | 536.0575 | 0 | 1608.4629 | 0 | 2144.5204
85.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 347.8539 |  |  |  | 1 | 1486.0705 | 0 | 4459.0165 | 0 | 5945.087
85.2 | 1 | Grader | hr | P | 1 | 66.667 | 5164.8 | 165 | 12782.8161 | 77.4716 | 77.4716 | 0 | 0 | 12782.8161 | 0 | 12782.8161 | 62
| 2 | Water Cart - Hire | hr | P | 2 | 66.667 | 5164.8 | 100 | 15494.3225 | 154.9432 | 77.4716 | 0 | 0 | 15494.3225 | 0 | 15494.3225 | 62
| 3 | SD Roller | day | P | 1 | 600.003 | 5164.8 | 365 | 3141.9043 | 8.608 | 8.608 | 0 | 0 | 3141.9043 | 0 | 3141.9043 | 62
| 4 | MW Roller - Day | day | P | 1 | 600.003 | 5164.8 | 365 | 3141.9043 | 8.608 | 8.608 | 0 | 0 | 3141.9043 | 0 | 3141.9043 | 62
| 5 | Labour | hr | L | 3 | 66.667 | 5164.8 | 48 | 11155.9122 | 232.4148 | 77.4716 | 11155.9122 | 0 | 0 | 0 | 11155.9122 | 62
85.3 | 6 | Intermediate Trim: QTY = 7173.333 |  |  |  |  | 0.15
85.4 | 7 | Grader | hr | P | 1 | 350 | 14346.6667 | 165 | 6763.4286 | 40.9905 | 40.9905 | 0 | 0 | 6763.4286 | 0 | 6763.4286 | 63
| 8 | Water Cart - Hire | hr | P | 2 | 350 | 14346.6667 | 100 | 8198.0952 | 81.981 | 40.9905 | 0 | 0 | 8198.0952 | 0 | 8198.0952 | 63
| 9 | MW Roller - Day | day | P | 1 | 3150 | 14346.6667 | 365 | 1662.3915 | 4.5545 | 4.5545 | 0 | 0 | 1662.3915 | 0 | 1662.3915 | 63
| 10 | Labour | hr | L | 3 | 350 | 14346.6667 | 48 | 5902.6286 | 122.9714 | 40.9905 | 5902.6286 | 0 | 0 | 0 | 5902.6286 | 63
86 | Line No 69 Item No 9006PS | Extra over Items MRS05-4151.2PS, MRS05-4153.2,MRS07-4203.2PS and 9005.2 for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | m3 * |  |  |  | 130017 |  |  |  | 0 | 0 | 0 | 0 | 89867.7504 | 89867.7504
| 1 | Gravel Haulage (18 km) | km | S | 1 | 1 | 374448.96 | 0.24 | 89867.7504 | 0 |  | 0 | 0 | 0 | 89867.7504 | 89867.7504 | 613
87 | Line No 71 Item No | BITUMEN SURFACING
88 | Line No 73 Item No | Seal Design by Contractor. Application rates are indicative only
89 | Line No 74 Item No MRS30 - 5401 | Preparation of the existing sealed surface for resealing (Provisional quantity, if ordered) | litre |  |  |  | 1500 |  |  |  | 1 | 0 | 0 | 0 | 2565 | 2565
| 1 | Surface Preparation Seal | m² | S | 1 | 1 | 1500 | 1.71 | 2565 | 1 | 1 | 0 | 0 | 0 | 2565 | 2565 | 64
90 | Line No 75 Item No MRS11 - 5105 | Enrichment spray, 60% bitumen emulsion, total 0.9L/m2 applied in 3 passes (Provisional quantity, if ordered) | litre |  |  |  | 1350 |  |  |  | 1 | 0 | 0 | 0 | 11785.5 | 11785.5
| 1 | Enrichmnet Spray | litre | S | 1 | 1 | 1350 | 8.73 | 11785.5 | 1 | 1 | 0 | 0 | 0 | 11785.5 | 11785.5 | 64
91 | Line No 76 Item No MRS30- 5402P | Crack Filling (Provisional Quantity, if ordered) | m |  |  |  | 142 |  |  |  | 1 | 0 | 0 | 0 | 1485.32 | 1485.32
| 1 | Crack Filling | m | S | 1 | 1 | 142 | 10.46 | 1485.32 | 1 | 1 | 0 | 0 | 0 | 1485.32 | 1485.32 | 64
92 | Line No 77 Item No MRS30- 5403P | Strain alleviating fabric strips (Provisional Quantity, if ordered) | m |  |  |  | 8 |  |  |  | 1 | 0 | 0 | 0 | 64 | 64
| 1 | Strain Alleviating Strips | m | S | 1 | 1 | 8 | 8 | 64 | 1 | 1 | 0 | 0 | 0 | 64 | 64 | 64
93 | Line No 78 Item No MRS11 - 5102 | Primerseal, Grade AMC5, spray rate 1.5 L/m2, including supply of binder, all areas. (Seal design by Contractor) (Provisional Quantity, if ordered) | litre |  |  |  | 38375 |  | 66772.5 |  |  | 0 | 0 | 0 | 66772.5 | 66772.5
93.01 | 4 | Ann Street | m3 |  |  | 3.736% | 1433.7029 |  |  |  | 1 | 0 | 0 | 0 | 2494.643 | 2494.643 |  | 2494.643
93.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 1306.4115 |  |  |  | 1 | 0 | 0 | 0 | 2273.156 | 2273.156
93.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 1748.5815 |  |  |  | 1 | 0 | 0 | 0 | 3042.5319 | 3042.5319
93.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 2813.8094 |  |  |  | 1 | 0 | 0 | 0 | 4896.0283 | 4896.0283
93.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 267.9818 |  |  |  | 1 | 0 | 0 | 0 | 466.2884 | 466.2884
93.06 | 39 | Heards Road | m3 |  |  | 2.793% | 1071.9274 |  |  |  | 1 | 0 | 0 | 0 | 1865.1536 | 1865.1536
93.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 40.1973 |  |  |  | 1 | 0 | 0 | 0 | 69.9433 | 69.9433
93.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 17820.7926 |  |  |  | 2 | 0 | 0 | 0 | 31008.1791 | 31008.1791
93.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 1768.6802 |  |  |  | 1 | 0 | 0 | 0 | 3077.5035 | 3077.5035
93.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 5426.6323 |  |  |  | 1 | 0 | 0 | 0 | 9442.3403 | 9442.3403
93.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 127.2914 |  |  |  | 1 | 0 | 0 | 0 | 221.487 | 221.487
93.12 | 83 | Amos Street | m3 |  |  | 3.142% | 1205.9183 |  |  |  | 1 | 0 | 0 | 0 | 2098.2978 | 2098.2978
93.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 3343.0735 |  |  |  | 1 | 0 | 0 | 0 | 5816.9479 | 5816.9479
| 1 | AMC5 | litre | S | 1 | 1 | 38375 | 1.74 | 66772.5 | 8.3466 | 8.3466 | 0 | 0 | 0 | 66772.5 | 66772.5 | 64
94 | Line No 79 Item No MRS11 - 5103 | Second Seal C170 Bitumen, 1.5 L/m2 including binder (Seal design by Contractor) (Provisional Quantity, if ordered) | litre |  |  |  | 38375 |  | 61400 |  |  | 0 | 0 | 0 | 61400 | 61400
94.01 | 4 | Ann Street | m3 |  |  | 3.736% | 1433.7029 |  |  |  | 1 | 0 | 0 | 0 | 2293.9246 | 2293.9246
94.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 1306.4115 |  |  |  | 1 | 0 | 0 | 0 | 2090.2584 | 2090.2584
94.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 1748.5815 |  |  |  | 1 | 0 | 0 | 0 | 2797.7304 | 2797.7304
94.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 2813.8094 |  |  |  | 1 | 0 | 0 | 0 | 4502.095 | 4502.095
94.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 267.9818 |  |  |  | 1 | 0 | 0 | 0 | 428.7709 | 428.7709
94.06 | 39 | Heards Road | m3 |  |  | 2.793% | 1071.9274 |  |  |  | 1 | 0 | 0 | 0 | 1715.0838 | 1715.0838
94.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 40.1973 |  |  |  | 1 | 0 | 0 | 0 | 64.3156 | 64.3156
94.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 17820.7926 |  |  |  | 2 | 0 | 0 | 0 | 28513.2682 | 28513.2682
94.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 1768.6802 |  |  |  | 1 | 0 | 0 | 0 | 2829.8883 | 2829.8883
94.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 5426.6323 |  |  |  | 1 | 0 | 0 | 0 | 8682.6117 | 8682.6117
94.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 127.2914 |  |  |  | 1 | 0 | 0 | 0 | 203.6662 | 203.6662
94.12 | 83 | Amos Street | m3 |  |  | 3.142% | 1205.9183 |  |  |  | 1 | 0 | 0 | 0 | 1929.4693 | 1929.4693
94.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 3343.0735 |  |  |  | 1 | 0 | 0 | 0 | 5348.9176 | 5348.9176
| 1 | C170 | litre | S | 1 | 1 | 38375 | 1.6 | 61400 | 4.912 | 4.912 | 0 | 0 | 0 | 61400 | 61400 | 64
95 | Line No 80 Item No MRS11 - 5112 | Spreading cover aggregate to Primerseal (14mm), spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | m3 |  |  |  | 233 |  | 126838.21 |  |  | 0 | 0 | 0 | 126838.21 | 126838.21
95.01 | 4 | Ann Street | m3 |  |  | 3.736% | 1433.7029 |  |  |  | 1 | 0 | 0 | 0 | 4738.718 | 4738.718
95.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 1306.4115 |  |  |  | 1 | 0 | 0 | 0 | 4317.9907 | 4317.9907
95.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 1748.5815 |  |  |  | 1 | 0 | 0 | 0 | 5779.4645 | 5779.4645
95.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 2813.8094 |  |  |  | 1 | 0 | 0 | 0 | 9300.2877 | 9300.2877
95.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 267.9818 |  |  |  | 1 | 0 | 0 | 0 | 885.7417 | 885.7417
95.06 | 39 | Heards Road | m3 |  |  | 2.793% | 1071.9274 |  |  |  | 1 | 0 | 0 | 0 | 3542.9668 | 3542.9668
95.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 40.1973 |  |  |  | 1 | 0 | 0 | 0 | 132.8613 | 132.8613
95.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 17820.7926 |  |  |  | 2 | 0 | 0 | 0 | 58901.8224 | 58901.8224
95.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 1768.6802 |  |  |  | 1 | 0 | 0 | 0 | 5845.8952 | 5845.8952
95.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 5426.6323 |  |  |  | 1 | 0 | 0 | 0 | 17936.2692 | 17936.2692
95.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 127.2914 |  |  |  | 1 | 0 | 0 | 0 | 420.7273 | 420.7273
95.12 | 83 | Amos Street | m3 |  |  | 3.142% | 1205.9183 |  |  |  | 1 | 0 | 0 | 0 | 3985.8376 | 3985.8376
95.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 3343.0735 |  |  |  | 1 | 0 | 0 | 0 | 11049.6276 | 11049.6276
| 1 | Spread - 16mm | m³ | S | 1 | 1 | 233 | 544.37 | 126838.21 | 8.3466 | 8.3466 | 0 | 0 | 0 | 126838.21 | 126838.21 | 64
96 | Line No 81 Item No MRS11 - 5112 | Spreading cover aggregate to Second Seal (10mm), 130 m2/m3 (Seal design by Contractor) (Provisional Quantity, if ordered) | m3 |  |  |  | 197 |  | 94171.91 |  |  | 0 | 0 | 0 | 94171.91 | 94171.91
96.01 | 4 | Ann Street | m3 |  |  | 3.736% | 1433.7029 |  |  |  | 1 | 0 | 0 | 0 | 3518.2941 | 3518.2941
96.02 | 11 | Barberos Road | m3 |  |  | 3.404% | 1306.4115 |  |  |  | 1 | 0 | 0 | 0 | 3205.9222 | 3205.9222
96.03 | 18 | Burke Offset Road | m3 |  |  | 4.557% | 1748.5815 |  |  |  | 1 | 0 | 0 | 0 | 4291.0036 | 4291.0036
96.04 | 25 | Fabris Road | m3 |  |  | 7.332% | 2813.8094 |  |  |  | 1 | 0 | 0 | 0 | 6905.0632 | 6905.0632
96.05 | 32 | Harvey Road | m3 |  |  | 0.6983% | 267.9818 |  |  |  | 1 | 0 | 0 | 0 | 657.6251 | 657.6251
96.06 | 39 | Heards Road | m3 |  |  | 2.793% | 1071.9274 |  |  |  | 1 | 0 | 0 | 0 | 2630.5003 | 2630.5003
96.07 | 46 | Mile Road | m3 |  |  | 0.1047% | 40.1973 |  |  |  | 1 | 0 | 0 | 0 | 98.6438 | 98.6438
96.08 | 53 | Wallaman Falls Road | m3 |  |  | 46.44% | 17820.7926 |  |  |  | 2 | 0 | 0 | 0 | 43732.0671 | 43732.0671
96.09 | 61 | Allingham Road | m3 |  |  | 4.609% | 1768.6802 |  |  |  | 1 | 0 | 0 | 0 | 4340.3255 | 4340.3255
96.1 | 68 | Taylors Beach Road | m3 |  |  | 14.14% | 5426.6323 |  |  |  | 1 | 0 | 0 | 0 | 13316.9077 | 13316.9077
96.11 | 76 | Taraken Road | m3 |  |  | 0.3317% | 127.2914 |  |  |  | 1 | 0 | 0 | 0 | 312.3719 | 312.3719
96.12 | 83 | Amos Street | m3 |  |  | 3.142% | 1205.9183 |  |  |  | 1 | 0 | 0 | 0 | 2959.3128 | 2959.3128
96.13 | 90 | Lannercost Extension Road | m3 |  |  | 8.712% | 3343.0735 |  |  |  | 1 | 0 | 0 | 0 | 8203.8727 | 8203.8727
| 1 | Spreading - 10mm | m³ | S | 1 | 1 | 197 | 478.03 | 94171.91 | 4.912 | 4.912 | 0 | 0 | 0 | 94171.91 | 94171.91 | 64
97 | Line No 82 Item No MRS22 - 5011 | Supply of Primerseal cover aggregate, precoated, 14 mm nominal size, spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | m3 |  |  |  | 233 |  | 27955.34 |  | 1 | 0 | 0 | 0 | 27955.34 | 27955.34
| 1 | Cover Agg - 14mm | m³ | S | 1 | 1 | 233 | 119.98 | 27955.34 | 1 | 1 | 0 | 0 | 0 | 27955.34 | 27955.34 | 64
98 | Line No 83 Item No MRS22 - 5011 | Supply of Second Seal cover aggregate, precoated, 10 mm nominal size,spread rate 130 m2/m3 (Seal design by Contractor) (Provisional Quantity) | m3 |  |  |  | 197 |  | 22422.54 |  | 1 | 0 | 0 | 0 | 22422.54 | 22422.54
| 1 | Cover Agg - 10mm | m³ | S | 1 | 1 | 197 | 113.82 | 22422.54 | 1 | 1 | 0 | 0 | 0 | 22422.54 | 22422.54 | 64
99 | Line No 85 Item No | ROAD FURNITURE, ROAD SIGNS, LINE MARKING, DELINEATION
100 | Line No 87 Item No MRS14 - 6111 | Road edge guide posts (Provisional Quantity, if ordered) | each |  |  |  | 3 |  | 195 |  | 1 | 0 | 195 | 0 | 0 | 195
| 1 | Guide Post | each | M | 1 | 1 | 3 | 65 | 195 |  | 1 | 0 | 195 | 0 | 0 | 195 | 67
101 | Line No 88 Item No MRS45 - 6301 | Spotting only for longitudinal lines (Provisional Quantity, if ordered) | m |  |  |  | 3470 |  | 3470 |  | 4 | 0 | 0 | 0 | 3470 | 3470
| 1 | Line Marking | m² | S | 1 | 1 | 3470 | 1 | 3470 | 3.47 | 3.47 | 0 | 0 | 0 | 3470 | 3470 | 67
102 | Line No 89 Item No MRS45 - 6353 | Temporary raised pavement markers (Provisional Quantity, if ordered) | each |  |  |  | 694 |  | 2429 |  | 0 | 0 | 2429 | 0 | 0 | 2429
| 1 | Temporary Pavement Mark | each | M | 1 | 1 | 694 | 3.5 | 2429 |  |  | 0 | 2429 | 0 | 0 | 2429 | 67
[5 empty] | DC Rate | DC
103 | VAR01 | VAR01 - TC001 This equates to $3.10/m3 for delivery of 14,397m3 of material which is summation of items at MRS04 -34411.PS; MRS05-4151.2PS;MRS05-4153.2PS & 9005.2PS. This adjustment is made on the basis that Allciv will not have any contractual relationship with the quarry chosen to have any ability to pass on or recoiver cost from the quarry associated with waiting time or slow production rates. This additional amount of $3.10/m3 will cover these costs should they arise (provisional Quantity , if ordered) | m³ |  |  |  | 11433 |  | 26623.3326 |  | 0 | 0 | 0 | 0 | 26623.3326 | 26623.3326
| 1 | Quantity = Tonnes |  |  |  |  | 11433
| 2 | Haul Distance (9.7 KM Established) |  |  | 9.7027
| 3 | Gravel Haulage (18 km) | km | S | 9.7027 | 1 | 5716.5 | 0.24 | 13311.6663 | 5477.0133 | 564.4855 | 0 | 0 | 0 | 13311.6663 | 13311.6663 | 613
| 3 | Gravel Haulage (18 km) | km | S | 9.7027 | 1 | 5716.5 | 0.24 | 13311.6663 | 8825.7876 | 909.6252 | 0 | 0 | 0 | 13311.6663 | 13311.6663 | 613
104 | VAR02 | MRS04 - 3101.1PS - Clearing of Shoulders - width 1m in with to hing point | m² |  |  |  | 7578 |  | 11597.8922 |  | 23.6812 | 3410.1 | 0 | 8187.7922 | 0 | 11597.8922
104.01 | 1 | Grader | hr | P | 1 | 320 | 7578 | 165 | 3907.4062 | 23.6812 | 23.6812 | 0 | 0 | 3907.4062 | 0 | 3907.4062 | 88
| 2 | Tipper | hr | P | 2 | 320 | 7578 | 90 | 4262.625 | 47.3625 | 23.6812 | 0 | 0 | 4262.625 | 0 | 4262.625 | 88
| 3 | Labour | hr | L | 3 | 320 | 7578 | 48 | 3410.1 | 71.0437 | 23.6812 | 3410.1 | 0 | 0 | 0 | 3410.1 | 88
| 4 | Water Cart - Hire | day | P | 1 | 2880 | 378.9 | 100 | 13.1562 | 0.13156 | 0.13156 | 0 | 0 | 13.1562 | 0 | 13.1562 | 88
| 5 | CAT297 | hr | P | 1 | 2880 | 378.9 | 35 | 4.6047 | 0.13156 | 0.13156 | 0 | 0 | 4.6047 | 0 | 4.6047 | 88
105 | VAR02 | MRS04- 3208.9PS: Special Excavation all material, grading of shoulders to acheive pavemnent surface drainage and disposal of material at HSC disposal site and disposal of material at HSC disposal site,including haulage up to 18km (provisional Quantity,as directed)##CRLF####CRLF##Qty = area x 50mm | m³ |  |  |  | 690 |  | 45057 |  | 11 | 13248 | 0 | 31809 | 0 | 45057
105.01 | 1 | Grader | hr | P | 1 | 7.5 | 690 | 165 | 15180 | 92 | 92 | 0 | 0 | 15180 | 0 | 15180 | 53
| 2 | Tipper | hr | P | 2 | 7.5 | 690 | 90 | 16560 | 184 | 92 | 0 | 0 | 16560 | 0 | 16560 | 53
| 3 | Labour | hr | L | 3 | 7.5 | 690 | 48 | 13248 | 276 | 92 | 13248 | 0 | 0 | 0 | 13248 | 53
| 4 | Water Cart - Hire | day | P | 1 | 67.5 | 34.5 | 100 | 51.1111 | 0.51111 | 0.51111 | 0 | 0 | 51.1111 | 0 | 51.1111 | 53
| 5 | CAT297 | hr | P | 1 | 67.5 | 34.5 | 35 | 17.8889 | 0.51111 | 0.51111 | 0 | 0 | 17.8889 | 0 | 17.8889 | 53
106 | VAR04.1 | 9009.1PS- Moisture conditioning of sub-base 2.3 Gravel | tonne |  |  |  | 9366 |  | 22368.9302 |  | 8.9404 | 3862.2613 | 0 | 18506.6689 | 0 | 22368.9302
| 3 | Excavator - 25T | hr | P | 1 | 116.4002 | 9366 | 130 | 10460.2911 | 80.4638 | 80.4638 | 0 | 0 | 10460.2911 | 0 | 10460.2911 | 62
| 4 | Water Cart - Hire | day | P | 1 | 116.4002 | 9366 | 100 | 8046.3778 | 80.4638 | 80.4638 | 0 | 0 | 8046.3778 | 0 | 8046.3778 | 62
| 5 | Labour | hr | L | 1 | 116.4002 | 9366 | 48 | 3862.2613 | 80.4638 | 80.4638 | 3862.2613 | 0 | 0 | 0 | 3862.2613 | 62
107 | VAR03.5 | MRS08 - 4301.5PS Deliver Subbase 2.3 Plant mixed 3% cement | m³ |  |  |  | 2057 |  | 67653.9072 |  |  | 0 | 0 | 0 | 67653.9072 | 67653.9072
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 4936.8
| 2 | Haul Distance |  |  | 57.1
| 3 | Gravel Haulage (18 km) | km | S | 57.1 | 1 | 4936.8 | 0.24 | 67653.9072 | 0 | 0 | 0 | 0 | 0 | 67653.9072 | 67653.9072 | 62
108 | VAR3.9 | 9008.1PS - EXTRA OVER ITEMS VAR 3.2, VAR3.5 ,VAR3.7 for haulage in eccess of 18km ##CRLF####CRLF##Wallaman job site - 32.5km - 18km = 14.5km | m3*km |  |  |  | 16894 |  | 22800 |  | 0 | 0 | 0 | 0 | 22800 | 22800
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 40545.6
| 2 | Haul Distance |  |  | 2.343
| 3 | Gravel Haulage (18 km) | km | S | 2.343 | 1 | 40545.6 | 0.24 | 22800 | 30.4595 | 13 | 0 | 0 | 0 | 22800 | 22800 | 62
109 | VAR3.6 | MRS08-4301.6PS - Installation sub-base 2.3 3% cement | m³ |  |  |  | 2057 |  | 69648.4963 |  | 13 | 22709.28 | 0 | 46939.2163 | 0 | 69648.4963
109.01 | 1 | Grader | hr | P | 1 | 66.6667 | 4936.8 | 165 | 12218.58 | 74.052 | 74.052 | 0 | 0 | 12218.58 | 0 | 12218.58 | 62
| 2 | Water Cart - Hire | hr | P | 2 | 66.6667 | 4936.8 | 100 | 14810.4 | 148.104 | 74.052 | 0 | 0 | 14810.4 | 0 | 14810.4 | 62
| 3 | SD Roller | day | P | 1 | 600 | 4936.8 | 365 | 3003.22 | 8.228 | 8.228 | 0 | 0 | 3003.22 | 0 | 3003.22 | 62
| 4 | MW Roller - Day | day | P | 1 | 600 | 4936.8 | 365 | 3003.22 | 8.228 | 8.228 | 0 | 0 | 3003.22 | 0 | 3003.22 | 62
| 5 | Labour | hr | L | 5 | 66.6667 | 4936.8 | 48 | 17772.48 | 370.26 | 74.052 | 17772.48 | 0 | 0 | 0 | 17772.48 | 62
109.02 | 6 | Intermediate Trim: QTY based on depth |  |  |  |  | 0.3
109.03 | 7 | Grader | hr | P | 1 | 200 | 6856.6667 | 165 | 5656.75 | 34.2833 | 34.2833 | 0 | 0 | 5656.75 | 0 | 5656.75 | 62
| 8 | Water Cart - Hire | hr | P | 2 | 200 | 6856.6667 | 100 | 6856.6667 | 68.5667 | 34.2833 | 0 | 0 | 6856.6667 | 0 | 6856.6667 | 62
| 9 | MW Roller - Day | day | P | 1 | 1800 | 6856.6667 | 365 | 1390.3796 | 3.8093 | 3.8093 | 0 | 0 | 1390.3796 | 0 | 1390.3796 | 62
| 10 | Labour | hr | L | 3 | 200 | 6856.6667 | 48 | 4936.8 | 102.85 | 34.2833 | 4936.8 | 0 | 0 | 0 | 4936.8 | 62
110 | VAR3.2 | MRS08 4301.2PS Delivery Subtype 2.2 CMB 1.5% Cement | m³ |  |  |  | 801.75 |  | 26369.2368 |  | 0 | 0 | 0 | 0 | 26369.2368 | 26369.2368
| 1 | Quantity * 2.4 = Tonnes |  |  |  |  | 1924.2
| 2 | Haul Distance |  |  | 57.1
| 3 | Gravel Haulage (18 km) | km | S | 57.1 | 1 | 1924.2 | 0.24 | 26369.2368 | 285.5 | 5 | 0 | 0 | 0 | 26369.2368 | 26369.2368 | 62
111 | VAR3.3 | MRS08-4301.3PS Installation subtype 2.2 Cement Treated Base 1.5% cement | m³ |  |  |  | 801.75 |  | 27146.6611 |  | 5 | 8851.32 | 0 | 18295.3411 | 0 | 27146.6611
111.01 | 1 | Grader | hr | P | 1 | 66.6667 | 1924.2 | 165 | 4762.395 | 28.863 | 28.863 | 0 | 0 | 4762.395 | 0 | 4762.395 | 62
| 2 | Water Cart - Hire | hr | P | 2 | 66.6667 | 1924.2 | 100 | 5772.6 | 57.726 | 28.863 | 0 | 0 | 5772.6 | 0 | 5772.6 | 62
| 3 | SD Roller | day | P | 1 | 600 | 1924.2 | 365 | 1170.555 | 3.207 | 3.207 | 0 | 0 | 1170.555 | 0 | 1170.555 | 62
| 4 | MW Roller - Day | day | P | 1 | 600 | 1924.2 | 365 | 1170.555 | 3.207 | 3.207 | 0 | 0 | 1170.555 | 0 | 1170.555 | 62
| 5 | Labour | hr | L | 5 | 66.6667 | 1924.2 | 48 | 6927.12 | 144.315 | 28.863 | 6927.12 | 0 | 0 | 0 | 6927.12 | 62
111.02 | 6 | Intermediate Trim: QTY based on depth |  |  |  |  | 0.3
111.03 | 7 | Grader | hr | P | 1 | 200 | 2672.5 | 165 | 2204.8125 | 13.3625 | 13.3625 | 0 | 0 | 2204.8125 | 0 | 2204.8125 | 62
| 8 | Water Cart - Hire | hr | P | 2 | 200 | 2672.5 | 100 | 2672.5 | 26.725 | 13.3625 | 0 | 0 | 2672.5 | 0 | 2672.5 | 62
| 9 | MW Roller - Day | day | P | 1 | 1800 | 2672.5 | 365 | 541.9236 | 1.4847 | 1.4847 | 0 | 0 | 541.9236 | 0 | 541.9236 | 62
| 10 | Labour | hr | L | 3 | 200 | 2672.5 | 48 | 1924.2 | 40.0875 | 13.3625 | 1924.2 | 0 | 0 | 0 | 1924.2 | 62
112 | VAR05 | Dayworks to undertake pavement repairs, sweeping and seal patching Wallaman Fall Road Ch 34600 - Ch 34800 | LS |  |  |  | 1 |  | 5791.0041 |  | 14 | 216 | 0 | 608.3333 | 4966.6708 | 5791.0041
112.01 | 7 | Grader | hr | P | 1 | 200 | 300 | 165 | 247.5 | 1.5 | 1.5 | 0 | 0 | 247.5 | 0 | 247.5 | 64
| 8 | Water Cart - Hire | hr | P | 2 | 200 | 300 | 100 | 300 | 3 | 1.5 | 0 | 0 | 300 | 0 | 300 | 64
| 9 | MW Roller - Day | day | P | 1 | 1800 | 300 | 365 | 60.8333 | 0.16667 | 0.16667 | 0 | 0 | 60.8333 | 0 | 60.8333 | 64
| 10 | Labour | hr | L | 3 | 200 | 300 | 48 | 216 | 4.5 | 1.5 | 216 | 0 | 0 | 0 | 216 | 64
| 1 | C170 | litre | S | 1 | 1 | 300 | 1.6 | 480 | 0.0384 | 0.0384 | 0 | 0 | 0 | 480 | 480 | 64
| 1 | Spread - 16mm | m³ | S | 1 | 1 | 4.6154 | 544.37 | 2512.4769 | 1.5 | 1.5 | 0 | 0 | 0 | 2512.4769 | 2512.4769 | 64
| 1 | Spreading - 10mm | m³ | S | 1 | 1 | 2.4 | 478.03 | 1147.272 | 1.5 | 1.5 | 0 | 0 | 0 | 1147.272 | 1147.272 | 64
| 1 | Cover Agg - 14mm | m³ | S | 1 | 1 | 4.6154 | 119.98 | 553.7538 | 1 | 1 | 0 | 0 | 0 | 553.7538 | 553.7538 | 64
| 1 | Cover Agg - 10mm | m³ | S | 1 | 1 | 2.4 | 113.82 | 273.168 | 1 | 1 | 0 | 0 | 0 | 273.168 | 273.168 | 64
113 | VAR06 | Dayworks - EIR7561 - removal of loose gravel from verge intersection of Dangercamp road | LS |  |  |  | 1 |  | 918 |  | 2 | 288 | 0 | 630 | 0 | 918
113.01 | 1 | CAT297 | hr | P | 1 | 0.5 | 1 | 35 | 70 | 2 | 2 | 0 | 0 | 70 | 0 | 70 | 53
| 2 | Tipper | hr | P | 2 | 0.5 | 1 | 90 | 360 | 4 | 2 | 0 | 0 | 360 | 0 | 360 | 53
| 3 | Labour | hr | L | 3 | 0.5 | 1 | 48 | 288 | 6 | 2 | 288 | 0 | 0 | 0 | 288 | 53
| 4 | Water Cart - Hire | day | P | 1 | 0.5 | 1 | 100 | 200 | 2 | 2 | 0 | 0 | 200 | 0 | 200 | 53
114 | VAR07 | Holding 7mm Seal - Variation works Neame street | m² |  |  |  | 2051 |  | 8011.2915 |  | 1 | 0 | 0 | 0 | 8011.2915 | 8011.2915
| 1 | C170 | litre | S | 1 | 1 | 1845.9 | 1.6 | 2953.44 | 0.23628 | 0.23628 | 0 | 0 | 0 | 2953.44 | 2953.44 | 64
| 1 | Spreading - 10mm | m³ | S | 1 | 1 | 8.5458 | 478.03 | 4085.1647 | 0.23628 | 0.23628 | 0 | 0 | 0 | 4085.1647 | 4085.1647 | 64
| 1 | Cover Agg - 10mm | m³ | S | 1 | 1 | 8.5458 | 113.82 | 972.6867 | 1 | 1 | 0 | 0 | 0 | 972.6867 | 972.6867 | 64
| VAR08 | Additional establishment for sealing works Neame Street | each |  |  |  | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| 1 | C170 | litre | S | 1 | 1 | 0 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64
115 | VAR09 | Hawkin Creek road washout works - rate for installation of rock revised due to qty of rock installation rate for this works only is $111 | m³ |  |  |  | 147 |  | 12061.35 |  | 2 | 1587.6 | 6945.75 | 3528 | 0 | 12061.35
Purchase Material
115.01 | 1 | Rock | hr | M | 1 | 1 | 220.5 | 31.5 | 6945.75 |  |  | 0 | 6945.75 | 0 | 0 | 6945.75 | QMR
Install
115.02 | 2 | Excavator - 25T | hr | P | 1 | 20 | 220.5 | 130 | 1433.25 | 11.025 | 11.025 | 0 | 0 | 1433.25 | 0 | 1433.25 | 221
| 2 | Tipper | hr | P | 1 | 20 | 220.5 | 90 | 992.25 | 11.025 | 11.025 | 0 | 0 | 992.25 | 0 | 992.25 | 221
| 3 | Labour | hr | L | 3 | 20 | 220.5 | 48 | 1587.6 | 33.075 | 11.025 | 1587.6 | 0 | 0 | 0 | 1587.6 | 221
| 4 | Water Cart - Hire | day | P | 1 | 20 | 220.5 | 100 | 1102.5 | 11.025 | 11.025 | 0 | 0 | 1102.5 | 0 | 1102.5 | 221
116 | VAR10 | Var 7.1 supply and Lay DG 7 asphalt ##CRLF##Var 7.2 Supply and Spray 10mm C170 ##CRLF####CRLF## | LS |  |  |  | 410 |  | 19604.5771 |  | 1 | 0 | 0 | 0 | 19604.5771 | 19604.5771
| 1 | C170 | litre | S | 1 | 1 | 410 | 1.6 | 656 | 0.05248 | 0.05248 | 0 | 0 | 0 | 656 | 656 | 64
| 1 | Spreading - 10mm | m³ | S | 1 | 1 | 1.7083 | 478.03 | 816.6346 | 1.5 | 1.5 | 0 | 0 | 0 | 816.6346 | 816.6346 | 64
| 1 | Cover Agg - 10mm | m³ | S | 1 | 1 | 1.7083 | 113.82 | 194.4425 | 1 | 1 | 0 | 0 | 0 | 194.4425 | 194.4425 | 64
| 1 | DG10 | m³ | S | 1 | 1 | 51.25 | 350 | 17937.5 | 1 | 1 | 0 | 0 | 0 | 17937.5 | 17937.5 | 65
| Line No. | Resource Name | Unit | Type | No | Production | Quantity | Rate |  |  |  | Labour | Material | Plant | Subcontract | Total
| Line No OH 1 Item No | Project Management |  |  |  |  | 1 |  | 36000 |  |  | 36000 | 0 | 0 | 0 | 36000
| 1 | Project Manager | week | L | 1 | 1 | 9 | 4000 | 36000 |  |  | 36000 | 0 | 0 | 0 | 36000 | 901
| Line No OH 2 Item No | Project Supervision |  |  |  |  | 1 |  | 49740 |  |  | 49740 | 0 | 0 | 0 | 49740
| 1 | Project Supervisor | week | L | 1 | 1 | 12 | 4145 | 49740 |  |  | 49740 | 0 | 0 | 0 | 49740 | 902
| Line No OH 3 Item No | Project Administration |  |  |  |  | 1 |  | 33600 |  |  | 33600 | 0 | 0 | 0 | 33600
| 1 | Project Administrator | hr | L | 1 | 1 | 700 | 48 | 33600 |  |  | 33600 | 0 | 0 | 0 | 33600 | 916
| Line No OH 4 Item No | Project Facilities |  |  |  |  | 1 |  | 10220 |  |  | 0 | 0 | 10220 | 0 | 10220
| 1 | Crib Facilities | week | P | 1 | 1 | 14 | 730 | 10220 |  |  | 0 | 0 | 10220 | 0 | 10220 | 903
| Line No OH 5 Item No | GPS Hire |  |  |  |  | 1 |  | 8000 |  |  | 0 | 0 | 8000 | 0 | 8000
| 1 | GPS Hire | item | P | 1 | 1 | 1 | 8000 | 8000 |  |  | 0 | 0 | 8000 | 0 | 8000 | 16
| Line No OH 6 Item No | Water Pumps |  |  |  |  | 1 |  | 5000 |  |  | 0 | 0 | 5000 | 0 | 5000
| 1 | Pump | each | P | 1 | 1 | 2 | 2500 | 5000 |  |  | 0 | 0 | 5000 | 0 | 5000 | 903
| Line No OH 7 Item No | Accommodation |  |  |  |  | 1 |  | 67260 |  |  | 22260 | 0 | 0 | 45000 | 67260
| 1 | LAFHA | item | L | 6 | 1 | 14 | 265 | 22260 |  |  | 22260 | 0 | 0 | 0 | 22260 | 911
| 2 | Accommodation | day | S | 6 | 1 | 60 | 125 | 45000 |  |  | 0 | 0 | 0 | 45000 | 45000 | 911
| Line No OH 8 Item No | Small Tools |  |  |  |  | 1 |  | 5000 |  |  | 0 | 5000 | 0 | 0 | 5000
| 1 | Small Tools | Item | M | 1 | 1 | 5000 | 1 | 5000 |  |  | 0 | 5000 | 0 | 0 | 5000 | 905

## Resources
| Resource Name | Description | Type | Unit | Currency | Base Rate
Labour Resources | LAFHA |  | L | item | AUD | 265
| Labour | Labour | L | hr | AUD | 48
| Project Administrator |  | L | hr | AUD | 48
| Project Manager | Weekly Rate - Project Manager | L | week | AUD | 4000
| Project Supervisor | Project Supervisor | L | week | AUD | 4145
| Re-establishment |  | L | each | AUD | 1500
| Traffic Controller (Allci |  | L | item | AUD | 45
Material Resources | 375 RCP |  | M | m | AUD | 96.09
| 450 RCP FJ CL2 |  | M | m | AUD | 136
| 525 RCP |  | M | m | AUD | 185
| 600 RCP |  | M | m | AUD | 235
| A34 |  | M | m² | AUD | 2.25
| CBR15 (Fill) |  | M | tonne | AUD | 26.5
| Cold Mix Asphalt |  | M | tonne | AUD | 400
| Guide Post |  | M | each | AUD | 65
| Rock |  | M | tonne | AUD | 31.5
| Sand |  | M | tonne | AUD | 24
| Small Tools |  | M | Item | AUD | 1
| Temporary Pavement Mark |  | M | each | AUD | 3.5
Plant Resources | Backhoe |  | P | hr | AUD | 100
| CAT297 | CAT297C MTL - No Operator | P | hr | AUD | 35
| Crib Facilities | Site Office & Tiolet, 1 Pump out during project. | P | week | AUD | 730
| Excavator - 25T |  | P | hr | AUD | 130
| Float |  | P | LS | AUD | 1
| GPS Hire |  | P | item | AUD | 8000
| Grader | Grader - Wet Hire | P | hr | AUD | 165
| MW Roller - Day |  | P | day | AUD | 365
| PF Roller | Pad Foot Roller - Dry | P | day | AUD | 365
| Plate Compactor | Plate Compactor - Dry Hire | P | hr | AUD | 10
| Pump |  | P | each | AUD | 2500
| SD Roller | SD Roller - Dry | P | day | AUD | 365
| Temporary Fence |  | P | m | AUD | 11.25
| Tipper | Tipper (Wet Hire) | P | hr | AUD | 90
| Ute - Hire |  | P | day | AUD | 25
| WS220 |  | P | day | AUD | 1000
| Water Cart - Hire | Water Cart Hire | P | hr | AUD | 100
Sub-Contract Resources | AMC5 |  | S | litre | AUD | 1.74
| Accommodation |  | S | day | AUD | 125
| C170 |  | S | litre | AUD | 1.6
| CAR | CAR Insurance | S | Item | AUD | 1
| Concrete Sub-contract | CUM Rate | S | m² | AUD | 1100
| Cover Agg - 10mm |  | S | m³ | AUD | 113.82
| Cover Agg - 14mm |  | S | m³ | AUD | 119.98
| Crack Filling |  | S | m | AUD | 10.46
| DG10 | Asphalt Supply & Compact | S | tonne | AUD | 350
| Electrician | Electrician - Hourly Rate | S | hr | AUD | 95
| Enrichmnet Spray |  | S | litre | AUD | 8.73
| Gravel Haulage (18 km) |  | S | km | AUD | 0.24
| Retention Costs |  | S | item | AUD | 1
| Spread - 16mm |  | S | m³ | AUD | 544.37
| Spreading - 10mm |  | S | m³ | AUD | 478.03
| Strain Alleviating Strips |  | S | m | AUD | 8
| Surface Preparation Seal |  | S | m² | AUD | 1.71
| Survey |  | S | hr | AUD | 5.9
| Line Marking |  | S | m² | AUD | 1

## Model Inputs
WBS | Description | Model Input | Qty / Prodn | UOM
3 | Contractor's site facilities, including establishment at commencement and disestablishment at completion of the project. | 1 | Q | Lump
4 | Contractor's site facilities (disestablishment and re-establishment between general localities within the Shire) (Provisional Quantity, if ordered) | 12 | Q | Per r
8.1 | Traffic Control Hours | 624 | Q | 0
11 | Survey of existing road formation, delineation, road furniture and culverts prior to works, to provide locality, geometry and detail for reconstruction | 5645 | Q | m of
13 | Special excavation, removing existing seal (contaminated material) at repair areas and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 769 | Q | m3
13.05 | Depth to remove | 0.03 | Q | 0
13.1 | WS220 | 3000 | P | day
15 | Ann Street | 214 | Q | m3
15.1 | Excavator - 25T | 23.7778 | P | hr
16 | Barberos Road | 195 | Q | m3
16.1 | Excavator - 25T | 21.6667 | P | hr
17 | Burke Offset Road | 261 | Q | m3
17.1 | Excavator - 25T | 29 | P | hr
18 | Fabris Road | 420 | Q | m3
18.1 | Excavator - 25T | 46.6667 | P | hr
19 | Harvey Road | 40 | Q | m3
19.1 | Excavator - 25T | 4.4444 | P | hr
20 | Heards Road | 160 | Q | m3
20.1 | Excavator - 25T | 17.7778 | P | hr
21 | Mile Road | 6 | Q | m3
21.1 | Excavator - 25T | 0.66667 | P | hr
22 | Wallaman Falls Road | 16140 | Q | m2
22.1 | Excavator - 25T | 36 | P | hr
23 | Allingham Road | 264 | Q | m3
23.1 | Excavator - 25T | 29.3333 | P | hr
24 | Taylors Beach Road | 4915 | Q | m2
24.1 | Excavator - 25T | 36 | P | hr
25 | Taraken Road | 19 | Q | m3
25.1 | Excavator - 25T | 2.1111 | P | hr
26 | Amos St | 180 | Q | m3
26.1 | Excavator - 25T | 20 | P | hr
27 | Lannercost Extension Road | 3028 | Q | m2
27.1 | Excavator - 25T | 36 | P | hr
28.1 | Backhoe | 24 | P | hr
29.1 | Backhoe | 42 | P | hr
30.1 | Backhoe | 24 | P | hr
31.1 | Backhoe | 9 | P | hr
32.1 | Backhoe | 30 | P | hr
33 | Excavation and disposal of Unsuitable Material with individual excavation <= 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | 160 | Q | m3
33.1 | Excavator - 25T | 8 | P | hr
35 | Ann Street | 214 | Q | m3
35.1 | Excavator - 25T | 23.7778 | P | hr
36 | Barberos Road | 195 | Q | m3
36.1 | Excavator - 25T | 23.7778 | P | hr
37 | Burke Offset Road | 261 | Q | m3
37.1 | Excavator - 25T | 23.7778 | P | hr
38 | Fabris Road | 420 | Q | m3
38.1 | Excavator - 25T | 23.7778 | P | hr
39 | Harvey Road | 40 | Q | m3
39.1 | Excavator - 25T | 23.7778 | P | hr
40 | Heards Road | 160 | Q | m3
40.1 | Excavator - 25T | 23.7778 | P | hr
41 | Mile Road | 6 | Q | m3
41.1 | Excavator - 25T | 23.7778 | P | hr
42 | Wallaman Falls Road | 2660 | Q | m3
42.1 | Excavator - 25T | 36 | P | hr
43 | Allingham Road | 264 | Q | m3
43.1 | Excavator - 25T | 23.7778 | P | hr
44 | Taylors Beach Road | 810 | Q | m3
44.1 | Excavator - 25T | 36 | P | hr
45 | Taraken Road | 19 | Q | m3
45.1 | Excavator - 25T | 23.7778 | P | hr
46 | Amos Street | 180 | Q | m3
46.1 | Excavator - 25T | 23.7778 | P | hr
47 | Lannercost Extension Road | 499 | Q | m3
47.1 | Excavator - 25T | 36 | P | hr
49 | Deliver select backfill material for backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 160 | Q | m3
50 | Backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 160 | Q | m3
50.1 | Grader | 25 | P | hr
52 | Deliver general fill material, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 52 | Q | m3
53 | Fill repair to formation, inlet structure backfill and drain repairs with general fill material (Contractor installation Rate) (Principal paid material) (Provisional Quantity, if ordered) | 52 | Q | m3
53.1 | Backhoe | 20 | Q | hr
54 | Subgrade treatment Type A, compact existing (Provisonal Quantity, if ordered) | 15971 | Q | m2
54.1 | Grader | 250 | P | hr
56 | Deliver -75 mm graded rock material for subgrade treatment Type I, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 4259 | Q | m3
57 | Subgrade in cuttings, subgrade treatment Type I, -75 mm graded rock fill (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | 4259 | Q | m3
57.2 | Grader | 66.667 | P | hr
58 | Supply and installation of geotextile, Strength Class D, Filtration Class IV for subgrade treatment Type I and drainage (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | 10648 | Q | m2
59 | Supply and installation of geotextile, Strength Class D, Filtration Class IV at culvert pipe repair joints in 200 mm wide circumferential strips with 500 mm end overlaps (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | 8 | Q | m2
60 | Extra over Items MRS04-3208.1PS to MRS04-3208.9PS, MRS04-3108PS and MRS04-3109PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 71570 | Q | m3 *
61 | Extra over Items MRS04-3502.2PS and MRS04-3411.2PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 59212 | Q | m3 *
63 | Removal and salvaging existing culverts for reinstallation; pipe culverts up to 600 dia, box culverts up to 600 x 600 (Provisional Quantity, if ordered) | 10 | Q | m
63.1 | Excavator - 25T | 1.667 | P | hr
64 | Removal and disposal at approved HSC site, of culvert pipes up to 600 dia, including all haulage (Provisional Quantity, if ordered) | 24 | Q | m
64.1 | Excavator - 25T | 2.667 | P | hr
65 | Demolition and removal of culvert end structures and disposal at approved HSC site, including all haulage (Provisional Quantity, if ordered) | 2 | Q | m3
65.1 | Excavator - 25T | 1.111 | P | hr
65.6 | Excavator - 25T | 1.111 | P | hr
66 | Supply and installation of concrete pipe culvert components, Class 2, 375 mm dia (Provisional Quantity, if ordered) | 7.2 | Q | m
66.1 | Excavator - 25T | 0.8 | P | hr
67 | Supply and installation of concrete pipe culvert components, Class 4, 450 mm dia (Provisional Quantity, if ordered) | 6 | Q | m
67.1 | Excavator - 25T | 0.667 | P | hr
68 | Supply and installation of concrete pipe culvert components, Class 8, 525 mm dia (Provisional Quantity, if ordered) | 6 | Q | m
68.1 | Excavator - 25T | 0.667 | P | hr
69 | Supply and installation of concrete pipe culvert components, Class 8, 600 mm dia (Provisional Quantity, if ordered) | 6 | Q | m
69.1 | Excavator - 25T | 0.667 | P | hr
70 | End structures to culverts and repairs to end structures, reinforced concrete (Provisional Quantity, if ordered) | 2 | Q | m3
70.1 | Concrete Sub-contract | 1 | P | m²
72 | Deliver rock for protection (300 mm rock) (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 6 | Q | m3
73 | Rock protection (300 mm rock) (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | 6 | Q | m3
73.1 | Excavator - 25T | 1 | P | hr
75 | Supply premix asphalt material, apply emulsion tack coat (0.3 L/m2) and patch potholes (Provisional Quantity, if ordered) | 20 | Q | tonne
78 | Deliver Subtype 2.2 Unbound Pavement material for Base course, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 3993 | Q | m3
79 | Base course, unbound pavement, Subtype 2.2 (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | 3993 | Q | m3
79.2 | Grader | 88.889 | P | hr
79.3 | Depth of Layer | 0.3 | P | 0
79.4 | Grader | 350 | P | hr
81 | Deliver Subtype 2.3 Unbound Pavement material for Subbase course, including haulage up to 18 km. (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 3993 | Q | m3
82 | Subbase course, unbound pavement, Subtype 2.3. (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | 3993 | Q | m3
82.2 | Grader | 88.889 | P | hr
82.3 | Depth of layer | 0.3 | P | 0
82.4 | Grader | 350 | P | hr
84 | Deliver unbound pavement, Wearing Course Type gravel for shoulders, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 2152 | Q | m3
85 | Unbound pavement, Wearing Course Type gravel for shoulders (Provisional quantity, if ordered) (Contractor installation rate) (Principal paid material) | 2152 | Q | m3
85.2 | Grader | 66.667 | P | hr
85.3 | Depth of Layer | 0.15 | P | 0
85.4 | Grader | 350 | P | hr
86 | Extra over Items MRS05-4151.2PS, MRS05-4153.2,MRS07-4203.2PS and 9005.2 for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 130017 | Q | m3 *
89 | Preparation of the existing sealed surface for resealing (Provisional quantity, if ordered) | 1500 | Q | litre
90 | Enrichment spray, 60% bitumen emulsion, total 0.9L/m2 applied in 3 passes (Provisional quantity, if ordered) | 1350 | Q | litre
91 | Crack Filling (Provisional Quantity, if ordered) | 142 | Q | m
92 | Strain alleviating fabric strips (Provisional Quantity, if ordered) | 8 | Q | m
93 | Primerseal, Grade AMC5, spray rate 1.5 L/m2, including supply of binder, all areas. (Seal design by Contractor) (Provisional Quantity, if ordered) | 38375 | Q | litre
94 | Second Seal C170 Bitumen, 1.5 L/m2 including binder (Seal design by Contractor) (Provisional Quantity, if ordered) | 38375 | Q | litre
95 | Spreading cover aggregate to Primerseal (14mm), spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | 233 | Q | m3
96 | Spreading cover aggregate to Second Seal (10mm), 130 m2/m3 (Seal design by Contractor) (Provisional Quantity, if ordered) | 197 | Q | m3
97 | Supply of Primerseal cover aggregate, precoated, 14 mm nominal size, spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | 233 | Q | m3
98 | Supply of Second Seal cover aggregate, precoated, 10 mm nominal size,spread rate 130 m2/m3 (Seal design by Contractor) (Provisional Quantity) | 197 | Q | m3
100 | Road edge guide posts (Provisional Quantity, if ordered) | 3 | Q | each
101 | Spotting only for longitudinal lines (Provisional Quantity, if ordered) | 3470 | Q | m
102 | Temporary raised pavement markers (Provisional Quantity, if ordered) | 694 | Q | each
103 | VAR01 - TC001 This equates to $3.10/m3 for delivery of 14,397m3 of material which is summation of items at MRS04 -34411.PS; MRS05-4151.2PS;MRS05-4153.2PS & 9005.2PS. This adjustment is made on the basis that Allciv will not have any contractual relationship with the quarry chosen to have any ability to pass on or recoiver cost from the quarry associated with waiting time or slow production rates. This additional amount of $3.10/m3 will cover these costs should they arise (provisional Quantity , if ordered) | 11433 | Q | m³
104 | MRS04 - 3101.1PS - Clearing of Shoulders - width 1m in with to hing point | 7578 | Q | m²
104.01 | Grader | 320 | P | hr
105 | MRS04- 3208.9PS: Special Excavation all material, grading of shoulders to acheive pavemnent surface drainage and disposal of material at HSC disposal site and disposal of material at HSC disposal site,including haulage up to 18km (provisional Quantity,as directed)##CRLF####CRLF##Qty = area x 50mm | 690 | Q | m³
105.01 | Grader | 7.5 | P | hr
106 | 9009.1PS- Moisture conditioning of sub-base 2.3 Gravel | 9366 | Q | tonne
107 | MRS08 - 4301.5PS Deliver Subbase 2.3 Plant mixed 3% cement | 2057 | Q | m³
108 | 9008.1PS - EXTRA OVER ITEMS VAR 3.2, VAR3.5 ,VAR3.7 for haulage in eccess of 18km ##CRLF####CRLF##Wallaman job site - 32.5km - 18km = 14.5km | 16894 | Q | m3*km
109 | MRS08-4301.6PS - Installation sub-base 2.3 3% cement | 2057 | Q | m³
109.01 | Grader | 66.6667 | P | hr
109.02 | Intermediate Trim: QTY based on depth | 0.3 | P | 0
109.03 | Grader | 200 | P | hr
110 | MRS08 4301.2PS Delivery Subtype 2.2 CMB 1.5% Cement | 801.75 | Q | m³
111 | MRS08-4301.3PS Installation subtype 2.2 Cement Treated Base 1.5% cement | 801.75 | Q | m³
111.01 | Grader | 66.6667 | P | hr
111.02 | Intermediate Trim: QTY based on depth | 0.3 | Q | 0
111.03 | Grader | 200 | P | hr
112 | Dayworks to undertake pavement repairs, sweeping and seal patching Wallaman Fall Road Ch 34600 - Ch 34800 | 1 | Q | LS
112.01 | Grader | 200 | P | hr
113 | Dayworks - EIR7561 - removal of loose gravel from verge intersection of Dangercamp road | 1 | Q | LS
113.01 | CAT297 | 0.5 | P | hr
114 | Holding 7mm Seal - Variation works Neame street | 2051 | Q | m²
115 | Hawkin Creek road washout works - rate for installation of rock revised due to qty of rock installation rate for this works only is $111 | 147 | Q | m³
115.01 | Rock | 1 | Q | hr
115.02 | Excavator - 25T | 20 | P | hr
116 | Var 7.1 supply and Lay DG 7 asphalt ##CRLF##Var 7.2 Supply and Spray 10mm C170 ##CRLF####CRLF## | 410 | Q | LS

## Non-Work Days
Non-Working Calendar 2011 - 2015 (Queensland - Australia)
| 2011-01-01 |  | 2012-01-01 |  | 2013-01-01 |  | 2014-01-01 |  | 2015-01-01
| 2011-01-08 | 2011-01-09 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-01 | 2011-01-02 |  | 2012-01-01 | 2013-01-05 | 2013-01-06 | 2014-01-04 | 2014-01-05 | 2015-01-03 | 2015-01-04
| 2011-01-08 | 2011-01-09 | 2012-01-07 | 2012-01-08 | 2013-01-12 | 2013-01-13 | 2014-01-11 | 2014-01-12 | 2015-01-10 | 2015-01-11
| 2011-01-15 | 2011-01-16 | 2012-01-14 | 2012-01-15 | 2013-01-19 | 2013-01-20 | 2014-01-18 | 2014-01-19 | 2015-01-17 | 2015-01-18
| 2011-01-22 | 2011-01-23 | 2012-01-21 | 2012-01-22 | 2013-01-26 | 2013-01-27 | 2014-01-25 | 2014-01-26 | 2015-01-24 | 2015-01-25
| 2011-01-29 | 2011-01-30 | 2012-01-28 | 2012-01-29 | 2013-02-02 | 2013-02-03 | 2014-02-01 | 2014-02-02 | 2015-01-31 | 2015-02-01
| 2011-02-05 | 2011-02-06 | 2012-02-04 | 2012-02-05 | 2013-02-09 | 2013-02-10 | 2014-02-08 | 2014-02-09 | 2015-02-07 | 2015-02-08
| 2011-02-12 | 2011-02-13 | 2012-02-11 | 2012-02-12 | 2013-02-16 | 2013-02-17 | 2014-02-15 | 2014-02-16 | 2015-02-14 | 2015-02-15
| 2011-02-19 | 2011-02-20 | 2012-02-18 | 2012-02-19 | 2013-02-23 | 2013-02-24 | 2014-02-22 | 2014-02-23 | 2015-02-21 | 2015-02-22
| 2011-02-26 | 2011-02-27 | 2012-02-25 | 2012-02-26 | 2013-03-02 | 2013-03-03 | 2014-03-01 | 2014-03-02 | 2015-02-28 | 2015-03-01
| 2011-03-05 | 2011-03-06 | 2012-03-03 | 2012-03-04 | 2013-03-09 | 2013-03-10 | 2014-03-08 | 2014-03-09 | 2015-03-07 | 2015-03-08
| 2011-03-12 | 2011-03-13 | 2012-03-10 | 2012-03-11 | 2013-03-16 | 2013-03-17 | 2014-03-15 | 2014-03-16 | 2015-03-14 | 2015-03-15
| 2011-03-19 | 2011-03-20 | 2012-03-17 | 2012-03-18 | 2013-03-23 | 2013-03-24 | 2014-03-22 | 2014-03-23 | 2015-03-21 | 2015-03-22
| 2011-03-26 | 2011-03-27 | 2012-03-24 | 2012-03-25 | 2013-03-30 | 2013-03-31 | 2014-03-29 | 2014-03-30 | 2015-03-28 | 2015-03-29
| 2011-04-02 | 2011-04-03 | 2012-03-31 | 2012-04-01 | 2013-04-06 | 2013-04-07 | 2014-04-05 | 2014-04-06 | 2015-04-04 | 2015-04-05
| 2011-04-09 | 2011-04-10 | 2012-04-07 | 2012-04-08 | 2013-04-13 | 2013-04-14 | 2014-04-12 | 2014-04-13 | 2015-04-11 | 2015-04-12
| 2011-04-16 | 2011-04-17 | 2012-04-14 | 2012-04-15 | 2013-04-20 | 2013-04-21 | 2014-04-19 | 2014-04-20 | 2015-04-18 | 2015-04-19
| 2011-04-23 | 2011-04-24 | 2012-04-21 | 2012-04-22 | 2013-04-27 | 2013-04-28 | 2014-04-26 | 2014-04-27 | 2015-04-25 | 2015-04-26
| 2011-04-30 | 2011-05-01 | 2012-04-28 | 2012-04-29 | 2013-05-04 | 2013-05-05 | 2014-05-03 | 2014-05-04 | 2015-05-02 | 2015-05-03
| 2011-05-07 | 2011-05-08 | 2012-05-05 | 2012-05-06 | 2013-05-11 | 2013-05-12 | 2014-05-10 | 2014-05-11 | 2015-05-09 | 2015-05-10
| 2011-05-14 | 2011-05-15 | 2012-05-12 | 2012-05-13 | 2013-05-18 | 2013-05-19 | 2014-05-17 | 2014-05-18 | 2015-05-16 | 2015-05-17
| 2011-05-21 | 2011-05-22 | 2012-05-19 | 2012-05-20 | 2013-05-25 | 2013-05-26 | 2014-05-24 | 2014-05-25 | 2015-05-23 | 2015-05-24
| 2011-05-28 | 2011-05-29 | 2012-05-26 | 2012-05-27 | 2013-06-01 | 2013-06-02 | 2014-05-31 | 2014-06-01 | 2015-05-30 | 2015-05-31
| 2011-06-04 | 2011-06-05 | 2012-06-02 | 2012-06-03 | 2013-06-08 | 2013-06-09 | 2014-06-07 | 2014-06-08 | 2015-06-06 | 2015-06-07
| 2011-06-11 | 2011-06-12 | 2012-06-09 | 2012-06-10 | 2013-06-15 | 2013-06-16 | 2014-06-14 | 2014-06-15 | 2015-06-13 | 2015-06-14
| 2011-06-18 | 2011-06-19 | 2012-06-16 | 2012-06-17 | 2013-06-22 | 2013-06-23 | 2014-06-21 | 2014-06-22 | 2015-06-20 | 2015-06-21
| 2011-06-25 | 2011-06-26 | 2012-06-23 | 2012-06-24 | 2013-06-29 | 2013-06-30 | 2014-06-28 | 2014-06-29 | 2015-06-27 | 2015-06-28
| 2011-07-02 | 2011-07-03 | 2012-06-30 | 2012-07-01 | 2013-07-06 | 2013-07-07 | 2014-07-05 | 2014-07-06 | 2015-07-04 | 2015-07-05
| 2011-07-09 | 2011-07-10 | 2012-07-07 | 2012-07-08 | 2013-07-13 | 2013-07-14 | 2014-07-12 | 2014-07-13 | 2015-07-11 | 2015-07-12
| 2011-07-16 | 2011-07-17 | 2012-07-14 | 2012-07-15 | 2013-07-20 | 2013-07-21 | 2014-07-19 | 2014-07-20 | 2015-07-18 | 2015-07-19
| 2011-07-23 | 2011-07-24 | 2012-07-21 | 2012-07-22 | 2013-07-27 | 2013-07-28 | 2014-07-26 | 2014-07-27 | 2015-07-25 | 2015-07-26
| 2011-07-30 | 2011-07-31 | 2012-07-28 | 2012-07-29 | 2013-08-03 | 2013-08-04 | 2014-08-02 | 2014-08-03 | 2015-08-01 | 2015-08-02
| 2011-08-06 | 2011-08-07 | 2012-08-04 | 2012-08-05 | 2013-08-10 | 2013-08-11 | 2014-08-09 | 2014-08-10 | 2015-08-08 | 2015-08-09
| 2011-08-13 | 2011-08-14 | 2012-08-11 | 2012-08-12 | 2013-08-17 | 2013-08-18 | 2014-08-16 | 2014-08-17 | 2015-08-15 | 2015-08-16
| 2011-08-20 | 2011-08-21 | 2012-08-18 | 2012-08-19 | 2013-08-24 | 2013-08-25 | 2014-08-23 | 2014-08-24 | 2015-08-22 | 2015-08-23
| 2011-08-27 | 2011-08-28 | 2012-08-25 | 2012-08-26 | 2013-08-31 | 2013-09-01 | 2014-08-30 | 2014-08-31 | 2015-08-29 | 2015-08-30
| 2011-09-03 | 2011-09-04 | 2012-09-01 | 2012-09-02 | 2013-09-07 | 2013-09-08 | 2014-09-06 | 2014-09-07 | 2015-09-05 | 2015-09-06
| 2011-09-10 | 2011-09-11 | 2012-09-08 | 2012-09-09 | 2013-09-14 | 2013-09-15 | 2014-09-13 | 2014-09-14 | 2015-09-12 | 2015-09-13
| 2011-09-17 | 2011-09-18 | 2012-09-15 | 2012-09-16 | 2013-09-21 | 2013-09-22 | 2014-09-20 | 2014-09-21 | 2015-09-19 | 2015-09-20
| 2011-09-24 | 2011-09-25 | 2012-09-22 | 2012-09-23 | 2013-09-28 | 2013-09-29 | 2014-09-27 | 2014-09-28 | 2015-09-26 | 2015-09-27
| 2011-10-01 | 2011-10-02 | 2012-09-29 | 2012-09-30 | 2013-10-05 | 2013-10-06 | 2014-10-04 | 2014-10-05 | 2015-10-03 | 2015-10-04
| 2011-10-08 | 2011-10-09 | 2012-10-06 | 2012-10-07 | 2013-10-12 | 2013-10-13 | 2014-10-11 | 2014-10-12 | 2015-10-10 | 2015-10-11
| 2011-10-15 | 2011-10-16 | 2012-10-13 | 2012-10-14 | 2013-10-19 | 2013-10-20 | 2014-10-18 | 2014-10-19 | 2015-10-17 | 2015-10-18
| 2011-10-22 | 2011-10-23 | 2012-10-20 | 2012-10-21 | 2013-10-26 | 2013-10-27 | 2014-10-25 | 2014-10-26 | 2015-10-24 | 2015-10-25
| 2011-10-29 | 2011-10-30 | 2012-10-27 | 2012-10-28 | 2013-11-02 | 2013-11-03 | 2014-11-01 | 2014-11-02 | 2015-10-31 | 2015-11-01
| 2011-11-05 | 2011-11-06 | 2012-11-03 | 2012-11-04 | 2013-11-09 | 2013-11-10 | 2014-11-08 | 2014-11-09 | 2015-11-07 | 2015-11-08
| 2011-11-12 | 2011-11-13 | 2012-11-10 | 2012-11-11 | 2013-11-16 | 2013-11-17 | 2014-11-15 | 2014-11-16 | 2015-11-14 | 2015-11-15
| 2011-11-19 | 2011-11-20 | 2012-11-17 | 2012-11-18 | 2013-11-23 | 2013-11-24 | 2014-11-22 | 2014-11-23 | 2015-11-21 | 2015-11-22
| 2011-11-26 | 2011-11-27 | 2012-11-24 | 2012-11-25 | 2013-11-30 | 2013-12-01 | 2014-11-29 | 2014-11-30 | 2015-11-28 | 2015-11-29
| 2011-12-03 | 2011-12-04 | 2012-12-01 | 2012-12-02 | 2013-12-07 | 2013-12-08 | 2014-12-06 | 2014-12-07 | 2015-12-05 | 2015-12-06
| 2011-12-10 | 2011-12-11 | 2012-12-08 | 2012-12-09 | 2013-12-14 | 2013-12-15 | 2014-12-13 | 2014-12-14 | 2015-12-12 | 2015-12-13
| 2011-12-17 | 2011-12-18 | 2012-12-15 | 2012-12-16 | 2013-12-21 | 2013-12-22 | 2014-12-20 | 2014-12-21 | 2015-12-19 | 2015-12-20
| 2011-12-24 | 2011-12-25 | 2012-12-22 | 2012-12-23 | 2013-12-28 | 2013-12-29 | 2014-12-27 | 2014-12-28 | 2015-12-26 | 2015-12-27
| 2011-12-31 |  | 2012-12-29 | 2012-12-30
Christmas Day | 2011-12-25 | 2011-12-23 | 2012-12-25 | 2012-01-02 | 2013-12-25 | 2013-01-02 | 2014-12-25 | 2014-01-02 | 2015-12-25 | 2015-01-02
Boxing Day | 2011-12-27 | 2011-12-24 | 2012-12-26 | 2012-01-03 | 2013-12-26 | 2013-01-03 | 2014-12-26 | 2014-01-03 | 2015-12-26 | 2015-01-05
New Years Day | 2011-01-01 | 2011-12-28 | 2012-01-01 | 2012-01-04 | 2013-01-01 | 2013-01-04 | 2014-01-01 | 2014-12-22 | 2015-01-01 | 2015-01-06
Australia Day | 2011-01-26 | 2011-12-29 | 2013-01-26 | 2012-01-05 | 2013-01-28 | 2013-12-23 | 2014-01-27 | 2014-12-23 | 2015-01-26 | 2015-01-07
Good Friday | 2011-04-22 | 2011-12-30 | 2012-04-06 | 2012-01-06 | 2013-03-29 | 2013-12-24 | 2014-04-18 | 2014-12-24 | 2015-04-03 | 2015-01-08
Easter Monday | 2011-04-25 |  | 2012-04-09 | 2012-12-24 | 2013-04-01 | 2013-12-27 | 2014-04-21 | 2014-12-29 | 2015-04-06 | 2015-01-09
ANZAC Day | 2011-04-26 |  | 2012-04-25 | 2012-12-27 | 2013-04-25 | 2013-12-30 | 2014-04-25 | 2014-12-30 | 2015-04-27 | 2015-12-24
Labour Day | 2011-05-02 |  | 2012-05-07 | 2012-12-28 | 2013-06-10 | 2013-12-31 | 2014-10-06 | 2014-12-31 | 2015-10-05 | 2015-12-27
Queen's Birthday | 2011-06-13 |  | 2012-06-11 | 2012-12-31 | 2013-10-07 |  | 2014-06-09 |  | 2015-06-08 | 2015-12-28
2015-12-29
2015-12-30
2015-12-31
|  | Xmas S/D | 2012-12-28: Xmas S/D; 2013-12-31: Xmas S/D; 2014-12-31: Xmas S/D; 2015-12-27: Xmas S/D
Working Hours | 9
Start Date | 2014-09-01

## Program Links
WBS | Task | Duration | WBS Predecessors | WBS Successors | Budget | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01
1 | HSC 14/12 REHABILITATION OF MULTIPLE ROADS AND STREETS | 0 |  | 3,5,7,9,10,11 | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
2 | ESTABLISHMENT / PRELIMINARIES | 0 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
3 | Contractor's site facilities, including establishment at commencement and disestablishment at completion of the project. | 5 | 1,10 | 5,6,8,29,49,52,56,123,28 | 27679 | 50% | 80% | 90% | 95% | 100% | 100% | 100%
4 | Contractor's site facilities (disestablishment and re-establishment between general localities within the Shire) (Provisional Quantity, if ordered) | 2 |  |  | 18000 | 0% | 0% | 11.76% | 41.18% | 41.18% | 100% | 100%
5 | Develop Environmental Management Plan (Construction) | 5 | 3,1 | 6 | 4000 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | Implement Environmental Management Plan (Construction) | 6 | 5,3 | 207 | 14800 | 20% | 70% | 90% | 95% | 100% | 100% | 100%
7 | Provision of Insurances - As outlined in Condiions of Contract | 1 | 1 | 11 | 12000 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | Provision for Traffic | 99 | 3,9 | 207 | 117220.267 | 17.86% | 62.5% | 80.36% | 84.82% | 89.29% | 100% | 100%
9 | Traffic Management Plan | 1 | 1 | 8 | 4000 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | Site Safety Plan (Construction) | 1 | 1 | 3 | 4000 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
11 | Survey of existing road formation, delineation, road furniture and culverts prior to works, to provide locality, geometry and detail for reconstruction | 15 | 1,7 | 13,22 | 33305.5 | 57.23% | 84.16% | 95.02% | 95.57% | 95.57% | 100% | 100%
12 | EARTHWORKS | 0 |  |  | 0
13 | Special excavation, removing existing seal (contaminated material) at repair areas and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 9 | 11 | 22 | 8544.4444 | 10.12% | 41.32% | 75.82% | 82.62% | 91.26% | 100% | 100%
14 | Special box excavation, all materials and disposal at approved HSC site for road repairs, including haulage up to 18 km (Provisional Quantity, if ordered) | 0 |  |  | 173481.0467 | 10.06% | 41.39% | 80.71% | 86.85% | 96.07% | 100% | 100%
15 | Ann Street | 1 | 99 | 35
16 | Barberos Road | 1 | 105 | 36
17 | Burke Offset Road | 1 | 94 | 37
18 | Fabris Road | 1 | 95 | 38
19 | Harvey Road | 1 | 96 | 39
20 | Heards Road | 1 | 97 | 40
21 | Mile Road | 1 | 102 | 41
22 | Wallaman Falls Road | 19 | 11,13 | 42,54
23 | Allingham Road | 1 | 93 | 43
24 | Taylors Beach Road | 6 | 103 | 44
25 | Taraken Road | 1 | 98 | 45
26 | Amos St | 1 | 101 | 46
27 | Lannercost Extension Road | 4 | 100 | 47
28 | Special excavation all materials, for pothole repairs and disposal at approved HSC disposal site, including haulage up to 18 km (Provisional Quantity, if ordered) | 3 | 3 | 29 | 8016 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
29 | Special excavation, all materials for culverts, inlet and outlet structures and disposal at approved HSC disposal site, including haulage up to 18 km (Provisional Quantity, if ordered) | 5 | 3,28 | 30 | 14028 | 0% | 0% | 0% | 92.09% | 92.09% | 100% | 100%
30 | Special excavation, removal of debris and silt from culvert inlets and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 3 | 29 | 31 | 8016 | 0% | 0% | 0% | 100% | 100% | 100% | 100%
31 | Special excavation, removal of debris and silt from culvert barrels including hydraulic pressure blasting applied for dislodging, removal and cleaning and disposal at approved HSC site, iincluding haulage up to 18 km (Provisional Quantity, if ordered) | 1 | 30 | 32 | 3106 | 0% | 0% | 0% | 33.33% | 33.33% | 100% | 100%
32 | Special excavation, removal of silt from table drains and reshape drains; and from road surfaces and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 4 | 31 | 33 | 10020 | 0% | 0% | 0% | 56.81% | 56.81% | 100% | 100%
33 | Excavation and disposal of Unsuitable Material with individual excavation <= 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | 3 | 32 | 76 | 9124.4444 | 0% | 3.16% | 22.27% | 22.27% | 22.27% | 100% | 100%
34 | Excavation and disposal of Unsuitable Material with individual excavation > 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | 0 |  |  | 94060.0108 | 0% | 5.669% | 67.82% | 84.17% | 100% | 100% | 100%
35 | Ann Street | 1 | 15 | 58
36 | Barberos Road | 1 | 16 | 59
37 | Burke Offset Road | 2 | 17 | 60
38 | Fabris Road | 2 | 18 | 61
39 | Harvey Road | 1 | 19 | 62
40 | Heards Road | 1 | 20 | 63
41 | Mile Road | 1 | 21 | 64
42 | Wallaman Falls Road | 9 | 22 | 65
43 | Allingham Road | 2 | 23 | 66
44 | Taylors Beach Road | 3 | 24 | 67
45 | Taraken Road | 1 | 25 | 68
46 | Amos Street | 1 | 26 | 69
47 | Lannercost Extension Road | 2 | 27 | 70
48 | PRINCIPAL SUPPLIED - Supply select backfill material for backfill to unsuitable excavations, -75 mm graded rock (Principal paid material) (Provisional Quantity, if ordered) | 0 | 49SS | 67 | 0
49 | Deliver select backfill material for backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 18 | 3,65SS | 50,48SS,52,56 | 691.2
50 | Backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 2 | 49 | 67 | 10338.9867
51 | PRINCIPAL SUPPLIED - Supply general fill material for repairs to formation, culverts and drains (Principal paid material) (Provisional Quantity, if ordered) | 0 | 52SS | 67 | 0
52 | Deliver general fill material, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 14 | 3,49 | 51SS,54 | 539.136
53 | Fill repair to formation, inlet structure backfill and drain repairs with general fill material (Contractor installation Rate) (Principal paid material) (Provisional Quantity, if ordered) | 3 | 86 | 207 | 6680
54 | Subgrade treatment Type A, compact existing (Provisonal Quantity, if ordered) | 8 | 22,52 | 67 | 28719.4071 | 10.17% | 41.66% | 81.83% | 85.23% | 91.28% | 100% | 100%
55 | PRINCIPAL SUPPLIED - Supply -75 mm graded rock material for subgrade treatment Type I (Principal paid material) (Provisional Quantity, if ordered) | 0 | 56SS |  | 0
56 | Deliver -75 mm graded rock material for subgrade treatment Type I, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 0 | 3,49 | 55SS,67 | 44157.312 | 0% | 5.515% | 51.2% | 69.28% | 86.08% | 100% | 100%
57 | Subgrade in cuttings, subgrade treatment Type I, -75 mm graded rock fill (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | 0 |  |  | 103203.572 | 0% | 6.339% | 58.85% | 79.63% | 99.22% | 100% | 100%
57.01 | Ann Street | 1 | 35 | 125
57.02 | Barberos Road | 1 | 36 | 126
57.03 | Burke Offset Road | 1 | 37 | 127
57.04 | Fabris Road | 2 | 38 | 128
57.05 | Harvey Road | 1 | 39 | 129
57.06 | Heards Road | 1 | 40 | 130
57.07 | Mile Road | 1 | 41 | 131
57.08 | Wallaman Falls Road | 8 | 42 | 132,49SS
57.09 | Allingham Road | 1 | 43 | 133
57.1 | Taylors Beach Road | 3 | 44,56,54,51,50,48 | 134
57.11 | Taraken Road | 1 | 45 | 135
57.12 | Amos Street | 1 | 46 | 136
57.13 | Lannercost Extension Road | 2 | 47 | 137
58 | Supply and installation of geotextile, Strength Class D, Filtration Class IV for subgrade treatment Type I and drainage (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | 0 |  |  | 26353.8 | 0% | 1.821% | 62.56% | 69.88% | 83.61% | 100% | 100%
59 | Supply and installation of geotextile, Strength Class D, Filtration Class IV at culvert pipe repair joints in 200 mm wide circumferential strips with 500 mm end overlaps (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | 0 |  |  | 19.8
60 | Extra over Items MRS04-3208.1PS to MRS04-3208.9PS, MRS04-3108PS and MRS04-3109PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 0 |  |  | 49469.184 | 0% | 0% | 0% | 85.98% | 100% | 100% | 100%
61 | Extra over Items MRS04-3502.2PS and MRS04-3411.2PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 0 |  |  | 40927.3344
62 | DRAINAGE AND PROTECTION | 0 |  |  | 0
63 | Removal and salvaging existing culverts for reinstallation; pipe culverts up to 600 dia, box culverts up to 600 x 600 (Provisional Quantity, if ordered) | 1 | 33 | 77 | 2723.4553
64 | Removal and disposal at approved HSC site, of culvert pipes up to 600 dia, including all haulage (Provisional Quantity, if ordered) | 1 | 76 | 78 | 4085.4893 | 0% | 0% | 0% | 100% | 100% | 100% | 100%
65 | Demolition and removal of culvert end structures and disposal at approved HSC site, including all haulage (Provisional Quantity, if ordered) | 1 | 77 | 79 | 817.2817 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
66 | Supply and installation of concrete pipe culvert components, Class 2, 375 mm dia (Provisional Quantity, if ordered) | 1 | 78 | 80 | 2859.048 | 0% | 0% | 0% | 100% | 100% | 100% | 100%
67 | Supply and installation of concrete pipe culvert components, Class 4, 450 mm dia (Provisional Quantity, if ordered) | 1 | 79 | 81 | 2974.9385
68 | Supply and installation of concrete pipe culvert components, Class 8, 525 mm dia (Provisional Quantity, if ordered) | 1 | 80 | 82 | 3268.9385
69 | Supply and installation of concrete pipe culvert components, Class 8, 600 mm dia (Provisional Quantity, if ordered) | 1 | 81 | 83 | 3568.9385
70 | End structures to culverts and repairs to end structures, reinforced concrete (Provisional Quantity, if ordered) | 2 | 82 | 85 | 2200 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
71 | PRINCIPAL SUPPLIED - Supply rock for protection (300 mm rock) (Principal paid material) (Provisional Quantity, if ordered) | 0 |  |  | 0
72 | Deliver rock for protection (300 mm rock) (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 2 | 83 | 86 | 62.208 | 0% | 0% | 0% | 0% | 22.86% | 100% | 100%
73 | Rock protection (300 mm rock) (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | 1 | 85 | 53 | 1356 | 0% | 0% | 0% | 0% | 79.21% | 100% | 100%
74 | Pothole Repairs (Asphalt) | 0 | 93 | 88 | 0
75 | Supply premix asphalt material, apply emulsion tack coat (0.3 L/m2) and patch potholes (Provisional Quantity, if ordered) | 1 | 87 | 141 | 8000 | 0% | 0% | 0% | 0% | 0% | 100% | 100%
76 | PAVEMENT | 0 |  |  | 0
77 | PRINCIPAL SUPPLIED - Supply Subtype 2.2 Unbound Pavement material for Base course. (Provisional Quantity, if ordered) (Principal paid material) | 0 | 91SS | 102 | 0
78 | Deliver Subtype 2.2 Unbound Pavement material for Base course, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 3 | 100 | 90SS,102 | 41399.424 | 0% | 51.44% | 99.08% | 100% | 100% | 100% | 100%
79 | Base course, unbound pavement, Subtype 2.2 (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | 0 |  |  | 84519.2022 | 0% | 51.24% | 98.69% | 99.61% | 99.61% | 100% | 100%
79.01 | Ann Street | 1 | 109 | 146,174,23,141,87
79.02 | Barberos Road | 1 | 110 | 147,175,17
79.03 | Burke Offset Road | 1 | 111 | 148,18
79.04 | Fabris Road | 1 | 112 | 149,19
79.05 | Harvey Road | 1 | 113 | 150,20
79.06 | Heards Road | 1 | 114 | 151,25
79.07 | Mile Road | 1 | 115 | 152,15
79.08 | Wallaman Falls Road | 6 | 116 | 153,27,91
79.09 | Allingham Road | 1 | 117 | 154,26
79.1 | Taylors Beach Road | 2 | 118,90,91 | 155,21
79.11 | Taraken Road | 1 | 119 | 156,24
79.12 | Amos Street | 1 | 120 | 157
79.13 | Lannercost Extension Road | 2 | 121 | 158,16
80 | PRINCIPAL SUPPLIED - Supply Subtype 2.3 Unbound Pavement material for Subbase course. (Provisional quantity, if ordered) (Principal paid material) | 0 | 107SS | 118 | 0
81 | Deliver Subtype 2.3 Unbound Pavement material for Subbase course, including haulage up to 18 km. (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 3 | 116SS | 118,106SS | 41399.424 | 13.66% | 49.68% | 96.43% | 97.8% | 97.8% | 100% | 100%
82 | Subbase course, unbound pavement, Subtype 2.3. (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | 0 |  |  | 84519.2022 | 13.22% | 48.95% | 94.17% | 97.88% | 97.88% | 100% | 100%
82.01 | Ann Street | 1 | 125 | 93
82.02 | Barberos Road | 1 | 126 | 94
82.03 | Burke Offset Road | 1 | 127 | 95
82.04 | Fabris Road | 1 | 128 | 96
82.05 | Harvey Road | 1 | 129 | 97
82.06 | Heards Road | 1 | 130 | 98
82.07 | Mile Road | 1 | 131 | 99
82.08 | Wallaman Falls Road | 6 | 132 | 100,107SS
82.09 | Allingham Road | 1 | 133 | 101
82.1 | Taylors Beach Road | 2 | 134107106 | 102
82.11 | Taraken Road | 1 | 135 | 103
82.12 | Amos Street | 1 | 136 | 104
82.13 | Lannercost Extension Road | 2 | 137 | 105
83 | PRINCIPAL SUPPLIED - Supply unbound pavement, Wearing Course Type gravel for shoulders (Principal paid material) (Provisional quantity, if ordered) | 0 | 123SS | 134 | 0
84 | Deliver unbound pavement, Wearing Course Type gravel for shoulders, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 2 | 3,132SS | 122SS,134 | 22311.936 | 0% | 49.96% | 100% | 100% | 100% | 100% | 100%
85 | Unbound pavement, Wearing Course Type gravel for shoulders (Provisional quantity, if ordered) (Contractor installation rate) (Principal paid material) | 0 |  |  | 68243.4033 | 0% | 49.96% | 100% | 100% | 100% | 100% | 100%
85.01 | Ann Street | 1 | 58 | 109
85.02 | Barberos Road | 1 | 59 | 110
85.03 | Burke Offset Road | 1 | 60 | 111
85.04 | Fabris Road | 1 | 61 | 112
85.05 | Harvey Road | 1 | 62 | 113
85.06 | Heards Road | 1 | 63 | 114
85.07 | Mile Road | 1 | 64 | 115
85.08 | Wallaman Falls Road | 4 | 65 | 116,123SS,140,201
85.09 | Allingham Road | 1 | 66 | 117
85.1 | Taylors Beach Road | 2 | 67123122 | 118
85.11 | Taraken Road | 1 | 68 | 119
85.12 | Amos Street | 1 | 69 | 120
85.13 | Lannercost Extension Road | 1 | 70 | 121
86 | Extra over Items MRS05-4151.2PS, MRS05-4153.2,MRS07-4203.2PS and 9005.2 for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 0 |  |  | 89867.7504 | 0% | 47.84% | 92.15% | 94.27% | 94.27% | 100% | 100%
87 | BITUMEN SURFACING | 0 |  |  | 0
88 | Seal Design by Contractor. Application rates are indicative only | 0 | 132 | 153 | 0
89 | Preparation of the existing sealed surface for resealing (Provisional quantity, if ordered) | 1 | 93,88 | 142 | 2565
90 | Enrichment spray, 60% bitumen emulsion, total 0.9L/m2 applied in 3 passes (Provisional quantity, if ordered) | 1 | 141 | 143 | 11785.5
91 | Crack Filling (Provisional Quantity, if ordered) | 1 | 142 | 144 | 1485.32 | 0% | 0% | 100% | 100% | 100% | 100% | 100%
92 | Strain alleviating fabric strips (Provisional Quantity, if ordered) | 1 | 143 | 146 | 64
93 | Primerseal, Grade AMC5, spray rate 1.5 L/m2, including supply of binder, all areas. (Seal design by Contractor) (Provisional Quantity, if ordered) | 0 |  |  | 66772.5 | 0% | 0% | 64.25% | 100% | 100% | 100% | 100%
93.01 | Ann Street | 1 | 93144 | 160174
93.02 | Barberos Road | 1 | 94 | 161175
93.03 | Burke Offset Road | 1 | 95 | 162176
93.04 | Fabris Road | 1 | 96 | 163177
93.05 | Harvey Road | 1 | 97 | 164178
93.06 | Heards Road | 1 | 98 | 165179
93.07 | Mile Road | 1 | 99 | 166180
93.08 | Wallaman Falls Road | 2 | 100201140 | 167181
93.09 | Allingham Road | 1 | 101 | 168182
93.1 | Taylors Beach Road | 1 | 102 | 169183
93.11 | Taraken Road | 1 | 103 | 170184
93.12 | Amos Street | 1 | 104 | 171185
93.13 | Lannercost Extension Road | 1 | 105 | 172186
94 | Second Seal C170 Bitumen, 1.5 L/m2 including binder (Seal design by Contractor) (Provisional Quantity, if ordered) | 0 |  |  | 61400 | 0% | 0% | 30.42% | 66.2% | 66.2% | 100% | 100%
94.01 | Ann Street | 1 | 146 | 188205
94.02 | Barberos Road | 1 | 147 | 189205
94.03 | Burke Offset Road | 1 | 148 | 190205
94.04 | Fabris Road | 1 | 149 | 191205
94.05 | Harvey Road | 1 | 150 | 192205
94.06 | Heards Road | 1 | 151 | 193205
94.07 | Mile Road | 1 | 152 | 194205
94.08 | Wallaman Falls Road | 2 | 153202 | 195,205FF
94.09 | Allingham Road | 1 | 154 | 196205
94.1 | Taylors Beach Road | 1 | 155 | 197205
94.11 | Taraken Road | 1 | 156 | 198205
94.12 | Amos Street | 1 | 157 | 199205
94.13 | Lannercost Extension Road | 1 | 158 | 200205
95 | Spreading cover aggregate to Primerseal (14mm), spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | 0 |  |  | 126838.21 | 0% | 0% | 52.53% | 82.85% | 82.85% | 100% | 100%
95.01 | Ann Street | 1 | 93146
95.02 | Barberos Road | 1 | 94147
95.03 | Burke Offset Road | 1 | 148
95.04 | Fabris Road | 1 | 149
95.05 | Harvey Road | 1 | 150
95.06 | Heards Road | 1 | 151
95.07 | Mile Road | 1 | 152
95.08 | Wallaman Falls Road | 2 | 153
95.09 | Allingham Road | 1 | 154
95.1 | Taylors Beach Road | 1 | 155
95.11 | Taraken Road | 1 | 156
95.12 | Amos Street | 1 | 157
95.13 | Lannercost Extension Road | 1 | 158
96 | Spreading cover aggregate to Second Seal (10mm), 130 m2/m3 (Seal design by Contractor) (Provisional Quantity, if ordered) | 0 |  |  | 94171.91 | 0% | 0% | 32.99% | 71.32% | 71.32% | 100% | 100%
96.01 | Ann Street | 1 | 160
96.02 | Barberos Road | 1 | 161
96.03 | Burke Offset Road | 1 | 162
96.04 | Fabris Road | 1 | 163
96.05 | Harvey Road | 1 | 164
96.06 | Heards Road | 1 | 165
96.07 | Mile Road | 1 | 166
96.08 | Wallaman Falls Road | 2 | 167
96.09 | Allingham Road | 1 | 168
96.1 | Taylors Beach Road | 1 | 169
96.11 | Taraken Road | 1 | 170
96.12 | Amos Street | 1 | 171
96.13 | Lannercost Extension Road | 1 | 172
97 | Supply of Primerseal cover aggregate, precoated, 14 mm nominal size, spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | 1 | 132 | 153202 | 27955.34 | 0% | 0% | 80.78% | 94.15% | 94.15% | 100% | 100%
98 | Supply of Second Seal cover aggregate, precoated, 10 mm nominal size,spread rate 130 m2/m3 (Seal design by Contractor) (Provisional Quantity) | 1 | 201 | 167 | 22422.54 | 0% | 0% | 77.7% | 88.86% | 88.86% | 100% | 100%
99 | ROAD FURNITURE, ROAD SIGNS, LINE MARKING, DELINEATION | 0 |  |  | 0
100 | Road edge guide posts (Provisional Quantity, if ordered) | 1 | 205 | 207 | 195 | 0% | 0% | 0% | 87.5% | 87.5% | 100% | 100%
101 | Spotting only for longitudinal lines (Provisional Quantity, if ordered) | 4 | 160,161,162,163,164,165,166,167FF,168,169,170,171,172 | 206204 | 3470 | 0% | 0% | 0% | 83.39% | 83.39% | 100% | 100%
102 | Temporary raised pavement markers (Provisional Quantity, if ordered) | 0 | 205 | 207 | 2429 | 0% | 0% | 0% | 0% | 82.52% | 100% | 100%
| Practical Completion |  | 206,204,8,6,53

## Budget & Revenue
WBS | Item No | Description | Tender Budget | Unit | Tender Quantity | Contract Quantity | Tender Sell Rate | Tender Sell Total | Final Contract Total | 2014-09-01 | %C - Sep 14 | 2014-10-01 | %C - Oct 14 | 2014-11-01 | %C - Nov 14 | 2014-12-01 | %C - Dec 14 | 2015-01-01 | %C - Jan 15 | 2015-02-01 | %C - Feb 15 | 2015-03-01 | %C - Mar 15 | Revenue Sep 14 | Revenue Oct 14 | Revenue Nov 14 | Revenue Dec 14 | Revenue Jan 15 | Revenue Feb 15 | Revenue Mar 15
Contract Items
1 |  | HSC 14/12 REHABILITATION OF MULTIPLE ROADS AND STREETS
2 |  | ESTABLISHMENT / PRELIMINARIES
3 | MRS28 - 1101 | Contractor's site facilities, including establishment at commencement and disestablishment at completion of the project. | 27679 | Lump | 1 | 1 | 35190.44 | 35190.44 | 35190.44 | 0.5 | 50% | 0.8 | 80% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 17595.22 | 28152.352 | 31671.396 | 33430.918 | 35190.44 | 35190.44 | 35190.44
4 | MRS28 - 1101 | Contractor's site facilities (disestablishment and re-establishment between general localities within the Shire) (Provisional Quantity, if ordered) | 18000 | Per r | 12 | 17 | 1907.07 | 22884.84 | 32420.19 |  | 0% |  | 0% | 2 | 11.76% | 7 | 41.18% | 7 | 41.18% | 17 | 100% | 17 | 100% | 0 | 0 | 3814.14 | 13349.49 | 13349.49 | 32420.19 | 32420.19
5 | MRS51 - 1331 | Develop Environmental Management Plan (Construction) | 4000 | Lump | 1 | 1 | 5085.51 | 5085.51 | 5085.51 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51
6 | MRS51 - 1332 | Implement Environmental Management Plan (Construction) | 14800 | Lump | 1 | 1 | 18816.38 | 18816.38 | 18816.38 | 0.2 | 20% | 0.7 | 70% | 0.9 | 90% | 0.95 | 95% | 1 | 100% | 1 | 100% | 1 | 100% | 3763.276 | 13171.466 | 16934.742 | 17875.561 | 18816.38 | 18816.38 | 18816.38
7 | n/a | Provision of Insurances - As outlined in Condiions of Contract | 12000 | Lump | 1 | 1 | 15256.52 | 15256.52 | 15256.52 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 15256.52 | 15256.52 | 15256.52 | 15256.52 | 15256.52 | 15256.52 | 15256.52
8 | MRS02 - 1201 | Provision for Traffic | 117220.267 | Lump | 1 | 1.12 | 149030.78 | 149030.78 | 166914.4736 | 0.2 | 17.86% | 0.7 | 62.5% | 0.9 | 80.36% | 0.95 | 84.82% | 1 | 89.29% | 1.12 | 100% | 1.12 | 100% | 29806.156 | 104321.546 | 134127.702 | 141579.241 | 149030.78 | 166914.4736 | 166914.4736
9 | MRS02 - 1202 | Traffic Management Plan | 4000 | Lump | 1 | 1 | 5085.51 | 5085.51 | 5085.51 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51
10 | n/a | Site Safety Plan (Construction) | 4000 | Lump | 1 | 1 | 5085.51 | 5085.51 | 5085.51 | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51 | 5085.51
11 | 9001S | Survey of existing road formation, delineation, road furniture and culverts prior to works, to provide locality, geometry and detail for reconstruction | 33305.5 | m of | 5645 | 5941 | 7.5 | 42337.5 | 44557.5 | 3400 | 57.23% | 5000 | 84.16% | 5645 | 95.02% | 5678 | 95.57% | 5678 | 95.57% | 5941 | 100% | 5941 | 100% | 25500 | 37500 | 42337.5 | 42585 | 42585 | 44557.5 | 44557.5
0
12 |  | EARTHWORKS | 0
0
13 | MRS04 - 3208 | Special excavation, removing existing seal (contaminated material) at repair areas and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 8544.4444 | m3 | 769 | 766.1 | 14.24 | 10950.56 | 10909.264 | 77.5 | 10.12% | 316.55 | 41.32% | 580.85 | 75.82% | 632.96 | 82.62% | 699.17 | 91.26% | 766.1 | 100% | 766.1 | 100% | 1103.6 | 4507.672 | 8271.304 | 9013.3504 | 9956.1808 | 10909.264 | 10909.264
14 | MRS04 - 3208 | Special box excavation, all materials and disposal at approved HSC site for road repairs, including haulage up to 18 km (Provisional Quantity, if ordered) | 173481.0467 | m3 | 9369 | 8972.02 | 23.52 | 220358.88 | 211021.9104 | 902.5 | 10.06% | 3713.86 | 41.39% | 7241.11 | 80.71% | 7792.06 | 86.85% | 8619.68 | 96.07% | 8972.02 | 100% | 8972.02 | 100% | 21226.8 | 87349.9872 | 170310.9072 | 183269.2512 | 202734.8736 | 211021.9104 | 211021.9104
28 | MRS04 - 3208 | Special excavation all materials, for pothole repairs and disposal at approved HSC disposal site, including haulage up to 18 km (Provisional Quantity, if ordered) | 8016 | m3 | 9 | 0.75 | 1132.37 | 10191.33 | 849.2775 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 0.75 | 100% | 0.75 | 100% | 0 | 0 | 0 | 0 | 0 | 849.2775 | 849.2775
29 | MRS04 - 3208 | Special excavation, all materials for culverts, inlet and outlet structures and disposal at approved HSC disposal site, including haulage up to 18 km (Provisional Quantity, if ordered) | 14028 | m3 | 15 | 12.65 | 1188.99 | 17834.85 | 15040.7235 |  | 0% |  | 0% |  | 0% | 11.65 | 92.09% | 11.65 | 92.09% | 12.65 | 100% | 12.65 | 100% | 0 | 0 | 0 | 13851.7335 | 13851.7335 | 15040.7235 | 15040.7235
30 | MRS04 - 3208 | Special excavation, removal of debris and silt from culvert inlets and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 8016 | m3 | 18 | 8.1 | 566.19 | 10191.42 | 4586.139 |  | 0% |  | 0% |  | 0% | 8.1 | 100% | 8.1 | 100% | 8.1 | 100% | 8.1 | 100% | 0 | 0 | 0 | 4586.139 | 4586.139 | 4586.139 | 4586.139
31 | MRS04 - 3208 | Special excavation, removal of debris and silt from culvert barrels including hydraulic pressure blasting applied for dislodging, removal and cleaning and disposal at approved HSC site, iincluding haulage up to 18 km (Provisional Quantity, if ordered) | 3106 | m3 | 7 | 3 | 564.13 | 3948.91 | 1692.39 |  | 0% |  | 0% |  | 0% | 1 | 33.33% | 1 | 33.33% | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 564.13 | 564.13 | 1692.39 | 1692.39
32 | MRS04 - 3208 | Special excavation, removal of silt from table drains and reshape drains; and from road surfaces and disposal at approved HSC site, including haulage up to 18 km (Provisional Quantity, if ordered) | 10020 | m3 | 101 | 88.9 | 126.13 | 12739.13 | 11212.957 |  | 0% |  | 0% |  | 0% | 50.5 | 56.81% | 50.5 | 56.81% | 88.9 | 100% | 88.9 | 100% | 0 | 0 | 0 | 6369.565 | 6369.565 | 11212.957 | 11212.957
33 | MRS04 - 3108 | Excavation and disposal of Unsuitable Material with individual excavation <= 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | 9124.4444 | m3 | 160 | 117.72 | 72.5 | 11600 | 8534.7 |  | 0% | 3.72 | 3.16% | 26.22 | 22.27% | 26.22 | 22.27% | 26.22 | 22.27% | 117.72 | 100% | 117.72 | 100% | 0 | 269.7 | 1900.95 | 1900.95 | 1900.95 | 8534.7 | 8534.7
34 | MRS04 - 3109 | Excavation and disposal of Unsuitable Material with individual excavation > 10 m3, including haulage up to 18 km (Provisional Quantity, if ordered) | 94060.0108 | m3 | 4259 | 2378.86 | 30.27 | 128919.93 | 72008.0922 |  | 0% | 134.85 | 5.669% | 1613.46 | 67.82% | 2002.26 | 84.17% | 2378.86 | 100% | 2378.86 | 100% | 2378.86 | 100% | 0 | 4081.9095 | 48839.4342 | 60608.4102 | 72008.0922 | 72008.0922 | 72008.0922
48 | MRS04 - 3502 | PRINCIPAL SUPPLIED - Supply select backfill material for backfill to unsuitable excavations, -75 mm graded rock (Principal paid material) (Provisional Quantity, if ordered) | 0
49 | MRS04 - 3502 | Deliver select backfill material for backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 691.2 | m3 | 160 |  | 13.18 | 2108.8 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | MRS04 - 3502 | Backfill to unsuitable excavations, -75 mm graded rock, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 10338.9867 | m3 | 160 |  | 82.15 | 13144 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | MRS04 - 3501 | PRINCIPAL SUPPLIED - Supply general fill material for repairs to formation, culverts and drains (Principal paid material) (Provisional Quantity, if ordered) | 0
52 | MRS04 - 3501 | Deliver general fill material, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 539.136 | m3 | 52 |  | 13.18 | 685.36 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | MRS04 - 3501 | Fill repair to formation, inlet structure backfill and drain repairs with general fill material (Contractor installation Rate) (Principal paid material) (Provisional Quantity, if ordered) | 6680 | m3 | 52 |  | 163.32 | 8492.64 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | MRS04 - 3402 | Subgrade treatment Type A, compact existing (Provisonal Quantity, if ordered) | 28719.4071 | m2 | 15971 | 30494.55 | 2.29 | 36573.59 | 69832.5195 | 3100 | 10.17% | 12703.7 | 41.66% | 24953.7 | 81.83% | 25990.95 | 85.23% | 27834.35 | 91.28% | 30494.55 | 100% | 30494.55 | 100% | 7099 | 29091.473 | 57143.973 | 59519.2755 | 63740.6615 | 69832.5195 | 69832.5195
55 | MRS04 - 3411 | PRINCIPAL SUPPLIED - Supply -75 mm graded rock material for subgrade treatment Type I (Principal paid material) (Provisional Quantity, if ordered) | 0
56 | MRS04 - 3411 | Deliver -75 mm graded rock material for subgrade treatment Type I, including haulage up to 18 km (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 44157.312 | m3 | 4259 | 1933.33 | 13.18 | 56133.62 | 25481.2894 |  | 0% | 106.62 | 5.515% | 989.79 | 51.2% | 1339.33 | 69.28% | 1664.13 | 86.08% | 1933.33 | 100% | 1933.33 | 100% | 0 | 1405.2516 | 13045.4322 | 17652.3694 | 21933.2334 | 25481.2894 | 25481.2894
57 | MRS04 - 3411 | Subgrade in cuttings, subgrade treatment Type I, -75 mm graded rock fill (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | 103203.572 | m3 | 4259 | 1681.88 | 30.81 | 131219.79 | 51818.7228 |  | 0% | 106.62 | 6.339% | 989.79 | 58.85% | 1339.33 | 79.63% | 1668.68 | 99.22% | 1681.88 | 100% | 1681.88 | 100% | 0 | 3284.9622 | 30495.4299 | 41264.7573 | 51412.0308 | 51818.7228 | 51818.7228
58 | MRS04 - 3304 | Supply and installation of geotextile, Strength Class D, Filtration Class IV for subgrade treatment Type I and drainage (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | 26353.8 | m2 | 10648 | 14641.85 | 3.15 | 33541.2 | 46121.8275 |  | 0% | 266.6 | 1.821% | 9159.45 | 62.56% | 10231.25 | 69.88% | 12241.85 | 83.61% | 14641.85 | 100% | 14641.85 | 100% | 0 | 839.79 | 28852.2675 | 32228.4375 | 38561.8275 | 46121.8275 | 46121.8275
59 | MRS04 - 3304 | Supply and installation of geotextile, Strength Class D, Filtration Class IV at culvert pipe repair joints in 200 mm wide circumferential strips with 500 mm end overlaps (Bidim A39 complies with this specification) (Provisional Quantity, if ordered) | 19.8 | m2 | 8 |  | 3.15 | 25.2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 9002PS | Extra over Items MRS04-3208.1PS to MRS04-3208.9PS, MRS04-3108PS and MRS04-3109PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 49469.184 | m3 * | 71570 | 2361.05 | 0.69 | 49383.3 | 1629.1245 |  | 0% |  | 0% |  | 0% | 2030 | 85.98% | 2361.05 | 100% | 2361.05 | 100% | 2361.05 | 100% | 0 | 0 | 0 | 1400.7 | 1629.1245 | 1629.1245 | 1629.1245
61 | 9003PS | Extra over Items MRS04-3502.2PS and MRS04-3411.2PS for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 40927.3344 | m3 * | 59212 |  | 0.69 | 40856.28 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
62 |  | DRAINAGE AND PROTECTION | 0
0
63 | MRS03 - 2101 | Removal and salvaging existing culverts for reinstallation; pipe culverts up to 600 dia, box culverts up to 600 x 600 (Provisional Quantity, if ordered) | 2723.4553 | m | 10 |  | 346.32 | 3463.2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | MRS03 - 2101 | Removal and disposal at approved HSC site, of culvert pipes up to 600 dia, including all haulage (Provisional Quantity, if ordered) | 4085.4893 | m | 24 | 4.8 | 216.45 | 5194.8 | 1038.96 |  | 0% |  | 0% |  | 0% | 4.8 | 100% | 4.8 | 100% | 4.8 | 100% | 4.8 | 100% | 0 | 0 | 0 | 1038.96 | 1038.96 | 1038.96 | 1038.96
65 | MRS03 - 2102 | Demolition and removal of culvert end structures and disposal at approved HSC site, including all haulage (Provisional Quantity, if ordered) | 817.2817 | m3 | 2 | 1.94 | 577.21 | 1154.42 | 1119.7874 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1.94 | 100% | 1.94 | 100% | 0 | 0 | 0 | 0 | 0 | 1119.7874 | 1119.7874
65.5 | MRS03 - 2221 | Installation of salvaged concrete culvert components, pipe culverts up to 600 mm dia, box culverts up to 600 x 600 (Provisional Quantity, if ordered) | 4086.4086 | m | 10 |  | 519.49 | 5194.9 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 2, 375 mm dia (Provisional Quantity, if ordered) | 2859.048 | m | 7.2 | 4.8 | 504.85 | 3634.92 | 2423.28 |  | 0% |  | 0% |  | 0% | 4.8 | 100% | 4.8 | 100% | 4.8 | 100% | 4.8 | 100% | 0 | 0 | 0 | 2423.28 | 2423.28 | 2423.28 | 2423.28
67 | MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 4, 450 mm dia (Provisional Quantity, if ordered) | 2974.9385 | m | 6 |  | 630.58 | 3783.48 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 8, 525 mm dia (Provisional Quantity, if ordered) | 3268.9385 | m | 6 |  | 692.88 | 4157.28 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | MRS03 - 2241 | Supply and installation of concrete pipe culvert components, Class 8, 600 mm dia (Provisional Quantity, if ordered) | 3568.9385 | m | 6 |  | 756.45 | 4538.7 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | MRS03 - 2308 | End structures to culverts and repairs to end structures, reinforced concrete (Provisional Quantity, if ordered) | 2200 | m3 | 2 | 2.14 | 1398.51 | 2797.02 | 2992.8114 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2.14 | 100% | 2.14 | 100% | 0 | 0 | 0 | 0 | 0 | 2992.8114 | 2992.8114
71 | MRS03 - 2643 | PRINCIPAL SUPPLIED - Supply rock for protection (300 mm rock) (Principal paid material) (Provisional Quantity, if ordered) | 0
72 | MRS03 - 2643 | Deliver rock for protection (300 mm rock) (Contractor delivery rate) (Principal paid material) (Provisional Quantity, if ordered) | 62.208 | m3 | 6 | 206.65 | 13.18 | 79.08 | 2723.647 |  | 0% |  | 0% |  | 0% |  | 0% | 47.25 | 22.86% | 206.65 | 100% | 206.65 | 100% | 0 | 0 | 0 | 0 | 622.755 | 2723.647 | 2723.647
73 | MRS03 - 2643 | Rock protection (300 mm rock) (Contractor installation rate) (Principal paid material) (Provisional Quantity, if ordered) | 1356 | m3 | 6 | 59.65 | 287.33 | 1723.98 | 17139.2345 |  | 0% |  | 0% |  | 0% |  | 0% | 47.25 | 79.21% | 59.65 | 100% | 59.65 | 100% | 0 | 0 | 0 | 0 | 13576.3425 | 17139.2345 | 17139.2345
74 |  | Pothole Repairs (Asphalt) | 0
75 | 9004PS | Supply premix asphalt material, apply emulsion tack coat (0.3 L/m2) and patch potholes (Provisional Quantity, if ordered) | 8000 | tonne | 20 | 1.75 | 400 | 8000 | 700 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1.75 | 100% | 1.75 | 100% | 0 | 0 | 0 | 0 | 0 | 700 | 700
0
76 |  | PAVEMENT | 0
0
77 | MRS05 - 4151 | PRINCIPAL SUPPLIED - Supply Subtype 2.2 Unbound Pavement material for Base course. (Provisional Quantity, if ordered) (Principal paid material) | 0
78 | MRS05 - 4151 | Deliver Subtype 2.2 Unbound Pavement material for Base course, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 41399.424 | m3 | 3993 | 3287.2 | 13.18 | 52627.74 | 43325.296 |  | 0% | 1690.83 | 51.44% | 3256.83 | 99.08% | 3287.2 | 100% | 3287.2 | 100% | 3287.2 | 100% | 3287.2 | 100% | 0 | 22285.1394 | 42925.0194 | 43325.296 | 43325.296 | 43325.296 | 43325.296
79 | MRS05 - 4151 | Base course, unbound pavement, Subtype 2.2 (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | 84519.2022 | m3 | 3993 | 3300 | 33.18 | 132487.74 | 109494 |  | 0% | 1690.83 | 51.24% | 3256.83 | 98.69% | 3287.2 | 99.61% | 3287.2 | 99.61% | 3300 | 100% | 3300 | 100% | 0 | 56101.7394 | 108061.6194 | 109069.296 | 109069.296 | 109494 | 109494
80 | MRS05 - 4153 | PRINCIPAL SUPPLIED - Supply Subtype 2.3 Unbound Pavement material for Subbase course. (Provisional quantity, if ordered) (Principal paid material) | 0
81 | MRS05 - 4153 | Deliver Subtype 2.3 Unbound Pavement material for Subbase course, including haulage up to 18 km. (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 41399.424 | m3 | 3993 | 3403.46 | 13.18 | 52627.74 | 44857.6028 | 465 | 13.66% | 1690.8 | 49.68% | 3281.81 | 96.43% | 3328.7 | 97.8% | 3328.7 | 97.8% | 3403.46 | 100% | 3403.46 | 100% | 6128.7 | 22284.744 | 43254.2558 | 43872.266 | 43872.266 | 44857.6028 | 44857.6028
82 | MRS05 - 4153 | Subbase course, unbound pavement, Subtype 2.3. (Provisional quantity, if ordered) (Contractor Installation Rate) (Principal paid material) | 84519.2022 | m3 | 3993 | 3518.36 | 33.18 | 132487.74 | 116739.1848 | 465 | 13.22% | 1722.4 | 48.95% | 3313.41 | 94.17% | 3443.6 | 97.88% | 3443.6 | 97.88% | 3518.36 | 100% | 3518.36 | 100% | 15428.7 | 57149.232 | 109938.9438 | 114258.648 | 114258.648 | 116739.1848 | 116739.1848
83 | 9005.1PS | PRINCIPAL SUPPLIED - Supply unbound pavement, Wearing Course Type gravel for shoulders (Principal paid material) (Provisional quantity, if ordered) | 0
84 | 9005.2PS | Deliver unbound pavement, Wearing Course Type gravel for shoulders, including haulage up to 18 km (Provisional quantity, if ordered) (Contractor delivery rate) (Principal paid material) | 22311.936 | m3 | 2152 | 365.52 | 13.18 | 28363.36 | 4817.5536 |  | 0% | 182.63 | 49.96% | 365.52 | 100% | 365.52 | 100% | 365.52 | 100% | 365.52 | 100% | 365.52 | 100% | 0 | 2407.0634 | 4817.5536 | 4817.5536 | 4817.5536 | 4817.5536 | 4817.5536
85 | 9005.3PS | Unbound pavement, Wearing Course Type gravel for shoulders (Provisional quantity, if ordered) (Contractor installation rate) (Principal paid material) | 68243.4033 | m3 | 2152 | 365.52 | 33.66 | 72436.32 | 12303.4032 |  | 0% | 182.63 | 49.96% | 365.52 | 100% | 365.52 | 100% | 365.52 | 100% | 365.52 | 100% | 365.52 | 100% | 0 | 6147.3258 | 12303.4032 | 12303.4032 | 12303.4032 | 12303.4032 | 12303.4032
86 | 9006PS | Extra over Items MRS05-4151.2PS, MRS05-4153.2,MRS07-4203.2PS and 9005.2 for haulage in excess of 18 km (Provisional Quantity, if ordered) (m3 x km, single trip) | 89867.7504 | m3 * | 130017 | 51245.68 | 0.69 | 89711.73 | 35359.5192 |  | 0% | 24517.04 | 47.84% | 47224.04 | 92.15% | 48310.88 | 94.27% | 48310.88 | 94.27% | 51245.68 | 100% | 51245.68 | 100% | 0 | 16916.7576 | 32584.5876 | 33334.5072 | 33334.5072 | 35359.5192 | 35359.5192
0
87 |  | BITUMEN SURFACING | 0
0
88 |  | Seal Design by Contractor. Application rates are indicative only | 0
89 | MRS30 - 5401 | Preparation of the existing sealed surface for resealing (Provisional quantity, if ordered) | 2565 | litre | 1500 |  | 1.75 | 2625 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | MRS11 - 5105 | Enrichment spray, 60% bitumen emulsion, total 0.9L/m2 applied in 3 passes (Provisional quantity, if ordered) | 11785.5 | litre | 1350 |  | 8.95 | 12082.5 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | MRS30- 5402P | Crack Filling (Provisional Quantity, if ordered) | 1485.32 | m | 142 | 1700 | 10.72 | 1522.24 | 18224 |  | 0% |  | 0% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 1700 | 100% | 0 | 0 | 18224 | 18224 | 18224 | 18224 | 18224
92 | MRS30- 5403P | Strain alleviating fabric strips (Provisional Quantity, if ordered) | 64 | m | 8 |  | 8.2 | 65.6 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | MRS11 - 5102 | Primerseal, Grade AMC5, spray rate 1.5 L/m2, including supply of binder, all areas. (Seal design by Contractor) (Provisional Quantity, if ordered) | 66772.5 | litre | 38375 | 39715 | 1.78 | 68307.5 | 70692.7 |  | 0% |  | 0% | 25516 | 64.25% | 39715 | 100% | 39715 | 100% | 39715 | 100% | 39715 | 100% | 0 | 0 | 45418.48 | 70692.7 | 70692.7 | 70692.7 | 70692.7
|  |  | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | MRS11 - 5103 | Second Seal C170 Bitumen, 1.5 L/m2 including binder (Seal design by Contractor) (Provisional Quantity, if ordered) | 61400 | litre | 38375 | 48813 | 1.64 | 62935 | 80053.32 |  | 0% |  | 0% | 14851 | 30.42% | 32316 | 66.2% | 32316 | 66.2% | 48813 | 100% | 48813 | 100% | 0 | 0 | 24355.64 | 52998.24 | 52998.24 | 80053.32 | 80053.32
95 | MRS11 - 5112 | Spreading cover aggregate to Primerseal (14mm), spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | 126838.21 | m3 | 233 | 300.8 | 557.98 | 130009.34 | 167840.384 |  | 0% |  | 0% | 158 | 52.53% | 249.2 | 82.85% | 249.2 | 82.85% | 300.8 | 100% | 300.8 | 100% | 0 | 0 | 88160.84 | 139048.616 | 139048.616 | 167840.384 | 167840.384
96 | MRS11 - 5112 | Spreading cover aggregate to Second Seal (10mm), 130 m2/m3 (Seal design by Contractor) (Provisional Quantity, if ordered) | 94171.91 | m3 | 197 | 206.1 | 489.98 | 96526.06 | 100984.878 |  | 0% |  | 0% | 68 | 32.99% | 147 | 71.32% | 147 | 71.32% | 206.1 | 100% | 206.1 | 100% | 0 | 0 | 33318.64 | 72027.06 | 72027.06 | 100984.878 | 100984.878
97 | MRS22 - 5011 | Supply of Primerseal cover aggregate, precoated, 14 mm nominal size, spread rate 110 m2/m3, all areas (Seal design by Contractor) (Provisional Quantity, if ordered) | 27955.34 | m3 | 233 | 300.8 | 122.98 | 28654.34 | 36992.384 |  | 0% |  | 0% | 243 | 80.78% | 283.2 | 94.15% | 283.2 | 94.15% | 300.8 | 100% | 300.8 | 100% | 0 | 0 | 29884.14 | 34827.936 | 34827.936 | 36992.384 | 36992.384
98 | MRS22 - 5011 | Supply of Second Seal cover aggregate, precoated, 10 mm nominal size,spread rate 130 m2/m3 (Seal design by Contractor) (Provisional Quantity) | 22422.54 | m3 | 197 | 206.1 | 116.67 | 22983.99 | 24045.687 |  | 0% |  | 0% | 160.14 | 77.7% | 183.14 | 88.86% | 183.14 | 88.86% | 206.1 | 100% | 206.1 | 100% | 0 | 0 | 18683.5338 | 21366.9438 | 21366.9438 | 24045.687 | 24045.687
0
99 |  | ROAD FURNITURE, ROAD SIGNS, LINE MARKING, DELINEATION | 0
0
100 | MRS14 - 6111 | Road edge guide posts (Provisional Quantity, if ordered) | 195 | each | 3 | 32 | 82.64 | 247.92 | 2644.48 |  | 0% |  | 0% |  | 0% | 28 | 87.5% | 28 | 87.5% | 32 | 100% | 32 | 100% | 0 | 0 | 0 | 2313.92 | 2313.92 | 2644.48 | 2644.48
101 | MRS45 - 6301 | Spotting only for longitudinal lines (Provisional Quantity, if ordered) | 3470 | m | 3470 | 4353 | 1.27 | 4406.9 | 5528.31 |  | 0% |  | 0% |  | 0% | 3630 | 83.39% | 3630 | 83.39% | 4353 | 100% | 4353 | 100% | 0 | 0 | 0 | 4610.1 | 4610.1 | 5528.31 | 5528.31
102 | MRS45 - 6353 | Temporary raised pavement markers (Provisional Quantity, if ordered) | 2429 | each | 694 | 206 | 4.45 | 3088.3 | 916.7 |  | 0% |  | 0% |  | 0% |  | 0% | 170 | 82.52% | 206 | 100% | 206 | 100% | 0 | 0 | 0 | 0 | 756.5 | 916.7 | 916.7
|  | Variations | Variations
103 | VAR01 | VAR01 - TC001 This equates to $3.10/m3 for delivery of 14,397m3 of material which is summation of items at MRS04 -34411.PS; MRS05-4151.2PS;MRS05-4153.2PS & 9005.2PS. This adjustment is made on the basis that Allciv will not have any contractual relationship with the quarry chosen to have any ability to pass on or recoiver cost from the quarry associated with waiting time or slow production rates. This additional amount of $3.10/m3 will cover these costs should they arise (provisional Quantity , if ordered) | 26623.3326 | m³ | 14397 | 14397 | 3.1 | 44630.7 | 44630.7 | 465 | 3.23% | 3503.78 | 24.34% | 8661.61 | 60.16% | 9660.89 | 67.1% | 10792.39 | 74.96% | 11433.4 | 79.42% | 11433.4 | 79.42% | 1441.5 | 10861.718 | 26850.991 | 29948.759 | 33456.409 | 35443.54 | 35443.54
104 | VAR02 | MRS04 - 3101.1PS - Clearing of Shoulders - width 1m in with to hing point | 11597.8922 | m² | 10400 | 10400 | 4.1 | 42640 | 42640 | 1008 | 9.692% | 4408 | 42.38% | 7578 | 72.87% | 7578 | 72.87% | 7578 | 72.87% | 7578 | 72.87% | 7578 | 72.87% | 4132.8 | 18072.8 | 31069.8 | 31069.8 | 31069.8 | 31069.8 | 31069.8
105 | VAR02 | MRS04- 3208.9PS: Special Excavation all material, grading of shoulders to acheive pavemnent surface drainage and disposal of material at HSC disposal site and disposal of material at HSC disposal site,including haulage up to 18km (provisional Quantity,as directed) Qty = area x 50mm | 45057 | m³ | 500 | 690 | 65 | 32500 | 44850 |  | 0% |  | 0% |  | 0% | 83.9 | 12.16% | 690 | 100% | 690 | 100% | 690 | 100% | 0 | 0 | 0 | 5453.5 | 44850 | 44850 | 44850
106 | VAR04.1 | 9009.1PS- Moisture conditioning of sub-base 2.3 Gravel | 22368.9302 | tonne | 10000 | 9365.93 | 3.93 | 39300 | 36808.1049 | 1384 | 14.78% | 5138.87 | 54.87% | 9365.93 | 100% | 9365.93 | 100% | 9365.93 | 100% | 9365.93 | 100% | 9365.93 | 100% | 5439.12 | 20195.7591 | 36808.1049 | 36808.1049 | 36808.1049 | 36808.1049 | 36808.1049
107 | VAR03.5 | MRS08 - 4301.5PS Deliver Subbase 2.3 Plant mixed 3% cement | 67653.9072 | m³ | 450 | 2057.01 | 35.67 | 16051.5 | 73373.5467 |  | 0% | 15.5 | 0.7535% | 812.33 | 39.49% | 1363.81 | 66.3% | 1931.71 | 93.91% | 2057.01 | 100% | 2057.01 | 100% | 0 | 552.885 | 28975.8111 | 48647.1027 | 68904.0957 | 73373.5467 | 73373.5467
108 | VAR3.9 | 9008.1PS - EXTRA OVER ITEMS VAR 3.2, VAR3.5 ,VAR3.7 for haulage in eccess of 18km Wallaman job site - 32.5km - 18km = 14.5km | 22800 | m3*km | 520 | 16893.59 | 1.35 | 702 | 22806.3465 |  | 0% | 224.75 | 1.33% | 16431.11 | 97.26% | 16431.11 | 97.26% | 16431.11 | 97.26% | 16893.59 | 100% | 16893.59 | 100% | 0 | 303.4125 | 22181.9985 | 22181.9985 | 22181.9985 | 22806.3465 | 22806.3465
109 | VAR3.6 | MRS08-4301.6PS - Installation sub-base 2.3 3% cement | 69648.4963 | m³ | 450 | 2057.01 | 57.25 | 25762.5 | 117763.8225 |  | 0% | 15.5 | 0.7535% | 812.33 | 39.49% | 1363.81 | 66.3% | 1931.71 | 93.91% | 2057.01 | 100% | 2057.01 | 100% | 0 | 887.375 | 46505.8925 | 78078.1225 | 110590.3975 | 117763.8225 | 117763.8225
110 | VAR3.2 | MRS08 4301.2PS Delivery Subtype 2.2 CMB 1.5% Cement | 26369.2368 | m³ | 321 | 801.76 | 35.67 | 11450.07 | 28598.7792 |  | 0% |  | 0% | 320.85 | 40.02% | 341.85 | 42.64% | 533.4 | 66.53% | 801.75 | 100% | 801.75 | 100% | 0 | 0 | 11444.7195 | 12193.7895 | 19026.378 | 28598.4225 | 28598.4225
111 | VAR3.3 | MRS08-4301.3PS Installation subtype 2.2 Cement Treated Base 1.5% cement | 27146.6611 | m³ | 321 | 801.76 | 57.25 | 18377.25 | 45900.76 |  | 0% |  | 0% | 320.85 | 40.02% | 341.85 | 42.64% | 533.4 | 66.53% | 801.75 | 100% | 801.75 | 100% | 0 | 0 | 18368.6625 | 19570.9125 | 30537.15 | 45900.1875 | 45900.1875
112 | VAR05 | Dayworks to undertake pavement repairs, sweeping and seal patching Wallaman Fall Road Ch 34600 - Ch 34800 | 5791.0041 | LS | 1 | 1 | 7682.25 | 7682.25 | 7682.25 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 7682.25 | 7682.25 | 7682.25 | 7682.25
113 | VAR06 | Dayworks - EIR7561 - removal of loose gravel from verge intersection of Dangercamp road | 918 | LS | 1 | 1 | 1068.75 | 1068.75 | 1068.75 |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 1068.75 | 1068.75 | 1068.75 | 1068.75
114 | VAR07 | Holding 7mm Seal - Variation works Neame street | 8011.2915 | m² | 2051 | 2051 | 4 | 8204 | 8204 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2051 | 100% | 2051 | 100% | 0 | 0 | 0 | 0 | 0 | 8204 | 8204
| VAR08 | Additional establishment for sealing works Neame Street |  | each | 1 | 1 | 5000 | 5000 | 5000 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 5000 | 5000
115 | VAR09 | Hawkin Creek road washout works - rate for installation of rock revised due to qty of rock installation rate for this works only is $111 | 12061.35 | m³ | 147 | 147 | 111 | 16317 | 16317 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 147 | 100% | 147 | 100% | 0 | 0 | 0 | 0 | 0 | 16317 | 16317
116 | VAR10 | Var 7.1 supply and Lay DG 7 asphalt Var 7.2 Supply and Spray 10mm C170 | 19604.5771 | LS | 1 | 1 | 26045.84 | 26045.84 | 26045.84 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 26045.84
|  | Total, all contract items and variations | 2129969.4933 |  |  |  |  | 2431322.48 | 2283797.9936 | [20 empty] | 2263039.7044

## Portfolio WBS
Portfolio WBS | Description | Quantity | UOM | BAC | BAC Rate | Final Qty (AQ) | Final Cost (AC) | Final Rate | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV | PQ | PV | AQ | AC | EV
11 | Survey - Construction | 180 | hr | 33305.5 | 185.0306 | 198 | 36667.3 | 185.1884 | 0 | 0 | 0 | 0 | 0 | 100 | 18503.0556 | 108 | 20034.6 | 18166.6364 | 100 | 18503.0556 | 108 | 20034.6 | 18166.6364 | 100 | 18503.0556 | 108 | 20034.6 | 18166.6364 | 150 | 27754.5833 | 164 | 30386.6 | 27586.3737 | 165 | 30530.0417 | 182 | 33608.3 | 30614.1465 | 180 | 33305.5 | 198 | 36667.3 | 33305.5
13 | QA Testing | 0 | Item | 0 | 0 | 1 | 4536 | 4536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 2430 | 0 | 0 | 0 | 0.9 | 4239 | 0 | 0 | 0 | 1 | 4536 | 0 | 0 | 0 | 1 | 4536 | 0 | 0 | 0 | 1 | 4536 | 0 | 0 | 0 | 1 | 4536 | 0
16 | GPS Hire | 8 | Weeks | 8000 | 1000 | 14.4 | 12966 | 900.4167 | 0 | 0 | 0 | 0 | 0 | 1 | 1000 | 1 | 900 | 555.5556 | 5 | 5000 | 5 | 4488 | 2777.7778 | 8 | 8000 | 8 | 7314 | 4444.4444 | 8 | 8000 | 11.3 | 10140 | 6277.7778 | 8 | 8000 | 13.6 | 12259.5 | 7555.5556 | 8 | 8000 | 14.4 | 12966 | 8000
41 | Demolition | 1 | Item | 7626.2264 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 0 | 1 | 7626.2264 | 0 | 0 | 7626.2264
53 | Cut to Spoil | 12149 | m3 | 236016.4911 | 19.4268 | 12149 | 359268.44 | 29.5719 | 1000 | 19426.8245 | 903 | 27908.58 | 17542.4225 | 4034 | 78367.8101 | 3747 | 124092.32 | 72792.3115 | 9615 | 186788.9178 | 8854 | 215681.595 | 172005.1043 | 10000 | 194268.2452 | 9946 | 252038.68 | 193219.1967 | 11878 | 230751.8217 | 11000 | 319105.3 | 213695.0697 | 12149 | 236016.4911 | 12149 | 359268.44 | 236016.4911 | 12149 | 236016.4911 | 12149 | 359268.44 | 236016.4911
57 | Remove & Replace unsuitable | 2378 | m3 | 162992.626 | 68.5419 | 2378 | 36487.555 | 15.3438 | 0 | 0 | 0 | 0 | 0 | 34 | 2330.4244 | 34 | 521.85 | 2330.4244 | 1615 | 110695.1602 | 1613 | 23166.375 | 110558.0764 | 2000 | 137083.7897 | 2002 | 27665.145 | 137220.8735 | 2378 | 162992.626 | 2100 | 28898.625 | 143937.9792 | 2378 | 162992.626 | 2378 | 36487.555 | 162992.626 | 2378 | 162992.626 | 2378 | 36487.555 | 162992.626
61 | Subgrade Preparation | 25482 | m2 | 131922.9791 | 5.1771 | 25482 | 3483.915 | 0.13672 | 0 | 0 | 0 | 0 | 0 | 15000 | 77656.5688 | 17000 | 2508.3 | 88010.778 | 25482 | 131922.9791 | 23500 | 3236.39 | 121661.9578 | 25482 | 131922.9791 | 23500 | 3236.39 | 121661.9578 | 25482 | 131922.9791 | 25482 | 3483.915 | 131922.9791 | 25482 | 131922.9791 | 25482 | 3483.915 | 131922.9791 | 25482 | 131922.9791 | 25482 | 3483.915 | 131922.9791
62 | Place & Compact Gravel (CBR80) | 24591 | Tonne | 408944.87 | 16.6299 | 9844 | 112261.32 | 11.404 | 1100 | 18292.8452 | 0 | 0 | 0 | 6750 | 112251.5503 | 1250 | 16948.92 | 51928.1885 | 15000 | 249447.8895 | 4500 | 57164.455 | 186941.4786 | 19401 | 322635.9003 | 6000 | 72503.555 | 249255.3048 | 20401 | 339265.7596 | 7500 | 78440.565 | 311569.131 | 24591 | 408944.87 | 9844 | 107704.35 | 408944.87 | 24591 | 408944.87 | 9844 | 112261.32 | 408944.87
63 | Trim All Layers | 29554 | m2 | 64324.1693 | 2.1765 | 29554 | 31078.215 | 1.0516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 32647.4433 | 15000 | 3857.2 | 32647.4433 | 23650 | 51474.1356 | 20850 | 25586.235 | 45379.9462 | 23650 | 51474.1356 | 20850 | 25856.235 | 45379.9462 | 29554 | 64324.1693 | 29554 | 31078.215 | 64324.1693 | 29554 | 64324.1693 | 29554 | 31078.215 | 64324.1693
64 | Sweep & Prime / Primer seal or Seal | 59019 | m2 | 430929.6926 | 7.3015 | 59019 | 358171.698 | 6.0688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27000 | 197141.6273 | 26911 | 144776.32 | 196491.7901 | 43000 | 313966.2953 | 43316 | 238241.242 | 316273.5825 | 48000 | 350474.0041 | 47300 | 260384.727 | 345362.9249 | 59019 | 430929.6926 | 53800 | 309481.994 | 392822.9462 | 59019 | 430929.6926 | 59019 | 358171.698 | 430929.6926
65 | Asphalt (Cold MIx) | 20 | Tonne | 25937.5 | 1296.875 | 2 | 500.6 | 250.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 25937.5 | 2 | 500.6 | 25937.5 | 20 | 25937.5 | 2 | 500.6 | 25937.5
67 | Line Marking & Signs | 1 | Item | 6094 | 6094 | 1 | 3719.88 | 3719.88 | 0 | 0 | 0 | 0 | 0 | 0.1 | 609.4 | 0.1 | 448.42 | 609.4 | 0.2 | 1218.8 | 0.2 | 681.96 | 1218.8 | 0.7 | 4265.8 | 0.7 | 2668.44 | 4265.8 |  | 0 | 0.7 | 2724.49 | 4265.8 | 1 | 6094 | 1 | 3719.88 | 6094 | 1 | 6094 | 1 | 3719.88 | 6094
72 | 525 > 750 | 31.2 | m | 2200 | 70.5128 | 31.2 | 12781.13 | 409.6516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.2 | 2200 | 31.2 | 12781.13 | 2200 | 31.2 | 2200 | 31.2 | 12781.13 | 2200
81 | SW >450 | 1 | Item | 4246.9385 | 4246.9385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 0 | 1 | 4246.9385 | 0 | 0 | 4246.9385
82 | SW<525 | 1 | Item | 8332.2857 | 8332.2857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 0 | 1 | 8332.2857 | 0 | 0 | 8332.2857
88 | Clean & Trim Table Drains | 141 | m3 | 53447.8922 | 379.0631 | 141 | 11515.3925 | 81.6695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 24639.0992 | 40 | 3205.11 | 15162.5226 | 65 | 24639.0992 | 55 | 4552.23 | 20848.4686 | 65 | 24639.0992 | 65 | 5169.72 | 24639.0992 | 141 | 53447.8922 | 141 | 11435.3925 | 53447.8922 | 141 | 53447.8922 | 141 | 11515.3925 | 53447.8922
141 | Traffic Controllers | 2442 | hr | 117220.267 | 48.0017 | 1473 | 82094.66 | 55.733 | 80 | 3840.1398 | 50 | 4305.04 | 3978.9636 | 485 | 23280.8475 | 290 | 18893.75 | 23077.9888 | 1225 | 58802.1405 | 736 | 43252.38 | 58570.3439 | 1475 | 70802.5773 | 884 | 51499.55 | 70348.0761 | 1860 | 89283.2501 | 1114 | 63826.72 | 88651.3085 | 2280 | 109443.9839 | 1368 | 76966.21 | 108864.4435 | 2442 | 117220.267 | 1473 | 82094.66 | 117220.267
151 | Supply & Place Silt fences & protective devices | 1 | Item | 14800 | 14800 | 1 | 3294.92 | 3294.92 | 0.2 | 2960 | 0.2 | 969.36 | 2960 | 0.5 | 7400 | 0.45 | 1407.96 | 6660 | 0.8 | 11840 | 0.65 | 1407.96 | 9620 | 0.8 | 11840 | 0.8 | 2544.92 | 11840 | 0.9 | 13320 | 0.9 | 3294.92 | 13320 | 1 | 14800 | 1 | 3294.92 | 14800 | 1 | 14800 | 1 | 3294.92 | 14800
221 | Place Protection Rock | 28.6354 | m3 | 6471.6 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.64 | 6472.64 | 0 | 0 | 0 | 28.64 | 6472.64 | 0 | 0 | 0 | 28.64 | 6472.64 | 0 | 0 | 0 | 28.64 | 6472.64 | 0 | 0 | 6471.6
222 | Supply & Place Geofabrics | 14642 | m2 | 26373.6 | 1.8012 | 14642 | 37594.3225 | 2.5676 | 0 | 0 | 0 | 5312.5 | 0 | 0 | 0 | 0 | 5312.5 | 0 | 9250 | 16661.3714 | 9159 | 22060.235 | 16497.4595 | 10500 | 18912.9081 | 10231 | 31275.655 | 18428.3774 | 12500 | 22515.3668 | 12242 | 32198.665 | 22050.6496 | 14641 | 26371.7988 | 14641 | 37594.3225 | 26371.7988 | 14641 | 26371.7988 | 14641 | 37594.3225 | 26373.6
613 | Deliver Road Base Gravel | 24591 | tonne | 307979.0574 | 12.5241 | 24591 | 187160.795 | 7.6109 | 1100 | 13776.4614 | 1067 | 8111.045 | 13363.1676 | 8000 | 100192.4468 | 7837 | 59559.59 | 98151.0257 | 18500 | 231695.0332 | 18645 | 141701.38 | 233511.0213 | 22500 | 281791.2566 | 20626 | 156761.355 | 258321.176 | 22804 | 285598.5696 | 22804 | 173309.795 | 285598.5696 | 24591 | 307979.0574 | 24591 | 187160.795 | 307979.0574 | 24591 | 307979.0574 | 24591 | 187160.795 | 307979.0574
901 | Project Management | 14 | Weeks | 48000 | 3428.5714 | 32 | 123128.13 | 3847.7541 | 2 | 6857.1429 | 6 | 21821.88 | 9000 | 6 | 20571.4286 | 10 | 37971.88 | 15000 | 8 | 27428.5714 | 16 | 63096.88 | 24000 | 10 | 34285.7143 | 20 | 79246.88 | 30000 | 12 | 41142.8571 | 24 | 91359.38 | 36000 | 14 | 48000 | 28 | 107509.38 | 42000 | 14 | 48000 | 32 | 123128.13 | 48000
902 | Project Supervision | 22 | Weeks | 49740 | 2260.9091 | 28 | 64840.5 | 2315.7321 | 2 | 4521.8182 | 1.5 | 3366 | 2664.6429 | 6 | 13565.4545 | 8 | 18013.5 | 14211.4286 | 10 | 22609.0909 | 15 | 34605 | 26646.4286 | 13 | 29391.8182 | 18 | 40995 | 31975.7143 | 16 | 36174.5455 | 23 | 53320.5 | 40857.8571 | 20 | 45218.1818 | 27 | 63130.5 | 47963.5714 | 22 | 49740 | 28 | 64840.5 | 49740
903 | Project Facilities | 20 | Weeks | 16345 | 817.25 | 24 | 30417.647 | 1267.402 | 0 | 0 | 1 | 9804.26 | 681.0417 | 4 | 3269 | 5 | 11488.22 | 3405.2083 | 8 | 6538 | 9 | 13821.77 | 6129.375 | 11 | 8989.75 | 12 | 18600.36 | 8172.5 | 14 | 11441.5 | 16 | 21448.227 | 10896.6667 | 18 | 14710.5 | 20 | 27285.857 | 13620.8333 | 20 | 16345 | 24 | 30417.647 | 16345
904 | Project Insurance, Fees & Levies | 1 | Item | 18750 | 18750 | 1 | 12162.09 | 12162.09 | 0.5 | 9375 | 0.6 | 7581.75 | 11250 | 0.5 | 9375 | 0.75 | 9309.02 | 14062.5 | 0.5 | 9375 | 0.9 | 10840.22 | 16875 | 0.5 | 9375 | 0.9 | 11089.41 | 16875 | 0.5 | 9375 | 0.95 | 11707.29 | 17812.5 | 1 | 18750 | 1 | 12162.09 | 18750 | 1 | 18750 | 1 | 12162.09 | 18750
905 | Small Tools | 1 | Item | 5000 | 5000 | 1 | 3413.1 | 3413.1 | 0.1 | 500 | 0.1 | 881.26 | 500 | 0.3 | 1500 | 0.3 | 1574.18 | 1500 | 0.5 | 2500 | 0.5 | 1739.62 | 2500 | 0.6 | 3000 | 0.6 | 2403.98 | 3000 | 0.7 | 3500 | 0.7 | 2904.89 | 3500 | 0.9 | 4500 | 0.9 | 3413.1 | 4500 | 1 | 5000 | 1 | 3413.1 | 5000
907 | Site Establishment | 1 | Item | 17154 | 17154 | 1 | 43545.1542 | 43545.1542 | 0.5 | 8577 | 0.5 | 28767.095 | 8577 | 0.5 | 8577 | 0.5 | 29388.905 | 8577 | 0.5 | 8577 | 0.6 | 33807.425 | 10292.4 | 0.75 | 12865.5 | 0.75 | 38294.425 | 12865.5 | 1 | 17154 | 0.9 | 39093.1242 | 15438.6 | 1 | 17154 | 0.9 | 41265.1542 | 15438.6 | 1 | 17154 | 1 | 43545.1542 | 17154
910 | De-Establishment & Cleanup | 1 | Item | 18000 | 18000 | 1 | 21497.045 | 21497.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 739.25 | 0 | 0.25 | 4500 | 0.25 | 5441.92 | 4500 | 0.25 | 4500 | 0.25 | 5626.92 | 4500 | 0.5 | 9000 | 0.5 | 10359.815 | 9000 | 1 | 18000 | 1 | 21497.045 | 18000
911 | Accommodation | 360 | Night | 67260 | 186.8333 | 240 | 44449.3 | 185.2054 | 30 | 5605 | 66 | 12235.97 | 18496.5 | 90 | 16815 | 100 | 18465.17 | 28025 | 150 | 28025 | 182 | 33585.04 | 51005.5 | 210 | 39235 | 221 | 40939.25 | 61935.25 | 270 | 50445 | 237 | 43793.14 | 66419.25 | 330 | 61655 | 238 | 44122.03 | 66699.5 | 360 | 67260 | 240 | 44449.3 | 67260
916 | Site Administration | 700 | Hr | 33600 | 48 | 1424 | 68350.729 | 47.9991 | 60 | 2880 | 105 | 5061.125 | 2477.5281 | 180 | 8640 | 441 | 21148.614 | 10405.618 | 300 | 14400 | 818 | 39284.409 | 19301.1236 | 420 | 20160 | 983 | 47196.964 | 23194.382 | 540 | 25920 | 1310 | 62881.144 | 30910.1124 | 660 | 31680 | 1420 | 68170.729 | 33505.618 | 700 | 33600 | 1424 | 68350.729 | 33600
QMR | Supply Rock | 320 | Tonne | 9595.75 | 29.9867 | 0 | 0 | 0 | 100 | 2998.6719 | 0 | 0 | 0 | 100 | 2998.6719 | 0 | 0 | 0 | 100 | 2998.6719 | 0 | 0 | 0 | 320 | 9595.75 | 0 | 0 | 0 | 320 | 9595.75 | 0 | 0 | 0 | 320 | 9595.75 | 0 | 0 | 0 | 320 | 9595.75 | 0 | 0 | 9595.75
QMS | Sand | 6.3 | Tonne | 151.2 | 24 | 36 | 862.1 | 23.9472 | 0 | 0 | 0 | 0 | 0 | 6.3 | 151.2 | 0 | 0 | 0 | 6.3 | 151.2 | 0 | 0 | 0 | 6.3 | 151.2 | 0 | 0 | 0 | 6.3 | 151.2 | 0 | 862.1 | 0 | 6.3 | 151.2 | 36 | 862.1 | 151.2 | 6.3 | 151.2 | 36 | 862.1 | 151.2
SWP | Supply Stormwater Pipe | 25.2 | m | 4027.848 | 159.8352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 0 | 25.2 | 4027.848 | 0 | 0 | 4027.848

## Actual Costs
Date | Description | Resource | Unit | Quantity | Rate | Total | Portfolio WBS
Portfolio WBS 011
2014-10-04 | Induction Travel Taylor Beach Markup and Wallaman Falls Road Model | Survey |  | 1 | 2508 | 2508 | 11
2014-10-04 | Survey at Wallaman falls Road- Field Hours and Office Hours | Survey |  | 1 | 7514 | 7514 | 11
2014-10-04 | Survey on Wallaman Falls Road, Taylors Beach Road | Survey |  | 1 | 10012.6 | 10012.6 | 11
2015-01-19 | Field hours and Survey Crew and Taylors Beach Road. | Survey |  | 1 | 4030 | 4030 | 11
2015-01-19 | Field hours and Survey Crew and Wallamans Falls Road. | Survey |  | 1 | 6322 | 6322 | 11
2015-02-10 | Office hours Crew Allingham Street Model | Survey |  | 1.5 | 110 | 165 | 11
2015-02-10 | Field hours and Survey Crew for Taylors Beach Road. | Survey |  | 1 | 1505 | 1505 | 11
2015-02-10 | Neame Street Detail Survey | Survey |  | 1 | 1551.7 | 1551.7 | 11
2015-03-16 | Field hours and Survey Crew for Wallaman Fall Road. | Survey |  | 1 | 513 | 513 | 11
2015-03-16 | Neame Street - Field Hours-Survey Crew, Office Hours | Survey |  | 1 | 1368 | 1368 | 11
2015-03-16 | Field hours and Survey Crew for Taylors Beach | Survey |  | 1 | 1178 | 1178 | 11
| Subtotal for 011 |  |  |  |  | 36667.3
Portfolio WBS 013
2014-10-29 | California Bearing Ration | QA Testing |  | 1 | 2430 | 2430 | 13
2014-11-24 | California Bearing Ratio, | QA Testing |  | 1 | 1809 | 1809 | 13
2014-12-22 | California Bearing Ratio, Wallaman Falls Rd | QA Testing |  | 1 | 297 | 297 | 13
| Subtotal for 013 |  |  |  |  | 4536
Portfolio WBS 016
2014-10-04 | Hire of Equipment 22/9/14 - 5/10/14 | GPS Hire |  | 1 | 900 | 900 | 16
2014-11-21 | FRU-Contro Box CB450 Software, Accu Grade | CB450 |  | 1 | 375 | 375 | 16
2014-11-21 | Allciv Equipment Hire | Survey |  | 1 | 1800 | 1800 | 16
2014-11-27 | Instrument -SPS730 Robotic UTS & TSC3 Core & Road Internal | Robotic UTS |  | 1 | 1413 | 1413 | 16
2014-12-18 | Instrument -SPS730 Robotic UTS & TSC3 Core & Road Internal | Robotic UTS |  | 1 | 2826 | 2826 | 16
2015-01-30 | Instrument -SPS730 Robotic UTS & TSC3 Core & Road Internal | Robotic UTS |  | 1 | 2826 | 2826 | 16
2015-02-26 | Instrument -SPS730 Robotic UTS & TSC3 Core & Road Internal | Robotic UTS |  | 1 | 2119.5 | 2119.5 | 16
2015-03-06 | Instrument -SPS730 Robotic UTS & TSC3 Core & Road Internal 1/3/15 - 3/3/15 | Robotic UTS |  | 1 | 706.5 | 706.5 | 16
| Subtotal for 016 |  |  |  |  | 12966
Portfolio WBS 053
2014-09-25 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 1.5 | 42.79 | 64.185 | 53
2014-09-25 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-09-25 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-09-25 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 53
2014-09-25 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 53
2014-09-25 | Allciv - New Holland Grader | New Holland | hr | 7 | 42.79 | 299.53 | 53
2014-09-25 | 25T Excavator Hire | Excavator - 25T | hr | 5 | 130 | 650 | 53
2014-09-25 | Hire of 14T Excavator | Excavator - 14T | hr | 6 | 80 | 480 | 53
2014-09-25 | Tipper (Wet Hire) | Tipper | hr | 10 | 90 | 900 | 53
2014-09-25 | Labour | Labour | hr | 5 | 45 | 225 | 53
2014-09-25 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 53
2014-09-25 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 53
2014-09-25 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-09-26 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 53
2014-09-26 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 53
2014-09-26 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-09-26 | Tipper (Wet Hire) | Tipper | hr | 10 | 90 | 900 | 53
2014-09-26 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 10 | 80 | 800 | 53
2014-09-26 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 10 | 80 | 800 | 53
2014-09-26 | 25T Excavator Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-09-26 | Allciv - Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-09-26 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 53
2014-09-26 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2014-09-26 | Hire of 14T Excavator | Excavator - 14T | hr | 3.5 | 80 | 280 | 53
2014-09-26 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 53
2014-09-27 | Hire of 14T Excavator | Excavator - 14T | hr | 1 | 80 | 80 | 53
2014-09-27 | 24T Excavator Hire | Excavator - 25T | hr | 6 | 130 | 780 | 53
2014-09-27 | Labour | Labour | hr | 1 | 45 | 45 | 53
2014-09-27 | ATS Labour Hire | Labour | hr | 5.5 | 46.85 | 257.675 | 53
2014-09-27 | ATS Labour Hire | Labour | hr | 7.5 | 42.6 | 319.5 | 53
2014-09-28 | Travel Allowance for for Henry Miller, James Sherlick, Jeffrey Loder and Steven Loder | Travel Allowance | hr | 19 | 20 | 380 | 53
2014-09-29 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-09-29 | 24T Excavator Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-09-29 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-09-29 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-09-29 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-09-29 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-09-29 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 6.5 | 80 | 520 | 53
2014-09-29 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 8.5 | 80 | 680 | 53
2014-09-29 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 53
2014-09-29 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 53
2014-09-30 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 53
2014-09-30 | Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 53
2014-09-30 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 53
2014-09-30 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-09-30 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-09-30 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 10 | 80 | 800 | 53
2014-09-30 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 53
2014-09-30 | 24T Excavator Hire | Excavator - 25T | hr | 8.5 | 130 | 1105 | 53
2014-10-01 | Allciv - Stabilising Crew - Maitenence on tractor | Labour | hr | 3.5 | 54.58 | 191.03 | 53
2014-10-01 | Allciv - Labour Hire- Maitencence on Tractor | Labour | hr | 3.5 | 42.72 | 149.52 | 53
2014-10-02 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 7.5 | 80 | 600 | 53
2014-10-02 | 24T Excavator Hire | Excavator - 25T | hr | 6.5 | 130 | 845 | 53
2014-10-02 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-02 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-10-02 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-02 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 53
2014-10-02 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-10-02 | ATS Labour Hire | Labour | hr | 0.5 | 42.6 | 21.3 | 53
2014-10-02 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 6.5 | 80 | 520 | 53
2014-10-03 | ATS Labour Hire | Labour | hr | 4.5 | 42.6 | 191.7 | 53
2014-10-03 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-10-03 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 4 | 80 | 320 | 53
2014-10-03 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 53
2014-10-03 | Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 53
2014-10-03 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 53
2014-10-03 | 24T Excavator Hire | Excavator - 25T | hr | 4 | 130 | 520 | 53
2014-10-03 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 4 | 80 | 320 | 53
2014-10-03 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 53
2014-10-08 | 24T Excavator Dry Hire Shannons Excavator | Excavator - Dry Hire | hr | 9 | 55 | 495 | 53
2014-10-08 | 24T Excavator Hire | Excavator - 25T | hr | 9 | 130 | 1170 | 53
2014-10-08 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-10-08 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 53
2014-10-08 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-09 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-10 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2014-10-10 | Truck Tipper Hire | Truck Tipper | hr | 10 | 80 | 800 | 53
2014-10-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 53
2014-10-10 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-10-10 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-10 | Backhoe Hire | Backhoe | hr | 1 | 92.5 | 92.5 | 53
2014-10-10 | Truck Tipper Hire | Truck Tipper | hr | 10 | 80 | 800 | 53
2014-10-10 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 10 | 51 | 510 | 53
2014-10-10 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 53
2014-10-10 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-11 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 53
2014-10-11 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 53
2014-10-11 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 53
2014-10-11 | ATS Labour Hire | Labour |  | 3.5 | 49.7 | 173.95 | 53
2014-10-11 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2014-10-11 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2014-10-11 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 2.5 | 51 | 127.5 | 53
2014-10-13 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 53
2014-10-13 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 53
2014-10-14 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-10-14 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-10-14 | Water Cart Hire | Water Cart - Hire | hr | 3 | 90 | 270 | 53
2014-10-14 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 7.5 | 51 | 382.5 | 53
2014-10-14 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-10-14 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-14 | Allciv - Stabilising Crew | Labour | hr | 9.5 | 54.58 | 518.51 | 53
2014-10-14 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-14 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 53
2014-10-14 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-10-14 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9 | 80 | 720 | 53
2014-10-14 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-15 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-15 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-15 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 53
2014-10-15 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 7 | 51 | 357 | 53
2014-10-15 | Allciv - Stabilising Crew | Labour | hr | 9.5 | 54.58 | 518.51 | 53
2014-10-15 | Hire of 14T Excavator | Excavator - 14T | hr | 3 | 80 | 240 | 53
2014-10-15 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 53
2014-10-15 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-10-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 53
2014-10-15 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-10-15 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-16 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-10-16 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-10-16 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 7.5 | 80 | 600 | 53
2014-10-16 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-16 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9 | 80 | 720 | 53
2014-10-16 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-10-16 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-10-16 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-16 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 53
2014-10-16 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 10 | 51 | 510 | 53
2014-10-16 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 53
2014-10-16 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 53
2014-10-17 | Hire of 14T Excavator | Excavator - 14T | hr | 3.5 | 80 | 280 | 53
2014-10-17 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 7 | 51 | 357 | 53
2014-10-17 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2014-10-17 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2014-10-17 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2014-10-17 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-10-17 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 53
2014-10-17 | Truck Tipper Hire | Truck Tipper | hr | 10 | 80 | 800 | 53
2014-10-17 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-17 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-10-17 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-10-18 | Labour Hire | Labour | hr | 7.5 | 42.72 | 320.4 | 53
2014-10-19 | Travel Allowance for Ben King week ending 19/10/2014 | Travel Allowance |  | 6 | 46 | 276 | 53
2014-10-20 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-20 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 53
2014-10-20 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 53
2014-10-20 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 7 | 51 | 357 | 53
2014-10-20 | Truck Tipper Hire | Truck Tipper | hr | 7.25 | 80 | 580 | 53
2014-10-20 | Tipper (Wet Hire) | Tipper | hr | 7.5 | 80 | 600 | 53
2014-10-20 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-20 | Truck Tipper Hire | Truck Tipper | hr | 7.5 | 80 | 600 | 53
2014-10-20 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-20 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2014-10-20 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-10-20 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-21 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 53
2014-10-21 | Hire of 14T Excavator | Excavator - 14T | hr | 3 | 80 | 240 | 53
2014-10-21 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-10-21 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 7 | 51 | 357 | 53
2014-10-21 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 53
2014-10-21 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-21 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-21 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-10-21 | Tipper (Wet Hire) | Tipper | hr | 4 | 80 | 320 | 53
2014-10-21 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 53
2014-10-21 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-10-22 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 53
2014-10-22 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2014-10-22 | ATS Labour Hire | Labour |  | 6 | 49.7 | 298.2 | 53
2014-10-22 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-22 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 53
2014-10-22 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 3.5 | 51 | 178.5 | 53
2014-10-22 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-22 | Tipper (Wet Hire) | Tipper | hr | 1 | 80 | 80 | 53
2014-10-22 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-10-22 | Truck Tipper Hire | Truck Tipper | hr | 1 | 80 | 80 | 53
2014-10-22 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-10-23 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-23 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 53
2014-10-23 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 53
2014-10-23 | Allciv - New Holland Grader | New Holland | hr | 2 | 35 | 70 | 53
2014-10-23 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 53
2014-10-23 | ATS Labour Hire | Labour |  | 7.5 | 49.7 | 372.75 | 53
2014-10-23 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-10-23 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 53
2014-10-23 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 10 | 51 | 510 | 53
2014-10-24 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 53
2014-10-24 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-10-24 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-10-24 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 53
2014-10-24 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-10-24 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 6 | 51 | 306 | 53
2014-10-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 53
2014-10-27 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 53
2014-10-27 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 53
2014-10-27 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-27 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 10 | 51 | 510 | 53
2014-10-27 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2014-10-27 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-10-27 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-10-27 | Allciv - Stabilising Crew | Labour | hr | 9.5 | 54.58 | 518.51 | 53
2014-10-28 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-10-28 | Allciv - New Holland Grader | New Holland | hr | 2 | 35 | 70 | 53
2014-10-28 | Hire of 14T Excavator | Excavator - 14T | hr | 3 | 80 | 240 | 53
2014-10-28 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 53
2014-10-28 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2014-10-28 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 53
2014-10-28 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-10-28 | Backhoe Hire | Backhoe | hr | 2.5 | 92.5 | 231.25 | 53
2014-10-28 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-10-28 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-10-28 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 80 | 200 | 53
2014-10-28 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2014-10-28 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 10.5 | 51 | 535.5 | 53
2014-10-28 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-28 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 53
2014-10-29 | Truck Tipper Hire | Truck Tipper | hr | 5.25 | 80 | 420 | 53
2014-10-29 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 53
2014-10-29 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-10-29 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2014-10-29 | Allciv - Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2014-10-29 | Labour Hire | Labour | hr | 13 | 42.72 | 555.36 | 53
2014-10-29 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2014-10-29 | Hire of 14T Excavator | Excavator - 14T | hr | 5.5 | 80 | 440 | 53
2014-10-29 | Allciv - New Holland Grader | New Holland | hr | 2 | 35 | 70 | 53
2014-10-30 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 53
2014-10-30 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-10-30 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-10-30 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-10-30 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2014-10-30 | Truck Tipper Hire | Truck Tipper | hr | 2.5 | 80 | 200 | 53
2014-10-30 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-10-30 | Hire of 14T Excavator | Excavator - 14T | hr | 5.5 | 80 | 440 | 53
2014-10-30 | Labour Hire | Labour | hr | 13 | 42.72 | 555.36 | 53
2014-10-30 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 53
2014-10-31 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 53
2014-10-31 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-10-31 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 53
2014-10-31 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-10-31 | Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 53
2014-10-31 | Truck Tipper Hire | Truck Tipper | hr | 7.5 | 80 | 600 | 53
2014-10-31 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-10-31 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-10-31 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-10-31 | 9T Vibrating Rammer Hired 1/10/14 - 31/10/14 | Vibrating Rammer |  | 1 | 2801.25 | 2801.25 | 53
2014-10-31 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2014-10-31 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 9.5 | 51 | 484.5 | 53
2014-11-01 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2014-11-01 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 53
2014-11-01 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 53
2014-11-01 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-11-01 | Truck Tipper Hire | Truck Tipper | hr | 5.5 | 80 | 440 | 53
2014-11-01 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-11-01 | 24T Excavator Dry Hire | Excavator - Dry Hire | hr | 6 | 51 | 306 | 53
2014-11-03 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-11-03 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-11-03 | Hire of 14T Excavator | Excavator - 14T | hr | 7 | 80 | 560 | 53
2014-11-04 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 53
2014-11-04 | Film Polythene | Small Tools |  | 1 | 122.73 | 122.73 | 53
2014-11-06 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-11-06 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-11-06 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 53
2014-11-06 | Truck Tipper Hire | Truck Tipper | hr | 7.5 | 80 | 600 | 53
2014-11-06 | Tipper (Wet Hire) | Tipper | hr | 5.75 | 80 | 460 | 53
2014-11-06 | Truck Tipper Hire | Truck Tipper | hr | 5.5 | 80 | 440 | 53
2014-11-06 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-11-06 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-06 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 53
2014-11-06 | Truck Tipper Hire | Truck Tipper | hr | 7.5 | 80 | 600 | 53
2014-11-06 | Hire of 14T Excavator | Excavator - 14T | hr | 7 | 80 | 560 | 53
2014-11-06 | Western Star Truck | Western Star | hr | 7.5 | 80 | 600 | 53
2014-11-07 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-07 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-11-07 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 53
2014-11-07 | Tipper (Wet Hire) | Tipper | hr | 5 | 80 | 400 | 53
2014-11-07 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-11-07 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-07 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 53
2014-11-07 | Western Star Truck | Western Star | hr | 5 | 80 | 400 | 53
2014-11-07 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-11-07 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-07 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-08 | Western Star Truck | Western Star | hr | 6.5 | 80 | 520 | 53
2014-11-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 53
2014-11-08 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 53
2014-11-08 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 53
2014-11-08 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-11-10 | Western Star Truck | Western Star | hr | 4.5 | 80 | 360 | 53
2014-11-10 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-11-10 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-10 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 53
2014-11-10 | 24T Excavator Dry Hire | Excavator - 25T | hr | 6 | 130 | 780 | 53
2014-11-10 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 53
2014-11-10 | Allciv - New Holland Grader | New Holland | hr | 2 | 35 | 70 | 53
2014-11-11 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 53
2014-11-11 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-11 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-11 | Western Star Truck | Western Star | hr | 4.5 | 80 | 360 | 53
2014-11-11 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-11-11 | 24T Excavator Dry Hire | Excavator - 25T | hr | 6.5 | 130 | 845 | 53
2014-11-11 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-11 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 53
2014-11-11 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-11-11 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 53
2014-11-12 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-11-12 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-12 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-12 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 53
2014-11-12 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 53
2014-11-12 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-12 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-11-12 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 53
2014-11-12 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-13 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-13 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-13 | Western Star Truck | Western Star | hr | 9.5 | 80 | 760 | 53
2014-11-13 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 3 | 80 | 240 | 53
2014-11-13 | 24T Excavator | Excavator - 25T | hr | 5 | 125 | 625 | 53
2014-11-13 | Western Star Truck | Western Star | hr | 6.5 | 80 | 520 | 53
2014-11-13 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-13 | Labour Hire | Labour | hr | 12.5 | 42.72 | 534 | 53
2014-11-13 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 53
2014-11-13 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-11-13 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 53
2014-11-13 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-13 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-14 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-14 | 24T Excavator | Excavator - 25T | hr | 8.5 | 125 | 1062.5 | 53
2014-11-14 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-14 | Western Star Truck | Western Star | hr | 9 | 80 | 720 | 53
2014-11-14 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 53
2014-11-14 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 53
2014-11-14 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 53
2014-11-14 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2014-11-14 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-11-14 | Western Star Truck | Western Star | hr | 3.5 | 80 | 280 | 53
2014-11-14 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2014-11-15 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 53
2014-11-15 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 53
2014-11-15 | 24T Excavator Dry Hire | Excavator - 25T | hr | 6.5 | 130 | 845 | 53
2014-11-15 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-15 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 53
2014-11-15 | 24T Excavator | Excavator - 25T | hr | 8 | 125 | 1000 | 53
2014-11-15 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-11-15 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-15 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 53
2014-11-15 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-17 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 53
2014-11-17 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-11-17 | 24T Excavator Dry Hire | Excavator - 25T | hr | 9.5 | 130 | 1235 | 53
2014-11-17 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 5.5 | 80 | 440 | 53
2014-11-17 | Allciv - Stabilising Crew | Labour | hr | 1 | 54.58 | 54.58 | 53
2014-11-17 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2014-11-18 | Western Star Truck | Western Star | hr | 4 | 80 | 320 | 53
2014-11-18 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-18 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2014-11-18 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 53
2014-11-18 | Western Star Truck | Western Star | hr | 4 | 80 | 320 | 53
2014-11-18 | 24T Excavator Dry Hire | Excavator - 25T | hr | 9 | 130 | 1170 | 53
2014-11-18 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-11-18 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-18 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-18 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 53
2014-11-18 | Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 53
2014-11-19 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-11-19 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-19 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-19 | Allciv - Stabilising Crew | Labour | hr | 2.5 | 54.58 | 136.45 | 53
2014-11-19 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-19 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2014-11-19 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 90 | 225 | 53
2014-11-19 | Backhoe Hire | Backhoe | hr | 5.5 | 92.5 | 508.75 | 53
2014-11-19 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 53
2014-11-19 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2014-11-20 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-20 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 53
2014-11-20 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-20 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-11-20 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 53
2014-11-20 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-20 | Labour Hire | Labour | hr | 11.75 | 42.72 | 501.96 | 53
2014-11-20 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 53
2014-11-20 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 53
2014-11-20 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-11-20 | Tipper (Wet Hire) | Tipper | hr | 8 | 90 | 720 | 53
2014-11-21 | Tipper (Wet Hire) | Tipper | hr | 4.5 | 90 | 405 | 53
2014-11-24 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 53
2014-11-24 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2014-11-24 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-25 | 24T Excavator Dry Hire | Excavator - 25T | hr | 6.5 | 130 | 845 | 53
2014-11-25 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-11-25 | Tipper (Wet Hire) | Tipper | hr | 9 | 90 | 810 | 53
2014-11-25 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-11-26 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-11-26 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-11-26 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-11-26 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-11-26 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 53
2014-11-26 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-11-26 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 53
2014-11-27 | 24T Excavator Dry Hire | Excavator - 25T | hr | 7 | 130 | 910 | 53
2014-11-28 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-28 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-11-30 | Vibrating Multi Tyre Roller Hired 31/10/14 -* 30/11/14 | Multi Tyre Roller |  | 1 | 1218 | 1218 | 53
2014-12-04 | Allciv - Stabilising Crew | Labour | hr | 9.5 | 54.58 | 518.51 | 53
2014-12-04 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-12-04 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-12-04 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 53
2014-12-05 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-12-05 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 53
2014-12-05 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 53
2014-12-08 | Hire of 14T Excavator | Excavator - 14T | hr | 4.5 | 80 | 360 | 53
2014-12-08 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 53
2014-12-08 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-12-08 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-12-08 | Western Star Truck | Western Star | hr | 5 | 80 | 400 | 53
2014-12-08 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-12-08 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-12-09 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-12-09 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 53
2014-12-09 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 53
2014-12-09 | Backhoe Hire | Backhoe | hr | 4.5 | 92.5 | 416.25 | 53
2014-12-09 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-12-09 | Western Star Truck | Western Star | hr | 9 | 80 | 720 | 53
2014-12-09 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2014-12-09 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-12-10 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 53
2014-12-10 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2014-12-10 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-12-10 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 53
2014-12-10 | Backhoe Hire | Backhoe | hr | 6 | 92.5 | 555 | 53
2014-12-10 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-12-10 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-12-10 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 53
2014-12-10 | Western Star Truck | Western Star | hr | 10 | 80 | 800 | 53
2014-12-11 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 53
2014-12-11 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2014-12-11 | Western Star Truck & Dog | Western Star | hr | 7 | 120 | 840 | 53
2014-12-11 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2014-12-11 | Hire of 14T Excavator | Excavator - 14T | hr | 8.5 | 80 | 680 | 53
2014-12-11 | Backhoe Hire | Backhoe | hr | 2.5 | 92.5 | 231.25 | 53
2014-12-11 | Western Star Truck | Western Star | hr | 2 | 80 | 160 | 53
2014-12-11 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2014-12-11 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-12-11 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 53
2014-12-11 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2014-12-11 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2014-12-11 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 53
2014-12-13 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2014-12-13 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 53
2014-12-13 | Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 53
2014-12-13 | Western Star Truck | Truck Tipper | hr | 10 | 80 | 800 | 53
2014-12-13 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 53
2014-12-13 | Western Star Truck and Trailer | Western Star | hr | 3.5 | 120 | 420 | 53
2014-12-13 | 2.2 Roadbase Cartage 219.38 | Truck Tipper |  | 8.5 | 75 | 637.5 | 53
2014-12-13 | Truck Tipper Hire | Truck Tipper | hr | 10 | 80 | 800 | 53
2014-12-13 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2014-12-13 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 53
2014-12-13 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2014-12-13 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 53
2014-12-15 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2014-12-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 53
2014-12-15 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-12-15 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2014-12-15 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 53
2014-12-15 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2014-12-15 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2014-12-15 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2014-12-15 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2014-12-15 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 53
2015-01-05 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2015-01-05 | Allciv - Stabilising Crew | Labour | hr | 11 | 54.58 | 600.38 | 53
2015-01-05 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-05 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 53
2015-01-05 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2015-01-05 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 53
2015-01-05 | Tipper (Wet Hire) | Tipper | hr | 8 | 90 | 720 | 53
2015-01-05 | Hire of 14T Excavator | Excavator - 14T | hr | 11 | 80 | 880 | 53
2015-01-05 | ATS Labour Hire | Labour | hr | 5.5 | 46.85 | 257.675 | 53
2015-01-05 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 53
2015-01-06 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 53
2015-01-06 | ATS Labour Hire | Labour |  | 4.5 | 49.7 | 223.65 | 53
2015-01-06 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2015-01-06 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-01-06 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 53
2015-01-06 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-06 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 90 | 225 | 53
2015-01-06 | Hire of 14T Excavator | Excavator - 14T | hr | 4.5 | 80 | 360 | 53
2015-01-06 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 53
2015-01-06 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 53
2015-01-07 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 53
2015-01-07 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2015-01-07 | Tipper (Wet Hire) | Tipper | hr | 5 | 90 | 450 | 53
2015-01-07 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2015-01-07 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 53
2015-01-07 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-07 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2015-01-07 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-01-07 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 53
2015-01-07 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 53
2015-01-08 | Truck & Dog Hire | Truck & Dog | hr | 4.5 | 120 | 540 | 53
2015-01-08 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 53
2015-01-08 | Allciv - 120H Grader | 120H Grader | hr | 10 | 135 | 1350 | 53
2015-01-08 | Tipper (Wet Hire) | Tipper | hr | 4 | 90 | 360 | 53
2015-01-08 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 53
2015-01-08 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-08 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 120 | 360 | 53
2015-01-08 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2015-01-08 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 53
2015-01-08 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2015-01-08 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 53
2015-01-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 53
2015-01-08 | Allciv - Stabilising Crew | Labour | hr | 8.5 | 54.58 | 463.93 | 53
2015-01-09 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2015-01-09 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 53
2015-01-09 | Hire of 14T Excavator | Excavator - 14T | hr | 9 | 80 | 720 | 53
2015-01-09 | Tipper (Wet Hire) | Tipper | hr | 5 | 90 | 450 | 53
2015-01-09 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2015-01-10 | Hire of 14T Excavator | Excavator - 14T | hr | 3.5 | 80 | 280 | 53
2015-01-10 | ATS Labour Hire | Labour |  | 4.5 | 49.7 | 223.65 | 53
2015-01-10 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 90 | 225 | 53
2015-01-10 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-01-10 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 53
2015-01-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 53
2015-01-12 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 53
2015-01-12 | Tipper (Wet Hire) | Tipper | hr | 7 | 90 | 630 | 53
2015-01-12 | Hire of 14T Excavator | Excavator - 14T | hr | 7 | 80 | 560 | 53
2015-01-12 | ATS Labour Hire | Labour |  | 7 | 49.7 | 347.9 | 53
2015-01-12 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-12 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 53
2015-01-12 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-01-12 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2015-01-12 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-01-13 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-13 | Tipper (Wet Hire) | Tipper | hr | 4 | 90 | 360 | 53
2015-01-13 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2015-01-13 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 53
2015-01-13 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2015-01-13 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-01-13 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2015-01-14 | Hire of 14T Excavator | Excavator - 14T | hr | 6.5 | 80 | 520 | 53
2015-01-14 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2015-01-14 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2015-01-14 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 53
2015-01-14 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2015-01-14 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-15 | Hire of 14T Excavator | Excavator - 14T | hr | 5 | 80 | 400 | 53
2015-01-15 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 53
2015-01-15 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-15 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2015-01-15 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 53
2015-01-15 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 53
2015-01-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2015-01-15 | CAT297C MTL - No Operator | CAT297 | hr | 2 | 35 | 70 | 53
2015-01-16 | Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 53
2015-01-16 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-01-16 | ATS Labour Hire/ Travel Cost 52Hours | Labour |  | 52 | 20 | 1040 | 53
2015-01-16 | Tipper (Wet Hire) | Tipper | hr | 4 | 90 | 360 | 53
2015-01-16 | Hire of 14T Excavator | Excavator - 14T | hr | 5 | 80 | 400 | 53
2015-01-16 | ATS Labour Hire/Travel Cost | Labour | hr | 15 | 20 | 300 | 53
2015-01-16 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-16 | ATS Labour Hire | Labour |  | 3.5 | 49.7 | 173.95 | 53
2015-01-16 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 53
2015-01-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2015-01-19 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 53
2015-01-19 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 53
2015-01-19 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-19 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 53
2015-01-19 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2015-01-19 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 53
2015-01-19 | Tipper (Wet Hire) | Tipper | hr | 8 | 90 | 720 | 53
2015-01-20 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2015-01-21 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-21 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 90 | 225 | 53
2015-01-21 | Hire of 14T Excavator | Excavator - 14T | hr | 5.5 | 80 | 440 | 53
2015-01-21 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-01-21 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 53
2015-01-27 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2.5 | 80 | 200 | 53
2015-01-27 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 53
2015-01-27 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-01-27 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 53
2015-01-27 | Allciv - Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 53
2015-01-27 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 53
2015-01-27 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 53
2015-01-27 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 53
2015-01-27 | Tipper (Wet Hire) | Tipper | hr | 7.5 | 90 | 675 | 53
2015-01-28 | Backhoe Hire | Backhoe | hr | 3.5 | 92.5 | 323.75 | 53
2015-01-28 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2.5 | 80 | 200 | 53
2015-01-29 | Tipper (Wet Hire) | Tipper | hr | 3.5 | 90 | 315 | 53
2015-01-29 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 53
2015-01-29 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-01-29 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-01-29 | Travel Cost | Labour |  | 5 | 20 | 100 | 53
2015-01-30 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 53
2015-01-30 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-01-30 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 53
2015-01-30 | CAT297C MTL - No Operator | CAT297 | hr | 2 | 35 | 70 | 53
2015-01-30 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 53
2015-01-30 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 53
2015-01-30 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 53
2015-01-30 | ATS Labour Hire/ Travel Cost week ending 1/2/15 | Labour |  | 4 | 20 | 80 | 53
2015-01-30 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 53
2015-01-30 | ATS Labour Hire | Labour | hr | 3.5 | 46.85 | 163.975 | 53
2015-01-30 | ATS Labour Hire Travel Costs | Labour | hr | 1 | 20 | 20 | 53
2015-02-02 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 53
2015-02-02 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-02-02 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-02-02 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-02-02 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 53
2015-02-02 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 53
2015-02-02 | CAT297C MTL - No Operator | CAT297 | hr | 4 | 35 | 140 | 53
2015-02-02 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 53
2015-02-03 | Hire of 14T Excavator | Excavator - 14T | hr | 4.5 | 80 | 360 | 53
2015-02-03 | Hire of 14T Excavator | Excavator - 14T | hr | 3 | 80 | 240 | 53
2015-02-03 | Truck Tipper Hire | Truck Tipper | hr | 5.5 | 80 | 440 | 53
2015-02-03 | CAT297C MTL - No Operator | CAT297 | hr | 8 | 35 | 280 | 53
2015-02-03 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-02-03 | Tipper (Wet Hire) | Tipper | hr | 5.5 | 90 | 495 | 53
2015-02-03 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 53
2015-02-04 | Hire of 14T Excavator | Excavator - 14T | hr | 9 | 80 | 720 | 53
2015-02-06 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 53
2015-02-06 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 53
2015-02-06 | Tipper (Wet Hire) | Tipper | hr | 10 | 90 | 900 | 53
2015-02-06 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-02-06 | CAT297C MTL - No Operator | CAT297 | hr | 11.5 | 35 | 402.5 | 53
2015-02-06 | ATS Labour Hire | Labour | hr | 5.5 | 46.85 | 257.675 | 53
2015-02-06 | ATS Labour Hire | Labour |  | 6 | 49.7 | 298.2 | 53
2015-02-07 | ATS Labour Hire Travel Costs | Labour | hr | 6 | 20 | 120 | 53
2015-02-07 | ATS Travel Cost week ending 8/2/15 | Labour |  | 6 | 20 | 120 | 53
2015-02-09 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 53
2015-02-16 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 53
2015-02-17 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5.5 | 42.79 | 235.345 | 53
2015-02-17 | CAT297C MTL - No Operator | CAT297 | hr | 10.5 | 35 | 367.5 | 53
2015-02-17 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 53
2015-02-17 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-02-17 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 53
2015-02-17 | Hire of 14T Excavator | Excavator - 14T | hr | 7 | 80 | 560 | 53
2015-02-17 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2015-02-17 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 53
2015-02-17 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2015-02-17 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-02-17 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 53
2015-02-18 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 53
2015-02-18 | Allciv - Stabilising Crew | Labour | hr | 11 | 54.58 | 600.38 | 53
2015-02-18 | Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 53
2015-02-18 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-02-18 | Hire of 14T Excavator | Excavator - 14T | hr | 11 | 80 | 880 | 53
2015-02-18 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2015-02-18 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2015-02-18 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 53
2015-02-19 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 53
2015-02-19 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-02-19 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 53
2015-02-19 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 53
2015-02-19 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 53
2015-02-19 | Bobcat Hire | Bobcat Hire |  | 8 | 35 | 280 | 53
2015-02-20 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 53
2015-02-20 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 11 | 42.79 | 470.69 | 53
2015-02-20 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-02-20 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 53
2015-02-20 | Truck Tipper Hire | Truck Tipper | hr | 2.5 | 80 | 200 | 53
2015-02-20 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 53
2015-02-20 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 53
2015-02-20 | Bobcat Hire | Bobcat Hire |  | 11 | 35 | 385 | 53
2015-02-22 | ATS Labour Hire Travel Costs Week Ending 8/3/15 | Labour | hr | 4 | 20 | 80 | 53
2015-02-22 | ATS Labour Hire Travel Costs Week Ending 1/3/15 | Labour | hr | 3 | 20 | 60 | 53
2015-02-22 | ATS Labour Hire Travel Costs Week Ending 22/2/15 | Labour | hr | 6 | 20 | 120 | 53
2015-02-23 | Bobcat Hire | Bobcat Hire |  | 6 | 35 | 210 | 53
2015-02-23 | Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 53
2015-02-24 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 53
2015-02-24 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 53
2015-02-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 53
2015-02-24 | Bobcat Hire | Bobcat Hire |  | 6 | 35 | 210 | 53
2015-02-24 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 53
2015-02-24 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2015-02-24 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 53
2015-02-24 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 53
2015-02-24 | Hire of 14T Excavator | Excavator - 14T | hr | 7 | 80 | 560 | 53
2015-02-24 | CAT297C MTL - No Operator | CAT297 | hr | 11.5 | 35 | 402.5 | 53
2015-02-24 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 53
2015-02-24 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-02-25 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2015-02-25 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 53
2015-02-25 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 53
2015-02-25 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 53
2015-02-25 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 53
2015-02-25 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 53
2015-02-25 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 53
2015-02-25 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 53
2015-02-25 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 53
2015-02-26 | CAT297C MTL - No Operator | CAT297 | hr | 10.5 | 35 | 367.5 | 53
2015-02-26 | Bobcat Hire | Bobcat Hire |  | 6 | 35 | 210 | 53
2015-02-26 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 53
2015-02-26 | Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 53
2015-02-27 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 53
| Subtotal for 053 |  |  |  |  | 359268.44
Portfolio WBS 057
2014-10-17 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 57
2014-11-01 | ATS Labour Hire | Labour |  | 8.5 | 49.7 | 422.45 | 57
2014-11-03 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 57
2014-11-03 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 57
2014-11-04 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 57
2014-11-04 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 57
2014-11-04 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 57
2014-11-04 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 57
2014-11-05 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 57
2014-11-05 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 57
2014-11-06 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 57
2014-11-06 | ATS Labour Hire | Labour | hr | 1 | 42.6 | 42.6 | 57
2014-11-07 | Hire of 14T Excavator | Excavator - 14T | hr | 8.5 | 80 | 680 | 57
2014-11-07 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 57
2014-11-07 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 57
2014-11-07 | 24T Excavator Dry Hire | Excavator - 25T | hr | 10 | 130 | 1300 | 57
2014-11-07 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 57
2014-11-08 | 24T Excavator Dry Hire | Excavator - 25T | hr | 7 | 130 | 910 | 57
2014-11-08 | Hire of 14T Excavator | Excavator - 14T | hr | 6.5 | 80 | 520 | 57
2014-11-10 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 57
2014-11-10 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 57
2014-11-10 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 57
2014-11-13 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 57
2014-11-13 | Hire of 14T Excavator | Excavator - 14T | hr | 3.5 | 80 | 280 | 57
2014-11-14 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 57
2014-11-15 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 57
2014-11-15 | ATS Labour Hire | Labour |  | 9 | 49.7 | 447.3 | 57
2014-11-18 | Western Star Truck | Western Star | hr | 3.75 | 80 | 300 | 57
2014-11-18 | Backhoe Hire | Backhoe | hr | 10 | 92.5 | 925 | 57
2014-11-18 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 57
2014-11-18 | Western Star Truck | Western Star | hr | 3.75 | 80 | 300 | 57
2014-11-18 | Hire of 14T Excavator | Excavator - 14T | hr | 9 | 80 | 720 | 57
2014-11-19 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 57
2014-11-19 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 57
2014-11-19 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 57
2014-11-19 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 57
2014-11-20 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 57
2014-11-20 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 57
2014-11-21 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 57
2014-11-21 | Hire of 14T Excavator | Excavator - 14T | hr | 5 | 80 | 400 | 57
2014-11-24 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 57
2014-11-24 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 57
2014-11-24 | Hire of 14T Excavator | Excavator - 14T | hr | 8.5 | 80 | 680 | 57
2014-11-24 | ATS Labour Hire | Labour |  | 9.5 | 49.7 | 472.15 | 57
2014-11-24 | Allciv - New Holland Grader | New Holland | hr | 1 | 35 | 35 | 57
2014-11-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 57
2014-11-24 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 57
2014-11-26 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 57
2014-11-27 | Western Star Truck | Western Star | hr | 5.75 | 80 | 460 | 57
2014-11-27 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 57
2014-11-27 | Hire of 14T Excavator | Excavator - 14T | hr | 2.5 | 80 | 200 | 57
2014-11-28 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 57
2014-11-28 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 57
2014-12-03 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 57
2014-12-03 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9 | 42.79 | 385.11 | 57
2014-12-03 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 57
2014-12-03 | Allciv - Stabilising Crew | Labour | hr | 9.5 | 54.58 | 518.51 | 57
2014-12-03 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 57
2014-12-03 | CAT297C MTL - No Operator | CAT297 | hr | 1 | 35 | 35 | 57
2014-12-03 | Water Cart Hire | Water Cart - Hire | hr | 9.5 | 90 | 855 | 57
2014-12-03 | Backhoe Hire | Backhoe | hr | 4.5 | 92.5 | 416.25 | 57
2014-12-04 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 57
2014-12-04 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 57
2014-12-04 | Hire of 14T Excavator | Excavator - 14T | hr | 7 | 80 | 560 | 57
2015-01-19 | CAT297C MTL - No Operator | CAT297 | hr | 2.5 | 35 | 87.5 | 57
2015-01-19 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 57
2015-01-20 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 57
2015-01-20 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 57
2015-01-20 | CAT297C MTL - No Operator | CAT297 | hr | 6.5 | 35 | 227.5 | 57
2015-02-23 | ATS Labour Hire | Labour | hr | 9 | 46.85 | 421.65 | 57
2015-02-23 | ATS Labour Hire | Labour |  | 9 | 49.7 | 447.3 | 57
2015-02-23 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 57
2015-02-23 | CAT297C MTL - No Operator | CAT297 | hr | 9 | 35 | 315 | 57
2015-02-23 | Hire of 14T Excavator | Excavator - 14T | hr | 9 | 80 | 720 | 57
2015-02-23 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 57
2015-02-25 | 140M Cat Grader Hired 25/2/15 - 28/2/15 | Cat 140M Grader |  | 1 | 900 | 900 | 57
2015-02-26 | Bulk GP / GB Cement x 4 | Cement |  | 1 | 34.51 | 34.51 | 57
2015-02-26 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 57
2015-02-26 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 57
2015-02-26 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 57
2015-02-26 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 57
2015-02-27 | Bobcat Hire | Bobcat Hire |  | 6 | 35 | 210 | 57
2015-02-28 | Smooth Drum Roller Hired from 16/2/15 - 27/2/15 | SD Roller-Flexi Hire |  | 1 | 710.5 | 710.5 | 57
2015-02-28 | Vibrating Multi Tyre Roller Hired 17/2/15 - 27/2/15 | Multi Tyre Roller |  | 1 | 1080.8 | 1080.8 | 57
| Subtotal for 057 |  |  |  |  | 36487.555
Portfolio WBS 061
2014-10-07 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 61
2014-10-14 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 61
2014-10-15 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 61
2014-10-16 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 61
2014-10-18 | 2.2 Roadbase | Roadbase 2.2 |  | 20.6 | 7.5 | 154.5 | 61
2014-11-06 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 61
2014-11-06 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 61
2015-01-08 | ATS Labour Hire | Labour | hr | 3 | 46.85 | 140.55 | 61
2015-01-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 61
| Subtotal for 061 |  |  |  |  | 3483.915
Portfolio WBS 0613
2014-09-01 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 0.5 | 80 | 40 | 613
2014-09-10 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 80.14 | 7.5 | 601.05 | 613
2014-09-27 | Truck Tipper Hire | Truck Tipper | hr | 6.25 | 80 | 500 | 613
2014-09-27 | Truck Tipper Hire | Truck Tipper | hr | 6.5 | 80 | 520 | 613
2014-09-27 | Water Cart Hire | Water Cart - Hire | hr | 7.5 | 90 | 675 | 613
2014-09-27 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 6.5 | 80 | 520 | 613
2014-09-29 | Truck & Dog (27T & 29T) | Truck & Dog | hr | 2 | 120 | 240 | 613
2014-09-29 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 613
2014-09-30 | BCLA Pty Ltd - Tractor/Profiler | Tractor/Profiler | day | 1 | 1800 | 1800 | 613
2014-09-30 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 613
2014-09-30 | Truck Tipper Hire | Truck Tipper | hr | 4.75 | 80 | 380 | 613
2014-09-30 | Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 613
2014-09-30 | Truck Tipper Hire | Truck Tipper | hr | 4.75 | 80 | 380 | 613
2014-09-30 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 10 | 80 | 800 | 613
2014-09-30 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 613
2014-10-01 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9.5 | 80 | 760 | 613
2014-10-01 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 613
2014-10-01 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 0.5 | 80 | 40 | 613
2014-10-01 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 613
2014-10-01 | Truck & Dog (27T & 29T) | Truck & Dog | hr | 2 | 120 | 240 | 613
2014-10-04 | Water Cart Hire | Water Cart - Hire | hr | 6 | 90 | 540 | 613
2014-10-05 | Water Cart Hire | Water Cart - Hire | hr | 6 | 90 | 540 | 613
2014-10-06 | Water Cart Hire | Water Cart - Hire | hr | 6 | 90 | 540 | 613
2014-10-07 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 613
2014-10-07 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 8 | 80 | 640 | 613
2014-10-07 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-10-07 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 7.5 | 80 | 600 | 613
2014-10-07 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 613
2014-10-08 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 613
2014-10-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 613
2014-10-08 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 613
2014-10-08 | 2.2 Roadbase | Roadbase 2.2 |  | 130.1 | 7.5 | 975.75 | 613
2014-10-08 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 106.74 | 7.5 | 800.55 | 613
2014-10-08 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 106.18 | 7.5 | 796.35 | 613
2014-10-08 | 2.2 Roadbase | Roadbase 2.2 |  | 164.23 | 7.5 | 1231.725 | 613
2014-10-08 | 2.2 Roadbase 327 KJT | Roadbase 2.2 |  | 89.74 | 7.5 | 673.05 | 613
2014-10-08 | 2.2 Roadbase 501 - LPI | Roadbase 2.2 |  | 90.3 | 7.5 | 677.26 | 613
2014-10-08 | 2.2 Roadbase | Roadbase 2.2 |  | 59.73 | 7.5 | 447.975 | 613
2014-10-09 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 4.5 | 80 | 360 | 613
2014-10-09 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-10-09 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-10-10 | 2.2 Roadbase 327 - KJT | Roadbase 2.2 |  | 90.74 | 7.5 | 680.55 | 613
2014-10-10 | 2.2 Roadbase 501 - LPI | Roadbase 2.2 |  | 121.17 | 7.5 | 908.775 | 613
2014-10-10 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 80.14 | 7.5 | 601.05 | 613
2014-10-10 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10.5 | 140 | 1470 | 613
2014-10-10 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 78.66 | 7.5 | 589.95 | 613
2014-10-10 | 2.2 Roadbase 055 - VAF | Roadbase 2.2 |  | 99.24 | 7.5 | 744.3 | 613
2014-10-10 | 2.2 Roadbase 131 - TOR | Roadbase 2.2 |  | 105.68 | 7.5 | 792.6 | 613
2014-10-13 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 613
2014-10-13 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 613
2014-10-13 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 613
2014-10-13 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 7.5 | 80 | 600 | 613
2014-10-13 | Allciv - Stabilising Crew | Labour | hr | 6.5 | 54.58 | 354.77 | 613
2014-10-13 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 613
2014-10-14 | Truck Tipper Hire | Truck Tipper | hr | 0.5 | 80 | 40 | 613
2014-10-14 | Allciv - Stabilising Crew | Labour | hr | 0.5 | 54.58 | 27.29 | 613
2014-10-17 | Truck Tipper Hire | Truck & Dog | hr | 9.5 | 120 | 1140 | 613
2014-10-17 | Truck Tipper Hire | Truck & Dog | hr | 9.5 | 120 | 1140 | 613
2014-10-17 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9.5 | 80 | 760 | 613
2014-10-17 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 8 | 80 | 640 | 613
2014-10-17 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2014-10-18 | Truck Tipper Hire | Truck & Dog | hr | 5 | 120 | 600 | 613
2014-10-18 | Truck Tipper Hire | Truck & Dog | hr | 2.75 | 120 | 330 | 613
2014-10-18 | Allciv - Stabilising Crew | Labour | hr | 2 | 54.58 | 109.16 | 613
2014-10-18 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 3.5 | 80 | 280 | 613
2014-10-18 | Allciv - New Holland Grader | New Holland | hr | 2 | 35 | 70 | 613
2014-10-18 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-10-21 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 613
2014-10-21 | Tipper (Wet Hire) | Tipper | hr | 5 | 80 | 400 | 613
2014-10-21 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 613
2014-10-21 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-10-22 | Tipper (Wet Hire) | Tipper | hr | 4.25 | 80 | 340 | 613
2014-10-22 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-10-22 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-10-22 | 2.2 Roadbase 327-KJT | Roadbase 2.2 |  | 22.08 | 7.5 | 165.6 | 613
2014-10-24 | Truck Tipper Hire | Truck Tipper | hr | 7.5 | 80 | 600 | 613
2014-10-27 | Tipper (Wet Hire) | Tipper | hr | 8 | 80 | 640 | 613
2014-10-27 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 613
2014-10-28 | Truck Tipper Hire | Truck Tipper | hr | 5.5 | 80 | 440 | 613
2014-10-28 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2014-10-28 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 613
2014-10-28 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-10-28 | Tipper (Wet Hire) | Tipper | hr | 5 | 80 | 400 | 613
2014-10-29 | Tipper (Wet Hire) | Tipper | hr | 1 | 80 | 80 | 613
2014-10-29 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-10-29 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 50.93 | 7.5 | 381.975 | 613
2014-10-29 | Tipper (Wet Hire) | Tipper | hr | 1 | 80 | 80 | 613
2014-10-29 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 173.74 | 7.5 | 1303.05 | 613
2014-10-29 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 73.42 | 7.5 | 550.65 | 613
2014-10-29 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 53.84 | 7.5 | 403.8 | 613
2014-10-30 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-10-30 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2014-10-30 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 221.03 | 7.5 | 1657.725 | 613
2014-10-30 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 162.96 | 7.5 | 1222.2 | 613
2014-10-30 | Truck & Dog Hire | Truck & Dog |  | 8.5 | 120 | 1020 | 613
2014-10-30 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 155.76 | 7.5 | 1168.2 | 613
2014-10-31 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-10-31 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 155.59 | 7.5 | 1166.925 | 613
2014-10-31 | 2.2 Roadbase 327-KJT | Roadbase 2.2 |  | 181.69 | 7.5 | 1362.675 | 613
2014-10-31 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 183.21 | 7.5 | 1374.075 | 613
2014-10-31 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 159.67 | 7.5 | 1197.525 | 613
2014-10-31 | 2.2 Roadbase 621-SVJ | Roadbase 2.2 |  | 6 | 120 | 720 | 613
2014-10-31 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 162.29 | 7.5 | 1217.175 | 613
2014-10-31 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 175.74 | 7.5 | 1318.05 | 613
2014-11-01 | Truck Tipper Hire | Truck Tipper |  | 2.5 | 120 | 300 | 613
2014-11-01 | 2.2 Roadbase 131 - TOR | Roadbase 2.2 |  | 81.18 | 7.5 | 608.85 | 613
2014-11-01 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 81.64 | 7.5 | 612.3 | 613
2014-11-01 | 2.2 Roadbase 327-KJT | Roadbase 2.2 |  | 90.63 | 7.5 | 679.725 | 613
2014-11-01 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 80.99 | 7.5 | 607.425 | 613
2014-11-01 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 613
2014-11-01 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 110.64 | 7.5 | 829.8 | 613
2014-11-01 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 77.97 | 7.5 | 584.775 | 613
2014-11-01 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 613
2014-11-01 | 2.2 Roadbase 501.- LPI | Roadbase 2.2 |  | 90.77 | 7.5 | 680.775 | 613
2014-11-01 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 100.05 | 7.5 | 750.375 | 613
2014-11-01 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 87.25 | 7.5 | 654.375 | 613
2014-11-03 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 171.18 | 7.5 | 1283.85 | 613
2014-11-03 | 2.2 Roadbase 649-EYJ | Roadbase 2.2 |  | 124.21 | 7.5 | 931.565 | 613
2014-11-04 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-04 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 613
2014-11-04 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-04 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-04 | Tipper (Wet Hire) | Tipper | hr | 4 | 80 | 320 | 613
2014-11-04 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 79.8 | 7.5 | 598.5 | 613
2014-11-04 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 613
2014-11-05 | Tipper (Wet Hire) | Tipper | hr | 3.5 | 80 | 280 | 613
2014-11-05 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 613
2014-11-05 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-11-05 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 613
2014-11-05 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-11-05 | 2.2 Roadbase 148-KQT | Roadbase 2.2 |  | 58.68 | 7.5 | 440.1 | 613
2014-11-07 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 613
2014-11-07 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-07 | Tipper (Wet Hire) | Tipper | hr | 4.25 | 80 | 340 | 613
2014-11-07 | Western Star Truck | Western Star | hr | 4 | 80 | 320 | 613
2014-11-08 | Tipper (Wet Hire) | Tipper | hr | 6 | 80 | 480 | 613
2014-11-08 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 613
2014-11-08 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 613
2014-11-08 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 613
2014-11-08 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 613
2014-11-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 613
2014-11-10 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 613
2014-11-10 | Water Cart Hire | Water Cart - Hire | hr | 8.5 | 90 | 765 | 613
2014-11-10 | Tipper (Wet Hire) | Tipper | hr | 3 | 80 | 240 | 613
2014-11-10 | Truck Tipper Hire | Truck Tipper | hr | 9 | 80 | 720 | 613
2014-11-10 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 613
2014-11-11 | Tipper (Wet Hire) | Tipper | hr | 6 | 80 | 480 | 613
2014-11-11 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 613
2014-11-12 | Western Star Truck | Western Star | hr | 5 | 80 | 400 | 613
2014-11-12 | Western Star Truck | Western Star | hr | 3 | 80 | 240 | 613
2014-11-12 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 24.88 | 7.5 | 186.6 | 613
2014-11-12 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 8 | 80 | 640 | 613
2014-11-12 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 50.56 | 7.5 | 379.2 | 613
2014-11-12 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 613
2014-11-12 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 613
2014-11-13 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-11-13 | Allciv - Stabilising Crew | Labour | hr | 4.5 | 54.58 | 245.61 | 613
2014-11-13 | Western Star Truck | Western Star | hr | 3.5 | 80 | 280 | 613
2014-11-14 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 29.34 | 7.5 | 220.05 | 613
2014-11-14 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 613
2014-11-14 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 613
2014-11-14 | Western Star Truck | Western Star | hr | 3 | 80 | 240 | 613
2014-11-15 | 2.2 Roadbase 327-KJT | Roadbase 2.2 |  | 149.85 | 7.5 | 1123.875 | 613
2014-11-15 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 613
2014-11-15 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 160.15 | 7.5 | 1201.125 | 613
2014-11-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 613
2014-11-15 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 102.27 | 7.5 | 767.025 | 613
2014-11-15 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 145.59 | 7.5 | 1091.925 | 613
2014-11-15 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 613
2014-11-17 | Western Star Truck | Western Star | hr | 6 | 80 | 480 | 613
2014-11-17 | Tipper (Wet Hire) | Tipper | hr | 4 | 80 | 320 | 613
2014-11-17 | Western Star Truck | Western Star | hr | 5 | 80 | 400 | 613
2014-11-17 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-11-17 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2014-11-18 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 135.1 | 7.5 | 1013.25 | 613
2014-11-19 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-11-19 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 613
2014-11-19 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 613
2014-11-19 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-11-19 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2014-11-19 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-11-19 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 129.28 | 7.5 | 969.6 | 613
2014-11-19 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 613
2014-11-19 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-11-19 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 210.34 | 7.5 | 1577.55 | 613
2014-11-19 | Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 613
2014-11-19 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 613
2014-11-19 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-11-19 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 192.07 | 7.5 | 1440.525 | 613
2014-11-19 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 174.18 | 7.5 | 1306.35 | 613
2014-11-20 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-20 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 162.7 | 7.5 | 1220.25 | 613
2014-11-20 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 165.36 | 7.5 | 1240.2 | 613
2014-11-20 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 219.9 | 7.5 | 1649.25 | 613
2014-11-20 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 129.9 | 7.5 | 974.25 | 613
2014-11-20 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 146.34 | 7.5 | 1097.55 | 613
2014-11-21 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 613
2014-11-21 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 613
2014-11-21 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-21 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-21 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 54.37 | 7.5 | 407.775 | 613
2014-11-21 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 58.57 | 7.5 | 439.275 | 613
2014-11-21 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 613
2014-11-21 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 51.93 | 7.5 | 389.475 | 613
2014-11-21 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 613
2014-11-21 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 110.94 | 7.5 | 832.05 | 613
2014-11-21 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 66.8 | 7.5 | 501 | 613
2014-11-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 613
2014-11-24 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2014-11-24 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 613
2014-11-24 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2014-11-24 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 81.06 | 7.5 | 607.95 | 613
2014-11-24 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2014-11-24 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 77.26 | 7.5 | 579.45 | 613
2014-11-24 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 80.62 | 7.5 | 604.65 | 613
2014-11-24 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 205.85 | 7.5 | 1543.875 | 613
2014-11-24 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 87.42 | 7.5 | 655.65 | 613
2014-11-25 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 613
2014-11-25 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 135.32 | 7.5 | 1014.9 | 613
2014-11-25 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 204.62 | 7.5 | 1534.65 | 613
2014-11-25 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 172.94 | 7.5 | 1297.05 | 613
2014-11-25 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 154.4 | 7.5 | 1158 | 613
2014-11-25 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 132 | 7.5 | 990 | 613
2014-11-26 | Truck Tipper Hire | Truck Tipper | hr | 10 | 80 | 800 | 613
2014-11-26 | Backhoe Hire | Backhoe | hr | 1 | 92.5 | 92.5 | 613
2014-11-26 | Truck Tipper Hire | Truck Tipper | hr | 10 | 80 | 800 | 613
2014-11-26 | Backhoe Hire | Backhoe | hr | 0.5 | 92.5 | 46.25 | 613
2014-11-26 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 219.38 | 7.5 | 1645.35 | 613
2014-11-26 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 133.29 | 7.5 | 999.675 | 613
2014-11-26 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 154.2 | 7.5 | 1156.5 | 613
2014-11-26 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 161.5 | 7.5 | 1211.25 | 613
2014-11-26 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 144.78 | 7.5 | 1085.85 | 613
2014-11-27 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 613
2014-11-27 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 613
2014-11-27 | 2.2 Roadbase 976 - MFJ | Roadbase 2.2 |  | 161.24 | 7.5 | 1209.3 | 613
2014-11-27 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 58.16 | 7.5 | 436.2 | 613
2014-11-27 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 155.42 | 7.5 | 1165.65 | 613
2014-11-28 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 613
2014-11-28 | 2.2 Roadbase 327-KJT | Roadbase 2.2 |  | 150.64 | 7.5 | 1129.8 | 613
2014-11-28 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 182.62 | 7.5 | 1369.65 | 613
2014-11-28 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 108.5 | 7.5 | 813.75 | 613
2014-11-28 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 103.26 | 7.5 | 774.45 | 613
2014-11-28 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 116.24 | 7.5 | 871.8 | 613
2014-11-29 | Backhoe Hire | Backhoe | hr | 6.5 | 92.5 | 601.25 | 613
2014-11-29 | Water Cart Hire | Water Cart - Hire | hr | 4 | 80 | 320 | 613
2014-11-29 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-11-30 | Smooth Drum Roller Hired from 17/11/14 - 30/11/14 | SD Roller-Flexi Hire |  | 1 | 659.63 | 659.63 | 613
2014-11-30 | Vibrating Multi Tyre Roller Hired 31/10/14 -* 30/11/14 | Multi Tyre Roller |  | 1 | 1218 | 1218 | 613
2014-12-01 | 2.2 Roadbase 055-VAF | Roadbase 2.2 |  | 66.2 | 7.5 | 496.5 | 613
2014-12-01 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 54.16 | 7.5 | 406.2 | 613
2014-12-01 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 86.8 | 7.5 | 651 | 613
2014-12-01 | 2.2 Roadbase 906-BHB | Roadbase 2.2 |  | 77.78 | 7.5 | 583.35 | 613
2014-12-01 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 108.92 | 7.5 | 816.9 | 613
2014-12-01 | 2.2 Roadbase Cartage 219.38 | Truck Tipper |  | 4 | 80 | 320 | 613
2014-12-01 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 613
2014-12-01 | Truck Tipper Hire | Truck Tipper | hr | 6.5 | 80 | 520 | 613
2014-12-04 | 2.2 Roadbase | Roadbase 2.2 |  | 4 | 120 | 480 | 613
2014-12-04 | 2.2 Roadbase | Roadbase 2.2 |  | 4 | 120 | 480 | 613
2014-12-04 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 613
2014-12-05 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 613
2014-12-05 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2014-12-05 | Western Star Truck and Trailer | Western Star | hr | 6 | 120 | 720 | 613
2014-12-10 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 613
2014-12-11 | Allciv - 120H Grader | 120H Grader | hr | 8 | 135 | 1080 | 613
2014-12-11 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2014-12-11 | 2.2 Roadbase Cartage 219.38 | Truck Tipper |  | 10 | 120 | 1200 | 613
2014-12-11 | Truck Hire 90.66 x 2.3 Roadbase | Truck & Dog |  | 4.5 | 120 | 540 | 613
2014-12-15 | Western Star Truck | Western Star Truck Traile | hr | 8.5 | 80 | 680 | 613
2014-12-15 | Western Star Truck and Trailer | Western Star | hr | 3.5 | 120 | 420 | 613
2014-12-15 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 4.5 | 120 | 540 | 613
2014-12-16 | ATS Labour Hire | Labour | hr | 6.5 | 46.85 | 304.525 | 613
2014-12-16 | Western Star Truck and Trailer | Western Star | hr | 7 | 120 | 840 | 613
2014-12-16 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 7.5 | 120 | 900 | 613
2014-12-16 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-12-16 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2014-12-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 613
2014-12-16 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2015-01-05 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-05 | Truck & Dog | Tipper | hr | 2.5 | 120 | 300 | 613
2015-01-05 | ATS Labour Hire | Labour | hr | 5.5 | 46.85 | 257.675 | 613
2015-01-06 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 613
2015-01-08 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 120 | 360 | 613
2015-01-08 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2015-01-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2015-01-08 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 613
2015-01-09 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-09 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 613
2015-01-09 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 90 | 225 | 613
2015-01-09 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 4.5 | 120 | 540 | 613
2015-01-09 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2015-01-10 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2015-01-12 | Tipper (Wet Hire) | Tipper | hr | 3 | 90 | 270 | 613
2015-01-13 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 613
2015-01-13 | Tipper (Wet Hire) | Tipper | hr | 4 | 90 | 360 | 613
2015-01-14 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-14 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 613
2015-01-14 | Tipper (Wet Hire) | Tipper | hr | 8 | 90 | 720 | 613
2015-01-15 | Tipper (Wet Hire) | Tipper | hr | 7 | 90 | 630 | 613
2015-01-15 | ATS Labour Hire | Labour | hr | 4.25 | 46.85 | 199.1125 | 613
2015-01-15 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 4 | 120 | 480 | 613
2015-01-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2015-01-15 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-15 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 80 | 240 | 613
2015-01-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 613
2015-01-16 | ATS Labour Hire | Labour | hr | 4.75 | 46.85 | 222.5375 | 613
2015-01-16 | Tipper (Wet Hire) | Tipper | hr | 3.5 | 90 | 315 | 613
2015-01-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 613
2015-01-16 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-19 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-20 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2015-01-20 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2015-01-20 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-20 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 613
2015-01-20 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2015-01-20 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-20 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 613
2015-01-20 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 613
2015-01-20 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-20 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 613
2015-01-20 | Tipper (Wet Hire) | Tipper | hr | 8 | 90 | 720 | 613
2015-01-21 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 613
2015-01-21 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-21 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-21 | Tipper (Wet Hire) | Tipper | hr | 5 | 90 | 450 | 613
2015-01-27 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2 | 80 | 160 | 613
2015-01-27 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-01-28 | Tipper (Wet Hire) | Tipper | hr | 6 | 90 | 540 | 613
2015-01-28 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2 | 80 | 160 | 613
2015-01-28 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-28 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 613
2015-01-28 | Tipper (Wet Hire) | Tipper | hr | 4 | 90 | 360 | 613
2015-01-29 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-01-29 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 613
2015-02-02 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-02-03 | Tipper (Wet Hire) | Tipper | hr | 3 | 90 | 270 | 613
2015-02-03 | Truck Tipper Hire | Truck Tipper | hr | 5 | 80 | 400 | 613
2015-02-03 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 120 | 360 | 613
2015-02-03 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 613
2015-02-04 | Tipper (Wet Hire) | Tipper | hr | 10 | 90 | 900 | 613
2015-02-04 | Truck Tipper Hire | Truck Tipper | hr | 1 | 80 | 80 | 613
2015-02-05 | Smooth Drum Roller Hired from 31/01/15 - 5/2/15 | SD Roller-Flexi Hire |  | 11 | 317.8 | 3495.8 | 613
2015-02-05 | Tipper (Wet Hire) | Tipper | hr | 7.5 | 90 | 675 | 613
2015-02-05 | Backhoe Hire | Backhoe | hr | 6 | 92.5 | 555 | 613
2015-02-09 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2 | 80 | 160 | 613
2015-02-10 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 613
2015-02-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 613
2015-02-11 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2015-02-11 | Allciv - Stabilising Crew | Labour | hr | 4.5 | 54.58 | 245.61 | 613
2015-02-17 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 4 | 120 | 480 | 613
2015-02-17 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2015-02-17 | Truck & Dog Hire | Truck & Dog | hr | 3.5 | 120 | 420 | 613
2015-02-17 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 613
2015-02-18 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 613
2015-02-18 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 613
2015-02-20 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 613
2015-02-20 | ATS Labour Hire | Labour | hr | 2.5 | 46.85 | 117.125 | 613
2015-02-20 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2015-02-23 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2015-02-23 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2015-02-23 | Bobcat Hire | Bobcat Hire |  | 3.5 | 35 | 122.5 | 613
2015-02-23 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2015-02-23 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2015-02-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 613
2015-02-24 | Bobcat Hire | Bobcat Hire |  | 2.5 | 35 | 87.5 | 613
2015-02-24 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2 | 120 | 240 | 613
2015-02-24 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2015-02-24 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 613
2015-02-25 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2015-02-25 | Bobcat Hire | Bobcat Hire |  | 4 | 35 | 140 | 613
2015-02-25 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 613
2015-02-25 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 613
2015-02-26 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 613
2015-02-26 | Bobcat Hire | Bobcat Hire |  | 5 | 35 | 175 | 613
| Subtotal for 0613 |  |  |  |  | 187160.795
Portfolio WBS 062
2014-10-08 | Water Cart Hire | Water Cart - Hire | hr | 8 | 90 | 720 | 62
2014-10-08 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9 | 140 | 1260 | 62
2014-10-08 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 62
2014-10-10 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 62
2014-10-10 | Water Cart Hire | Water Cart - Hire | hr | 9 | 90 | 810 | 62
2014-10-11 | Water Cart Hire | Water Cart - Hire | hr | 3 | 90 | 270 | 62
2014-10-13 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 6.5 | 140 | 910 | 62
2014-10-13 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 62
2014-10-13 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 62
2014-10-13 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 62
2014-10-14 | Water Cart Hire | Water Cart - Hire | hr | 3 | 90 | 270 | 62
2014-10-15 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 62
2014-10-16 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 62
2014-10-17 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10 | 140 | 1400 | 62
2014-10-29 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 62
2014-10-30 | Backhoe Hire | Backhoe | hr | 6 | 92.5 | 555 | 62
2014-10-30 | Water Cart Hire | Water Cart - Hire | hr | 4.5 | 90 | 405 | 62
2014-10-30 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10.5 | 140 | 1470 | 62
2014-10-30 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 62
2014-10-30 | Allciv - Stabilising Crew | Labour | hr | 1.5 | 54.58 | 81.87 | 62
2014-10-31 | Water Cart Hire | Water Cart - Hire | hr | 5.5 | 90 | 495 | 62
2014-10-31 | Backhoe Hire | Backhoe | hr | 4.5 | 92.5 | 416.25 | 62
2014-10-31 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 62
2014-10-31 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 62
2014-10-31 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 11 | 140 | 1540 | 62
2014-10-31 | Grader Cat 12H GPS/UTS (with robotic total station and rover unit) | Grader 12H GPS/ | hr | 10 | 150 | 1500 | 62
2014-11-01 | Grader Cat 12H GPS/UTS (with robotic total station and rover unit) | Grader 12H GPS/ | hr | 9.5 | 150 | 1425 | 62
2014-11-01 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 8 | 140 | 1120 | 62
2014-11-01 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 62
2014-11-01 | Hire of 14T Excavator | Excavator - 14T | hr | 2.5 | 80 | 200 | 62
2014-11-01 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 62
2014-11-01 | Water Cart Hire | Water Cart - Hire | hr | 1.5 | 90 | 135 | 62
2014-11-01 | Backhoe Hire | Backhoe | hr | 8.5 | 92.5 | 786.25 | 62
2014-11-01 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 62
2014-11-01 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 62
2014-11-01 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 62
2014-11-02 | Water Cart Hire | Water Cart - Hire | hr | 7 | 80 | 560 | 62
2014-11-03 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 62
2014-11-03 | Truck Tipper Hire | Truck Tipper | hr | 8.5 | 80 | 680 | 62
2014-11-03 | Truck Tipper Hire | Truck Tipper | hr | 8 | 80 | 640 | 62
2014-11-03 | Water Cart Hire | Water Cart - Hire | hr | 1.5 | 90 | 135 | 62
2014-11-03 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 62
2014-11-03 | Backhoe Hire | Backhoe | hr | 8.5 | 92.5 | 786.25 | 62
2014-11-03 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2014-11-03 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 62
2014-11-04 | Water Cart Hire | Water Cart - Hire | hr | 3 | 90 | 270 | 62
2014-11-04 | Backhoe Hire | Backhoe | hr | 7 | 92.5 | 647.5 | 62
2014-11-04 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 8.5 | 140 | 1190 | 62
2014-11-04 | Water Cart Hire | Water Cart - Hire | hr | 5.5 | 80 | 440 | 62
2014-11-04 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 62
2014-11-04 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 62
2014-11-05 | Backhoe Hire | Backhoe | hr | 8.5 | 92.5 | 786.25 | 62
2014-11-05 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 62
2014-11-05 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 62
2014-11-05 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 62
2014-11-05 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 62
2014-11-05 | Water Cart Hire | Water Cart - Hire | hr | 3.5 | 80 | 280 | 62
2014-11-05 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 62
2014-11-05 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 62
2014-11-06 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 62
2014-11-06 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 62
2014-11-06 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 62
2014-11-06 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 62
2014-11-14 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 62
2014-11-14 | Water Cart Hire | Water Cart - Hire | hr | 6.5 | 90 | 585 | 62
2014-11-15 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9.5 | 140 | 1330 | 62
2014-11-15 | Water Cart Hire | Water Cart - Hire | hr | 9.5 | 80 | 760 | 62
2014-11-15 | Water Cart Hire | Water Cart - Hire | hr | 9.5 | 90 | 855 | 62
2014-11-16 | Water Cart Hire | Water Cart - Hire | hr | 8.5 | 80 | 680 | 62
2014-11-19 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 62
2014-11-20 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 62
2014-11-20 | 140M Cat Grader Hired 31/10/2014 - 13/11/14 | Cat 140M Grader |  | 1 | 1500 | 1500 | 62
2014-11-24 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 62
2014-11-25 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5 | 140 | 700 | 62
2014-11-25 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 62
2014-11-25 | Allciv - 120H Grader | 120H Grader | hr | 3.5 | 135 | 472.5 | 62
2014-11-25 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 62
2014-11-26 | Allciv - Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 62
2014-11-26 | Water Cart | Water Cart - Hire | hr | 9 | 90 | 810 | 62
2014-11-26 | Allciv - Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 62
2014-11-27 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10.5 | 140 | 1470 | 62
2014-11-27 | 2.2 Roadbase 643 - RUP | Roadbase 2.2 |  | 160 | 7.5 | 1200 | 62
2014-11-27 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 62
2014-11-27 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 62
2014-11-27 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 62
2014-11-28 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 62
2014-11-29 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 62
2014-11-29 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 62
2014-11-30 | Vibrating Multi Tyre Roller Hired 31/10/14 -* 30/11/14 | Multi Tyre Roller |  | 1 | 1218 | 1218 | 62
2014-11-30 | Smooth Drum Roller Hired from 30/10/14 - 30/11/14 | SD Roller-Flexi Hire |  | 1 | 1421 | 1421 | 62
2014-11-30 | Smooth Drum Roller Hired from 17/11/14 - 30/11/14 | SD Roller-Flexi Hire |  | 1 | 659.63 | 659.63 | 62
2014-12-01 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 62
2014-12-01 | Water Cart Hire | Water Cart - Hire | hr | 8 | 90 | 720 | 62
2014-12-01 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 62
2014-12-01 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 62
2014-12-01 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10.5 | 140 | 1470 | 62
2014-12-02 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 3.5 | 140 | 490 | 62
2014-12-02 | Water Cart Hire | Water Cart - Hire | hr | 4 | 90 | 360 | 62
2014-12-02 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 62
2014-12-02 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 62
2014-12-02 | Allciv - Labour Hire | Labour | hr | 7.5 | 42.72 | 320.4 | 62
2014-12-03 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 62
2014-12-03 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 62
2014-12-03 | Water Cart Hire | Water Cart - Hire | hr | 4.5 | 80 | 360 | 62
2014-12-04 | Vibrating Multi Tyre Roller Hired 30/11/14 | Multi Tyre Roller |  | 1 | 1380.8 | 1380.8 | 62
2014-12-04 | Water Cart Hire | Water Cart - Hire | hr | 4 | 90 | 360 | 62
2014-12-04 | Allciv - 120H Grader | 120H Grader | hr | 4 | 135 | 540 | 62
2014-12-04 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2014-12-10 | Allciv - 120H Grader | 120H Grader | hr | 10 | 135 | 1350 | 62
2014-12-10 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2014-12-11 | Water Cart Hire | Water Cart - Hire | hr | 8 | 90 | 720 | 62
2014-12-12 | Water Cart Hire | Water Cart - Hire | hr | 7 | 80 | 560 | 62
2014-12-15 | Allciv - 120H Grader | 120H Grader | hr | 9 | 135 | 1215 | 62
2014-12-15 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2014-12-15 | Backhoe Hire | Backhoe | hr | 11.5 | 92.5 | 1063.75 | 62
2014-12-16 | ATS Labour Hire | Labour |  | 8.5 | 49.7 | 422.45 | 62
2014-12-16 | Hire of 14T Excavator | Excavator - 14T | hr | 6 | 80 | 480 | 62
2014-12-31 | Smooth Drum Roller Hired from 30/11/14 - 31/12/14 | SD Roller-Flexi Hire |  | 1 | 426.3 | 426.3 | 62
2015-01-15 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 62
2015-01-15 | Allciv - 120H Grader | 120H Grader | hr | 3.5 | 135 | 472.5 | 62
2015-01-16 | Allciv - 120H Grader | 120H Grader | hr | 2 | 135 | 270 | 62
2015-01-19 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 62
2015-01-20 | Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 62
2015-01-20 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 62
2015-01-20 | Allciv - 120H Grader | 120H Grader | hr | 11 | 135 | 1485 | 62
2015-01-21 | Allciv - 120H Grader | 120H Grader | hr | 4 | 135 | 540 | 62
2015-01-21 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 62
2015-01-22 | Backhoe Hire | Backhoe | hr | 3.5 | 92.5 | 323.75 | 62
2015-01-28 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5 | 65 | 325 | 62
2015-01-28 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 62
2015-01-29 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 62
2015-02-02 | ATS Labour Hire | Labour | hr | 5.5 | 42.6 | 234.3 | 62
2015-02-02 | CAT297C MTL - No Operator | CAT297 | hr | 4 | 35 | 140 | 62
2015-02-02 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 62
2015-02-03 | Allciv - 120H Grader | 120H Grader | hr | 4 | 135 | 540 | 62
2015-02-03 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 62
2015-02-03 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 62
2015-02-04 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 62
2015-02-04 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 62
2015-02-04 | Allciv - Stabilising Crew | Labour | hr | 6.5 | 54.58 | 354.77 | 62
2015-02-04 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 62
2015-02-04 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 62
2015-02-04 | CAT297C MTL - No Operator | CAT297 | hr | 4 | 35 | 140 | 62
2015-02-04 | ATS Labour Hire | Labour |  | 9 | 49.7 | 447.3 | 62
2015-02-05 | CAT297C MTL - No Operator | CAT297 | hr | 4 | 35 | 140 | 62
2015-02-05 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 62
2015-02-05 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 62
2015-02-05 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 62
2015-02-05 | ATS Labour Hire | Labour | hr | 5.5 | 46.85 | 257.675 | 62
2015-02-06 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2015-02-16 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 4.5 | 120 | 540 | 62
2015-02-17 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 5.75 | 120 | 690 | 62
2015-02-17 | Allciv - 120H Grader | 120H Grader | hr | 5 | 135 | 675 | 62
2015-02-17 | Water Cart Hire | Water Cart - Hire | hr | 5.5 | 90 | 495 | 62
2015-02-18 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 62
2015-02-18 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 120 | 360 | 62
2015-02-18 | Water Cart Hire | Water Cart - Hire | hr | 11 | 90 | 990 | 62
2015-02-18 | Allciv - Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 62
2015-02-18 | Allciv - 120H Grader | 120H Grader | hr | 11.5 | 135 | 1552.5 | 62
2015-02-18 | CAT297C MTL - No Operator | CAT297 | hr | 6 | 35 | 210 | 62
2015-02-19 | CAT297C MTL - No Operator | CAT297 | hr | 10 | 35 | 350 | 62
2015-02-19 | Allciv - 120H Grader | 120H Grader | hr | 10.5 | 135 | 1417.5 | 62
2015-02-19 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 62
2015-02-19 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 62
2015-02-19 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 62
2015-02-19 | Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 62
2015-02-20 | ATS Labour Hire10.5 | Labour | hr | 10 | 42.6 | 426 | 62
2015-02-20 | Allciv - 120H Grader | 120H Grader | hr | 7 | 135 | 945 | 62
2015-02-20 | CAT297C MTL - No Operator | CAT297 | hr | 10.5 | 35 | 367.5 | 62
2015-02-20 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 90 | 945 | 62
2015-02-21 | Water Cart Hire | Water Cart - Hire | hr | 6 | 90 | 540 | 62
2015-02-22 | Water Cart Hire | Water Cart - Hire | hr | 6 | 90 | 540 | 62
2015-02-23 | Water Cart Hire | Water Cart - Hire | hr | 9 | 90 | 810 | 62
2015-02-23 | Allciv - 120H Grader | 120H Grader | hr | 3 | 135 | 405 | 62
2015-02-23 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 62
2015-02-24 | Allciv - 120H Grader | 120H Grader | hr | 11 | 135 | 1485 | 62
2015-02-24 | Water Cart Hire | Water Cart - Hire | hr | 11.5 | 90 | 1035 | 62
2015-02-24 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 62
2015-02-24 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 62
2015-02-25 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 62
2015-02-25 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 62
2015-02-25 | CAT297C MTL - No Operator | CAT297 | hr | 5 | 35 | 175 | 62
2015-02-25 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 62
2015-02-25 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 62
2015-02-26 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 90 | 945 | 62
2015-02-27 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 62
2015-02-27 | Water Cart Hire | Water Cart - Hire | hr | 8 | 90 | 720 | 62
2015-02-28 | Vibrating Multi Tyre Roller Hired 17/2/15 - 27/2/15 | Multi Tyre Roller |  | 1 | 1080.8 | 1080.8 | 62
2015-02-28 | Smooth Drum Roller Hired from 16/2/15 - 27/2/15 | SD Roller-Flexi Hire |  | 1 | 710.5 | 710.5 | 62
2015-03-02 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2015-03-02 | ATS Labour Hire | Labour |  | 3.5 | 49.7 | 173.95 | 62
2015-03-02 | ATS Labour Hire | Labour | hr | 6.5 | 42.6 | 276.9 | 62
2015-03-02 | Water Cart Hire | Water Cart - Hire | hr | 8.5 | 90 | 765 | 62
2015-03-02 | ATS Labour Hire | Labour | hr | 4.5 | 42.6 | 191.7 | 62
2015-03-03 | Water Cart Hire | Water Cart - Hire | hr | 7 | 90 | 630 | 62
2015-03-03 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 62
2015-03-03 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 954.46 | 62
2015-03-04 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2015-03-04 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 62
2015-03-04 | CAT297C MTL - No Operator | CAT297 | hr | 10.5 | 35 | 367.5 | 62
2015-03-04 | Water Cart Hire | Water Cart - Hire | hr | 2 | 90 | 180 | 62
| Subtotal for 062 |  |  |  |  | 112261.32
Portfolio WBS 0623
2014-09-26 | Hire of 14T Excavator | Excavator - 14T | hr | 6.5 | 80 | 520 | 623
2014-09-26 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 623
2014-09-26 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 151.3 | 3 | 453.9 | 623
2014-09-26 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 623
2014-09-26 | Smooth Drum Roller Hired from 26/9/14 - 30/9/14 | SD Roller-Flexi Hire |  | 1 | 1126.3 | 1126.3 | 623
2014-09-27 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 560.9 | 3 | 1682.7 | 623
2014-09-27 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 7 | 140 | 980 | 623
2014-09-27 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 6.5 | 80 | 520 | 623
2014-09-29 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 623
2014-09-30 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-09-30 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 660.75 | 3 | 1982.25 | 623
2014-09-30 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 623
2014-09-30 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9.5 | 140 | 1330 | 623
2014-10-01 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2014-10-01 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 90 | 945 | 623
2014-10-01 | Backhoe Hire | Backhoe | hr | 1 | 92.5 | 92.5 | 623
2014-10-01 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 103.15 | 3 | 309.45 | 623
2014-10-01 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 623
2014-10-01 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 11.5 | 140 | 1610 | 623
2014-10-01 | Allciv - Tipper (Mack Truck) & tag | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 623
2014-10-01 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 623
2014-10-01 | Labour | Labour | hr | 6.5 | 45 | 292.5 | 623
2014-10-01 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 623
2014-10-02 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 8 | 140 | 1120 | 623
2014-10-02 | Labour | Labour | hr | 3.5 | 45 | 157.5 | 623
2014-10-02 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-10-02 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 623
2014-10-07 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 464.65 | 3 | 1393.95 | 623
2014-10-07 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9.5 | 140 | 1330 | 623
2014-10-07 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 623
2014-10-07 | ATS Labour Hire | Labour | hr | 8.5 | 46.85 | 398.225 | 623
2014-10-07 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-10-07 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-10-08 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 623
2014-10-09 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9.5 | 140 | 1330 | 623
2014-10-09 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-10-09 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-10-09 | Travel Allowance for James Sherlock, Steven Loder and Henry Muller Week Ending 5/10/14 | Travel Allowance | hr | 15 | 30 | 450 | 623
2014-10-09 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 399.45 | 3 | 1198.35 | 623
2014-10-12 | Travel Allowance for James Sherlock, Steven Loder and Henry Miller Week ending 12/10/14 | Travel Allowance | hr | 15 | 20 | 300 | 623
2014-10-12 | Travel Allowance for Benjamin King Week ending 12/10/14 | Travel Allowance | hr | 2 | 46 | 92 | 623
2014-10-13 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 545.5 | 3 | 1636.5 | 623
2014-10-13 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 623
2014-10-13 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 623
2014-10-13 | ATS Labour Hire | Labour | hr | 3.5 | 42.6 | 149.1 | 623
2014-10-13 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 623
2014-10-13 | Hire of 14T Excavator | Excavator - 14T | hr | 7.5 | 80 | 600 | 623
2014-10-13 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2014-10-14 | Water Cart Hire | Water Cart - Hire | hr | 4 | 90 | 360 | 623
2014-10-14 | Truck Tipper Hire | Truck Tipper | hr | 0.5 | 80 | 40 | 623
2014-10-14 | ATS Labour Hire | Labour | hr | 1 | 42.6 | 42.6 | 623
2014-10-14 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2014-10-14 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 4 | 140 | 560 | 623
2014-10-14 | Backhoe Hire | Backhoe | hr | 2.5 | 92.5 | 231.25 | 623
2014-10-14 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 49.4 | 3 | 148.2 | 623
2014-10-15 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 623
2014-10-16 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 623
2014-10-17 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 934.69 | 3 | 2804.07 | 623
2014-10-17 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 623
2014-10-17 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 90 | 945 | 623
2014-10-17 | Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 623
2014-10-18 | Water Cart Hire | Water Cart - Hire | hr | 6.5 | 90 | 585 | 623
2014-10-18 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 623
2014-10-18 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 6.5 | 140 | 910 | 623
2014-10-18 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 623
2014-10-18 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 305.8 | 3 | 917.4 | 623
2014-10-18 | Allciv - Stabilising Crew | Labour | hr | 4.5 | 54.58 | 245.61 | 623
2014-10-18 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 623
2014-10-18 | ATS Labour Hire | Labour |  | 6.5 | 49.7 | 323.05 | 623
2014-10-18 | Hire of 14T Excavator | Excavator - 14T | hr | 2 | 80 | 160 | 623
2014-10-18 | ATS Labour Hire | Labour | hr | 7.5 | 42.6 | 319.5 | 623
2014-10-19 | ATS Labour Hire Travel allowance for James Sherlock | Travel Allowance | hr | 6 | 20 | 120 | 623
2014-10-20 | Water Cart Hire | Water Cart - Hire | hr | 11 | 90 | 990 | 623
2014-10-21 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 623
2014-10-21 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-10-21 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 623
2014-10-21 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 252.3 | 3 | 756.9 | 623
2014-10-21 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2014-10-21 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-10-21 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 623
2014-10-21 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 623
2014-10-22 | Water Cart Hire | Water Cart - Hire | hr | 3 | 90 | 270 | 623
2014-10-22 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 204.8 | 3 | 614.4 | 623
2014-10-22 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-10-22 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-10-22 | Water Cart Hire | Water Cart - Hire | hr | 3 | 90 | 270 | 623
2014-10-22 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10 | 140 | 1400 | 623
2014-10-23 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-10-23 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 623
2014-10-23 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2014-10-23 | Water Cart Hire | Water Cart - Hire | hr | 2.75 | 80 | 220 | 623
2014-10-23 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 623
2014-10-23 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 623
2014-10-23 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 623
2014-10-23 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10.5 | 140 | 1470 | 623
2014-10-23 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-10-24 | Water Cart Hire | Water Cart - Hire | hr | 2.5 | 90 | 225 | 623
2014-10-24 | Backhoe Hire | Backhoe | hr | 8 | 92.5 | 740 | 623
2014-10-24 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 623
2014-10-24 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 623
2014-10-24 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2014-10-24 | Hire of 14T Excavator | Excavator - 14T | hr | 3 | 80 | 240 | 623
2014-10-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 623
2014-10-24 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-10-24 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 623
2014-10-24 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 11 | 140 | 1540 | 623
2014-10-24 | Water Cart Hire | Water Cart - Hire | hr | 10 | 80 | 800 | 623
2014-10-24 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 307.75 | 3 | 923.25 | 623
2014-10-24 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 49 | 3 | 147 | 623
2014-10-24 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 185.6 | 3 | 556.8 | 623
2014-10-25 | Water Cart Hire | Water Cart - Hire | hr | 6.25 | 80 | 500 | 623
2014-10-26 | Water Cart Hire | Water Cart - Hire | hr | 6.75 | 80 | 540 | 623
2014-10-27 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-10-27 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-10-27 | Water Cart Hire | Water Cart - Hire | hr | 1.5 | 80 | 120 | 623
2014-10-28 | Grader Cat 12H GPS/UTS (with robotic total station and rover unit) | Grader 12H GPS/ | hr | 9.5 | 150 | 1425 | 623
2014-10-28 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 623
2014-10-28 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2014-10-28 | Water Cart Hire | Water Cart - Hire | hr | 7.5 | 90 | 675 | 623
2014-10-28 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 8.5 | 140 | 1190 | 623
2014-10-28 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 623
2014-10-29 | Hire of 14T Excavator | Excavator - 14T | hr | 5.5 | 80 | 440 | 623
2014-10-29 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 623
2014-10-29 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 623
2014-10-29 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 623
2014-10-29 | Grader Cat 12H GPS/UTS (with robotic total station and rover unit) | Grader 12H GPS/ | hr | 10 | 150 | 1500 | 623
2014-10-29 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2014-10-29 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 623
2014-10-29 | Allciv - Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 623
2014-10-29 | Backhoe Hire | Backhoe | hr | 4 | 92.5 | 370 | 623
2014-10-29 | Water Cart Hire | Water Cart - Hire | hr | 11 | 80 | 880 | 623
2014-10-29 | Water Cart Hire | Water Cart - Hire | hr | 6.5 | 90 | 585 | 623
2014-10-29 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 623
2014-10-30 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 623
2014-10-30 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 623
2014-10-30 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 623
2014-10-30 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 623
2014-10-30 | Truck Tipper Hire | Truck Tipper | hr | 1 | 80 | 80 | 623
2014-10-30 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 623
2014-10-30 | Grader Cat 12H GPS/UTS (with robotic total station and rover unit) | Grader 12H GPS/ | hr | 9.5 | 150 | 1425 | 623
2014-10-31 | CAT297C MTL - No Operator | CAT297 | hr | 1.5 | 35 | 52.5 | 623
2014-10-31 | 9T Vibrating Rammer Hired 1/10/14 - 31/10/14 | Vibrating Rammer |  | 1 | 2801.25 | 2801.25 | 623
2014-10-31 | 13T Smooth Drum Roller Hired from 30/9/14 - 31/10/14 | SD Roller-Flexi Hire |  | 1 | 3268.3 | 3268.3 | 623
2014-10-31 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 623
2014-10-31 | 13T Smooth Drum Roller & Transport Hired from 31/10/14 - 31/10/14 | SD Roller-Flexi Hire |  | 1 | 984.2 | 984.2 | 623
2014-11-04 | Truck Tipper Hire | Truck Tipper | hr | 5.5 | 80 | 440 | 623
2014-11-04 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 623
2014-11-04 | Tipper (Wet Hire) | Tipper | hr | 5 | 80 | 400 | 623
2014-11-04 | Allciv - Stabilising Crew | Labour | hr | 2 | 54.58 | 109.16 | 623
2014-11-04 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 623
2014-11-04 | Truck Tipper Hire | Truck Tipper | hr | 5.5 | 80 | 440 | 623
2014-11-04 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 292.9 | 3 | 878.7 | 623
2014-11-05 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2014-11-05 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 623
2014-11-05 | Hire of 14T Excavator | Excavator - 14T | hr | 4.5 | 80 | 360 | 623
2014-11-05 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 623
2014-11-05 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 623
2014-11-05 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 623
2014-11-05 | Tipper (Wet Hire) | Tipper | hr | 3 | 80 | 240 | 623
2014-11-05 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 130.5 | 3 | 391.5 | 623
2014-11-05 | 13T Smooth Drum Roller Hired from 31/10/13 - 5/11/14 | SD Roller-Flexi Hire |  | 1 | 317.8 | 317.8 | 623
2014-11-06 | Tipper (Wet Hire) | Tipper | hr | 1 | 80 | 80 | 623
2014-11-06 | Truck Tipper Hire | Truck Tipper | hr | 1 | 80 | 80 | 623
2014-11-06 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 623
2014-11-06 | Truck Tipper Hire | Truck Tipper | hr | 1 | 80 | 80 | 623
2014-11-07 | Backhoe Hire | Backhoe | hr | 3.5 | 92.5 | 323.75 | 623
2014-11-07 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 334.1 | 3 | 1002.3 | 623
2014-11-07 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 623
2014-11-07 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 623
2014-11-08 | Water Cart Hire | Water Cart - Hire | hr | 7 | 90 | 630 | 623
2014-11-08 | ATS Labour Hire | Labour | hr | 5.5 | 42.6 | 234.3 | 623
2014-11-08 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 623
2014-11-08 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2014-11-08 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 7 | 140 | 980 | 623
2014-11-08 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 456.8 | 3 | 1370.4 | 623
2014-11-08 | ATS Labour Hire | Labour |  | 7 | 49.7 | 347.9 | 623
2014-11-10 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 22.53 | 7.5 | 168.975 | 623
2014-11-10 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 623
2014-11-10 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9 | 140 | 1260 | 623
2014-11-10 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 442.9 | 3 | 1328.7 | 623
2014-11-10 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-11-11 | 2.2 Roadbase 145-KQT | Roadbase 2.2 |  | 23.9 | 7.5 | 179.25 | 623
2014-11-11 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 58.38 | 7.5 | 437.85 | 623
2014-11-11 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 6 | 140 | 840 | 623
2014-11-11 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-11-11 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-11-11 | Allciv - New Holland Grader | New Holland | hr | 1 | 35 | 35 | 623
2014-11-11 | Hire of 14T Excavator | Excavator - 14T | hr | 6.5 | 80 | 520 | 623
2014-11-11 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 267.6 | 3 | 802.8 | 623
2014-11-11 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2014-11-11 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 623
2014-11-11 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 623
2014-11-12 | Water Cart Hire | Water Cart - Hire | hr | 7 | 90 | 630 | 623
2014-11-12 | ATS Labour Hire | Labour | hr | 5.5 | 42.6 | 234.3 | 623
2014-11-12 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2014-11-12 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10 | 140 | 1400 | 623
2014-11-12 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 210.4 | 3 | 631.2 | 623
2014-11-13 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 175.9 | 3 | 527.7 | 623
2014-11-13 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 623
2014-11-13 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 623
2014-11-13 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-11-14 | Hire of 14T Excavator | Excavator - 14T | hr | 4.5 | 80 | 360 | 623
2014-11-14 | Backhoe Hire | Backhoe | hr | 3.5 | 92.5 | 323.75 | 623
2014-11-14 | Western Star Truck | Western Star | hr | 3 | 80 | 240 | 623
2014-11-14 | Truck Tipper Hire | Truck Tipper | hr | 9.5 | 80 | 760 | 623
2014-11-14 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 623
2014-11-15 | Hire of 14T Excavator | Excavator - 14T | hr | 9 | 80 | 720 | 623
2014-11-15 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 623
2014-11-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 623
2014-11-15 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 623
2014-11-15 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 623
2014-11-15 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 183.47 | 7.5 | 1376.025 | 623
2014-11-15 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 122.15 | 3 | 366.45 | 623
2014-11-15 | Allciv - 120H Grader | 120H Grader | hr | 6 | 135 | 810 | 623
2014-11-17 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 623
2014-11-17 | Hire of 14T Excavator | Excavator - 14T | hr | 10 | 80 | 800 | 623
2014-11-17 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 623
2014-11-17 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2014-11-17 | Allciv - Stabilising Crew | Labour | hr | 1.5 | 54.58 | 81.87 | 623
2014-11-17 | Tipper (Wet Hire) | Tipper | hr | 4.5 | 80 | 360 | 623
2014-11-17 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 3.5 | 80 | 280 | 623
2014-11-17 | Western Star Truck | Western Star | hr | 4 | 80 | 320 | 623
2014-11-17 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2014-11-17 | Tandem Tipper Truck | Truck Tandem Tipper | hr | 9 | 80 | 720 | 623
2014-11-17 | Western Star Truck | Western Star | hr | 3.5 | 80 | 280 | 623
2014-11-17 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 623
2014-11-17 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 623
2014-11-17 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 623
2014-11-17 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4 | 42.79 | 171.16 | 623
2014-11-17 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 623
2014-11-17 | ATS Labour Hire | Labour | hr | 6.5 | 42.6 | 276.9 | 623
2014-11-17 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10 | 140 | 1400 | 623
2014-11-17 | Allciv - 120H Grader | 120H Grader | hr | 7 | 135 | 945 | 623
2014-11-17 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 592.21 | 3 | 1776.63 | 623
2014-11-18 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 623
2014-11-18 | Tipper (Wet Hire) | Tipper | hr | 1.5 | 80 | 120 | 623
2014-11-18 | Water Cart Hire | Water Cart - Hire | hr | 9.5 | 80 | 760 | 623
2014-11-18 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 108.1 | 3 | 324.3 | 623
2014-11-18 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 7.5 | 140 | 1050 | 623
2014-11-19 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 146.05 | 3 | 438.15 | 623
2014-11-19 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 11.5 | 140 | 1610 | 623
2014-11-19 | Water Cart Hire | Water Cart - Hire | hr | 10.75 | 80 | 860 | 623
2014-11-20 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 623
2014-11-20 | Allciv - 120H Grader | 120H Grader | hr | 10.5 | 135 | 1417.5 | 623
2014-11-20 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 623
2014-11-20 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9.5 | 140 | 1330 | 623
2014-11-21 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 339.4 | 3 | 1018.2 | 623
2014-11-21 | Water Cart Hire | Water Cart - Hire | hr | 6 | 80 | 480 | 623
2014-11-21 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2014-11-21 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 623
2014-11-21 | Allciv - 120H Grader | 120H Grader | hr | 5 | 135 | 675 | 623
2014-11-21 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 4 | 140 | 560 | 623
2014-11-22 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 623
2014-11-22 | Water Cart Hire | Water Cart - Hire | hr | 5 | 80 | 400 | 623
2014-11-23 | Water Cart Hire | Water Cart - Hire | hr | 5 | 80 | 400 | 623
2014-11-23 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 623
2014-11-24 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 83.6 | 3 | 250.8 | 623
2014-11-24 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-11-24 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-11-24 | Allciv - 120H Grader | 120H Grader | hr | 4 | 135 | 540 | 623
2014-11-24 | Tipper (Wet Hire) | Tipper | hr | 3.5 | 90 | 315 | 623
2014-11-24 | Backhoe Hire | Backhoe | hr | 8 | 92.5 | 740 | 623
2014-11-24 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2014-11-24 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 623
2014-11-24 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 8.5 | 140 | 1190 | 623
2014-11-25 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 5.5 | 140 | 770 | 623
2014-11-25 | Backhoe Hire | Backhoe | hr | 7 | 92.5 | 647.5 | 623
2014-11-26 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 10.5 | 140 | 1470 | 623
2014-11-26 | Allciv - 120H Grader | 120H Grader | hr | 10 | 135 | 1350 | 623
2014-11-26 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 623
2014-11-26 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 584.55 | 3 | 1753.62 | 623
2014-11-26 | Water Cart Hire | Water Cart - Hire | hr | 9.5 | 80 | 760 | 623
2014-11-26 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 623
2014-11-26 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 623
2014-11-26 | Allciv - 120H Grader | 120H Grader | hr | 10 | 135 | 1350 | 623
2014-11-26 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 623
2014-11-26 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 623
2014-11-27 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-11-27 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 623
2014-11-27 | 2.2 Roadbase 012-TET | Roadbase 2.2 |  | 220.44 | 7.5 | 1653.3 | 623
2014-11-28 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 623
2014-11-28 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 623
2014-11-28 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2014-11-28 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2014-11-28 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2014-11-28 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9.5 | 140 | 1330 | 623
2014-11-29 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 7 | 140 | 980 | 623
2014-11-30 | Smooth Drum Roller Hired from 30/10/14 - 30/11/14 | SD Roller-Flexi Hire |  | 1 | 1421 | 1421 | 623
2014-11-30 | Vibrating Multi Tyre Roller Hired 31/10/14 -* 30/11/14 | Multi Tyre Roller |  | 1 | 1218 | 1218 | 623
2014-11-30 | Smooth Drum Roller Hired from 17/11/14 - 30/11/14 | SD Roller-Flexi Hire |  | 1 | 659.63 | 659.63 | 623
2014-12-01 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 170.3 | 3 | 510.9 | 623
2014-12-01 | Allciv - 120H Grader | 120H Grader | hr | 6 | 135 | 810 | 623
2014-12-01 | Backhoe Hire | Backhoe | hr | 9 | 92.5 | 832.5 | 623
2014-12-01 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 623
2014-12-01 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2014-12-01 | Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 623
2014-12-03 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 12.55 | 3 | 37.65 | 623
2014-12-05 | Moisture Conditioning of 2.3 Gravel | Moisture Conditioning |  | 12.7 | 3 | 38.1 | 623
2014-12-11 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 623
2014-12-12 | Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 623
2014-12-12 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 623
2014-12-13 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 623
2014-12-13 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 623
2014-12-13 | Truck Tipper Hire | Truck Tipper | hr | 1.5 | 80 | 120 | 623
2014-12-13 | 2.2 Roadbase Cartage 219.38 | Truck Tipper |  | 1.5 | 75 | 112.5 | 623
2014-12-15 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 623
2014-12-15 | Truck Tipper Hire | Truck Tipper | hr | 4.5 | 80 | 360 | 623
2014-12-15 | Truck Tipper Hire | Truck Tipper | hr | 10.5 | 80 | 840 | 623
2014-12-16 | Truck Tipper Hire | Truck Tipper | hr | 4 | 80 | 320 | 623
2014-12-16 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2014-12-16 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 623
2014-12-16 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 623
2014-12-16 | Allciv - Labour Hire | Labour | hr | 7.5 | 42.72 | 320.4 | 623
2014-12-16 | Water Cart Hire | Water Cart - Hire | hr | 9 | 80 | 720 | 623
2014-12-16 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2014-12-16 | Backhoe Hire | Backhoe | hr | 4.5 | 92.5 | 416.25 | 623
2014-12-16 | Allciv - New Holland Grader | New Holland | hr | 3 | 35 | 105 | 623
2014-12-16 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 623
2014-12-16 | Allciv - 120H Grader | 120H Grader | hr | 4 | 135 | 540 | 623
2014-12-16 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 9 | 140 | 1260 | 623
2014-12-16 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2014-12-17 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 623
2014-12-17 | Water Cart Hire | Water Cart - Hire | hr | 5 | 80 | 400 | 623
2014-12-17 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 6.5 | 140 | 910 | 623
2014-12-17 | Backhoe Hire | Backhoe | hr | 1 | 92.5 | 92.5 | 623
2014-12-17 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2014-12-18 | Labour Hire | Labour | hr | 11.5 | 42.72 | 491.28 | 623
2014-12-31 | Smooth Drum Roller Hired from 30/11/14 - 31/12/14 | SD Roller-Flexi Hire |  | 1 | 142.1 | 142.1 | 623
2015-01-05 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2015-01-06 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 623
2015-01-06 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2015-01-06 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 623
2015-01-06 | Backhoe Hire | Backhoe | hr | 1 | 92.5 | 92.5 | 623
2015-01-06 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 623
2015-01-06 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 623
2015-01-06 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 623
2015-01-06 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 623
2015-01-07 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2015-01-07 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2015-01-07 | Allciv - 120H Grader | 120H Grader | hr | 7 | 135 | 945 | 623
2015-01-07 | Tipper (Wet Hire) | Tipper | hr | 5 | 90 | 450 | 623
2015-01-07 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 7 | 120 | 840 | 623
2015-01-08 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2015-01-08 | Truck Tipper Hire | Truck Tipper | hr | 3.5 | 80 | 280 | 623
2015-01-08 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 623
2015-01-08 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 120 | 360 | 623
2015-01-08 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 623
2015-01-08 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2015-01-09 | Allciv - 120H Grader | 120H Grader | hr | 4.5 | 135 | 607.5 | 623
2015-01-09 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 623
2015-01-09 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 623
2015-01-09 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2015-01-09 | Allciv - Stabilising Crew | Labour | hr | 4.5 | 54.58 | 245.61 | 623
2015-01-09 | Truck Tipper Hire | Truck Tipper | hr | 3 | 80 | 240 | 623
2015-01-09 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 5 | 120 | 600 | 623
2015-01-09 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 623
2015-01-09 | Allciv - 120H Grader | 120H Grader | hr | 4.5 | 135 | 607.5 | 623
2015-01-09 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 623
2015-01-09 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2015-01-10 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 7 | 120 | 840 | 623
2015-01-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 623
2015-01-10 | Hire of 14T Excavator | Excavator - 14T | hr | 3.5 | 80 | 280 | 623
2015-01-10 | Allciv - Stabilising Crew | Labour | hr | 2 | 54.58 | 109.16 | 623
2015-01-10 | ATS Labour Hire | Labour |  | 4.5 | 49.7 | 223.65 | 623
2015-01-10 | Tipper (Wet Hire) | Tipper | hr | 3 | 90 | 270 | 623
2015-01-10 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2015-01-10 | Allciv - Stabilising Crew | Labour | hr | 2.5 | 54.58 | 136.45 | 623
2015-01-10 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2015-01-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 623
2015-01-10 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 623
2015-01-10 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 623
2015-01-10 | Allciv - 120H Grader | 120H Grader | hr | 8 | 135 | 1080 | 623
2015-01-12 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 3 | 120 | 360 | 623
2015-01-12 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 623
2015-01-12 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 623
2015-01-12 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 623
2015-01-12 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 623
2015-01-12 | Allciv - 120H Grader | 120H Grader | hr | 4 | 135 | 540 | 623
2015-01-12 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 623
2015-01-13 | CAT297C MTL - No Operator | CAT297 | hr | 3 | 35 | 105 | 623
2015-01-13 | Allciv - 120H Grader | 120H Grader | hr | 2 | 135 | 270 | 623
2015-01-13 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 623
2015-01-13 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2015-01-13 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2015-01-14 | Allciv - 120H Grader | 120H Grader | hr | 2 | 135 | 270 | 623
2015-01-14 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 623
2015-01-14 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2015-01-14 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 623
2015-01-14 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2015-01-15 | Hire of 14T Excavator | Excavator - 14T | hr | 5 | 80 | 400 | 623
2015-01-15 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2015-01-15 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 623
2015-01-15 | Allciv - 120H Grader | 120H Grader | hr | 3.5 | 135 | 472.5 | 623
2015-01-15 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2015-01-15 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 623
2015-01-16 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 623
2015-01-16 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 623
2015-01-16 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 623
2015-01-16 | Hire of 14T Excavator | Excavator - 14T | hr | 5 | 80 | 400 | 623
2015-01-16 | ATS Labour Hire/Travel Hours | Labour | hr | 59 | 20 | 1180 | 623
2015-01-19 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 623
2015-01-19 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 623
2015-01-20 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 623
2015-01-27 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 623
2015-01-28 | Hire of 14T Excavator | Excavator - 14T | hr | 5.5 | 80 | 440 | 623
2015-01-28 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5 | 65 | 325 | 623
2015-01-28 | Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 623
2015-01-28 | ATS Labour Hire | Labour |  | 9.5 | 49.7 | 472.15 | 623
2015-01-28 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 623
2015-01-29 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 623
2015-01-29 | Travel Hours | Labour | hr | 5 | 20 | 100 | 623
2015-01-30 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 623
2015-01-30 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 623
2015-01-31 | Smooth Drum Roller Hired from 31/12/15 - 31/01/15 | SD Roller-Flexi Hire |  | 1 | 2273.6 | 2273.6 | 623
2015-02-07 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 1 | 120 | 120 | 623
2015-02-09 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2 | 80 | 160 | 623
2015-02-09 | Truck Tipper Hire | Truck Tipper | hr | 6 | 80 | 480 | 623
2015-02-11 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 623
2015-02-11 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 623
2015-02-11 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 623
2015-02-11 | Hire of 14T Excavator | Excavator - 14T | hr | 10.5 | 80 | 840 | 623
2015-02-11 | ATS Labour Hire | Labour | hr | 4.5 | 46.85 | 210.825 | 623
2015-02-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 623
2015-02-16 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 623
2015-02-16 | Tipper (Wet Hire) | Tipper | hr | 2.5 | 90 | 225 | 623
2015-02-16 | Backhoe Hire | Backhoe | hr | 6.5 | 92.5 | 601.25 | 623
2015-02-17 | Truck & Dog Hire | Truck & Dog | hr | 3 | 120 | 360 | 623
2015-02-17 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 623
2015-02-17 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 623
2015-02-18 | Truck & Dog Hire | Truck & Dog | hr | 4 | 120 | 480 | 623
2015-02-19 | To Cover Cost of Fuel Driving from Prossie to Ingham and return in my own vehicle | Bobcat Hire |  | 3 | 35 | 105 | 623
2015-02-19 | Truck Tipper Hire | Truck Tipper | hr | 2.5 | 80 | 200 | 623
2015-02-19 | Bobcat Hire | Bobcat Hire |  | 2.5 | 35 | 87.5 | 623
2015-02-19 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2.5 | 42.79 | 106.975 | 623
2015-02-21 | Bobcat Hire | Bobcat Hire |  | 9.5 | 35 | 332.5 | 623
2015-02-21 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 623
2015-02-24 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 623
2015-02-24 | Truck Tipper Hire | Truck Tipper | hr | 2 | 80 | 160 | 623
2015-02-24 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 2 | 120 | 240 | 623
2015-02-24 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 623
2015-02-24 | ATS Labour Hire | Labour | hr | 4.5 | 42.6 | 191.7 | 623
2015-02-24 | Bobcat Hire | Bobcat Hire |  | 3 | 35 | 105 | 623
2015-03-02 | Backhoe Hire | Backhoe | hr | 1 | 92.5 | 92.5 | 623
2015-03-02 | Labour Hire | Excavator - 25T | hr | 2 | 45 | 90 | 623
2015-03-03 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 623
2015-03-04 | Western Star Truck and Trailer | Western Star Truck Traile | hr | 5.5 | 120 | 660 | 623
2015-03-04 | Truck and Dog Hire | Truck Tandem Tipper | hr | 4.5 | 125 | 562.5 | 623
2015-03-04 | Truck and Dog Hire | Truck Tandem Tipper | hr | 4.5 | 125 | 562.5 | 623
| Subtotal for 0623 |  |  |  |  | 222714.59
Portfolio WBS 063
2014-11-03 | Grader John deer 770 GP Fitted with Trimble UTS | Grader-John Deer | hr | 8 | 140 | 1120 | 63
2014-11-03 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 63
2014-11-20 | 140M Cat Grader Hired 31/10/2014 - 13/11/14 | Cat 140M Grader |  | 1 | 1500 | 1500 | 63
2014-11-27 | Allciv - 120H Grader | 120H Grader | hr | 6 | 135 | 810 | 63
2014-12-03 | ATS Labour Hire | Labour |  | 9 | 49.7 | 447.3 | 63
2014-12-03 | Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 63
2014-12-03 | Bobcat Hire | Bobcat Hire |  | 10.5 | 95 | 997.5 | 63
2014-12-04 | Bobcat Hire | Bobcat Hire |  | 10.5 | 95 | 997.5 | 63
2014-12-05 | Hire of 14T Excavator | Excavator - 14T | hr | 6 | 80 | 480 | 63
2014-12-05 | Water Cart Hire | Water Cart - Hire | hr | 9 | 90 | 810 | 63
2014-12-05 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 63
2014-12-05 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 63
2014-12-05 | Bobcat Hire | Bobcat Hire |  | 10 | 95 | 950 | 63
2014-12-05 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 63
2014-12-05 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 63
2014-12-05 | Labour Hire | Labour | hr | 12 | 42.72 | 512.64 | 63
2014-12-05 | Allciv - Stabilising Crew | Labour | hr | 7.5 | 54.58 | 409.35 | 63
2014-12-05 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 63
2014-12-05 | Allciv - 120H Grader | 120H Grader | hr | 5 | 135 | 675 | 63
2014-12-05 | CAT297C MTL - No Operator | CAT297 | hr | 3 | 35 | 105 | 63
2014-12-05 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7.5 | 42.79 | 320.925 | 63
2014-12-05 | Allciv - New Holland Grader | New Holland | hr | 1 | 35 | 35 | 63
2014-12-06 | Water Cart Hire | Water Cart - Hire | hr | 8 | 90 | 720 | 63
2014-12-06 | Allciv - New Holland Grader | New Holland | hr | 2 | 35 | 70 | 63
2014-12-06 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 63
2014-12-06 | Allciv - 120H Grader | 120H Grader | hr | 3 | 135 | 405 | 63
2014-12-06 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 63
2014-12-06 | Bobcat Hire | Bobcat Hire |  | 9 | 95 | 855 | 63
2014-12-08 | Allciv - Stabilising Crew | Labour | hr | 10.5 | 54.58 | 573.09 | 63
2014-12-08 | Water Cart Hire | Water Cart - Hire | hr | 8 | 90 | 720 | 63
2014-12-08 | Bobcat Hire | Bobcat Hire |  | 11 | 95 | 1045 | 63
2014-12-08 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 63
2014-12-08 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 63
2014-12-08 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 63
2014-12-09 | Bobcat Hire | Bobcat Hire |  | 9.5 | 95 | 902.5 | 63
2014-12-09 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 10 | 42.79 | 427.9 | 63
2014-12-10 | Truck Hire covers diesel for forward and return trips | Bobcat Hire |  | 5 | 65 | 325 | 63
2014-12-12 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 63
2014-12-12 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 63
2014-12-12 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 63
2014-12-12 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 63
2014-12-12 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 63
2014-12-13 | Allciv - 120H Grader | 120H Grader | hr | 9 | 135 | 1215 | 63
2014-12-15 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 63
2014-12-15 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 80 | 840 | 63
2014-12-17 | ATS Labour Hire | Labour |  | 7 | 49.7 | 347.9 | 63
2014-12-17 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 63
2014-12-17 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 63
2014-12-17 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 63
2014-12-31 | Smooth Drum Roller Hired from 30/11/14 - 31/12/14 | SD Roller-Flexi Hire |  | 1 | 710.5 | 710.5 | 63
2015-01-22 | Allciv - 120H Grader | 120H Grader | hr | 2 | 135 | 270 | 63
2015-02-03 | Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 63
2015-02-03 | Allciv - Stabilising Crew | Labour | hr | 6.5 | 54.58 | 354.77 | 63
2015-02-03 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 63
2015-02-03 | ATS Labour Hire | Labour | hr | 1.5 | 42.6 | 63.9 | 63
2015-02-03 | ATS Labour Hire | Labour |  | 6 | 49.7 | 298.2 | 63
2015-02-03 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6.5 | 42.79 | 278.135 | 63
2015-02-03 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 63
2015-02-03 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 5 | 42.79 | 213.95 | 63
2015-02-04 | Allciv - 120H Grader | 120H Grader | hr | 3 | 135 | 405 | 63
2015-02-05 | Allciv - 120H Grader | 120H Grader | hr | 2 | 135 | 270 | 63
2015-02-06 | Allciv - 120H Grader | 120H Grader | hr | 2 | 135 | 270 | 63
2015-02-12 | ATS Labour Hire | Labour |  | 9 | 49.7 | 447.3 | 63
2015-02-12 | ATS Labour Hire | Labour | hr | 9 | 46.85 | 421.65 | 63
2015-02-16 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 63
2015-02-25 | 140M Cat Grader Hired 25/2/15 - 28/2/15 | Cat 140M Grader |  | 1 | 900 | 900 | 63
| Subtotal for 063 |  |  |  |  | 31078.215
Portfolio WBS 064
2014-11-04 | 14mm Seal Agg | Cover Agg - 14mm |  | 250.98 | 48 | 12047.04 | 64
2014-11-07 | Water Cart Hire | Water Cart - Hire | hr | 10.5 | 90 | 945 | 64
2014-11-18 | 14mm Seal Agg | Cover Agg - 14mm |  | 114.88 | 48 | 5514.24 | 64
2014-11-25 | Suppy and Spray Primer Seal on the 7/11/14 | Primer Seal |  | 17464 | 1.67 | 29164.88 | 64
2014-11-25 | Allciv - New Holland Grader | New Holland | hr | 2.5 | 35 | 87.5 | 64
2014-11-28 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 64
2014-11-28 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 64
2014-11-28 | Allciv - New Holland Grader | New Holland | hr | 3 | 35 | 105 | 64
2014-11-28 | 22 kg bags Ezstreet | Ezstreet |  | 15 | 47 | 705 | 64
2014-11-28 | 10mm Seal Agg | Cover Agg - 10mm |  | 224.92 | 50 | 11246 | 64
2014-11-30 | Spreading of 10mm Cover Agg on the 26/11/14 | Cover Agg - 10mm |  | 68 | 172.43 | 11725.24 | 64
2014-11-30 | Second Seal on the 26/11/14 | Primer Seal |  | 14779 | 1.57 | 23203.03 | 64
2014-11-30 | Docket 14343 04/12/2014 & travel | Primer Seal |  | 1 | 628.75 | 628.75 | 64
2014-11-30 | Spreading of14 mm Cover Agg on the 7/11/14 | Cover Agg - 14mm |  | 109 | 225.31 | 24558.79 | 64
2014-11-30 | Spreading of14 mm Cover Agg on the 26/11/14 | Cover Agg - 14mm |  | 49 | 225.31 | 11040.19 | 64
2014-11-30 | Suppy and Spray Primer Seal on the 26/11/14 | Primer Seal |  | 7955 | 1.67 | 13284.85 | 64
2014-12-01 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 64
2014-12-08 | 14mm Seal Agg | Cover Agg - 14mm |  | 8.86 | 48 | 425.28 | 64
2014-12-08 | 22 kg bags Ezstreet x 10 | Ezstreet |  | 10 | 47 | 470 | 64
2014-12-09 | CRS 170/60Bulk | C170 |  | 350 | 1.76 | 616 | 64
2014-12-09 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 64
2014-12-09 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 64
2014-12-09 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 9 | 65 | 585 | 64
2014-12-09 | Water Cart Hire | Water Cart - Hire | hr | 5.5 | 90 | 495 | 64
2014-12-09 | 14mm Seal Agg | Cover Agg - 14mm |  | 5.76 | 36 | 207.36 | 64
2014-12-09 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 64
2014-12-09 | 7mm Seal Agg | Cover Agg - 7mm |  | 2.38 | 36 | 85.68 | 64
2014-12-10 | 22 kg bags Ezstreet x 8 | Ezstreet |  | 8 | 47 | 376 | 64
2014-12-10 | Water Cart Hire | Water Cart - Hire | hr | 4 | 90 | 360 | 64
2014-12-10 | 7mm Seal Agg | Cover Agg - 7mm |  | 6.9 | 36 | 248.4 | 64
2014-12-11 | Spreading of14 mm Cover Agg on the 3/12/14 Wallerman Falls Rd | Cover Agg - 14mm |  | 70 | 225.31 | 15771.7 | 64
2014-12-11 | Suppy and Spray Primer Seal on the 09/12/14 | Primer Seal |  | 549 | 1.67 | 916.83 | 64
2014-12-11 | Spreading of14 mm Cover Agg on the 9/12/14 Heards Rd | Cover Agg - 14mm |  | 3.5 | 225.31 | 788.585 | 64
2014-12-11 | Spreading of14 mm Cover Agg on the 3/12/14 Blackrock Rd | Cover Agg - 14mm |  | 1.7 | 225.31 | 383.027 | 64
2014-12-11 | Suppy and Spray Primer Seal on the 03/12/14 Blackrock Rd | Primer Seal |  | 274 | 1.67 | 457.58 | 64
2014-12-11 | Suppy and Spray Primer Seal on the 03/12/14 | Primer Seal |  | 10980 | 1.67 | 18336.6 | 64
2014-12-13 | Allciv - Stabilising Crew | Labour | hr | 4.5 | 54.58 | 245.61 | 64
2014-12-13 | Western Star Truck and Trailer | Western Star | hr | 5 | 120 | 600 | 64
2014-12-13 | Truck Tipper Hire | Truck Tipper | hr | 7 | 80 | 560 | 64
2014-12-16 | Cover Agg - 10mm | Cover Agg - 10mm |  | 11.68 | 50 | 584 | 64
2014-12-17 | 14mm Seal Agg | Cover Agg - 14mm |  | 11.96 | 48 | 574.08 | 64
2014-12-17 | 14mm Seal Agg | Cover Agg - 14mm |  | 10.62 | 48 | 509.76 | 64
2014-12-17 | Water Cart Hire | Water Cart - Hire | hr | 5 | 80 | 400 | 64
2014-12-18 | Spreading 14mm Cover aggl Taylors Beach Rd 17/12/2014 | Primer Seal |  | 16 | 225.31 | 3604.96 | 64
2014-12-18 | Supply & spray primer seal Taylors Beach Rd 17/12/2014 | Primer Seal |  | 2346 | 1.67 | 3917.82 | 64
2014-12-19 | Second seal Wallerman Falls Rd 18/12/2014 | Primer Seal |  | 17380 | 1.57 | 27286.6 | 64
2014-12-19 | Spreading 10mm Cover Agg Wallerman Falls Rd 18/12/2014 | Primer Seal |  | 79 | 172.43 | 13621.97 | 64
2015-01-13 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 64
2015-01-13 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 64
2015-01-14 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5.5 | 65 | 357.5 | 64
2015-01-14 | 7mm Seal Agg | Cover Agg - 7mm |  | 19.8 | 36 | 712.8 | 64
2015-01-15 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5.5 | 65 | 357.5 | 64
2015-01-16 | CRS 170/60 - Bulk | Cement |  | 1780 | 1.17 | 2082.6 | 64
2015-01-19 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 64
2015-01-20 | 7mm Seal Agg | Cover Agg - 7mm |  | 6.26 | 36 | 225.36 | 64
2015-01-20 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 64
2015-01-20 | CRS 170/60 - Bulk | Cement |  | 700 | 1.76 | 1232 | 64
2015-01-20 | CRS 170/60 - Bulk | Cement |  | 1800 | 1.17 | 2106 | 64
2015-01-21 | ATS Labour Hire | Labour | hr | 3.5 | 42.6 | 149.1 | 64
2015-01-21 | CAT297C MTL - No Operator | CAT297 | hr | 4 | 35 | 140 | 64
2015-01-21 | 7mm Seal Agg | Cover Agg - 7mm |  | 6 | 36 | 216 | 64
2015-01-21 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 64
2015-01-21 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 64
2015-01-21 | 7mm Seal Agg | Cover Agg - 7mm |  | 5.9 | 36 | 212.4 | 64
2015-01-21 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5 | 65 | 325 | 64
2015-01-21 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 64
2015-01-21 | CAT297C MTL - No Operator | CAT297 | hr | 4 | 35 | 140 | 64
2015-01-21 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 64
2015-01-22 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 64
2015-01-22 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 64
2015-01-22 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 64
2015-01-22 | 7mm Seal Agg | Cover Agg - 7mm |  | 3.6 | 36 | 129.6 | 64
2015-01-22 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 64
2015-01-22 | CRS 170/60 - Bulk | Cement |  | 750 | 1.76 | 1320 | 64
2015-01-22 | ATS Labour Hire | Labour |  | 10 | 49.7 | 497 | 64
2015-01-22 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 64
2015-01-22 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 10 | 65 | 650 | 64
2015-01-23 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 6 | 65 | 390 | 64
2015-01-23 | Allciv - Stabilising Crew | Labour | hr | 6 | 54.58 | 327.48 | 64
2015-01-23 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 64
2015-01-23 | Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 64
2015-01-23 | ATS Labour Hire | Labour | hr | 2.5 | 46.85 | 117.125 | 64
2015-01-23 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 64
2015-01-23 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 64
2015-01-23 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 64
2015-01-27 | CRS 170/60 - Bulk | Cement |  | 800 | 1.76 | 1408 | 64
2015-01-27 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 3 | 65 | 195 | 64
2015-01-29 | ATS Labour Hire | Labour | hr | 9 | 46.85 | 421.65 | 64
2015-01-29 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-01-29 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-01-29 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5.5 | 65 | 357.5 | 64
2015-01-29 | Allciv - Stabilising Crew | Labour | hr | 5 | 54.58 | 272.9 | 64
2015-01-30 | ATS Labour Hire | Labour |  | 4 | 49.7 | 198.8 | 64
2015-01-30 | 6 kg bags Ezstreet x 8 | Ezstreet |  | 6 | 47 | 282 | 64
2015-01-30 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 6 | 65 | 390 | 64
2015-01-30 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 64
2015-01-30 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 64
2015-01-30 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 64
2015-02-02 | Allciv - Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 64
2015-02-02 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 2 | 42.79 | 85.58 | 64
2015-02-02 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 64
2015-02-02 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 64
2015-02-02 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-02-02 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 3 | 65 | 195 | 64
2015-02-02 | 7mm Seal Agg | Cover Agg - 7mm |  | 6.54 | 36 | 235.44 | 64
2015-02-04 | CRS 170/60 - Bulk | Cement |  | 500 | 1.76 | 880 | 64
2015-02-05 | ATS Labour Hire | Labour | hr | 6 | 46.85 | 281.1 | 64
2015-02-05 | ATS Labour Hire | Labour |  | 11.5 | 49.7 | 571.55 | 64
2015-02-05 | 7mm Seal Agg | Cover Agg - 7mm |  | 5.34 | 36 | 192.24 | 64
2015-02-05 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-02-05 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 64
2015-02-05 | Allciv - Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 64
2015-02-07 | ATS Labour Hire | Labour |  | 1 | 49.7 | 49.7 | 64
2015-02-09 | Allciv - Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 64
2015-02-09 | Allciv - Stabilising Crew | Labour | hr | 1 | 54.58 | 54.58 | 64
2015-02-09 | Labour Hire | Labour | hr | 1 | 42.72 | 42.72 | 64
2015-02-09 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 1 | 65 | 65 | 64
2015-02-10 | Cover Agg - 10mm | Cover Agg - 10mm |  | 9.92 | 50 | 496 | 64
2015-02-10 | Cover Agg - 10mm | Cover Agg - 10mm |  | 7.04 | 48 | 337.92 | 64
2015-02-11 | 14mm Seal Agg | Cover Agg - 14mm |  | 10.94 | 48 | 525.12 | 64
2015-02-11 | Cover Agg - 10mm | Cover Agg - 10mm |  | 10.64 | 48 | 510.72 | 64
2015-02-11 | 14mm Seal Agg | Cover Agg - 14mm |  | 10.94 | 48 | 525.12 | 64
2015-02-11 | Cover Agg - 10mm | Cover Agg - 10mm |  | 9.02 | 50 | 451 | 64
2015-02-11 | Cover Agg - 10mm | Cover Agg - 10mm |  | 10.86 | 50 | 543 | 64
2015-02-11 | Cover Agg - 10mm | Cover Agg - 10mm |  | 11.24 | 50 | 562 | 64
2015-02-11 | Cover Agg - 10mm | Cover Agg - 10mm |  | 11.26 | 50 | 563 | 64
2015-02-11 | Cover Agg - 10mm | Cover Agg - 10mm |  | 11.24 | 50 | 562 | 64
2015-02-12 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 64
2015-02-12 | Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 64
2015-02-12 | Allciv - Stabilising Crew | Labour | hr | 9.5 | 54.58 | 518.51 | 64
2015-02-13 | Second Seal C170 Barbero Road | Second Seal C170 |  | 538 | 1.57 | 844.66 | 64
2015-02-13 | Spreading 14mm Cover agg at lAllingham Street | Primer Seal |  | 4.5 | 225.31 | 1013.895 | 64
2015-02-13 | Spreading 10mm Cover Agg Alingham Street | Primer Seal |  | 4 | 172.43 | 689.72 | 64
2015-02-13 | Second Seal C170 for Taylors Beach Road | Second Seal C170 |  | 8242 | 1.57 | 12939.94 | 64
2015-02-13 | Spreading 10mm Cover Agg Barero Road | Primer Seal |  | 1.5 | 172.43 | 258.645 | 64
2015-02-13 | Spreading 10mm Cover Agg Taylors Road | Primer Seal |  | 32 | 172.43 | 5517.76 | 64
2015-02-13 | Second Seal C170 for Alingham Street | Second Seal C170 |  | 1344 | 1.57 | 2110.08 | 64
2015-02-13 | Spreading 10mm Cover Agg Anne Street | Primer Seal |  | 2 | 172.43 | 344.86 | 64
2015-02-13 | Spreading 10mm Cover Agg Blackrock Road | Primer Seal |  | 1.5 | 172.43 | 258.645 | 64
2015-02-13 | Second Seal C170 Anne Street | Second Seal C170 |  | 537 | 1.57 | 843.09 | 64
2015-02-13 | Spreading 14mm Cover aggl Barbero Road | Primer Seal |  | 1.5 | 225.31 | 337.965 | 64
2015-02-13 | Spreading 14mm Cover aggl Barbero Road | Primer Seal |  | 1.5 | 225.31 | 337.965 | 64
2015-02-13 | Second Seal C170 for Blackrock Road | Second Seal C170 |  | 269 | 1.57 | 422.33 | 64
2015-02-13 | Spreading 10mm Cover Agg Heards Road | Primer Seal |  | 2 | 172.43 | 344.86 | 64
2015-02-13 | Second Seal C170 for Heards Road | Second Seal C170 |  | 539 | 1.57 | 846.23 | 64
2015-02-13 | Spreading 14mm Cover agg at Taylors Beach Road | Primer Seal |  | 25 | 225.31 | 5632.75 | 64
2015-02-17 | 7mm Seal Agg | Cover Agg - 7mm |  | 5 | 36 | 180 | 64
2015-02-17 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 64
2015-02-17 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-02-17 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 5 | 65 | 325 | 64
2015-02-18 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-02-24 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 64
2015-02-24 | Hire of 14T Excavator | Excavator - 14T | hr | 4 | 80 | 320 | 64
2015-02-24 | Allciv Paveline - Emulsion Truck | Paveline-Emulsion Truck | hr | 2 | 65 | 130 | 64
2015-02-25 | ATS Labour Hire | Labour | hr | 5.5 | 42.6 | 234.3 | 64
2015-02-25 | ATS Labour Hire | Labour | hr | 3.5 | 46.85 | 163.975 | 64
2015-02-25 | ATS Labour Hire | Labour | hr | 1.5 | 42.6 | 63.9 | 64
2015-02-25 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 64
2015-02-25 | 7mm Seal Agg | Cover Agg - 7mm |  | 5.2 | 36 | 187.2 | 64
2015-02-25 | Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 64
2015-02-25 | CAT297C MTL - No Operator | CAT297 | hr | 5.5 | 35 | 192.5 | 64
2015-02-25 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 64
2015-02-27 | 7mm Seal Agg & Inviromental Levy | Cover Agg - 7mm | each | 5.76 | 60.45 | 348.192 | 64
2015-02-27 | 7mm Seal Agg | Cover Agg - 7mm |  | 5.7 | 51 | 290.7 | 64
2015-02-27 | ATS Labour Hire | Labour | hr | 1.5 | 42.6 | 63.9 | 64
2015-02-27 | 7mm Seal Agg | Cover Agg - 7mm |  | 6.92 | 36 | 249.12 | 64
2015-02-27 | ATS Labour Hire | Labour | hr | 3 | 46.85 | 140.55 | 64
2015-02-27 | Bobcat Hire | Bobcat Hire |  | 5.5 | 35 | 192.5 | 64
2015-02-27 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 64
2015-03-02 | 4 x 22 kg bags Ezstreet | Ezstreet |  | 4 | 47 | 188 | 64
2015-03-02 | ATS Labour Hire | Labour |  | 6 | 49.7 | 298.2 | 64
2015-03-02 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 1813.465 | 64
2015-03-02 | Bobcat Hire | Bobcat Hire |  | 6 | 35 | 210 | 64
2015-03-02 | ATS Labour Hire | Labour | hr | 5.5 | 42.6 | 234.3 | 64
2015-03-02 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 64
2015-03-02 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 64
2015-03-02 | Labour Hire | Labour | hr | 6.5 | 42.72 | 277.68 | 64
2015-03-02 | CRS Bulk 170/60 | C170 |  | 400 | 1.76 | 704 | 64
2015-03-03 | Cover Agg - 10mm | Cover Agg - 10mm |  | 9.72 | 50 | 486 | 64
2015-03-03 | 14mm Seal Agg | Cover Agg - 14mm |  | 6.3 | 48 | 302.4 | 64
2015-03-03 | 14mm Seal Agg | Cover Agg - 14mm |  | 11.36 | 48 | 545.28 | 64
2015-03-03 | 14mm Seal Agg | Cover Agg - 14mm |  | 10.24 | 48 | 491.52 | 64
2015-03-03 | Hire of Street Sweeping Machine | Street Sweepers |  | 7.5 | 106.82 | 801.15 | 64
2015-03-03 | Cover Agg - 10mm | Cover Agg - 10mm |  | 11.32 | 50 | 566 | 64
2015-03-04 | Hire of Street Sweeping Machine | Street Sweepers |  | 4 | 106.82 | 427.28 | 64
2015-03-18 | Spreading of 10mm Cover Agg on the Spray Sheet 6894 3/3/15 Neame Street | Cover Agg - 10mm |  | 14 | 172.43 | 2414.02 | 64
2015-03-18 | Second Seal C170 Neame Street 3/3/15 | Second Seal C170 |  | 4927 | 1.57 | 7735.39 | 64
2015-03-18 | Second Seal C170 Neame Street 3/3/15 | Establishment Fee |  | 1 | 4500 | 4500 | 64
2015-03-18 | Spreading of14 mm Cover Agg on the 3/3/15 Spray Sheet 6893 Atkinson Street | Cover Agg - 14mm |  | 0.1 | 225.31 | 22.531 | 64
2015-03-18 | Second Seal C170 Atkinson Street 3/3/15 | Second Seal C170 |  | 24 | 1.57 | 37.68 | 64
2015-03-18 | Spre ading of14 mm Cover Agg on the 3/3/15 Neame Street | Cover Agg - 14mm |  | 19 | 225.31 | 4280.89 | 64
2015-03-18 | Spreading of 10mm Cover Agg on the Spray Sheet 6893 3/3/15 Atkinson Street | Cover Agg - 10mm |  | 0.1 | 172.43 | 17.243 | 64
2015-03-19 | 4 x 22 kg bags Ezstreet | Ezstreet |  | 5 | 47 | 235 | 64
2015-03-23 | Hire of Street Sweeping Machine | Street Sweepers |  | 5 | 117.723 | 588.615 | 64
2015-03-30 | Supply and lay DG07 Corrector - Taylors Beach Road | Second Seal C170 |  | 1 | 13500 | 13500 | 64
2015-03-30 | Second Seal C170 1.1 l/m2; 10mm Spray sheet 6910 Taylors Beach Road. | Second Seal C170 |  | 1 | 7500 | 7500 | 64
| Subtotal for 064 |  |  |  |  | 358171.698
Portfolio WBS 065
2015-02-05 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 65
2015-02-25 | Bobcat Hire | Bobcat Hire |  | 7 | 35 | 245 | 65
| Subtotal for 065 |  |  |  |  | 500.6
Portfolio WBS 067
2014-10-05 | Spray & Mark Paint | Small Tools |  | 1 | 224.21 | 224.21 | 67
2014-10-08 | Spray & Mark Paint x 4 x 12Pack | Small Tools |  | 1 | 224.21 | 224.21 | 67
2014-11-07 | Spot Marking Paint x 9 | Small Tools |  | 1 | 2.26 | 2.26 | 67
2014-11-28 | Mortar Mix 20Kg and Rapid Concrete mix | Concrete Mix |  | 1 | 60.4 | 60.4 | 67
2014-11-28 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 67
2014-12-01 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 67
2014-12-01 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 67
2014-12-01 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 67
2014-12-17 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 67
2014-12-17 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 67
2014-12-18 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 67
2014-12-18 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 67
2015-01-06 | Spray & Mark Paint x 1 | Small Tools |  | 1 | 56.05 | 56.05 | 67
2015-02-06 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 67
2015-02-06 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 67
2015-02-06 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 67
2015-02-06 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 67
| Subtotal for 067 |  |  |  |  | 3719.88
Portfolio WBS 072
2015-02-02 | Tipper (Wet Hire) | Tipper | hr | 6 | 90 | 540 | 72
2015-02-07 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 72
2015-02-07 | Ply film faced, Threaded rod, nuts, washers, screws, nails, dynabolt, pipe, drill bits, turps and Sprayer pressure. | Small Tools |  | 1 | 619.37 | 619.37 | 72
2015-02-07 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 72
2015-02-09 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 72
2015-02-09 | Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 72
2015-02-09 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 72
2015-02-09 | N32 20mm Concrete .60M3 and Min Charge | N20 | each | 1 | 478.1 | 478.1 | 72
2015-02-09 | Backhoe Hire | Backhoe | hr | 8 | 92.5 | 740 | 72
2015-02-09 | Allciv - Stabilising Crew | Labour | hr | 9 | 54.58 | 491.22 | 72
2015-02-09 | Threaded Rod, Nut, Washer, Wheel Cut, Ply Film, Cement and Mortar Mix | Small Tools |  | 1 | 392.64 | 392.64 | 72
2015-02-10 | Backhoe Hire | Backhoe | hr | 3.5 | 92.5 | 323.75 | 72
2015-02-10 | N32 20mm Concrete | N20 | each | 1 | 486.3 | 486.3 | 72
2015-02-10 | Gumboots and Deformed Bars | Small Tools |  | 1 | 211.2 | 211.2 | 72
2015-02-10 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 72
2015-02-10 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 72
2015-02-10 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 72
2015-02-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3.5 | 42.79 | 149.765 | 72
2015-02-10 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 72
2015-02-10 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 72
2015-02-11 | Labour Hire | Labour | hr | 13 | 42.72 | 555.36 | 72
2015-02-11 | ATS Labour Hire | Labour | hr | 6 | 46.85 | 281.1 | 72
2015-02-11 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 72
2015-02-11 | Allciv - Stabilising Crew | Labour | hr | 3.5 | 54.58 | 191.03 | 72
2015-02-11 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 72
2015-02-12 | Tipper (Wet Hire) | Tipper | hr | 2 | 90 | 180 | 72
2015-02-12 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 72
2015-02-12 | .40 M3 N32 Concrete | N32 | each | 1 | 237.4 | 237.4 | 72
2015-02-12 | Backhoe Hire | Backhoe | hr | 2.5 | 92.5 | 231.25 | 72
2015-02-12 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 72
2015-02-12 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 72
2015-02-16 | Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 72
2015-02-16 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 72
2015-02-16 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 72
| Subtotal for 072 |  |  |  |  | 12781.13
Portfolio WBS 088
2014-11-12 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 88
2014-11-12 | Hire of 14T Excavator | Excavator - 14T | hr | 5 | 80 | 400 | 88
2014-11-13 | 80mm A Camlock adaptor & 80mm B Camlock adaptor | Small Tools |  | 1 | 60.14 | 60.14 | 88
2014-11-27 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 88
2014-11-27 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 88
2014-11-27 | Water Cart Hire | Water Cart - Hire | hr | 10 | 90 | 900 | 88
2014-11-27 | Allciv - Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 88
2014-12-04 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 88
2014-12-04 | Water Cart Hire | Water Cart - Hire | hr | 5 | 90 | 450 | 88
2014-12-04 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 88
2014-12-13 | Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 88
2015-01-23 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 88
2015-01-23 | Tipper Hire /Float Backhoe | Truck & Dog | hr | 2 | 90 | 180 | 88
2015-01-23 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 88
2015-01-23 | ATS Labour Hire | Labour |  | 1.5 | 49.7 | 74.55 | 88
2015-02-07 | Backhoe Hire | Backhoe | hr | 7 | 92.5 | 647.5 | 88
2015-02-07 | Hire of 14T Excavator | Excavator - 14T | hr | 8 | 80 | 640 | 88
2015-02-07 | ATS Labour Hire | Labour |  | 7 | 49.7 | 347.9 | 88
2015-02-07 | Tipper (Wet Hire) | Tipper | hr | 3 | 90 | 270 | 88
2015-02-09 | Hire of 14T Excavator | Excavator - 14T | hr | 11 | 80 | 880 | 88
2015-02-09 | ATS Labour Hire | Labour | hr | 10.25 | 46.85 | 480.2125 | 88
2015-02-09 | ATS Labour Hire | Labour |  | 11 | 49.7 | 546.7 | 88
2015-02-10 | Hire of 14T Excavator | Excavator - 14T | hr | 9.5 | 80 | 760 | 88
2015-02-10 | Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 88
2015-02-10 | ATS Labour Hire | Labour |  | 9.5 | 49.7 | 472.15 | 88
2015-02-11 | Backhoe Hire | Backhoe | hr | 4.5 | 92.5 | 416.25 | 88
2015-02-11 | Tipper (Wet Hire) | Tipper | hr | 3 | 90 | 270 | 88
2015-02-15 | ATS Travel Cost week ending 1/3/15 | Labour |  | 5 | 20 | 100 | 88
2015-02-15 | ATS Travel Cost week ending 22/2/15 | Labour |  | 6 | 20 | 120 | 88
2015-02-15 | ATS Travel Cost week ending15/2/15 | Labour |  | 4 | 20 | 80 | 88
2015-03-15 | ATS Travel Cost week ending 8/3/15 | Labour |  | 4 | 20 | 80 | 88
| Subtotal for 088 |  |  |  |  | 11515.3925
Portfolio WBS 141
2014-09-15 | 40 Brackets centre mount | Signs - General |  | 40 | 1.91 | 76.4 | 141
2014-09-24 | ATS Labour Hire | Labour | hr | 5.5 | 42.6 | 234.3 | 141
2014-09-25 | Allciv - Site Administration | Labour | hr | 1 | 42.72 | 42.72 | 141
2014-09-25 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-09-26 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 141
2014-09-27 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2014-09-29 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-09-30 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-09-30 | Road Liner Barrirers and Delivery Hired 26/9/14 - 30/9/14 | Road Barriers |  | 1 | 801.16 | 801.16 | 141
2014-09-30 | Hire of Traffic Lights Hired from 25/9/14 - 29/9/14 | Traffic Lights |  | 1 | 304.5 | 304.5 | 141
2014-09-30 | Road Liner Barrirers and Delivery Hired 26/9/14 - 30/9/14 | Road Barriers |  | 1 | 801.16 | 801.16 | 141
2014-10-01 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 141
2014-10-02 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-03 | ATS Labour Hire | Labour | hr | 4.5 | 42.6 | 191.7 | 141
2014-10-07 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-08 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-09 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-10 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-11 | ATS Labour Hire | Labour | hr | 3 | 42.6 | 127.8 | 141
2014-10-12 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 141
2014-10-13 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-14 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-15 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-16 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-17 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-18 | ATS Labour Hire | Labour | hr | 6.5 | 42.6 | 276.9 | 141
2014-10-19 | Travel Allowance for Henry Miller Week ending 19/10/2014 | Travel Allowance |  | 6 | 20 | 120 | 141
2014-10-20 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-21 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-22 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-23 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-24 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-25 | Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 141
2014-10-26 | Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 141
2014-10-26 | Travel Allowance for Henry Miller, James Sherlock and Benjamin King. Week ending 26/10/2014 | Travel Allowance |  | 1 | 384 | 384 | 141
2014-10-27 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-28 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-10-29 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 141
2014-10-30 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-30 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-31 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-31 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-10-31 | Hire of Traffic Lights Hired from 20/10/14 - 31/10/14 | Traffic Lights |  | 1 | 1009 | 1009 | 141
2014-10-31 | Road Liner Barrirers and Delivery Hired 30/9/14 - 31/10/14 Pick up charge to return 8 Water Barriers | Road Barriers |  | 1 | 489.88 | 489.88 | 141
2014-10-31 | Hire of Traffic Lights Hired from 30/9/14 - 31/10/14 | Traffic Lights |  | 1 | 1573.25 | 1573.25 | 141
2014-11-01 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-11-01 | ATS Labour Hire | Labour | hr | 8 | 42.6 | 340.8 | 141
2014-11-03 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-11-03 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-11-04 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 141
2014-11-04 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 141
2014-11-05 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-06 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-11-07 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-08 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2014-11-10 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 7.75 |  |  | 141
2014-11-10 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-10 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 7.75 |  |  | 141
2014-11-10 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 7.75 |  |  | 141
2014-11-11 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-12 | Allciv - Site Administration | Labour | hr | 1.5 | 42.72 | 64.08 | 141
2014-11-12 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 9 |  |  | 141
2014-11-12 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 9 |  |  | 141
2014-11-12 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-13 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-11-14 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-15 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 9 |  |  | 141
2014-11-15 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 10.5 |  |  | 141
2014-11-15 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 141
2014-11-16 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 141
2014-11-16 | 2 x TC's + Ute, Signs & Comms Hire of Traffic Control from 10/11/14 - 15/11/14 | Traffic Control Crew |  | 1 | 3189.38 | 3189.38 | 141
2014-11-17 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-17 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-17 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-18 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-18 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-18 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-19 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-19 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-19 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11.5 |  |  | 141
2014-11-20 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 8 |  |  | 141
2014-11-20 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-20 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 8 |  |  | 141
2014-11-21 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 5.5 |  |  | 141
2014-11-21 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 141
2014-11-21 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-23 | 2 x TC's + Ute, Signs & Comms Hire of Traffic Control from 17/11/14 - 21/11/14 | Traffic Control Crew |  | 1 | 4865 | 4865 | 141
2014-11-24 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-24 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2014-11-25 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11.5 |  |  | 141
2014-11-25 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11.5 |  |  | 141
2014-11-25 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-26 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-11-27 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-11-27 | Hire of Traffic Lights Hired from 31/10/14 - 27/11/14 | Traffic Lights |  | 1 | 1319.5 | 1319.5 | 141
2014-11-28 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 141
2014-11-29 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2014-11-30 | 2 x TC's + Ute, Signs & Comms Hire of Traffic Control from 24/11/14 - 25/11/14 | Traffic Control Crew |  | 1 | 2386.75 | 2386.75 | 141
2014-11-30 | Road Liner Barrirers and Delivery Hired Hired 1/11/14 - 30/11/14 | Road Barriers |  | 1 | 127.12 | 127.12 | 141
2014-11-30 | Hire of Traffic Lights Hired from31/10/14 - 30/11/14 | Traffic Lights |  | 1 | 1522.5 | 1522.5 | 141
2014-12-01 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-02 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 141
2014-12-03 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 141
2014-12-04 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 7 |  |  | 141
2014-12-04 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-04 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 7 |  |  | 141
2014-12-05 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 7 |  |  | 141
2014-12-05 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-05 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 6 |  |  | 141
2014-12-05 | Road Liner Barrirers and Delivery Hired 30/11/14 - 4/12/14 | Road Barriers |  | 1 | 19.07 | 19.07 | 141
2014-12-06 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2014-12-07 | 2 x TC's + Ute, Signs & Comms Hire of Traffic Control from 5/12/14 | Traffic Control Crew |  | 1 | 1211.5 | 1211.5 | 141
2014-12-08 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-09 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-10 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-11 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2014-12-12 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 141
2014-12-13 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-12-15 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2014-12-16 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 141
2014-12-17 | ATS Labour Hire | Labour | hr | 7.5 | 42.6 | 319.5 | 141
2014-12-31 | Hire of Traffic Lights Hired from 1/12/2014-31/12/2014 | Traffic Lights |  | 1 | 1116.5 | 1116.5 | 141
2015-01-05 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 141
2015-01-06 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 141
2015-01-07 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-01-07 | ATS Labour Hire | Labour | hr | 6.5 | 42.6 | 276.9 | 141
2015-01-08 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2015-01-08 | ATS Labour Hire | Labour | hr | 10.75 | 42.6 | 457.95 | 141
2015-01-09 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-01-10 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 141
2015-01-12 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-01-13 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-01-14 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-01-15 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-01-15 | ATS Labour Hire/Travel Hours | Labour | hr | 54 | 20 | 1080 | 141
2015-01-16 | ATS Labour Hire/Travel Hours Week ending 9/11/14 | Labour | hr | 3 | 20 | 60 | 141
2015-01-17 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 141
2015-01-18 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 141
2015-01-19 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 141
2015-01-20 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-01-21 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-01-22 | ATS Labour Hire/Travel Hours Week ending 2/11/14 | Labour | hr | 3 | 20 | 60 | 141
2015-01-22 | ATS Labour Hire/Travel Hours | Labour | hr | 2 | 20 | 40 | 141
2015-01-22 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-01-22 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 141
2015-01-23 | Allciv - Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 141
2015-01-23 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2015-01-27 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 141
2015-01-28 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 141
2015-01-29 | Travel Hours | Labour | hr | 5 | 20 | 100 | 141
2015-01-29 | Allciv - Site Administration | Labour | hr | 2 | 42.72 | 85.44 | 141
2015-01-29 | ATS Labour Hire | Labour | hr | 10.75 | 42.6 | 457.95 | 141
2015-01-30 | ATS Labour Hire/Travel Hours week ending the 1/2/15 | Labour | hr | 4 | 20 | 80 | 141
2015-01-30 | ATS Labour Hire/Travel Hours | Labour | hr | 1 | 20 | 20 | 141
2015-01-30 | ATS Labour Hire/Travel Hours | Labour | hr | 7 | 20 | 140 | 141
2015-01-30 | ATS Labour Hire | Labour | hr | 7 | 42.6 | 298.2 | 141
2015-01-30 | ATS Labour Hire/Travel Hours Week Ending the 1/2/15 | Labour | hr | 17 | 20 | 340 | 141
2015-01-30 | ATS Labour Hire | Labour | hr | 7.5 | 42.6 | 319.5 | 141
2015-01-31 | Hire of Traffic Lights Hired from 31/12/14 - 30/1/15 | Traffic Lights |  | 1 | 1268.75 | 1268.75 | 141
2015-02-02 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-02-02 | ATS Labour Hire/ | Labour | hr | 10 | 42.6 | 426 | 141
2015-02-03 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 141
2015-02-04 | ATS Labour Hire | Labour | hr | 8.5 | 42.6 | 362.1 | 141
2015-02-05 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 141
2015-02-05 | ATS Travel Hours week ending the 8/2/15 | Labour | hr | 4 | 20 | 80 | 141
2015-02-05 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 8 |  |  | 141
2015-02-05 | ATS Travel Hours week ending the 15/2/15 | Labour | hr | 4 | 20 | 80 | 141
2015-02-06 | 1x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 16 |  |  | 141
2015-02-07 | ATS Travel Hours week ending 15/2/15 | Labour | hr | 2 | 20 | 40 | 141
2015-02-07 | ATS Travel Hours week ending 22/2/15 | Labour | hr | 5 | 20 | 100 | 141
2015-02-08 | 2 x TC's + Ute, Signs & Comms Hire of Traffic Control from 5/12/14 | Traffic Control Crew |  | 1 | 1786.63 | 1786.63 | 141
2015-02-09 | ATS Labour Hire/ | Labour | hr |  | 42.6 |  | 141
2015-02-09 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 141
2015-02-10 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 141
2015-02-11 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-02-12 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 141
2015-02-15 | ATS Labour Hire Sick Hours Week Ending 15/2/15 | Labour | hr | 4 | 42.6 | 170.4 | 141
2015-02-16 | ATS Labour Hire | Labour | hr | 2 | 42.6 | 85.2 | 141
2015-02-17 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-02-18 | 1 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 9 |  |  | 141
2015-02-18 | ATS Labour Hire | Labour | hr | 11.25 | 42.6 | 479.25 | 141
2015-02-19 | 1x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 10 |  |  | 141
2015-02-19 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-02-20 | 1 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 10.5 |  |  | 141
2015-02-20 | 1 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 11 |  |  | 141
2015-02-20 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-02-21 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 141
2015-02-22 | 1 x TC's + Ute, Signs & Comms Hire of Traffic Control | Traffic Control Crew |  | 1 | 1792.25 | 1792.25 | 141
2015-02-23 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 141
2015-02-24 | ATS Labour Hire | Labour | hr | 11.5 | 42.6 | 489.9 | 141
2015-02-25 | ATS Labour Hire | Labour | hr | 10.5 | 42.6 | 447.3 | 141
2015-02-26 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 141
2015-02-27 | ATS Labour Hire | Labour | hr | 9 | 42.6 | 383.4 | 141
2015-02-28 | Hire of Traffic Lights Hired from 9/2/15 - 27/2/15 | Traffic Lights |  | 1 | 482.13 | 482.13 | 141
2015-02-28 | Hire of Traffic Lights Hired from 9/2/15 - 27/2/15 | Traffic Lights |  | 1 | 482.13 | 482.13 | 141
2015-03-01 | ATS Travel Hours week ending 1/3/15 | Labour | hr | 3 | 20 | 60 | 141
2015-03-01 | ATS Travel Hours week ending the 1/3/15 | Labour | hr | 2 | 20 | 40 | 141
2015-03-01 | ATS Travel Hours week ending the 1/3/15 | Labour | hr | 2 | 20 | 40 | 141
2015-03-01 | 1 x TC's + Ute, Signs & Comms Hire of Traffic Control 23/2/15 - 27/2/15 | Traffic Control Crew |  | 1 | 3447.75 | 3447.75 | 141
2015-03-02 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 141
2015-03-02 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 10.5 |  |  | 141
2015-03-03 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 141
2015-03-03 | 2 x TC's + Ute, Signs & Comms | Traffic Control Crew | hr | 5 |  |  | 141
2015-03-03 | Transport of Lights back to Flexihire | Traffic Lights |  | 1 | 80 | 80 | 141
2015-03-08 | 1 x TC's + Ute, Signs & Comms Hire of Traffic Control 3/3/15 | Traffic Control Crew |  | 1 | 228 | 228 | 141
2015-03-08 | 1 x TC's + Ute, Signs & Comms Hire of Traffic Control 2/3/15 | Traffic Control Crew |  | 1 | 615 | 615 | 141
| Subtotal for 141 |  |  |  |  | 82094.66
Portfolio WBS 151
2014-09-22 | Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 151
2014-09-22 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 151
2014-09-22 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 151
2014-09-24 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 151
2014-09-24 | ATS Labour Hire | Labour | hr | 3 | 42.6 | 127.8 | 151
2014-09-24 | Backhoe Hire | Backhoe | hr | 4 | 45 | 180 | 151
2014-10-01 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 151
2014-10-01 | Labour | Labour | hr | 5 | 45 | 225 | 151
2014-12-02 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 151
2014-12-02 | ATS Labour Hire | Labour |  | 5.5 | 49.7 | 273.35 | 151
2014-12-02 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 151
2014-12-04 | ATS Labour Hire | Labour |  | 10.5 | 49.7 | 521.85 | 151
2015-01-28 | Excavate & Locate Storm Water & Telstra Service | Service Locator |  | 5 | 150 | 750 | 151
| Subtotal for 151 |  |  |  |  | 3294.92
Portfolio WBS 222
2014-09-16 | Bidim A36 2.00M x 125M & Bidim A39 3.00M x 125M | A39 |  | 1 | 5312.5 | 5312.5 | 222
2014-11-04 | ATS Labour Hire | Labour | hr | 11 | 42.6 | 468.6 | 222
2014-11-05 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 222
2014-11-07 | ATS Labour Hire | Labour | hr | 1.5 | 42.6 | 63.9 | 222
2014-11-08 | ATS Labour Hire | Labour | hr | 1.5 | 42.6 | 63.9 | 222
2014-11-14 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 222
2014-11-14 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 222
2014-11-14 | Bidim A44 2.00M x 100M & Bidim A44 3.00M x 100M | A44 |  | 1 | 6330 | 6330 | 222
2014-11-15 | Allciv - Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 222
2014-11-15 | Allciv - New Holland Grader | New Holland | hr | 1 | 35 | 35 | 222
2014-11-17 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 222
2014-11-17 | Allciv - New Holland Grader | New Holland | hr | 1 | 35 | 35 | 222
2014-11-17 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 222
2014-11-17 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 222
2014-11-18 | ATS Labour Hire | Labour | hr | 10 | 42.6 | 426 | 222
2014-11-21 | Allciv - Stabilising Crew | Labour | hr | 1.5 | 54.58 | 81.87 | 222
2014-11-21 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 222
2014-11-21 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 222
2014-11-21 | Bidim A39 3.00M x 125M & Bidim A39 3.00M x 125M | A39 |  | 1 | 5100 | 5100 | 222
2014-11-21 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 1.5 | 42.79 | 64.185 | 222
2014-11-26 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 222
2014-11-26 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 222
2014-11-26 | Allciv - Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 222
2014-11-26 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 222
2014-11-28 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 222
2014-12-01 | Bidim A44 3.00M x 100M | A44 |  | 1 | 633 | 633 | 222
2014-12-09 | Bidim A44 3.00M x 100M | A44 |  | 1 | 7650 | 7650 | 222
2014-12-13 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 222
2014-12-15 | Allciv - Labour Hire | Labour | hr | 5.5 | 42.72 | 234.96 | 222
2014-12-15 | Allciv - Labour Hire | Labour | hr | 3 | 42.72 | 128.16 | 222
2014-12-31 | Smooth Drum Roller Hired from 30/11/14 - 31/12/14 | SD Roller-Flexi Hire |  | 1 | 142.1 | 142.1 | 222
2015-01-07 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 222
2015-01-07 | 3 x Roof Gal Nails | Small Tools |  | 1 | 25.89 | 25.89 | 222
2015-01-08 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 222
2015-01-09 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 222
2015-01-10 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 222
2015-01-10 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 222
2015-02-17 | ATS Labour Hire | Labour | hr | 10.75 | 46.85 | 503.6375 | 222
2015-02-17 | Hire of 14T Excavator | Excavator - 14T | hr | 3.5 | 80 | 280 | 222
2015-02-17 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 222
2015-02-19 | Bidim A36 3.00M x 125M & Bidim A39 2.00M x 125M | A39 |  | 1 | 1062.5 | 1062.5 | 222
2015-02-19 | Bidim A36 3.00M x 125M & Bidim A39 2.00M x 125M | A39 |  | 1 | 3400 | 3400 | 222
| Subtotal for 222 |  |  |  |  | 37594.3225
Portfolio WBS 901
2014-09-07 | Allciv - Project Engineer Week Ending 7/9/14 | Project Engineer |  | 38 | 74.63 | 2835.94 | 901
2014-09-07 | Project Manager F/N Ending 7/9/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-09-21 | Allciv - Project Engineer Week Ending 21/9/14 | Project Engineer |  | 38 | 74.63 | 2835.94 | 901
2014-09-21 | Project Manager F/N Ending 21/9/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-10-05 | Project Manager F/N Ending 5/10/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-10-19 | Project Manager F/N Ending 19/10/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-11-02 | Project Manager F/N Ending 2/11/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-11-16 | Project Manager F/N Ending 16/11/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-11-24 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 901
2014-11-30 | Project Manager F/N Ending 30/11/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-12-07 | Project Manager F/N Ending 7/12/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2014-12-21 | Project Manager F/N Ending 19/12/14 | Project Manager |  | 76 | 106.25 | 8075 | 901
2015-01-11 | Only 1Week Worked Due to Christmas Break Project Manager F/N Ending 11/12/14 | Project Manager |  | 38 | 106.25 | 4037.5 | 901
2015-01-25 | Project Manager F/N Ending 25/1/2015 | Project Manager |  | 76 | 106.25 | 8075 | 901
2015-02-08 | Project Manager F/N Ending 8/2/2015 | Project Manager |  | 76 | 106.25 | 8075 | 901
2015-02-22 | Project Manager F/N Ending 22/2/2015 | Project Manager |  | 76 | 106.25 | 8075 | 901
2015-03-08 | Project Manager F/N Ending 22/3/2015 | Project Manager |  | 71 | 106.25 | 7543.75 | 901
2015-03-08 | Project Manager F/N Ending 8/3/2015 | Project Manager |  | 76 | 106.25 | 8075 | 901
| Subtotal for 901 |  |  |  |  | 123128.13
Portfolio WBS 902
2014-09-08 | Project Supervisor | Project Supervisor | hr | 8.5 | 90 | 765 | 902
2014-09-09 | Project Supervisor | Project Supervisor | hr |  | 90 |  | 902
2014-09-23 | Project Supervisor | Project Supervisor | hr | 2.5 | 90 | 225 | 902
2014-09-24 | Project Supervisor | Project Supervisor | hr | 6.25 | 90 | 562.5 | 902
2014-09-25 | Project Supervisor | Project Supervisor | hr | 10.15 | 90 | 913.5 | 902
2014-09-26 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-09-29 | Site Supervisor | Project Supervisor | hr | 10.75 |  |  | 902
2014-09-30 | Site Supervisor | Project Supervisor | hr | 10.5 |  |  | 902
2014-10-01 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-10-02 | Project Supervisor | Project Supervisor | hr | 10.75 | 90 | 967.5 | 902
2014-10-03 | Site Supervisor | Project Supervisor | hr | 5 |  |  | 902
2014-10-07 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-10-08 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-10-10 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-10-11 | Project Supervisor | Project Supervisor | hr | 3 | 90 | 270 | 902
2014-10-13 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-10-14 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-10-15 | Project Supervisor | Project Supervisor | hr | 9.5 | 90 | 855 | 902
2014-10-16 | Project Supervisor | Project Supervisor | hr | 9 | 90 | 810 | 902
2014-10-17 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-10-18 | Project Supervisor | Project Supervisor | hr | 6.75 | 90 | 607.5 | 902
2014-10-20 | Project Supervisor | Project Supervisor | hr | 9.75 | 90 | 877.5 | 902
2014-10-21 | Project Supervisor | Project Supervisor | hr | 8.5 | 90 | 765 | 902
2014-10-29 | Project Supervisor | Project Supervisor | hr | 11 | 90 | 990 | 902
2014-10-30 | Project Supervisor | Project Supervisor | hr | 11.5 | 90 | 1035 | 902
2014-10-31 | Project Supervisor | Project Supervisor | hr | 11.5 | 90 | 1035 | 902
2014-11-01 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-11-03 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-11-04 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-11-05 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-11-06 | Project Supervisor | Project Supervisor | hr | 10.25 | 90 | 922.5 | 902
2014-11-07 | Project Supervisor | Project Supervisor | hr | 5.5 | 90 | 495 | 902
2014-11-10 | Project Supervisor | Project Supervisor | hr | 10.15 | 90 | 913.5 | 902
2014-11-11 | Project Supervisor | Project Supervisor | hr | 7 | 90 | 630 | 902
2014-11-12 | Project Supervisor | Project Supervisor | hr | 7.25 | 90 | 652.5 | 902
2014-11-13 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-11-14 | Project Supervisor | Project Supervisor | hr | 9 | 90 | 810 | 902
2014-11-15 | Project Supervisor | Project Supervisor | hr | 8.75 | 90 | 787.5 | 902
2014-11-17 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-11-18 | Project Supervisor | Project Supervisor | hr | 10.25 | 90 | 922.5 | 902
2014-11-19 | Project Supervisor | Project Supervisor | hr | 9 | 90 | 810 | 902
2014-11-20 | Project Supervisor | Project Supervisor | hr | 10.45 | 90 | 940.5 | 902
2014-11-21 | Project Supervisor | Project Supervisor | hr | 5.5 | 90 | 495 | 902
2014-11-26 | Project Supervisor | Project Supervisor | hr | 10.25 | 90 | 922.5 | 902
2014-11-26 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-11-27 | Project Supervisor | Project Supervisor | hr | 8.5 | 90 | 765 | 902
2014-12-02 | Project Supervisor | Project Supervisor | hr | 6.5 | 90 | 585 | 902
2014-12-03 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-12-04 | Project Supervisor | Project Supervisor | hr | 9.5 | 90 | 855 | 902
2014-12-11 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2014-12-12 | Project Supervisor | Project Supervisor | hr | 7.5 | 90 | 675 | 902
2014-12-13 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-12-15 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2014-12-16 | Project Supervisor | Project Supervisor | hr | 7 | 90 | 630 | 902
2015-01-06 | Project Supervisor | Project Supervisor | hr | 3.5 | 90 | 315 | 902
2015-01-07 | Project Supervisor | Project Supervisor | hr | 10.25 | 90 | 922.5 | 902
2015-01-08 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2015-01-09 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2015-01-10 | Project Supervisor | Project Supervisor | hr | 8 | 90 | 720 | 902
2015-01-12 | Project Supervisor | Project Supervisor | hr | 10.45 | 90 | 940.5 | 902
2015-01-13 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2015-01-14 | Project Supervisor | Project Supervisor | hr | 9.5 | 90 | 855 | 902
2015-01-15 | Project Supervisor | Project Supervisor | hr | 9 | 90 | 810 | 902
2015-01-16 | Project Supervisor | Project Supervisor | hr | 5.5 | 90 | 495 | 902
2015-01-19 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2015-01-20 | Project Supervisor | Project Supervisor | hr | 10.25 | 90 | 922.5 | 902
2015-01-21 | Project Supervisor | Project Supervisor | hr | 9.5 | 90 | 855 | 902
2015-01-22 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2015-01-23 | Project Supervisor | Project Supervisor | hr | 1.5 | 90 | 135 | 902
2015-01-27 | Project Supervisor | Project Supervisor | hr |  | 90 |  | 902
2015-01-28 | Project Supervisor | Project Supervisor | hr | 9 | 90 | 810 | 902
2015-02-02 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2015-02-03 | Project Supervisor | Project Supervisor | hr | 11.5 | 90 | 1035 | 902
2015-02-04 | Project Supervisor | Project Supervisor | hr | 10 | 90 | 900 | 902
2015-02-05 | Project Supervisor | Project Supervisor | hr | 11.5 | 90 | 1035 | 902
2015-02-06 | Project Supervisor | Project Supervisor | hr | 3 | 90 | 270 | 902
2015-02-18 | Project Supervisor | Project Supervisor | hr | 11.5 | 90 | 1035 | 902
2015-02-19 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2015-02-20 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2015-02-23 | Project Supervisor | Project Supervisor | hr | 9 | 90 | 810 | 902
2015-02-24 | Project Supervisor | Project Supervisor | hr | 11 | 90 | 990 | 902
2015-02-25 | Project Supervisor | Project Supervisor | hr | 10.5 | 90 | 945 | 902
2015-03-02 | Project Supervisor | Project Supervisor | hr | 9.5 | 90 | 855 | 902
2015-03-04 | Project Supervisor | Project Supervisor | hr | 9.5 | 90 | 855 | 902
| Subtotal for 902 |  |  |  |  | 64840.5
Portfolio WBS 903
2014-09-05 | 2.5 Toshiba Canvio External | Office Supplies |  | 1 | 90 | 90 | 903
2014-09-05 | PVC Sweep bend 50mm 90 Degree orange | PVC Fitting |  | 1 | 52.79 | 52.79 | 903
2014-09-13 | Toilet Paper | Small Tools |  | 1 | 29.01 | 29.01 | 903
2014-09-15 | 15 x General signs & delineation for traffic control. | Signs - General |  | 1 | 389.25 | 389.25 | 903
2014-09-16 | Adhesive blue tack, letter clip, whiteboard markers, copy paper, pens, notebooks, exercise books, marbig clipboards, staplers, power stapler, Photo coping double sided, single sides and colour coping. | Office Supplies |  | 1 | 113.64 | 113.64 | 903
2014-09-16 | PVC Pipe | PVC Fitting |  | 1 | 23.95 | 23.95 | 903
2014-09-16 | Spoons, knives, Chopping Boards, & ect | Small Tools |  | 1 | 44.5 | 44.5 | 903
2014-09-16 | Office Supplies-Canon inkjet | Office Supplies |  | 1 | 80.91 | 80.91 | 903
2014-09-16 | Tissues, Coffee, Teabags, Oragic Tea, Milk | Small Tools |  | 1 | 51.55 | 51.55 | 903
2014-09-16 | Cart Hise Gard & Grow used to roll night line into | Small Tools |  | 1 | 72.71 | 72.71 | 903
2014-09-17 | Three Room Office, Male & Female Toilets Hired 11/9/14 - 30/9/14 | Building Facilites |  | 1 | 2734.4 | 2734.4 | 903
2014-09-17 | 2 x Ice Bags | Small Tools |  | 1 | 8 | 8 | 903
2014-09-17 | Office Supplies Kitchen Jars | Office Supplies |  | 1 | 3.64 | 3.64 | 903
2014-09-17 | Towels, Knifes, Forks and Dessert Spoons | Small Tools |  | 1 | 38.18 | 38.18 | 903
2014-09-18 | 30 Photo Copies, Single and Double Sided, Notebooks, Pens, Clipboards, Sheet Protectors, Tudor Letter clips, Bantex Binder, Letter Clip, File Dividers, Artline Pens, Hand Towel and Bantex Clipboard. | Office Supplies |  | 1 | 113.64 | 113.64 | 903
2014-09-19 | 80M of Mesh Panels, Blocks and Clamps | Temporary Fence |  | 1 | 2504 | 2504 | 903
2014-09-22 | Indoor Broom, Hasp and Stapler L/Duty, Dustpan and Broom, Screw N/Point, Flat Bar | Small Tools |  | 1 | 43.05 | 43.05 | 903
2014-09-22 | General signs & delineation for traffic control. | Signs - General |  | 1 | 730.32 | 730.32 | 903
2014-09-23 | Pre Assebled Steps and landing | Building Facilites |  | 1 | 111.6 | 111.6 | 903
2014-09-23 | Office Supplies - Envelopes 100PK | Office Supplies |  | 1 | 4.55 | 4.55 | 903
2014-09-25 | Folding tablel and Bookcase | Crib Facilities |  | 1 | 18.69 | 18.69 | 903
2014-09-25 | Hire of Office, Toilet Male & Female and Folding Platic Chairs | Crib Facilities |  | 1 | 1706.58 | 1706.58 | 903
2014-09-25 | Office Supplies - Ink Cartridges | Office Supplies |  | 1 | 60.92 | 60.92 | 903
2014-09-29 | GME Bonnet/Bracket, Antenna phone Spring Based | Small Tools |  | 1 | 171.64 | 171.64 | 903
2014-09-29 | Kamb express cup urn | Small Tools |  | 1 | 90 | 90 | 903
2014-09-30 | Portable Building Hired 31/8/14 - 30/9/14 | 10/14 Chip Seal |  | 1 | 516.74 | 516.74 | 903
2014-10-01 | 240Lt x 13 Wheelie Bin & 240Lt x 7 Recycling Wheelie Bin | Waste Removal |  | 1 | 132.3 | 132.3 | 903
2014-10-13 | Staminade Powder | Small Tools |  | 1 | 36.18 | 36.18 | 903
2014-10-20 | General signs & delineation for traffic control. 60, 80, reduce speed, road work ahead. do not overtake sign. | Signs - General |  | 1 | 1015.41 | 1015.41 | 903
2014-10-21 | Mop and Bucket Coffee, Teabags, | Small Tools |  | 1 | 54.16 | 54.16 | 903
2014-10-21 | General signs & delineation for traffic control. End of Road works and 60km | Signs - General |  | 1 | 188.76 | 188.76 | 903
2014-10-27 | Delivery of Ice on the 25/9/14 & 27/10/14 | Bulk Ice |  | 1 | 103.64 | 103.64 | 903
2014-10-27 | Tissues, & Soap | Small Tools |  | 1 | 18.51 | 18.51 | 903
2014-10-30 | Folding tablel and Bookcase & Delivery | Crib Facilities |  | 1 | 135 | 135 | 903
2014-11-01 | Pump out toilets block and waste disposal | Waste Removal |  | 1 | 340 | 340 | 903
2014-11-01 | Three Room Office, Male & Female Toilets Hired1/11/14 - 30/11/14 | Building Facilites |  | 1 | 1706.58 | 1706.58 | 903
2014-11-03 | 2 x 600 x 600 M/Mess Speed, 2 x Probable delay | Signs - General |  | 1 | 144.16 | 144.16 | 903
2014-11-04 | Ice, Cool Drink, Servettes, Cheese Slices, butter, lettuce, onion, tomato, Bread, coleslaw, oil tomato sauce and bbq sauce ect | Small Tools |  | 1 | 99.59 | 99.59 | 903
2014-11-17 | Milk, Sugar and Spray and Wipe | Small Tools |  | 1 | 21.22 | 21.22 | 903
2014-11-19 | International Coffee | Small Tools |  | 1 | 22 | 22 | 903
2014-12-01 | Three Room Office, Male & Female Toilets Hired 1/12/14 - 31/12/14 | Building Facilites |  | 1 | 1706.58 | 1706.58 | 903
2014-12-02 | .12 287-MFH Construction or Demolition | Waste Removal |  | 1 | 8.18 | 8.18 | 903
2014-12-06 | CRS Sugar and Retangular Atlantis | Small Tools |  | 1 | 14.67 | 14.67 | 903
2014-12-12 | Pump out toilets block and waste disposal | Waste Removal |  |  | 540 |  | 903
2014-12-12 | Deliver 20 Container from venables crossing to Taylors Beach Road | Float |  | 1 | 250 | 250 | 903
2014-12-16 | Credit on Three Room Office, Male & Female Toilets Hired 12/12/14-31/12/14 | Building Facilites |  | -1 | 255.4 | -255.4 | 903
2014-12-16 | Hire 6m x 3m 11/12/2014 - 31/12/2014 Moving fees to Taylors Beach Cleaning fees | Building Facilites |  | 1 | 1988.76 | 1988.76 | 903
2014-12-16 | Relocate to Taylors Rd | Temporary Fence |  | 1 | 1056 | 1056 | 903
2014-12-16 | Credit on Folding table | Crib Facilities |  | -1 | 3.68 | -3.68 | 903
2014-12-17 | File Dividers Multi Coloured | Office Supplies |  | 1 | 13.48 | 13.48 | 903
2015-01-01 | 240Lt x 13 Wheelie Bin & 240Lt x 7 Recycling Wheelie Bin | Waste Removal |  | 1 | 167.7 | 167.7 | 903
2015-01-01 | Three Room Office, Male & Female Toilets Hired 1/1/15-31/1/15 | Building Facilites |  | 1 | 1422 | 1422 | 903
2015-01-01 | Tea Bags. Staminade Powder and Garbage Bags | Small Tools |  | 1 | 16.12 | 16.12 | 903
2015-01-01 | Three Room Office, Male & Female Toilets Hired 1/2/15 - 28/2/15 | Building Facilites |  | 1 | 1621.08 | 1621.08 | 903
2015-01-01 | 2 x Ice Bags | Small Tools |  | 2 | 9.09 | 18.18 | 903
2015-01-01 | Credit Note for the hire of Building Facitily , Male & Female Toilets Hired 6/2/15 - 28/2/15 | Building Facilites |  | 1 | -1222.67 | -1222.67 | 903
2015-01-03 | 2 x Bep Side Road Closed and 1 x MMSG on side Road | Signs - General |  | 1 | 230.02 | 230.02 | 903
2015-01-06 | Delivery of Ice on the November / December | Bulk Ice |  | 1 | 198 | 198 | 903
2015-01-07 | Copy Paper and blue tack | Office Supplies |  | 1 | 26.55 | 26.55 | 903
2015-01-07 | Minimum charge for metered stand pipe hire | Waste Removal |  | 1 | 60 | 60 | 903
2015-01-09 | Commercial & Industrial Waste | Waste Removal |  | 1 | 132.727 | 132.727 | 903
2015-01-12 | Cake for Vaughan | Small Tools |  | 1 | 9.09 | 9.09 | 903
2015-01-12 | 23 Masonary Products | Small Tools |  | 1 | 21.23 | 21.23 | 903
2015-01-14 | Stamindade Powder | Small Tools |  | 1 | 9.09 | 9.09 | 903
2015-01-14 | Toilet paper | Small Tools |  | 1 | 21.91 | 21.91 | 903
2015-01-14 | Rehire 14 Units of Blocks and Rehire 31 Units of Clamps, Rehire of 22.5 Mesh Panels | Temporary Fence |  | 1 | 56.25 | 56.25 | 903
2015-01-15 | Party Ice | Ice |  | 1 | 20 | 20 | 903
2015-01-15 | 2 x Party Ice | Small Tools |  | 1 | 7.27 | 7.27 | 903
2015-01-19 | Clip folder | Office Supplies |  | 1 | 3.59 | 3.59 | 903
2015-01-21 | Rehire 14 Units of Blocks and Rehire 31 Units of Clamps, Rehire of 22.5 Mesh Panels | Temporary Fence |  | 1 | 22.5 | 22.5 | 903
2015-01-21 | Bandex Binder | Office Supplies |  | 1 | 7.23 | 7.23 | 903
2015-02-03 | Commercial & Industrial Waste | Waste Removal |  | 1 | 314.32 | 314.32 | 903
2015-02-04 | Ìce`x 2 | Small Tools |  | 1 | 7.27 | 7.27 | 903
2015-02-04 | Deliver 20 Container from Taylors Beach Road to Andy Roadhouse | Float |  | 1 | 200 | 200 | 903
2015-02-09 | Rehire 1 Units of Blocks and Rehire 1 Units of Clamps, Rehire of 15 Mesh Panels | Temporary Fence |  | 1 | 720 | 720 | 903
2015-02-12 | The Cleaning & Sanitise of Building and Toilet. Transport of Both back to Ausco. | Building Facilites |  | 1 | 1600 | 1600 | 903
2015-02-12 | Canon Combo Pack | Office Supplies |  | 1 | 44.54 | 44.54 | 903
2015-02-16 | Rehire 14Units of Blocks and Rehire 14 Units of Clamps, Rehire of14 Mesh Panels | Temporary Fence |  | 1 | 59.4 | 59.4 | 903
2015-02-16 | Rehire 14Units of Blocks and Rehire 14 Units of Clamps, Rehire of14 Mesh Panels | Temporary Fence |  | 1 | 79.2 | 79.2 | 903
2015-02-17 | HP Black Ink Cartridge | Office Supplies |  | 1 | 35.41 | 35.41 | 903
2015-02-18 | Purchase of Sand. | Waste Removal |  | 1 | 49.1 | 49.1 | 903
2015-02-18 | A4 Fil Divider | Office Supplies |  | 1 | 3.39 | 3.39 | 903
2015-02-25 | Trasport of 140H Grader from Townsville to Ingham | Float |  | 1 | 975 | 975 | 903
2015-02-27 | Trasport of Tractor Stabiliser from Ingham to Proserpine. | Float |  | 1 | 1750 | 1750 | 903
2015-03-02 | Pavement Markers | Signs - General |  | 1 | 10.88 | 10.88 | 903
2015-03-03 | Commercial & Industrial Waste | Waste Removal |  | 1 | 10.91 | 10.91 | 903
2015-03-07 | Pump out toilets block and waste disposal | Waste Removal |  | 1 | 300 | 300 | 903
2015-03-30 | Crane to travel to Taylors Beach to load abultion dongas and site office | Float |  | 1 | 550 | 550 | 903
2015-03-30 | Crane to travel to venables crossing and load and position of 3 Dongas | Float |  | 1 | 440 | 440 | 903
2015-03-30 | Transport of 30T Crane to Transport 30T Excavator and Grader from Venables Crossing to Balck Beach Road | Float |  | 1 | 1570 | 1570 | 903
2015-03-30 | Hire of Float to transport grader from Taylors Beach Road to Railway Statione area. | Float |  | 1 | 250 | 250 | 903
| Subtotal for 903 |  |  |  |  | 30417.647
Portfolio WBS 904
2014-08-27 | Construction Risk Insurance | Insurance |  | 1 | 7014.04 | 7014.04 | 904
2014-09-17 | Hard Cooler Eskys | Small Tools |  | 1 | 190.8 | 190.8 | 904
2014-09-17 | Damage Waiver on Three Room Office and Toilets | Damage Waiver |  | 1 | 119.47 | 119.47 | 904
2014-09-23 | Damage Waiver on Pre-Assembled Steps and Landing | Damage Waiver |  | 1 | 15.62 | 15.62 | 904
2014-09-26 | Damage Waiver on 13T Smoothdrum Roller | Insurance |  | 1 | 50.4 | 50.4 | 904
2014-09-26 | Damage Waiver on Portable Build | Insurance |  | 1 | 61.09 | 61.09 | 904
2014-09-30 | Damage Waiver on Traffic Lights | Insurance |  | 1 | 36 | 36 | 904
2014-09-30 | Damage Waiver on Road Barriers | Insurance |  | 1 | 60.05 | 60.05 | 904
2014-09-30 | Damage Waiver on Road Barriers Hired 30/9/14 - 31/10/2014 | Insurance |  | 1 | 34.28 | 34.28 | 904
2014-10-14 | Construction Risk Insurance | Insurance |  | 1 | 386.87 | 386.87 | 904
2014-10-31 | Damage Waiver on 9T Vibrating Multityre Roller Hired 1/10/14 - 31/10/14 | Insurance |  | 1 | 662.4 | 662.4 | 904
2014-10-31 | Damage Waiver on Traffic Lights Hired 30/9/14 - 31/10/14 | Insurance |  | 1 | 186 | 186 | 904
2014-10-31 | Damage Waiver on 13T Smoothdrum Roller Hired 30/10/14- 31/10/14 | Insurance |  | 1 | 33.6 | 33.6 | 904
2014-10-31 | Damage Waiver on 13T Smooth Drum Roller Hired 30/9/14 - 31/10/14 | Insurance |  | 1 | 386.4 | 386.4 | 904
2014-10-31 | Damage Waiver on Traffic Lights Hired 20/10/14 - 31/10/14 | Insurance |  | 1 | 72 | 72 | 904
2014-11-27 | Damage Waiver on Traffic Lights Hired 31/10/14 - 27/11/14 | Insurance |  | 1 | 156 | 156 | 904
2014-11-30 | Damage Waiver on 13T Smoothdrum Roller Hired 17/11/14 - 30/11/14 | Insurance |  | 1 | 151.2 | 151.2 | 904
2014-11-30 | Damage Waiver on Traffic Lights Hired 1/12/2014-31/12/2014 | Insurance |  | 1 | 132 | 132 | 904
2014-11-30 | Insurance on 9Tonne Vibrating Multityre Roller Hired 31/10/14 -30/11/14 | Insurance |  | 1 | 576 | 576 | 904
2014-11-30 | Damage Waiver on 13T Smoothdrum Roller Hired 31/10/14 - 30/11/14 | Insurance |  | 1 | 336 | 336 | 904
2014-11-30 | Damage Waiver on Traffic Lights Hired 31/10/14 - 30/11/14 | Insurance |  | 1 | 180 | 180 | 904
2014-12-04 | Insurance on 9Tonne Vibrating Multityre Roller Hired 30/11/14 - 4/12/14 | Insurance |  | 1 | 86.4 | 86.4 | 904
2014-12-16 | Damage Waiver on Toilets & office buildings | Damage Waiver |  | 1 | 31.05 | 31.05 | 904
2014-12-16 | Credit on Damage Waiver on Toilets & office buildings | Damage Waiver |  | -1 | 35.74 | -35.74 | 904
2014-12-16 | Credit on Damage Waiver on folding table | Damage Waiver |  | -1 | 0.52 | -0.52 | 904
2014-12-31 | Damage Waiver on 13T Smoothdrum Roller Hired 30/11/2014-31/12/2014 | Insurance |  | 1 | 168 | 168 | 904
2015-01-01 | Damage Waiver on Toilets & office buildings | Damage Waiver |  | 1 | 199.08 | 199.08 | 904
2015-01-31 | Damage Waiver on 13T Smoothdrum Roller Hired 31/12/2014 - 31/01/15 | Insurance |  | 1 | 268.8 | 268.8 | 904
2015-01-31 | Damage Waiver on Traffic Lights | Insurance |  | 1 | 150 | 150 | 904
2015-02-28 | Damage Waiver on 13T Smoothdrum Roller Hired 16/2/15 - 27/2/15 | Insurance |  | 1 | 168 | 168 | 904
2015-02-28 | Damage Waiver on Traffic Lights | Insurance |  | 1 | 114 | 114 | 904
2015-02-28 | Damage Waiver on Vibrating Multi Tyre Roller Hired 17/2/15 - 27/2/15 | Multi Tyre Roller |  | 1 | 172.8 | 172.8 | 904
| Subtotal for 904 |  |  |  |  | 12162.09
Portfolio WBS 905
2014-09-12 | Key Cutting for 2/7 Abbott Street | Key Cutting |  | 1 | 23.64 | 23.64 | 905
2014-09-16 | Morning Fresh and Hand wash | Small Tools |  | 1 | 36.18 | 36.18 | 905
2014-09-16 | 1 x Reducing BSP Socket and Union Comp S/Tite | Small Tools |  | 1 | 7.59 | 7.59 | 905
2014-09-16 | Connetor Philmac, Elbow BSP, Reducing Nippple, Philmac Connector and Wrench Pipe | Small Tools |  | 1 | 77.85 | 77.85 | 905
2014-09-16 | Quickbit set and Water Cooler | Small Tools |  | 1 | 161.79 | 161.79 | 905
2014-09-16 | Morning Fresh and Hand wash | Small Tools |  | 1 | 29.01 | 29.01 | 905
2014-09-16 | Socket Reducing BSP and Comp | Small Tools |  | 1 | 7.59 | 7.59 | 905
2014-09-17 | Marking Fluro, Nut Nyloc, Nuts and Bolts, Screw L/Thread, Clip Saddle, Rubber Mat, Rubber Adjustable Jet, Mat Ultimate, Super Wipes and Garbage Bags. | Small Tools |  | 1 | 191.02 | 191.02 | 905
2014-09-17 | Office Supplies- Document Trays Storage Trays | Office Supplies |  | 1 | 21 | 21 | 905
2014-09-17 | 3 x Rapid Concrete 20 kg Mix | Concrete Mix |  | 1 | 31.06 | 31.06 | 905
2014-09-18 | 6 x Support Shelf Plastic Metal Pins | Small Tools |  | 1 | 18.08 | 18.08 | 905
2014-09-26 | Photo Copy Paper | Office Supplies |  | 1 | 21.33 | 21.33 | 905
2014-09-27 | ADPT FME To Telstra 4G USB Modem | Small Tools |  | 1 | 15.41 | 15.41 | 905
2014-09-29 | Shovels, Cable Ties, Concrete Pliet, Wrenchs, Ulitily Knife, Screwdriver and Toolbox | Small Tools |  | 1 | 239.71 | 239.71 | 905
2014-10-02 | Office Supplies - Black Retractable and Adhesive notes. | Office Supplies |  | 1 | 5 | 5 | 905
2014-10-08 | Ironing Board W/Cpver amd Fam Pedestal | Small Tools |  | 1 | 41.44 | 41.44 | 905
2014-10-09 | Foldback Clip, Clopfolder and Blue Tac | Office Supplies |  | 1 | 16.3 | 16.3 | 905
2014-10-09 | Out Door Broom | Small Tools |  | 1 | 8.18 | 8.18 | 905
2014-10-09 | 63 x Bassine Yard Broom and 50 Garden Stakes | Small Tools |  | 1 | 335.88 | 335.88 | 905
2014-10-09 | Office Supplies 3 x Uniball Signo | Office Supplies |  | 1 | 11.37 | 11.37 | 905
2014-10-09 | Birthday Cake | Small Tools |  | 1 | 14.91 | 14.91 | 905
2014-10-11 | Office Supplies Whiteboard Markers | Office Supplies |  | 1 | 4.96 | 4.96 | 905
2014-10-11 | Gree Starplug, Masonry Drill, Screws | Small Tools |  | 1 | 15.36 | 15.36 | 905
2014-10-13 | Ink Cartridges, Mechanical Pencil and Display Files. | Office Supplies |  | 1 | 84.75 | 84.75 | 905
2014-10-14 | Ink Cartridges, Mechanical Pencil and Display Files. | Office Supplies |  | 1 | 28.6 | 28.6 | 905
2014-10-14 | 2 x Gal Cap | Small Tools |  | 2 | 1.1 | 2.2 | 905
2014-10-14 | Petrol Caps | Small Tools |  | 1 | 1.36 | 1.36 | 905
2014-10-14 | Key Cuts and Key Tags | Small Tools |  | 1 | 5.16 | 5.16 | 905
2014-10-18 | Spare Jocke | Small Tools |  | 1 | 11.45 | 11.45 | 905
2014-10-18 | Flat Washer, Nuts & Bolts, Nyloc Nuts | Small Tools |  | 1 | 12.19 | 12.19 | 905
2014-10-19 | Pens and Corrector Tape | Office Supplies |  | 1 | 26.86 | 26.86 | 905
2014-10-20 | Key Cuts and Key Tags | Small Tools |  | 1 | 24.16 | 24.16 | 905
2014-10-20 | CSR Sugar | Small Tools |  | 1 | 2.55 | 2.55 | 905
2014-10-21 | Cup Hooks | Small Tools |  | 1 | 6.41 | 6.41 | 905
2014-10-27 | 1 Mush HD ZP Nuts & Bolts | Small Tools |  | 1 | 4 | 4 | 905
2014-10-27 | Key Cuts and Key Tags | Small Tools |  | 1 | 9.47 | 9.47 | 905
2014-10-29 | Floats for footvalve of pump | Small Tools |  | 1 | 9 | 9 | 905
2014-10-29 | General Rope | Small Tools |  | 1 | 11.36 | 11.36 | 905
2014-11-03 | Photocopies B & W A4 Double Sided | Office Supplies |  | 1 | 12.15 | 12.15 | 905
2014-11-04 | Tape Seal & Joining Sil | Small Tools |  | 1 | 18.11 | 18.11 | 905
2014-11-04 | Double A4 Pater and Magazine rack | Office Supplies |  | 1 | 45.38 | 45.38 | 905
2014-11-11 | Starter Fluoro | Small Tools |  | 1 | 2.26 | 2.26 | 905
2014-11-25 | Copy Paper and Cartridge Inks | Office Supplies |  | 1 | 87.54 | 87.54 | 905
2014-12-01 | Bulk GP / GB Cement x 7 | Cement |  | 1 | 60.39 | 60.39 | 905
2014-12-01 | Mortar Mix 20Kg x 3 | Concrete Mix |  | 1 | 31.06 | 31.06 | 905
2014-12-04 | 3 x Tie Wire | Small Tools |  | 1 | 28.77 | 28.77 | 905
2014-12-09 | 1 x 80mm x 50mm Socket, 1x Adapt Camlock and 2.5 QRT Ring x 2M BSP | Small Tools |  | 1 | 213.67 | 213.67 | 905
2014-12-09 | 7L Sprayer Pressure for the Paveline Truck | Small Tools |  | 1 | 22.73 | 22.73 | 905
2014-12-10 | Bosch Measuring Tool | Small Tools |  | 1 | 142.5 | 142.5 | 905
2014-12-11 | Yellow Brick Line x 2, PH Soil Test Kit, & 8m Tape Measures x | Small Tools |  | 1 | 43.14 | 43.14 | 905
2014-12-12 | Powerboard 6 Way and Mortar Mix | Small Tools |  | 1 | 20.71 | 20.71 | 905
2014-12-12 | 8 x 20Kg Cement | Small Tools |  | 1 | 69.02 | 69.02 | 905
2014-12-15 | 1 x Accent Quickspray and Screws | Small Tools |  | 1 | 32.37 | 32.37 | 905
2015-01-09 | Chain Galv and D Shackle | Small Tools |  | 1 | 235.2 | 235.2 | 905
2015-01-12 | Airfilter, Spark Plug and Airfilter oil | Small Tools |  | 1 | 118.09 | 118.09 | 905
2015-01-14 | Specs Safety Icon Clear, Wire Tie Belt and shield face tradesman | Small Tools |  | 1 | 147.62 | 147.62 | 905
2015-02-03 | 3m Alum Screed and Diamond Blade | Small Tools |  | 394.68 | 1 | 394.68 | 905
2015-02-04 | Cut off Disc | Small Tools |  | 1 | 8.91 | 8.91 | 905
2015-02-07 | Plow B & N x 10 | Small Tools |  | 1 | 29.09 | 29.09 | 905
2015-02-19 | Utilux Metal Plug 7 Pin | Small Tools |  | 1 | 16 | 16 | 905
2015-02-23 | Additive for the Flexihire Roller that could not start | Small Tools |  | 1 | 16.35 | 16.35 | 905
2015-02-23 | 3 x Harvest Hats | Small Tools |  | 1 | 43.18 | 43.18 | 905
| Subtotal for 905 |  |  |  |  | 3413.1
Portfolio WBS 907
2014-09-08 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 907
2014-09-08 | Allciv - Stabilising Crew | Labour | hr | 8.5 | 54.58 | 463.93 | 907
2014-09-08 | Labour Hire | Labour | hr | 10.5 | 42.72 | 448.56 | 907
2014-09-09 | Allciv - Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 907
2014-09-09 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 907
2014-09-09 | Frieght 20FT 6T Container from Nicholl St Proserpine Delivered to Lannercost Benables Crossing Ingham. | Float |  | 1954.55 | 1 | 1954.55 | 907
2014-09-09 | Labour Hire | Labour | hr | 10 | 42.72 | 427.2 | 907
2014-09-09 | Allciv - Stabilising Crew | Labour | hr | 10 | 54.58 | 545.8 | 907
2014-09-10 | Allciv - Labour Hire | Labour | hr | 13 | 42.72 | 555.36 | 907
2014-09-10 | Allciv - Stabilising Crew | Labour | hr | 13 | 54.58 | 709.54 | 907
2014-09-10 | Labour Hire | Labour | hr | 13 | 42.72 | 555.36 | 907
2014-09-10 | Allciv - Site Administration | Labour | hr | 13 | 42.72 | 555.36 | 907
2014-09-10 | Water Cart Hire | Water Cart - Hire | hr | 2 | 90 | 180 | 907
2014-09-10 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 13 | 42.79 | 556.27 | 907
2014-09-11 | Backhoe Hire | Backhoe | hr | 3 | 92.5 | 277.5 | 907
2014-09-11 | Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 907
2014-09-11 | Allciv - Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 907
2014-09-11 | Allciv - Site Administration | Labour | hr | 9 | 42.72 | 384.48 | 907
2014-09-11 | Water Cart Hire | Water Cart - Hire | hr | 2 | 90 | 180 | 907
2014-09-11 | Allciv - Stabilising Crew | Labour | hr | 9 | 54.58 | 491.22 | 907
2014-09-12 | Backhoe Hire | Backhoe | hr | 6 | 92.5 | 555 | 907
2014-09-13 | Trasport of Furniture from Proserpine to Ingham and back to Proserpine | Float |  | 1 | 702 | 702 | 907
2014-09-14 | Transport of Tractor & Profiler from Nicol Street to L & W repairs Challands Street Ingham | Float |  | 1 | 1865 | 1865 | 907
2014-09-15 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 907
2014-09-16 | Labour | Labour | hr | 8.5 | 45 | 382.5 | 907
2014-09-16 | Backhoe Hire | Backhoe | hr | 6 | 92.5 | 555 | 907
2014-09-16 | ATS Labour Hire | Labour | hr | 4.75 | 46.85 | 222.5375 | 907
2014-09-16 | ATS Labour Hire | Labour | hr | 4.75 | 46.85 | 222.5375 | 907
2014-09-16 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 907
2014-09-16 | Allciv - Stabilising Crew | Labour | hr | 8.5 | 54.58 | 463.93 | 907
2014-09-16 | Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 907
2014-09-16 | Allciv - Site Administration | Labour | hr | 8.5 | 42.72 | 363.12 | 907
2014-09-16 | Allciv - Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 907
2014-09-17 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 907
2014-09-17 | Labour | Labour | hr | 8 | 45 | 360 | 907
2014-09-17 | ATS Labour Hire | Labour | hr | 8.5 | 46.85 | 398.225 | 907
2014-09-17 | ATS Labour Hire | Labour |  | 8.5 | 46.85 | 398.225 | 907
2014-09-17 | Allciv - Site Administration | Labour | hr | 10.75 | 42.72 | 459.24 | 907
2014-09-17 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-09-17 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-09-18 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 907
2014-09-18 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-09-18 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-09-18 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 907
2014-09-18 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 907
2014-09-18 | Labour | Labour | hr | 8 | 45 | 360 | 907
2014-09-21 | Travel Allowance for Jeffrey Loder and Steven Loder | Travel Allowance | hr | 6 | 20 | 120 | 907
2014-09-21 | Allciv - Stabilising Crew | Labour | hr | 5.5 | 54.58 | 300.19 | 907
2014-09-22 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 907
2014-09-22 | ATS Labour Hire | Labour | hr | 3 | 42.6 | 127.8 | 907
2014-09-22 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 907
2014-09-22 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 907
2014-09-22 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 907
2014-09-22 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 907
2014-09-22 | Labour | Labour | hr | 8 | 45 | 360 | 907
2014-09-22 | Labour Hire | Labour | hr | 8.5 | 42.72 | 363.12 | 907
2014-09-22 | Steel Conduit, T & E Conduit, saddles, screw adapto, lockring and dager tape, rapid set, circuit breaker HD Conduit and coupling. | Conduit |  | 1 | 1837.07 | 1837.07 | 907
2014-09-23 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 907
2014-09-23 | Allciv - Stabilising Crew | Labour | hr | 2.5 | 54.58 | 136.45 | 907
2014-09-23 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 907
2014-09-23 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 907
2014-09-23 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 907
2014-09-23 | Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 907
2014-09-24 | Labour | Labour | hr | 5.5 | 45 | 247.5 | 907
2014-09-24 | Allciv - Labour Hire | Labour | hr | 2.5 | 42.72 | 106.8 | 907
2014-09-24 | Allciv - Stabilising Crew | Labour | hr | 6.5 | 54.58 | 354.77 | 907
2014-09-24 | Backhoe Hire | Backhoe | hr | 2.5 | 45 | 112.5 | 907
2014-09-24 | ATS Labour Hire | Labour | hr | 2.5 | 42.6 | 106.5 | 907
2014-09-24 | Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-09-29 | Key Cutting and Key Tag | Small Tools |  | 1 | 18.95 | 18.95 | 907
2014-09-29 | GME Microphine to suit | Small Tools |  | 1 | 41.81 | 41.81 | 907
2014-10-29 | GME Microphone | Small Tools |  | 1 | 41.81 | 41.81 | 907
2014-10-31 | Transport of 140M Grader | Float |  | 1 | 580 | 580 | 907
2014-11-13 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-11-13 | Allciv - Labour Hire | Labour | hr | 8 | 42.72 | 341.76 | 907
2014-11-16 | Transport of 120H Grader | Float |  | 1 | 2420 | 2420 | 907
2014-11-16 | Transport of 279 & Attachments | Float |  | 1 | 1315 | 1315 | 907
2014-12-08 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 907
2014-12-11 | 4 x Metric Poly, 1 x Plumber Tape, Bush, Elbow Poly | Small Tools |  | 1 | 30.73 | 30.73 | 907
2014-12-11 | Move to Taylors Beach | Crane 20T |  | 1 | 900 | 900 | 907
2014-12-12 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 907
2014-12-12 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 907
2014-12-12 | Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 907
2014-12-12 | ATS Labour Hire | Labour |  | 7.5 | 49.7 | 372.75 | 907
2014-12-12 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 907
2014-12-16 | Disconnect power at Venables Rd & reconnect at Taylors Beach Rd. Cable; conduit; adaptors; couplings; wire; brackets; labour etc | Electrician |  | 1 | 2125.2 | 2125.2 | 907
2015-01-12 | N20 Concrete Includes Minumum Freight Chg and Enviromental Levey | N20 | each | 2.6 | 307.192 | 798.6992 | 907
2015-02-03 | Allciv - Stabilising Crew | Labour | hr | 2 | 54.58 | 109.16 | 907
2015-02-04 | Allciv - Stabilising Crew | Labour | hr | 4 | 54.58 | 218.32 | 907
2015-02-10 | Disconnect power to site huts and isolate cables | Electrician |  | 1 | 280 | 280 | 907
2015-02-16 | Labour Hire | Labour | hr | 9 | 42.72 | 384.48 | 907
2015-02-16 | Supply 50mm HD Conduit | Conduit |  | 1 | 238 | 238 | 907
2015-02-16 | ATS Labour Hire | Labour |  | 9.5 | 49.7 | 472.15 | 907
2015-02-17 | Labour Hire | Labour | hr | 11 | 42.72 | 469.92 | 907
2015-03-04 | Transport of 20Ft Container | Float |  | 1 | 1200 | 1200 | 907
2015-03-08 | Transport of 16T Multi Tyre Roller from Neame Street Ingham to Flexi Hired | Float |  | 1 | 540 | 540 | 907
2015-03-08 | Transport of 13T Smooth Drum Roller from Neame Street Ingham to Flexi Hired | Float |  | 1 | 540 | 540 | 907
| Subtotal for 907 |  |  |  |  | 43545.1542
Portfolio WBS 910
2014-11-27 | Allciv - Stabilising Crew | Labour | hr | 6.5 | 54.58 | 354.77 | 910
2014-11-28 | Allciv - Labour Hire | Labour | hr | 4 | 42.72 | 170.88 | 910
2014-11-28 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 910
2014-12-01 | Allciv - Stabilising Crew | Labour | hr | 11.5 | 54.58 | 627.67 | 910
2014-12-02 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 910
2014-12-02 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 8 | 42.79 | 342.32 | 910
2014-12-02 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 910
2014-12-02 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 910
2014-12-02 | Allciv - Stabilising Crew | Labour | hr | 8 | 54.58 | 436.64 | 910
2014-12-02 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 910
2014-12-02 | Allciv - New Holland Grader | New Holland | hr | 1 | 35 | 35 | 910
2014-12-02 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 910
2014-12-05 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 910
2014-12-05 | Allciv - Labour Hire | Labour | hr | 1.5 | 42.72 | 64.08 | 910
2014-12-06 | Labour Hire | Labour | hr | 4.5 | 42.72 | 192.24 | 910
2014-12-06 | Allciv - Stabilising Crew | Labour | hr | 7 | 54.58 | 382.06 | 910
2014-12-06 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 910
2014-12-06 | ATS Labour Hire | Labour |  | 7 | 49.7 | 347.9 | 910
2014-12-06 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 910
2014-12-06 | Allciv - Labour Hire | Labour | hr | 7 | 42.72 | 299.04 | 910
2014-12-06 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 7 | 42.79 | 299.53 | 910
2014-12-10 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 910
2015-01-30 | Backhoe Hire | Backhoe | hr | 2 | 92.5 | 185 | 910
2015-02-03 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 910
2015-02-03 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 910
2015-02-03 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 910
2015-02-04 | Allciv - Stabilising Crew | Labour | hr | 3 | 54.58 | 163.74 | 910
2015-02-04 | CAT297C MTL - No Operator | CAT297 | hr | 6 | 35 | 210 | 910
2015-02-04 | ATS Labour Hire | Labour | hr | 6 | 42.6 | 255.6 | 910
2015-02-05 | CAT297C MTL - No Operator | CAT297 | hr | 3 | 35 | 105 | 910
2015-02-05 | Allciv - Stabilising Crew | Labour | hr | 4.5 | 54.58 | 245.61 | 910
2015-02-05 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 910
2015-02-06 | Allciv - Stabilising Crew | Labour | hr | 11.5 | 54.58 | 627.67 | 910
2015-02-06 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 4.5 | 42.79 | 192.555 | 910
2015-02-06 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 910
2015-02-09 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 6 | 42.79 | 256.74 | 910
2015-02-21 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 9.5 | 42.79 | 406.505 | 910
2015-02-21 | ATS Labour Hire | Labour | hr | 4 | 46.85 | 187.4 | 910
2015-02-21 | Labour Hire | Labour | hr | 9.5 | 42.72 | 405.84 | 910
2015-02-21 | ATS Labour Hire | Labour | hr | 4 | 42.6 | 170.4 | 910
2015-02-28 | Bobcat Hire | Bobcat Hire |  | 6 | 35 | 210 | 910
2015-03-01 | Bobcat Hire | Bobcat Hire |  | 5 | 35 | 175 | 910
2015-03-02 | Allciv - Labour Hire | Labour | hr | 3.5 | 42.72 | 149.52 | 910
2015-03-02 | Bobcat Hire | Bobcat Hire |  | 4.5 | 35 | 157.5 | 910
2015-03-02 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 3 | 42.79 | 128.37 | 910
2015-03-03 | ATS Labour Hire | Labour | hr | 5 | 42.6 | 213 | 910
2015-03-03 | Bulk GP / GB Cement x 6, Natural Broom and Mineral Turps | Cement |  | 1 | 100.16 | 100.16 | 910
2015-03-03 | ATS Labour Hire | Labour |  | 5 | 49.7 | 248.5 | 910
2015-03-03 | Backhoe Hire | Backhoe | hr | 1.5 | 92.5 | 138.75 | 910
2015-03-03 | Labour Hire | Excavator - 25T | hr | 13 | 45 | 585 | 910
2015-03-03 | Bobcat Hire- Labour Hire | Bobcat Hire |  | 13 | 35 | 455 | 910
2015-03-03 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 954.46 | 910
2015-03-04 | ATS Labour Hire | Labour |  | 7 | 49.7 | 347.9 | 910
2015-03-04 | ATS Labour Hire | Labour | hr | 6.5 | 46.85 | 1240.795 | 910
2015-03-04 | ATS Labour Hire | Labour | hr | 6.5 | 42.6 | 276.9 | 910
2015-03-04 | Bobcat Hire | Bobcat Hire |  | 7 | 35 | 245 | 910
2015-03-04 | Allciv - Labour Hire | Labour | hr | 5 | 42.72 | 213.6 | 910
2015-03-04 | Allciv - Tipper (Mack Truck) | Tipper - Allciv | hr | 13 | 42.79 | 556.27 | 910
2015-03-04 | Labour Hire | Labour | hr | 6 | 42.72 | 256.32 | 910
2015-03-04 | Bucket Plastic, Bannister Brush, Dustpan Set and Concrete Mix | Small Tools |  | 1 | 44.87 | 44.87 | 910
2015-03-04 | Backhoe Hire | Backhoe | hr | 5 | 92.5 | 462.5 | 910
2015-03-05 | Labour Hire | Excavator - 25T | hr | 11 | 45 | 495 | 910
2015-03-05 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 1813.465 | 910
2015-03-05 | Trasport of Bobcat in Mack from Ingham to Prossie and Return | Bobcat Hire |  | 12 | 35 | 420 | 910
2015-03-05 | ATS Labour Hire | Labour | hr | 9.5 | 42.6 | 404.7 | 910
2015-03-05 | ATS Labour Hire | Labour |  | 9.5 | 49.7 | 472.15 | 910
2015-03-06 | Drive Jacintas Ute from Ingam to Prossie | Bobcat Hire |  | 4.5 | 35 | 157.5 | 910
2015-03-18 | Wages Dive Iveco from Prosserpine to Mackay and Bobcat Hire | Bobcat Hire |  | 3 | 95 | 285 | 910
2015-03-18 | Dive Iveco from Prosserpine to Mackay and Bicbcat Hire | Bobcat Hire |  | 4 | 35 | 140 | 910
| Subtotal for 910 |  |  |  |  | 21497.045
Portfolio WBS 911
2014-09-03 | Accommodation & Meals | Accommodation |  | 1 | 293.64 | 293.64 | 911
2014-09-09 | 1/10 Abott Street Ingham | Accommodation |  | 1 | 1470 | 1470 | 911
2014-09-09 | 3/40 Abbott Street Ingham | Accommodation |  | 1 | 1680 | 1680 | 911
2014-09-09 | 2/11 Abbott Street Ingham | Accommodation |  | 1 | 1500 | 1500 | 911
2014-09-09 | 2/7 Abbott Street Ingham | Accommodation |  | 1 | 1380 | 1380 | 911
2014-09-12 | Accommodation & Meals | Accommodation |  | 1 | 550 | 550 | 911
2014-09-15 | 51 MCLllwraith Street Ingham | Accommodation |  | 1 | 3600 | 3600 | 911
2014-09-16 | Meals and Drinks | Accommodation |  | 1 | 15.91 | 15.91 | 911
2014-09-16 | Phik meals | Accommodation |  | 1 | 39.09 | 39.09 | 911
2014-09-17 | Accommadation Jude | Accommodation |  | 1 | 50 | 50 | 911
2014-09-17 | Meals and Drinks | Accommodation |  | 1 | 33.18 | 33.18 | 911
2014-09-24 | Electricity Account for 1/10 Abbott Street Billing Period 25/9/14-23/12/14 | Electrictiy |  | 1 | 383.15 | 383.15 | 911
2014-09-26 | Electricity Account for 2/7 Abbott Street, Igham Billing period 10/9/14 - 25/9/14 | Electrictiy |  | 1 | 48.13 | 48.13 | 911
2014-09-26 | Accommodation | Accommodation |  | 1 | 218.18 | 218.18 | 911
2014-09-26 | Electricity Account for 1/10 Abbott Street Billing Period 23/12/14 - 4/3/15 | Electrictiy |  | 1 | 295.24 | 295.24 | 911
2014-09-26 | Electricity Account for 1/10 Abbott Street Billing Period 15/9/14 - 25/9/14 | Electrictiy |  | 1 | 27.63 | 27.63 | 911
2014-09-29 | 1/13 Palm Avenue | Accommodation |  | 1 | 540 | 540 | 911
2014-09-30 | Electricity Account for 2/11 Palmer Street Ingham | Electrictiy |  | 1 | 89.09 | 89.09 | 911
2014-09-30 | Dinner & Drinks | Accommodation |  | 1 | 22.73 | 22.73 | 911
2014-10-07 | 4 Weeks Mcllwrath, 3/40 Hardy and 2/11 Palmer Street Ingham | Accommodation |  | 1 | 4520 | 4520 | 911
2014-10-07 | 1/10 Abott Street Ingham | Accommodation |  | 1 | 980 | 980 | 911
2014-10-08 | Electricity Account for 2/7 Abbott Street, Igham Billing period 25/9/14 - 3/10/14 | Electrictiy |  | 1 | 62.84 | 62.84 | 911
2014-10-19 | Accommodation-Judith | Accommodation |  | 1 | 218.18 | 218.18 | 911
2014-10-19 |  | Accommodation |  | 1 | 218.18 | 218.18 | 911
2014-10-29 | 2/7 Abbott Street Ingham | Accommodation |  | 1 | 230 | 230 | 911
2014-11-12 | 1/13 Palm Avenue | Accommodation |  | 1 | 540 | 540 | 911
2014-11-12 | 1/19 Palm Avenue | Accommodation |  | 1 | 540 | 540 | 911
2014-11-12 | 1/10 Abott Street Ingham | Accommodation |  | 1 | 490 | 490 | 911
2014-11-17 | Steve & Zac Accomadaton | Accommodation |  | 1 | 412.73 | 412.73 | 911
2014-11-20 | Electricity Account for3/40 Hardy Street, Igham Billing period 10/9/14 - 19/11/14 | Electrictiy |  | 1 | 307.14 | 307.14 | 911
2014-11-21 | 1/19 Palm Avenue | Accommodation |  | 1 | 540 | 540 | 911
2014-11-21 | 1/10 Abott Street Ingham 23/10/14 - 5/11/14 | Accommodation |  | 1 | 490 | 490 | 911
2014-11-25 | Mcllwrath, 3/40 Hardy and 2/11 Palmer Street Ingham 51 MCLllwraith Street Ingham 2/11 Abbott Street Ingham 1/13 Palm Street. 4/8 Palmer Street, 1/10 Abbott Street, 1/19 Palmer Street. | Accommodation |  | 1 | 9460 | 9460 | 911
2014-11-27 | 51 MCLllwraith Street Ingham | Accommodation |  | 1 | 2340 | 2340 | 911
2014-12-01 | 1/10 Abott Street Ingham 18/12/14 - 31/12/14 | Accommodation |  | 1 | 490 | 490 | 911
2014-12-05 | 1/19 Palm Avenue | Accommodation |  | 1 | 1080 | 1080 | 911
2014-12-05 | 1/13 Palm Avenue | Accommodation |  | 1 | 1080 | 1080 | 911
2014-12-08 | 51 MCLllwraith Street Ingham | Accommodation |  | 1 | 942.85 | 942.85 | 911
2014-12-17 | 2/11 Mcllwrath, 3/40 Hardy | Accommodation |  | 1 | 1590 | 1590 | 911
2014-12-17 | 1/13 Palm Avenue & 1/19 Palm Terrace | Accommodation |  | 1 | 1080 | 1080 | 911
2014-12-24 | 1/10 Abott Street Ingham 1/1/15-14/1/15 | Accommodation |  | 1 | 490 | 490 | 911
2014-12-29 | Electricity Account for 2/11 Palmer Street Ingham | Electrictiy |  | 1 | 601.36 | 601.36 | 911
2015-01-06 | Electricity Account for 49 MCilwraith Street Ingham Billing Period 25/10/14 - 24/12/14 | Electrictiy |  | 1 | 183.22 | 183.22 | 911
2015-01-07 | 2/11 Mcllwrath, 3/40 Hardy | Accommodation |  | 1 | 1060 | 1060 | 911
2015-01-29 | Electricity Account for 1/19 Palmer Street Ingham | Electrictiy |  | 1 | 870.77 | 870.77 | 911
2015-01-29 | Electricity Account for 1/13 Palmer Street Ingham billing period 27/10/14 - 27/01/15 | Electrictiy |  | 1 | 739.9 | 739.9 | 911
2015-02-20 | Electricity Account for3/40 Hardy Street, Igham Billing period 19/11/14 - 19/2/15 | Electrictiy |  | 1 | 307.14 | 307.14 | 911
2015-02-20 | Electricity Account for3/40 Hardy Street, Igham Billing period 19-2-15 - 4/3/15 | Electrictiy |  | 1 | 21.75 | 21.75 | 911
2015-03-06 | Phil 2/3/15 - 5/3 /15 | Accommodation |  | 1 | 327.27 | 327.27 | 911
| Subtotal for 911 |  |  |  |  | 44449.3
Portfolio WBS 916
2014-09-18 | Allciv - Site Administration | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-09-22 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-09-23 | Allciv - Site Administration | Labour | hr | 10.75 | 42.72 | 459.24 | 916
2014-09-24 | Allciv - Site Administration | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-25 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 916
2014-09-25 | Allciv - Site Administration | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-09-26 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-09-26 | Allciv - Site Administration | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2014-09-29 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-09-29 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-09-30 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-09-30 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-10-01 | Allciv - Site Administration | Labour | hr | 11 | 42.72 | 469.92 | 916
2014-10-01 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-10-02 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-02 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-10-03 | ATS Labour Hire | Labour | hr | 4.5 | 46.85 | 210.825 | 916
2014-10-03 | Allciv - Site Administration | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-10-07 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-08 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-08 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 916
2014-10-09 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-10-10 | Allciv - Site Administration | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2014-10-10 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-10-11 | ATS Labour Hire | Labour | hr | 3 | 46.85 | 140.55 | 916
2014-10-13 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-10-13 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-14 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-10-14 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-15 | Allciv - Site Administration | Labour | hr | 9.45 | 42.72 | 403.704 | 916
2014-10-15 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 916
2014-10-16 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-10-16 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-10-17 | Allciv - Site Administration | Labour | hr | 7.5 | 42.72 | 320.4 | 916
2014-10-19 | Travel Allowance for Steven Loder Week Ending the 19/10/2014 | Travel Allowance |  | 5 | 20 | 100 | 916
2014-10-20 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-10-20 | Labour Hire - Chad Carlill | Labour | hr | 10 | 40 | 400 | 916
2014-10-21 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-21 | Labour Hire - Chad Carlill | Labour | hr | 10 | 40 | 400 | 916
2014-10-22 | Allciv - Site Administration | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-10-22 | Labour Hire - Chad Carlill | Labour | hr | 10 | 40 | 400 | 916
2014-10-23 | Labour Hire - Chad Carlill | Labour | hr | 10 | 40 | 400 | 916
2014-10-24 | Labour Hire - Chad Carlill | Labour | hr | 11 | 40 | 440 | 916
2014-10-27 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-10-28 | Labour Hire - Chad Carlill | Labour | hr | 10 | 40 | 400 | 916
2014-10-28 | Allciv - Site Administration | Labour | hr | 11 | 42.72 | 469.92 | 916
2014-10-28 | ATS Labour Hire | Labour | hr | 3 | 46.85 | 140.55 | 916
2014-10-29 | ATS Labour Hire | Labour | hr | 11.5 | 46.85 | 538.775 | 916
2014-10-29 | Allciv - Site Administration | Labour | hr | 11 | 42.72 | 469.92 | 916
2014-10-29 | Labour Hire - Chad Carlill | Labour | hr | 10 | 40 | 400 | 916
2014-10-30 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-10-31 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-01 | ATS Labour Hire | Labour | hr | 9 | 46.85 | 421.65 | 916
2014-11-02 | Allciv - Site Administration | Labour | hr | 4.5 | 42.72 | 192.24 | 916
2014-11-03 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-11-03 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-04 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-04 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-11-05 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-05 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-11-06 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-06 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2014-11-07 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-07 | Allciv - Site Administration | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2014-11-08 | ATS Labour Hire | Labour | hr | 7 | 46.85 | 327.95 | 916
2014-11-10 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-10 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-11 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-11 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-12 | Allciv - Site Administration | Labour | hr | 9 | 42.72 | 384.48 | 916
2014-11-12 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-11-13 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-13 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-14 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-14 | Allciv - Labour Hire | Labour | hr | 7.5 | 42.72 | 320.4 | 916
2014-11-14 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-11-15 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-11-17 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2014-11-18 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-11-19 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-19 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-11-20 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-11-21 | Allciv - Site Administration | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-11-21 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-21 | ATS Labour Hire | Labour | hr | 5 | 46.85 | 234.25 | 916
2014-11-24 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-11-25 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-11-26 | Allciv - Site Administration | Labour | hr | 11 | 42.72 | 469.92 | 916
2014-11-26 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-26 | Allciv - Site Administration | Labour | hr | 11 | 42.72 | 469.92 | 916
2014-11-27 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-11-27 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-11-28 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 916
2014-11-28 | Allciv - Site Administration | Labour | hr | 7 | 42.72 | 299.04 | 916
2014-11-29 | ATS Labour Hire | Labour | hr | 2 | 46.85 | 93.7 | 916
2014-12-01 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-12-02 | Allciv - Site Administration | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-12-03 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-12-04 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-12-05 | Allciv - Site Administration | Labour | hr | 6 | 42.72 | 256.32 | 916
2014-12-08 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-12-09 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-12-09 | ATS Labour Hire | Labour | hr | 6.5 | 46.85 | 304.525 | 916
2014-12-10 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-12-11 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2014-12-11 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 916
2014-12-12 | ATS Labour Hire | Labour | hr | 7.5 | 46.85 | 351.375 | 916
2014-12-12 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2014-12-13 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2014-12-13 | Allciv - Site Administration | Labour | hr | 5 | 42.72 | 213.6 | 916
2014-12-15 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2014-12-16 | Allciv - Site Administration | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2014-12-16 | ATS Labour Hire | Labour | hr | 8.5 | 46.85 | 398.225 | 916
2014-12-17 | Allciv - Site Administration | Labour | hr | 8 | 42.72 | 341.76 | 916
2014-12-17 | ATS Labour Hire | Labour | hr | 7 | 46.85 | 327.95 | 916
2015-01-05 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2015-01-06 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 916
2015-01-07 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2015-01-07 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-08 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2015-01-09 | Allciv - Site Administration | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2015-01-09 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-10 | ATS Labour Hire | Labour | hr | 9 | 46.85 | 421.65 | 916
2015-01-12 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2015-01-12 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2015-01-13 | Allciv - Site Administration | Labour | hr | 9 | 42.72 | 384.48 | 916
2015-01-13 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-14 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2015-01-14 | Allciv - Site Administration | Labour | hr | 10.5 | 42.72 | 448.56 | 916
2015-01-15 | Allciv - Site Administration | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-15 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-16 | Allciv - Site Administration | Labour | hr | 9.5 | 42.72 | 405.84 | 916
2015-01-16 | ATS Labour Hire/Travel Hours | Labour | hr | 54 | 20 | 1080 | 916
2015-01-16 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-16 | ATS Labour Hire/Travel Hours | Labour | hr | 2 | 20 | 40 | 916
2015-01-19 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-19 | Allciv - Site Administration | Labour | hr | 9 | 42.72 | 384.48 | 916
2015-01-20 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2015-01-20 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2015-01-21 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2015-01-21 | ATS Labour Hire | Labour | hr | 9.5 | 46.85 | 445.075 | 916
2015-01-22 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2015-01-22 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-23 | ATS Labour Hire | Labour | hr | 4.5 | 46.85 | 210.825 | 916
2015-01-23 | Allciv - Site Administration | Labour | hr | 6.5 | 42.72 | 277.68 | 916
2015-01-27 | Allciv - Site Administration | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-27 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2015-01-28 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-01-28 | Allciv - Site Administration | Labour | hr | 10 | 42.72 | 427.2 | 916
2015-01-29 | ATS Labour Hire | Labour | hr | 2 | 46.85 | 93.7 | 916
2015-01-29 | Allciv - Site Administration | Labour | hr | 8 | 42.72 | 341.76 | 916
2015-01-29 | Travel Hours | Labour | hr | 5 | 20 | 100 | 916
2015-01-30 | Allciv - Site Administration | Labour | hr | 6 | 42.72 | 256.32 | 916
2015-01-30 | ATS Labour Hire/Travel Hours | Labour | hr | 4 | 20 | 80 | 916
2015-02-02 | Allciv - Site Administration | Labour | hr | 8.5 | 42.72 | 363.12 | 916
2015-02-02 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2015-02-03 | ATS Labour Hire | Labour | hr | 11.5 | 46.85 | 538.775 | 916
2015-02-04 | ATS Labour Hire | Labour | hr | 9 | 46.85 | 421.65 | 916
2015-02-07 | ATS Labour Hire/Travel Hours week ending 8/2/15 | Labour | hr | 5 | 20 | 100 | 916
2015-02-15 | ATS Labour Hire/Travel Hours week ending 15/2/15 | Labour | hr | 1 | 20 | 20 | 916
2015-02-15 | ATS Labour Hire/Travel Hours week ending 15/2/15 | Labour | hr | 4 | 20 | 80 | 916
2015-02-18 | ATS Labour Hire | Labour | hr | 11 | 46.85 | 515.35 | 916
2015-02-19 | ATS Labour Hire | Labour | hr | 10 | 46.85 | 468.5 | 916
2015-02-20 | ATS Labour Hire | Labour | hr | 8 | 46.85 | 374.8 | 916
2015-02-22 | ATS Labour Hire/Travel Hours week ending 22/2/15 | Labour | hr | 6 | 20 | 120 | 916
2015-02-24 | ATS Labour Hire | Labour | hr | 11.5 | 46.85 | 538.775 | 916
2015-02-25 | ATS Labour Hire | Labour | hr | 7 | 46.85 | 327.95 | 916
2015-02-26 | ATS Labour Hire | Labour | hr | 10.5 | 46.85 | 491.925 | 916
2015-02-27 | ATS Labour Hire | Labour | hr | 7.5 | 46.85 | 351.375 | 916
2015-02-28 | Labour Hire | Labour | hr | 2 | 42.72 | 85.44 | 916
2015-03-01 | ATS Labour Hire/Travel Hours week ending 1/3/15 | Labour | hr | 5 | 20 | 100 | 916
2015-03-12 | ATS Labour Hire/Travel Hours week ending 8/3/15 | Labour | hr | 4 | 20 | 80 | 916
| Subtotal for 916 |  |  |  |  | 68350.729
Portfolio WBS QMS
2015-01-12 | Stablised sand 3m includes minimum freight & environmental fee | Sand | each | 1 | 862.1 | 862.1 | QMS
| Subtotal for QMS |  |  |  |  | 862.1
| Grand Total |  |  |  |  | 1928962.5282